## Jurisdiction Setup
Setting | SEVENTS Initial Value / Decision | Status | Owner / Notes
Product architecture | Country-agnostic core; localization packs per jurisdiction | Baseline decision | Core engineering
Initial deployment country | United Arab Emirates (UAE) | Assumed; confirm legal entities | SEVENTS leadership
Legal entity / branch structure | TBD | Open decision | Finance / Legal
UAE VAT registration status | TBD — do not assume registered or unregistered | Must confirm before tax posting | Finance / UAE tax adviser
UAE VAT rates and treatments | Configurable, reviewed against current official guidance; no hard-coded assumptions | Must validate before activation | Finance / UAE tax adviser
GST | Not mandatory in generic core; only enabled for a jurisdiction/entity that requires it | Baseline decision | Product / Finance
Corporate tax | Separate from transaction-level VAT/GST; reporting support to be configured | Needs scope review | Finance / UAE tax adviser
Base/reporting currency | TBD; likely AED for UAE entity but confirm | Open decision | Finance
Project currencies / FX | Support project/transaction currency and approved exchange-rate source policy | Design requirement | Finance / Product
Fiscal year and accounting basis | TBD | Open decision | Finance
Invoice numbering and mandatory fields | Localization-pack configuration | Needs UAE validation | Finance / Legal
Language / timezone / date formats | Configurable; defaults confirmed by deployment | Open decision | Admin / Operations
Other operating countries | TBD | Open decision | Leadership / Finance
Localization pack version | Must be stored and auditable on relevant transactions | Design requirement | Engineering
Statutory filing integration | Not assumed in MVP; scope only after requirements confirmed | Open decision | Product / Finance

## Source Catalogue
S.No. | Department | Work Item Name | Who is Responsible | Description | Trigger | Action | Output/Evidence | Control/Handoff | Continuity/Escalation | Timing | Governance Understanding | Governance Inputs for SOP Creation | Reviewed by Kali | Reviewed by Sharique | Normalized Department ID | Normalized Role ID | Disposition | Capability Mapping | Workflow Template ID | Priority | Risk Tier | Process Owner | Mapping Status | Trigger Confirmed | Action Mapping Confirmed | Output Confirmed | Handoff Confirmed | SLA Confirmed | Approval Policy ID | Agent Policy ID | Phase Target | Review Notes | Reviewed By | Reviewed At | Published Version
1 | Company / Leadership | Approve the company vision, purpose and ownership expectations | Chairman | Trigger: When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. Action: The Chairman completes “Approve the company vision, purpose and ownership expectations” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. Output/Evidence: a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. Control/Handoff: The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. Continuity/Escalation: Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. Timing: Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. | The Chairman completes “Approve the company vision, purpose and ownership expectations” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. | a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. | The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. | Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. | Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | • In plain words: the owners put in writing what the company exists to do and what they expect from it, and the Chairman signs it off. • Starts when: the annual governance cycle comes round, or somebody proposes a change to the vision or to what owners expect. • How it runs: (1) the CEO drafts the vision and purpose paper. (2) The CFO says whether the ambition is fundable. (3) The CLO checks it does not clash with the constitution or the shareholder agreement. (4) The Chairman approves it or sends it back. (5) The Document Controller files the signed version and issues it to the chiefs. • Proof it happened: a signed vision and purpose statement carrying a version number and date, plus the resolution that approved it. • Where it usually breaks: the statement gets signed but never cascaded, so departments write plans against their own idea of the vision. | • Name the document. The SOP should point to one controlled "Vision, Purpose and Ownership Expectations" statement with a version number, not to a general idea of the vision. • Set the review rule: re-approved every year with the strategy cycle, and immediately after any change in ownership. • Say who is allowed to draft a change, and make clear nobody else may edit the wording informally. • Add the cascade step, which is the one usually missing. Within a set number of working days of signing, each chief confirms in writing that their plan lines up with it. • Include a distribution list and a withdrawal step so superseded copies stop circulating. | Yes | Yes
2 | Company / Leadership | Approve annual strategic priorities and enterprise risk appetite | Chairman | Trigger: When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. Action: The Chairman completes “Approve annual strategic priorities and enterprise risk appetite” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. Output/Evidence: a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. Control/Handoff: The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. Continuity/Escalation: Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. Timing: Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. | The Chairman completes “Approve annual strategic priorities and enterprise risk appetite” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. | a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. | The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. | Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. | Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | • In plain words: once a year the Chairman agrees the short list of things the company will push on, and how much risk it is willing to carry to get there. • Starts when: the annual planning cycle opens, or a major event forces the priorities or the risk limits to be reopened. • How it runs: (1) the CEO consolidates department plans into a short priority list. (2) The CFO attaches the cost and the downside of each. (3) A risk assessment sets out what could go wrong. (4) The Chairman approves the priorities and sets the risk limits. (5) The limits are issued to the chiefs and built into their approval authority. • Proof it happened: a signed priority list and risk appetite statement for the year, and the resolution approving both. • Where it usually breaks: the priorities get approved but the risk limits stay worded loosely, so nobody knows the point at which they must stop and escalate. | • Treat this as two outputs in the SOP: the annual priority list, and the risk appetite statement. They are approved together but used by different people afterwards. • Make risk appetite measurable. Set a limit for each category (money at risk, safety, legal and regulatory, delivery and reputation) instead of wording like "low appetite", which nobody can apply. • Write the escalation rule: who reports a breach or near breach, to whom, in what format, and within how many working days. • Link it to authority. State that no approval limit in the authority matrix may exceed the risk appetite agreed here. • Add a mid-year checkpoint so priorities are formally reconfirmed or changed, rather than quietly drifting. | Yes | Yes
3 | Company / Leadership | Approve the ownership reserved-matter and Delegation-of-Authority matrix | Chairman | Trigger: When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. Action: The Chairman completes “Approve the ownership reserved-matter and Delegation-of-Authority matrix” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. Output/Evidence: a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. Control/Handoff: The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. Continuity/Escalation: Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. Timing: Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. | The Chairman completes “Approve the ownership reserved-matter and Delegation-of-Authority matrix” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. | a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. | The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. | Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. | Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | • In plain words: two lists. One names the decisions only the owners may take. The other says how far each role can go on its own before it has to ask. • Starts when: the annual review falls due, a new role or entity is created, or somebody hits a limit that no longer fits the business. • How it runs: (1) the CEO drafts or updates both lists. (2) The CFO sets the money bands. (3) The CLO confirms they are legally valid. (4) The Chairman signs. (5) The Document Controller version-controls the matrix, reissues it and withdraws the old one. • Proof it happened: a signed authority matrix with a version number and an effective date, and evidence the superseded version was withdrawn. • Where it usually breaks: an old version stays in circulation, or a temporary increase in authority is granted verbally and never recorded. | • Attach the actual limit table as an annexure to the SOP. Free text descriptions of authority always end in argument. • Build version control into the steps: version number, effective date, reissue, and a positive withdrawal of the previous version. • Write a temporary authority procedure. Who may grant it, for how long, in what written form, and where it is logged. Verbal delegation during someone's leave is the most common breakdown. • State the no self-approval rule in plain words, and say how a conflict of interest is declared and handled. • Cover the breach case. If someone commits the company beyond their authority, who decides whether it is ratified or reversed, and how quickly. | Yes | Yes
4 | Company / Leadership | Approve material changes to ownership, legal structure or capital structure | Chairman | Trigger: When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. Action: The Chairman completes “Approve material changes to ownership, legal structure or capital structure” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. Output/Evidence: a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. Control/Handoff: The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. Continuity/Escalation: Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. Timing: Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. | The Chairman completes “Approve material changes to ownership, legal structure or capital structure” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. | a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. | The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. | Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. | Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | • In plain words: sign-off on the big structural moves. Who owns shares, which legal entities exist, and how the company is funded or borrows. • Starts when: a share transfer, new entity, restructuring, major loan or investor change is proposed. • How it runs: (1) the CEO submits the case with the reason and the options considered. (2) The CFO models the effect on cash, debt and any covenants. (3) The CLO prepares the documents and lists the filings required. (4) The Chairman and owners approve. (5) Only then is it executed, filed with the authorities and recorded. • Proof it happened: a signed resolution, the executed legal documents and the filing receipts from the relevant authority. • Where it usually breaks: work starts before the resolution is signed, or the decision is taken correctly and then the statutory filing is forgotten. | • Define "material" with numbers. Give a value threshold, plus a list of events that always count (share transfer, new entity, closing an entity, change of control, a facility above a stated amount). • Lock the sequence in the SOP: approve, then execute, then file, then record. Add a check that blocks execution until the signed resolution exists. • Include a filings checklist with statutory deadlines and a named owner for each. The filing after the decision is where these items slip. • Say when outside advice is compulsory, for example an auditor or legal opinion, so it is not left to judgement. • Add a completion check: statutory registers updated, group structure chart reissued, and bank or investor records amended. | Yes | Yes
5 | Company / Leadership | Maintain the ownership governance calendar and decision discipline | Chairman | Trigger: When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. Action: The Chairman completes “Maintain the ownership governance calendar and decision discipline” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. Output/Evidence: a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. Control/Handoff: The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. Continuity/Escalation: Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. Timing: Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | When the annual governance cycle, ownership review, company-structure proposal or a matter reserved for ownership requires a decision. | The Chairman completes “Maintain the ownership governance calendar and decision discipline” using the CEO's written recommendation, approved strategy papers, CFO financial analysis, CLO legal advice, risk assessment, authority matrix and complete supporting evidence. | a signed ownership decision, approved governance direction, Board/ownership resolution or controlled reserved-matter record. | The CEO owns the complete submission and implementation plan; the CFO confirms financial capacity, the CLO confirms legality and authority, and the Document Controller records the final decision before the CEO communicates it to affected functional chiefs. | Only an ownership-authorised alternate may act for the Chairman; no executive or department may self-approve a reserved ownership matter, and incomplete, conflicted or out-of-authority submissions are returned to the CEO or escalated to the owners. | Complete at the approved annual/quarterly governance date or within three working days of a complete reserved-matter paper; urgent statutory or ownership-protection matters are acknowledged the same working day. | • In plain words: keeping the rhythm of governance. The right meeting happens on the agreed date, papers go out in time, and decisions get written down and followed up. • Starts when: the governance year is set up, and then continuously as each meeting date approaches. • How it runs: (1) the calendar for the year is published. (2) Papers are requested a set number of days before each meeting. (3) Incomplete papers are returned before the meeting, not debated in it. (4) Decisions are minuted with an owner and a deadline. (5) Open actions carry forward to the next meeting until they are closed. • Proof it happened: the published calendar, circulated agendas and papers, signed minutes, and an action tracker showing what is still open. • Where it usually breaks: actions get minuted but never chased, so the same item reappears meeting after meeting with no owner feeling accountable. | • Name the calendar owner and put the paper cut-off in the SOP as a specific number of working days before each meeting. • Give the chair the stated right to return an incomplete paper unheard, and say how the item is rescheduled. • Standardise the paper template: purpose, options considered, recommendation, financial impact, legal view, and the exact decision being requested. • Make the action tracker a controlled document with owner, deadline, status and a view of overdue items, and require it to be tabled at every meeting. • Cover decisions taken between meetings. How they are authorised at the time, and how they are ratified and minuted at the next meeting. | Yes | Yes
6 | Company / Leadership | Appoint the CEO and approve the CEO mandate and employment terms | Chairman | Trigger: When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. Action: The Chairman completes “Appoint the CEO and approve the CEO mandate and employment terms” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. Output/Evidence: an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. Control/Handoff: The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. Continuity/Escalation: CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. Timing: Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. | The Chairman completes “Appoint the CEO and approve the CEO mandate and employment terms” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. | an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. | The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. | CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. | Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | • In plain words: the Chairman chooses the CEO and sets out in writing what the job covers, what the CEO may decide alone, and the terms of employment. • Starts when: the post becomes vacant, a term is ending, or the mandate needs revising after a change in strategy or structure. • How it runs: (1) the role and mandate are defined before any candidate is considered. (2) The CPCO runs the confidential appointment process. (3) The CLO drafts the employment and authority terms. (4) The Chairman appoints and signs. (5) The mandate is issued so the chiefs know what the CEO can and cannot decide. • Proof it happened: a signed CEO mandate and contract, the appointment resolution, and a confidential personnel file held by the CPCO. • Where it usually breaks: the contract gets signed but the authority boundary is left vague, so nobody is sure where CEO power stops and the owners' begins. | • Keep two documents apart in the SOP: the employment contract, and the CEO mandate. The contract is confidential, the mandate has to be visible to the chiefs. • List what the mandate must state as a minimum: scope, decisions reserved to owners, financial limits, reporting lines and reporting frequency. • Set the confidentiality rule for the appointment process. Who sees candidate information, where it is stored, and who may not. • Add the handover step. What the outgoing CEO must hand over, and by when, before the new mandate takes effect. • State that the mandate is reissued whenever the authority matrix changes, so the two documents cannot drift apart. | Yes | Yes
7 | Company / Leadership | Approve the CEO's annual objectives, KPIs and authority boundaries | Chairman | Trigger: When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. Action: The Chairman completes “Approve the CEO's annual objectives, KPIs and authority boundaries” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. Output/Evidence: an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. Control/Handoff: The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. Continuity/Escalation: CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. Timing: Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. | The Chairman completes “Approve the CEO's annual objectives, KPIs and authority boundaries” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. | an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. | The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. | CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. | Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | • In plain words: each year the Chairman agrees what the CEO will be measured on, the targets, and how far the CEO may go without asking. • Starts when: the annual objective-setting cycle opens, or objectives need reopening after a major change in the plan. • How it runs: (1) the CEO proposes objectives drawn from the approved strategy. (2) The CFO confirms the financial targets match the budget. (3) The Chairman challenges and agrees them. (4) Authority limits are confirmed or adjusted at the same time. (5) The agreed set is signed and filed. • Proof it happened: a signed CEO objectives and KPI sheet for the year, with targets, measures and authority limits stated. • Where it usually breaks: objectives are agreed verbally in a meeting and never signed, so the year-end review has nothing firm to measure against. | • Require every objective to carry a measure, a target and a data source. An objective with no source of truth cannot be reviewed fairly. • Set the deadline in the SOP: objectives agreed within a fixed number of working days of the budget approval, not months later. • Say how objectives are changed mid-year. Who requests it, who approves it, and that the original is retained rather than overwritten. • Cross-check with the budget. The financial KPIs must reconcile to the approved budget, and the SOP should name who verifies that. • Keep authority limits in the same signed record, so the CEO's targets and the CEO's freedom to act are read together. | Yes | Yes
8 | Company / Leadership | Conduct periodic CEO performance and leadership reviews | Chairman | Trigger: When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. Action: The Chairman completes “Conduct periodic CEO performance and leadership reviews” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. Output/Evidence: an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. Control/Handoff: The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. Continuity/Escalation: CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. Timing: Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. | The Chairman completes “Conduct periodic CEO performance and leadership reviews” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. | an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. | The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. | CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. | Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | • In plain words: at set points in the year the Chairman reviews how the CEO is performing, on results and on leadership conduct, and records the outcome. • Starts when: the scheduled review date arrives, or a serious performance or conduct concern arises in between. • How it runs: (1) the CEO submits a self-assessment against the agreed objectives. (2) The CFO supplies verified financial results. (3) The Chairman reviews evidence, not opinion. (4) The review is held and the outcome recorded. (5) Any development or corrective actions are set with dates. • Proof it happened: a signed performance review record, the supporting result data, and any agreed action plan. • Where it usually breaks: the review turns into a discussion about the business rather than about the CEO, and no written outcome is produced. | • Fix the frequency and put it in the governance calendar: a mid-year check and a full year-end review is the usual minimum. • Separate the two halves in the template: delivery against objectives, and leadership conduct. They need different evidence. • Name the source of the result data and require it to be verified by the CFO before the review, so the numbers are not argued in the meeting. • Write the underperformance path. What happens if objectives are missed, what a formal improvement plan looks like, and who else is told. • Set access rules on the record. It is a confidential document and the SOP should say who holds it and who may read it. | Yes | Yes
9 | Company / Leadership | Approve CEO succession, emergency cover and leadership-continuity arrangements | Chairman | Trigger: When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. Action: The Chairman completes “Approve CEO succession, emergency cover and leadership-continuity arrangements” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. Output/Evidence: an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. Control/Handoff: The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. Continuity/Escalation: CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. Timing: Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. | The Chairman completes “Approve CEO succession, emergency cover and leadership-continuity arrangements” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. | an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. | The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. | CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. | Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | • In plain words: making sure the company is never left without a CEO. A named successor plan for the long term, and immediate cover if the CEO is suddenly unavailable. • Starts when: the annual succession review falls due, the CEO gives notice, or the CEO becomes unavailable at short notice. • How it runs: (1) the CPCO maintains the succession and readiness assessment. (2) The CEO nominates emergency cover. (3) The CLO confirms the acting authority is legally valid. (4) The Chairman approves both the long-term plan and the emergency arrangement. (5) The acting authority letter is held ready to activate. • Proof it happened: an approved succession plan, a signed emergency delegation or acting-authority letter, and a record of when it was last reviewed. • Where it usually breaks: a successor is named on paper but the acting authority letter does not exist, so in a real emergency nobody can lawfully sign. | • Split the SOP into planned succession and emergency cover. They run on different timescales and need different documents. • Require a pre-signed acting-authority letter, held by the Chairman and the CLO, that can be activated the same day. • State clearly what an acting CEO may not do: reserved matters, changes to strategy, and commitments above a stated value. • Set the trigger and the end. What counts as CEO unavailability, who declares it, and how normal authority is formally restored. • Add an annual test or review of the arrangement, so it does not sit unexamined for years. | Yes | Yes
10 | Company / Leadership | Resolve strategic accountability deadlocks between the CEO and executives | Chairman | Trigger: When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. Action: The Chairman completes “Resolve strategic accountability deadlocks between the CEO and executives” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. Output/Evidence: an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. Control/Handoff: The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. Continuity/Escalation: CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. Timing: Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | When the CEO appointment cycle, annual objective setting, scheduled performance review, succession review or executive-accountability deadlock occurs. | The Chairman completes “Resolve strategic accountability deadlocks between the CEO and executives” using approved CEO mandate, performance evidence, company results, stakeholder feedback, succession information, CPCO records, CLO advice and ownership expectations. | an approved CEO mandate, objective/KPI decision, performance record, succession direction or documented resolution of executive accountability. | The Chairman owns CEO appointment and evaluation; the CPCO administers confidential people records, the CLO controls employment and governance terms, and the CEO remains accountable for the performance of all functional chiefs. | CEO appointment, removal, remuneration and succession decisions remain reserved to the Chairman/owners; conflicts of interest are declared and an ownership-authorised reviewer is used where the Chairman cannot act. | Complete objective and performance decisions to the approved annual calendar; acknowledge an executive deadlock or emergency CEO-cover requirement within one working day. | • In plain words: when the CEO and an executive cannot agree on something strategic, and the disagreement is blocking the business, the Chairman settles it. • Starts when: a disagreement over accountability, priority or authority has not been resolved at executive level and is holding up a decision. • How it runs: (1) the CEO puts the deadlock in writing with both positions. (2) Supporting evidence comes from the functions involved. (3) The CLO advises where authority actually sits. (4) The Chairman decides. (5) The decision is minuted and issued to everyone affected. • Proof it happened: a written deadlock submission, the Chairman's recorded decision, and confirmation it was communicated. • Where it usually breaks: the dispute is raised verbally and repeatedly without ever being written up, so it never reaches a decision point. | • Define what qualifies as a deadlock in the SOP, so this route is not used for ordinary disagreements the CEO should settle. • Require a written submission with both positions stated fairly, and give the other party the right to add their own words. • Put a clock on it. A deadlock must be escalated within a set number of days rather than allowed to sit, and acknowledged within a set number. • State that operational command stays with the CEO while the matter is open, so work does not stop while it is decided. • Make the decision binding and recorded, and log recurring deadlocks, because a pattern usually points to an unclear mandate that needs fixing. | Yes | Yes
11 | Company / Leadership | Approve the annual company budget and capital-allocation envelope | Chairman | Trigger: When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. Action: The Chairman completes “Approve the annual company budget and capital-allocation envelope” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. Output/Evidence: an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. Control/Handoff: The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. Continuity/Escalation: No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. Timing: Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. | The Chairman completes “Approve the annual company budget and capital-allocation envelope” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. | an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. | The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. | No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. | Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | • In plain words: the Chairman signs off the company budget for the year and decides how much money is available for investment and where it may be spent. • Starts when: the annual budget cycle reaches ownership submission, or a change big enough to reopen the budget occurs. • How it runs: (1) departments build their budgets. (2) The CFO consolidates and tests the numbers. (3) The CEO approves the management budget first and recommends it. (4) The Chairman challenges and approves the budget and the capital envelope. (5) The approved figures are issued and locked as the baseline. • Proof it happened: an approved budget document with a version and date, the ownership resolution, and the capital allocation limits in writing. • Where it usually breaks: the budget is approved but never frozen as a baseline, so later comparisons are made against a moving target. | • Make baselining a formal step. Once approved, the budget is locked and given a version, and any change goes through a documented revision. • State the capital envelope separately from the operating budget, with its own limit, because the two get approved together and then confused. • Put the calendar in the SOP: when departments submit, when the CFO consolidates, when the CEO approves, when ownership approves. Work backwards from the ownership date. • Require the submission pack contents to be listed: assumptions, prior year comparison, sensitivity, and headcount. A pack with missing parts is returned, not debated. • Say who is allowed to release the approved budget to departments, and in what form, so everyone works from one version. | Yes | Yes
12 | Company / Leadership | Approve major investments, borrowing, guarantees and commitments above authority | Chairman | Trigger: When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. Action: The Chairman completes “Approve major investments, borrowing, guarantees and commitments above authority” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. Output/Evidence: an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. Control/Handoff: The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. Continuity/Escalation: No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. Timing: Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. | The Chairman completes “Approve major investments, borrowing, guarantees and commitments above authority” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. | an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. | The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. | No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. | Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | • In plain words: any investment, loan, guarantee or commitment too big for the CEO to approve comes to the Chairman for a decision. • Starts when: a request exceeds the CEO's authority limit, or falls into a category reserved to ownership regardless of value. • How it runs: (1) the CEO submits the business case with the options considered. (2) The CFO tests the numbers, funding and effect on cash and covenants. (3) The CLO reviews the financing terms and any security being given. (4) The Chairman approves, defers or rejects. (5) Only then may the commitment be signed. • Proof it happened: an approved business case, the ownership resolution, and the executed agreement matching what was approved. • Where it usually breaks: the commitment gets signed on the strength of a verbal approval, and the paperwork is assembled afterwards. | • State the authority thresholds as figures in the SOP, and list the categories that always come to ownership whatever the value, such as guarantees and security over assets. • Add a hard block: no agreement may be signed until the signed resolution exists. Name who checks this before signature. • Set the minimum content of a business case: purpose, options, cost, funding source, cash effect, risks and what happens if it is not approved. • Require a check that the executed document matches what was approved. Terms often move between approval and signature. • Add a post-approval review for large items, comparing actual outcome against the case, and feed the lessons back into the next submission. | Yes | Yes
13 | Company / Leadership | Review annual financial statements, audit findings and management responses | Chairman | Trigger: When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. Action: The Chairman completes “Review annual financial statements, audit findings and management responses” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. Output/Evidence: an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. Control/Handoff: The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. Continuity/Escalation: No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. Timing: Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. | The Chairman completes “Review annual financial statements, audit findings and management responses” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. | an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. | The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. | No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. | Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | • In plain words: the Chairman reviews the audited accounts, what the auditors found, and how management intends to fix it. • Starts when: the audit is complete and the draft accounts and audit findings are ready for ownership review. • How it runs: (1) the CFO prepares the accounts and the management response to each finding. (2) The auditors present their findings. (3) The CEO owns the response and the corrective plan. (4) The Chairman reviews and signs off. (5) The findings become tracked actions with owners and dates. • Proof it happened: signed financial statements, the audit report, a written management response, and an action log against each finding. • Where it usually breaks: findings are discussed and accepted but never converted into tracked actions, so the same points reappear the following year. | • Require every audit finding to become a numbered action with an owner and a due date. The SOP should treat an accepted finding with no action as an open item. • Add a repeat-finding rule. Anything raised for a second year running is escalated and explained to the Chairman directly. • Put the timetable in the SOP, working back from the statutory filing deadline, so the review is not squeezed at the end. • Say how the auditors get access and to whom, and record any limitation of scope they report. • Include the closure step: who verifies a finding is genuinely fixed, and what evidence is required before it is closed. | Yes | Yes
14 | Company / Leadership | Review liquidity, solvency, major exposure and enterprise-financial risk | Chairman | Trigger: When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. Action: The Chairman completes “Review liquidity, solvency, major exposure and enterprise-financial risk” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. Output/Evidence: an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. Control/Handoff: The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. Continuity/Escalation: No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. Timing: Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. | The Chairman completes “Review liquidity, solvency, major exposure and enterprise-financial risk” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. | an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. | The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. | No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. | Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | • In plain words: the Chairman checks the company can pay what it owes, now and in the months ahead, and looks at the biggest financial exposures. • Starts when: the scheduled review date arrives, or a liquidity, solvency or major exposure warning is raised in between. • How it runs: (1) the CFO prepares the cash, liquidity and exposure position with a forward view. (2) Concentration risks are identified, such as one client, one project or one lender. (3) The CEO explains the actions in hand. (4) The Chairman reviews and directs. (5) Agreed actions are tracked to the next review. • Proof it happened: the reviewed liquidity and exposure report, the minuted direction, and the tracked actions arising. • Where it usually breaks: the review looks only backwards at last month's position, with no forward cash view, which is where the risk actually sits. | • Require a forward-looking view, not just historic results. A rolling cash forecast covering a stated number of weeks or months should be mandatory in the pack. • Set early-warning triggers with numbers: cash below a level, receivables past a number of days, covenant headroom below a margin. Breaching one triggers immediate reporting rather than waiting for the next review. • List the exposures the pack must always show: largest client, largest project, largest supplier, and lender concentration. • Fix the frequency, and add a shortened weekly version for periods of stress. Say who decides the company is in a stress period. • Name who may release cash information externally, since this data is sensitive with banks and clients. | Yes | Yes
15 | Company / Leadership | Decide shareholder funding, retained earnings and distribution recommendations | Chairman | Trigger: When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. Action: The Chairman completes “Decide shareholder funding, retained earnings and distribution recommendations” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. Output/Evidence: an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. Control/Handoff: The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. Continuity/Escalation: No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. Timing: Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | When the annual budget, audited accounts, capital request, borrowing proposal, guarantee, shareholder-funding need or material financial exposure requires ownership review. | The Chairman completes “Decide shareholder funding, retained earnings and distribution recommendations” using the CEO recommendation, CFO budget and cash-flow analysis, audited or reconciled financial statements, investment business case, risk analysis, CLO review and applicable authority limits. | an approved budget/capital decision, financing resolution, signed financial-statement review, shareholder-funding direction or controlled exposure decision. | The CFO owns financial accuracy and alternatives, the CEO recommends the company action, the CLO confirms financing and security terms, and Finance records implementation without bypassing payment or banking controls. | No borrowing, guarantee, major investment, shareholder distribution or capital commitment may proceed without the required ownership approval; liquidity, solvency, fraud or covenant threats escalate immediately to the Chairman. | Complete scheduled financial reviews to the annual/monthly governance calendar and decide complete material funding or commitment papers within three working days; urgent liquidity threats are reviewed the same working day. | • In plain words: deciding what happens with profit. Whether it stays in the business, is paid out to shareholders, or whether shareholders need to put money in. • Starts when: the year-end results are finalised, a funding need is identified, or shareholders request a distribution. • How it runs: (1) the CFO sets out distributable profit, cash available and what the business needs to retain. (2) The CLO confirms the distribution is legally permitted and the process is correct. (3) The CEO recommends. (4) The Chairman and owners decide. (5) The resolution is recorded and the payment or funding is executed. • Proof it happened: a shareholder resolution, the supporting distributable-profit calculation, and the payment or funding record. • Where it usually breaks: a distribution is decided on profit figures while the cash to pay it is committed elsewhere, leaving a squeeze afterwards. | • Make the SOP require a cash test as well as a profit test. Both must pass before a distribution is recommended. • Require the CLO to confirm the legal ability to distribute, and list the documents needed, since this is a statutory matter and not just a financial one. • State the retention policy, for example a minimum cash buffer or working capital cover that must survive the distribution. • Cover shareholder funding coming the other way: how it is requested, on what terms, and how it is documented as equity or loan. • Set the sequence and the record: resolution first, then payment, then the accounting entry and the register update. | Yes | Yes
16 | Company / Leadership | Review company performance, strategic portfolio and corrective priorities | Chairman | Trigger: When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. Action: The Chairman completes “Review company performance, strategic portfolio and corrective priorities” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. Output/Evidence: an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. Control/Handoff: The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. Continuity/Escalation: Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. Timing: Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. | The Chairman completes “Review company performance, strategic portfolio and corrective priorities” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. | an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. | The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. | Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. | Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | • In plain words: the Chairman steps back and looks at how the whole company is performing, which parts are working, which are not, and what must be fixed first. • Starts when: the scheduled quarterly or year-end ownership review falls due, or results move far enough off plan to force an earlier look. • How it runs: (1) the CEO presents one reconciled company position, not separate departmental views. (2) Functional chiefs supply verified evidence behind it. (3) The CFO reconciles the financial results. (4) The Chairman reviews performance against the approved plan and sets corrective priorities. (5) The priorities are minuted and tracked. • Proof it happened: the reviewed performance pack, minuted ownership direction, and a tracked list of corrective priorities. • Where it usually breaks: each function brings its own numbers and the meeting is spent reconciling data instead of deciding what to do. | • Make one reconciled pack a rule, prepared by the CEO with the CFO, and state that departments do not table separate performance numbers. • Require data certification. Each chief signs off their figures before the pack is issued, so accuracy is settled beforehand. • Fix the frequency and content: quarterly review plus a year-end review, and list the standing sections the pack must contain. • Add an exception rule. Results outside a stated tolerance are reported when they happen, not held back for the quarterly meeting. • Carry corrective priorities forward until closed, with the same owner and deadline showing each time. | Yes | Yes
17 | Company / Leadership | Approve entry into or exit from major markets, services and strategic alliances | Chairman | Trigger: When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. Action: The Chairman completes “Approve entry into or exit from major markets, services and strategic alliances” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. Output/Evidence: an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. Control/Handoff: The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. Continuity/Escalation: Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. Timing: Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. | The Chairman completes “Approve entry into or exit from major markets, services and strategic alliances” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. | an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. | The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. | Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. | Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | • In plain words: the Chairman approves moving into a new market or service line, pulling out of one, or tying the company to a major partner. • Starts when: a market entry, exit or alliance is proposed, or an existing market or partnership is under review. • How it runs: (1) the CEO submits the case with market evidence and the options considered. (2) The CFO sets out the investment, the return and the exit cost. (3) The CLO reviews licensing, registration and partner risk. (4) The Chairman approves, defers or rejects. (5) Approved moves become a mandated plan with milestones. • Proof it happened: an approved entry or exit decision, the ownership resolution, and the mandated implementation plan. • Where it usually breaks: entry is well examined and exit is not, so the company has no agreed way out and no idea what leaving would cost. | • Require an exit plan inside every entry case: what triggers withdrawal, what it would cost, and who decides. • List the compliance checks the SOP must force before entry: licences, registrations, tax presence, local partner rules and insurance. • Set review milestones at the point of approval, so performance against the case is checked rather than assumed. • Cover alliances separately. Due diligence on the partner, who signs, and what happens on partner default or reputational damage. • Add a stop rule for spending. No market entry cost is committed before the resolution is signed. | Yes | Yes
18 | Company / Leadership | Review material legal, regulatory, ethical and reputation matters | Chairman | Trigger: When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. Action: The Chairman completes “Review material legal, regulatory, ethical and reputation matters” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. Output/Evidence: an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. Control/Handoff: The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. Continuity/Escalation: Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. Timing: Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. | The Chairman completes “Review material legal, regulatory, ethical and reputation matters” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. | an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. | The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. | Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. | Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | • In plain words: the Chairman is told about the serious legal, regulatory, ethical and reputation issues and decides how the company handles them. • Starts when: a material legal claim, regulatory action, ethics allegation or reputation threat arises, or the scheduled review falls due. • How it runs: (1) the CLO reports the matter with the legal position and exposure. (2) The CFO quantifies the financial impact. (3) The CEO presents the proposed handling and one company position. (4) The Chairman gives direction, including on settlement or defence. (5) The matter stays on the register until closed. • Proof it happened: a legal and reputation register entry, the minuted ownership direction, and the record of the outcome. • Where it usually breaks: matters are reported once and then disappear from view until they escalate, because nothing keeps them on the agenda. | • Define what must be reported to the Chairman and when, using clear triggers: claim value above a figure, any regulator contact, any allegation involving senior staff, anything with press interest. • Set a same-day or next-day notification rule for serious matters, separate from the routine review cycle. • Make a standing register mandatory, showing exposure, stage and next action, tabled at every ownership meeting until each item closes. • State the no-suppression rule plainly, and give a route for raising concerns that bypasses the line manager where needed. • Say who may speak externally on a live legal matter, and require legal clearance before any statement is issued. | Yes | Yes
19 | Company / Leadership | Direct the ownership response to enterprise crisis and business-continuity threats | Chairman | Trigger: When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. Action: The Chairman completes “Direct the ownership response to enterprise crisis and business-continuity threats” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. Output/Evidence: an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. Control/Handoff: The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. Continuity/Escalation: Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. Timing: Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. | The Chairman completes “Direct the ownership response to enterprise crisis and business-continuity threats” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. | an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. | The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. | Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. | Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | • In plain words: when something threatens the business as a whole, the Chairman sets the ownership position and gives the CEO a clear mandate to act. • Starts when: a crisis or continuity threat is declared, such as a fatality, major site failure, cyber incident, loss of a licence or a funding shock. • How it runs: (1) the CEO notifies the Chairman immediately and states the facts known. (2) Life safety and containment actions proceed without waiting for approval. (3) The CLO and QHSE advise on legal and safety obligations. (4) The Chairman sets the ownership mandate and any spending authority. (5) Decisions and timings are logged throughout for the review afterwards. • Proof it happened: the incident notification, a crisis decision log with times, the ownership mandate, and the post-incident review. • Where it usually breaks: nobody keeps a timed log while the crisis is running, so the review afterwards cannot establish what was decided or when. | • Define the categories and severity levels that count as a crisis, so declaring one is not a judgement call in the moment. • Make immediate action explicit. Life safety and containment never wait for approval, and the SOP should say so in the first line. • Require a timed decision log from the moment of declaration, with a named person responsible for keeping it. • Set a temporary spending authority for crisis conditions, with a limit and a ratification step afterwards, so response is not delayed by approval routes. • Fix the post-incident review: how soon after standing down, who attends, and how the lessons become tracked actions. • Add the contact tree and out-of-hours numbers as an annexure, and require it to be checked at a stated interval. | Yes | Yes
20 | Company / Leadership | Chair ownership meetings, approve minutes and monitor reserved actions | Chairman | Trigger: When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. Action: The Chairman completes “Chair ownership meetings, approve minutes and monitor reserved actions” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. Output/Evidence: an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. Control/Handoff: The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. Continuity/Escalation: Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. Timing: Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | When a scheduled ownership review, strategic-market decision, major legal/reputation matter, enterprise crisis or Board/ownership meeting requires oversight. | The Chairman completes “Chair ownership meetings, approve minutes and monitor reserved actions” using the CEO performance pack, portfolio and risk dashboards, strategic business case, CLO legal/reputation assessment, CFO exposure analysis, crisis facts and documented executive recommendations. | an ownership performance direction, strategic entry/exit decision, crisis mandate, Board/ownership minutes or closed executive-action record. | The CEO presents one reconciled company position and owns execution; relevant functional chiefs provide verified evidence, the CLO advises on legal/reputation exposure, and the Document Controller preserves the controlled decision and action trail. | Operational command remains with the CEO unless ownership formally changes it; serious safety, criminal, insolvency, licence, reputation or business-continuity threats escalate immediately to the Chairman and owners. | Perform scheduled oversight quarterly and at year-end; acknowledge critical crisis or reputation matters immediately and issue ownership direction as soon as verified facts permit. | • In plain words: the Chairman runs the ownership meetings, approves the minutes as the official record, and keeps track of the actions reserved to owners until they are finished. • Starts when: each scheduled ownership meeting approaches, and continuously afterwards while actions remain open. • How it runs: (1) the agenda and papers are issued ahead of the meeting. (2) The meeting is chaired to the agenda and decisions are taken by those with the authority. (3) Draft minutes are prepared promptly. (4) The Chairman approves the minutes as the formal record. (5) Reserved actions are tracked meeting to meeting until closed. • Proof it happened: the issued agenda and papers, signed approved minutes, and an action register showing status and owner. • Where it usually breaks: minutes are drafted weeks later, so detail is lost and the record no longer settles what was actually decided. | • Set deadlines in the SOP: papers out a fixed number of days before, draft minutes within a fixed number of days after, approval before the next meeting. • Standardise the minute format so each item records the decision taken, the authority relied on, the owner and the deadline. Discussion summaries alone are not enough. • Require the action register to be tabled at every meeting, showing overdue items separately. • Say who may attend, who is a decision maker and who is only present to advise, and record attendance including apologies. • Cover storage: where approved minutes are held, for how long, and who controls access, since they are the company's legal record of decisions. | Yes | Yes
21 | Company / Leadership | Translate ownership vision into the multi-year company strategy | Chief Executive Officer (CEO) | Trigger: When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. Action: The Chief Executive Officer (CEO) completes “Translate ownership vision into the multi-year company strategy” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. Output/Evidence: an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. Control/Handoff: All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. Continuity/Escalation: A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. Timing: Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. | The Chief Executive Officer (CEO) completes “Translate ownership vision into the multi-year company strategy” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. | an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. | All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. | A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. | Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | • In plain words: the CEO turns what the owners want into a multi-year plan for the company, saying where it will grow, what it will build and what it will need. • Starts when: the owners approve or change the vision, the planning cycle opens, or a major shift in the market forces the strategy to be revisited. • How it runs: (1) the CEO drafts the strategy from the approved ownership direction. (2) The CFO confirms the funding and capacity to deliver it. (3) The CRO checks the operating model can support it. (4) The Chairman approves. (5) The strategy is issued to the chiefs as the basis for their plans. • Proof it happened: an approved multi-year strategy document with a version and date, and the resolution approving it. • Where it usually breaks: the strategy stays at slogan level with no numbers or dates, so departments cannot build anything from it. | • Require the strategy to carry numbers and dates. Target revenue, target markets, capability to build, and by when. Ambition without figures cannot be planned against. • Fix the horizon and the refresh rule, for example three years, reviewed annually and rewritten when ownership direction changes. • Add a capacity test as a formal step. The CFO on funding and the CRO on the operating model, both before approval rather than after. • Name the outputs departments must produce from it, so the link from strategy to department plan is a required step, not left to goodwill. • Keep version control tight. One approved version in circulation, with earlier versions marked superseded. | Yes | Yes
22 | Company / Leadership | Convert company strategy into the annual operating plan and priorities | Chief Executive Officer (CEO) | Trigger: When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. Action: The Chief Executive Officer (CEO) completes “Convert company strategy into the annual operating plan and priorities” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. Output/Evidence: an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. Control/Handoff: All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. Continuity/Escalation: A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. Timing: Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. | The Chief Executive Officer (CEO) completes “Convert company strategy into the annual operating plan and priorities” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. | an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. | All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. | A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. | Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | • In plain words: the CEO breaks the multi-year strategy into what the company will actually do this year, and the handful of priorities that matter most. • Starts when: the annual planning cycle opens, or the plan needs reworking after a significant forecast change. • How it runs: (1) departments submit their plans against the strategy. (2) The CEO consolidates them and resolves the clashes. (3) The CFO reconciles the whole thing to financial capacity. (4) The CEO approves the operating plan and names the priorities. (5) The plan and priorities are issued and become the baseline for reviews. • Proof it happened: an approved annual operating plan, the stated priorities for the year, and evidence it was issued to all chiefs. • Where it usually breaks: the priority list grows to twenty items, which means there are no priorities and everything competes for the same resource. | • Cap the number of priorities in the SOP. A small stated maximum forces the choices to be made rather than avoided. • Give the department plans a common template, otherwise consolidation becomes a rewriting exercise every year. • Set the planning calendar with named submission dates working back from the budget approval date. • Require the plan to state what will not be done this year. That is the part that prevents resource conflicts later. • Make the approved plan the single baseline for performance reviews, and say how a mid-year change to it is approved and recorded. | Yes | Yes
23 | Company / Leadership | Set company-wide objectives, KPIs and executive success measures | Chief Executive Officer (CEO) | Trigger: When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. Action: The Chief Executive Officer (CEO) completes “Set company-wide objectives, KPIs and executive success measures” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. Output/Evidence: an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. Control/Handoff: All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. Continuity/Escalation: A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. Timing: Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. | The Chief Executive Officer (CEO) completes “Set company-wide objectives, KPIs and executive success measures” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. | an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. | All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. | A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. | Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | • In plain words: the CEO sets the company's targets and decides how each executive's success will be measured. • Starts when: the operating plan is approved, a new executive is appointed, or targets need resetting after a major change. • How it runs: (1) company objectives are drawn from the approved plan. (2) Each is broken down to the function that owns it. (3) The CRO confirms each measure has a clear definition and a data source. (4) The CEO approves the set. (5) Targets are issued and built into executive objectives. • Proof it happened: an approved company objective and KPI set, with owners, measures, targets and data sources named. • Where it usually breaks: two functions calculate the same KPI differently, so reviews turn into arguments about the measurement rather than the result. | • Insist on a KPI definition sheet: the exact calculation, the data source, who produces it and how often. One definition, used everywhere. • Give every KPI a single accountable owner. Shared ownership of a number reliably produces no ownership. • Cascade deliberately. Say how a company KPI breaks down to department level, so the totals reconcile upwards. • Set a change-control rule for definitions, since quietly changing a calculation mid-year destroys comparability. • Keep the number of executive measures small and state the reporting frequency for each. | Yes | Yes
24 | Company / Leadership | Approve departmental plans, resource priorities and operating assumptions | Chief Executive Officer (CEO) | Trigger: When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. Action: The Chief Executive Officer (CEO) completes “Approve departmental plans, resource priorities and operating assumptions” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. Output/Evidence: an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. Control/Handoff: All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. Continuity/Escalation: A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. Timing: Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. | The Chief Executive Officer (CEO) completes “Approve departmental plans, resource priorities and operating assumptions” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. | an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. | All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. | A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. | Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | • In plain words: the CEO reviews and approves each department's plan, what resources it gets, and the assumptions it is working to. • Starts when: department plans are submitted in the planning cycle, or a department requests a material change to its plan or resources. • How it runs: (1) each chief submits their plan, resource need and assumptions. (2) The CEO tests it against the company plan and against other departments' claims on the same resource. (3) The CFO confirms affordability. (4) The CEO approves or sends it back with changes. (5) Approved plans and assumptions become the department baseline. • Proof it happened: approved department plans with resource allocations, and a written record of the assumptions each was approved on. • Where it usually breaks: assumptions are never written down, so when results miss, nobody can tell whether the plan was wrong or the execution was. | • Make the assumptions an explicit section of the plan template: volumes, prices, headcount, productivity and lead times. This is what makes later variance analysis possible. • Require plans to state resource needs in the same units the company allocates in, whether people, money or equipment, so competing claims can be compared. • Set a rule for double-counted resources. If two departments plan on the same person or asset, the CEO decides before approval, not during delivery. • State the resubmission route and its deadline, so a rejected plan does not drift. • Record what was approved, including anything cut, so departments cannot later work to their original submission. | Yes | Yes
25 | Company / Leadership | Communicate approved strategy and annual priorities to all functional chiefs | Chief Executive Officer (CEO) | Trigger: When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. Action: The Chief Executive Officer (CEO) completes “Communicate approved strategy and annual priorities to all functional chiefs” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. Output/Evidence: an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. Control/Handoff: All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. Continuity/Escalation: A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. Timing: Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | When the ownership strategy, annual planning cycle, material forecast change or executive planning review requires company-wide direction. | The Chief Executive Officer (CEO) completes “Communicate approved strategy and annual priorities to all functional chiefs” using the approved ownership direction, market outlook, project portfolio, department plans, financial capacity, workforce plan, risk register, process KPIs and functional-chief recommendations. | an approved company strategy deployment, annual operating plan, company objectives/KPIs, resource priorities or executive communication record. | All functional chiefs own their department plans and evidence; the CFO reconciles financial capacity, the CRO maintains the operating-model links, and matters reserved to ownership are submitted to the Chairman before commitment. | A Chairman-approved acting CEO may coordinate the approved plan during absence; strategic deviations, funding beyond authority and unresolved executive disagreement remain with the CEO or escalate to the Chairman. | Complete the annual plan to the approved planning calendar, review it quarterly and communicate approved changes within two working days of the decision. | • In plain words: once the strategy and yearly priorities are approved, the CEO makes sure every functional chief hears the same version and knows what it means for them. • Starts when: the plan or priorities are approved, and again whenever an approved change is made during the year. • How it runs: (1) the approved plan is turned into one communication pack. (2) The CEO briefs the chiefs together, so the same message lands at once. (3) Each chief confirms what their department will do about it. (4) The pack is issued in writing for reference. (5) Cascade to the wider team follows to an agreed timescale. • Proof it happened: the issued communication pack, a record of the briefing and attendance, and written confirmation from each chief. • Where it usually breaks: the briefing happens but nothing is issued in writing, so within weeks there are several versions of the plan in circulation. | • Require a written pack alongside the briefing. Verbal-only communication is where the versions start to diverge. • Set the deadline: communicated within a stated number of working days of approval, not whenever the diary allows. • Add a confirmation step. Each chief responds in writing with what changes in their department, which turns listening into commitment. • Define how far the cascade goes and by when, and who is responsible for each level below the chiefs. • Say what is not for wider release, and who decides, since parts of a plan may be commercially sensitive. | Yes | Yes
26 | Company / Leadership | Set the executive-governance calendar and management-review cadence | Chief Executive Officer (CEO) | Trigger: When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. Action: The Chief Executive Officer (CEO) completes “Set the executive-governance calendar and management-review cadence” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. Output/Evidence: an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. Control/Handoff: The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. Continuity/Escalation: Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. Timing: Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. | The Chief Executive Officer (CEO) completes “Set the executive-governance calendar and management-review cadence” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. | an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. | The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. | Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. | Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | • In plain words: the CEO sets the meeting rhythm for the executive team. What is reviewed daily, weekly, monthly and quarterly, and by whom. • Starts when: the governance year is set up, and then continuously as the cadence needs adjusting. • How it runs: (1) the CEO fixes the calendar of executive reviews for the year. (2) Each meeting gets a purpose, a standing agenda and a required pack. (3) Attendance and decision rights are set. (4) The calendar is issued and locked into diaries. (5) Compliance with the cadence is monitored and slippage corrected. • Proof it happened: the published executive governance calendar, standing agendas, and the meeting records showing they took place as planned. • Where it usually breaks: too many overlapping meetings review the same numbers, so the same discussion happens three times and decisions get deferred at each. | • Give each meeting in the calendar one clear purpose and one decision scope, and remove overlaps. If two meetings review the same data, merge them. • Specify the pack for each meeting and the cut-off for circulating it, with the right to return incomplete packs. • Set decision rights per meeting: what can be decided there, and what has to escalate. This is what stops circular deferral. • Add a minimum quorum and a rule for what happens when key attendees are absent. • Track cadence compliance. Repeatedly cancelled reviews should be visible to the CEO as an exception. | Yes | Yes
27 | Company / Leadership | Approve departmental mandates, accountabilities and process ownership | Chief Executive Officer (CEO) | Trigger: When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. Action: The Chief Executive Officer (CEO) completes “Approve departmental mandates, accountabilities and process ownership” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. Output/Evidence: an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. Control/Handoff: The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. Continuity/Escalation: Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. Timing: Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. | The Chief Executive Officer (CEO) completes “Approve departmental mandates, accountabilities and process ownership” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. | an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. | The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. | Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. | Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | • In plain words: the CEO writes down what each department is responsible for, what it must deliver, and which processes it owns, so the gaps and overlaps are settled. • Starts when: the organisation changes, a new function is created, or a dispute reveals that ownership of a process is unclear. • How it runs: (1) the CRO maps the processes and identifies gaps and overlaps. (2) Each chief confirms or disputes the ownership proposed. (3) The CEO decides the disputed items. (4) The mandates are approved and issued. (5) The process ownership register is kept current as the company changes. • Proof it happened: approved department mandates, a process ownership register naming a single owner for each process, and the issue record. • Where it usually breaks: the mandates are written once at a moment in time and never updated, so they stop matching how the company actually works. | • Require one named owner per process. Where two functions both touch it, name the owner and describe the other's role as a contributor. • Make the register a living document with a review trigger tied to organisation changes, not only to an annual date. • List the standard sections of a department mandate: purpose, accountabilities, processes owned, key interfaces, and what it does not cover. • Add a dispute route with a deadline, so unclear ownership gets decided rather than tolerated. • Link the mandates to the SOP library, so every process in the register can be traced to a document and an owner. | Yes | Yes
28 | Company / Leadership | Approve executive authority limits, deputies and temporary delegations | Chief Executive Officer (CEO) | Trigger: When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. Action: The Chief Executive Officer (CEO) completes “Approve executive authority limits, deputies and temporary delegations” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. Output/Evidence: an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. Control/Handoff: The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. Continuity/Escalation: Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. Timing: Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. | The Chief Executive Officer (CEO) completes “Approve executive authority limits, deputies and temporary delegations” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. | an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. | The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. | Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. | Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | • In plain words: the CEO sets how much each executive can approve on their own, names their deputies, and puts temporary authority in place when someone is away. • Starts when: the authority framework is reviewed, a role changes, or an executive will be absent and needs cover. • How it runs: (1) limits are proposed within the authority delegated by ownership. (2) The CFO confirms the money limits are workable, the CLO confirms they are valid. (3) The CEO approves and signs. (4) Deputies and temporary delegations are recorded in writing with start and end dates. (5) The framework is reissued and the previous version withdrawn. • Proof it happened: a signed executive authority schedule with a version and effective date, and dated written delegations for any temporary cover. • Where it usually breaks: cover is arranged verbally before leave, with no end date, so temporary authority quietly becomes permanent. | • Require every temporary delegation to be in writing with a start date and an end date, and to lapse automatically at the end date. • State what can never be delegated, and confirm no executive limit may exceed the authority ownership has given the CEO. • Keep a live delegation log, so at any moment it is clear who holds which authority today. • Add version control and withdrawal of the superseded schedule, since two live versions of authority limits is a serious control failure. • Cover the breach case: what happens when someone approves beyond their limit, who reviews it, and how it is ratified or reversed. | Yes | Yes
29 | Company / Leadership | Chair executive meetings and control the company decision/action register | Chief Executive Officer (CEO) | Trigger: When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. Action: The Chief Executive Officer (CEO) completes “Chair executive meetings and control the company decision/action register” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. Output/Evidence: an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. Control/Handoff: The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. Continuity/Escalation: Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. Timing: Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. | The Chief Executive Officer (CEO) completes “Chair executive meetings and control the company decision/action register” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. | an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. | The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. | Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. | Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | • In plain words: the CEO runs the executive meetings and keeps the single register of what the company has decided and what is still outstanding. • Starts when: each executive meeting approaches, and continuously afterwards while actions remain open. • How it runs: (1) the agenda and packs are issued before the meeting. (2) The CEO chairs to the agenda and decisions are taken by those authorised. (3) Decisions and actions are recorded with owner and deadline. (4) The register is updated and reissued. (5) Open and overdue items are reviewed at the next meeting until closed. • Proof it happened: circulated agendas and packs, minutes recording each decision, and a maintained decision and action register. • Where it usually breaks: several functions keep their own action lists, so there is no single answer to what the company has actually committed to. | • Make it one register for the whole company, held in a named place, with departments feeding it rather than keeping parallel lists. • Require every action to carry an owner, a deadline and a status, and treat an action with no owner as invalid. • Show overdue items separately in the pack, with an ageing view, so slippage is visible rather than buried. • Record the decision alongside the authority relied on, which makes the register useful for audit as well as follow-up. • Set the closure rule: what evidence is needed to close an item and who is allowed to close it. The owner closing their own action unchecked is a weak control. | Yes | Yes
30 | Company / Leadership | Resolve cross-department ownership, priority and authority conflicts | Chief Executive Officer (CEO) | Trigger: When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. Action: The Chief Executive Officer (CEO) completes “Resolve cross-department ownership, priority and authority conflicts” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. Output/Evidence: an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. Control/Handoff: The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. Continuity/Escalation: Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. Timing: Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | When the annual governance review, organisation change, authority issue, scheduled executive meeting or cross-department ownership conflict requires executive control. | The Chief Executive Officer (CEO) completes “Resolve cross-department ownership, priority and authority conflicts” using approved organisation structure, process/RACI records, Delegation of Authority, department mandates, legal advice, decision papers, performance facts and outstanding executive actions. | an approved executive-governance calendar, accountability assignment, authority/deputy decision, executive minutes or resolved cross-department ownership record. | The CRO maintains process and RACI consistency, the CLO controls legal authority, the CPCO controls organisation/job records, and each functional chief remains accountable for decisions within the approved mandate. | Only a Chairman-approved acting CEO may exercise CEO-reserved authority; functional deputies act only within documented limits, and unresolved authority conflicts escalate to the CEO and then the Chairman where ownership rights are affected. | Hold executive reviews to the weekly/monthly calendar, issue decisions and actions within one working day, and acknowledge material authority conflicts the same working day. | • In plain words: when two departments disagree over who owns something, whose work comes first, or who has the right to decide, the CEO settles it. • Starts when: a cross-department conflict over ownership, priority or authority has not been resolved between the chiefs concerned. • How it runs: (1) the conflict is submitted in writing with both positions and the business impact. (2) The CRO confirms what the process ownership register says. (3) The CLO advises where authority formally sits, if relevant. (4) The CEO decides and sets the priority. (5) The decision is recorded and, where it exposes a gap, the mandates are updated. • Proof it happened: the written submission, the recorded CEO decision, and any resulting change to mandates or the authority framework. • Where it usually breaks: the same conflict is decided repeatedly case by case, because the underlying mandate is never corrected. | • Require a written submission with both positions and the cost of delay, so the decision is made on impact rather than on who complained loudest. • Put a time limit on it. Escalated within a stated number of days, decided within a stated number. • State that work continues on the agreed default while the conflict is open, so delivery does not stall. • Add a root-cause step. A conflict that recurs triggers a review of the mandates or the authority framework rather than another one-off ruling. • Log the outcomes, because the pattern shows exactly where the operating model is unclear. | Yes | Yes
31 | Company / Leadership | Review the integrated company performance dashboard and material exceptions | Chief Executive Officer (CEO) | Trigger: When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. Action: The Chief Executive Officer (CEO) completes “Review the integrated company performance dashboard and material exceptions” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. Output/Evidence: an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. Control/Handoff: Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. Continuity/Escalation: A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. Timing: Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. | The Chief Executive Officer (CEO) completes “Review the integrated company performance dashboard and material exceptions” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. | an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. | Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. | A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. | Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | • In plain words: the CEO looks at one combined view of how the company is doing and concentrates on the things that are off track. • Starts when: the daily exception check, weekly operating review, or monthly performance close falls due. • How it runs: (1) each chief certifies their own data. (2) The CFO reconciles the financial results. (3) The CRO maintains the KPI definitions so everyone measures the same way. (4) The CEO reviews the dashboard and works through the exceptions. (5) Decisions and corrective actions go onto the company action register. • Proof it happened: the dashboard for the period, certified source data, and the recorded decisions and actions arising. • Where it usually breaks: the dashboard reports everything equally, so genuine exceptions are lost in a wall of green and amber. | • Set tolerance bands per KPI so the dashboard flags exceptions automatically. Reviewing everything is the same as reviewing nothing. • Require data certification by each chief before the pack is issued, with a stated cut-off time. • Separate the layers in the SOP: what is checked daily, what weekly, what monthly. The same measure should not appear at every level. • State one source of truth per KPI, ideally the system of record, so manual spreadsheets do not compete with it. • Require every exception to leave the meeting with an owner, an action and a date, or an explicit decision to accept it. | Yes | Yes
32 | Company / Leadership | Review project portfolio progress, profitability, cash and delivery exposure | Chief Executive Officer (CEO) | Trigger: When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. Action: The Chief Executive Officer (CEO) completes “Review project portfolio progress, profitability, cash and delivery exposure” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. Output/Evidence: an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. Control/Handoff: Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. Continuity/Escalation: A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. Timing: Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. | The Chief Executive Officer (CEO) completes “Review project portfolio progress, profitability, cash and delivery exposure” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. | an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. | Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. | A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. | Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | • In plain words: the CEO reviews the whole set of live projects together, looking at progress, whether they are making money, the cash they consume and where delivery risk is building. • Starts when: the project portfolio review falls due, or a project passes a gate or breaches a tolerance. • How it runs: (1) the COO submits progress and delivery status. (2) The CFO reports margin, cash and billing position per project. (3) Risks and dependencies are consolidated across projects. (4) The CEO ranks the exposures and directs action. (5) Actions are tracked to the next review. • Proof it happened: the portfolio review pack, per-project margin and cash figures, and the recorded decisions and actions. • Where it usually breaks: progress is reported by percentage complete with no link to cost or cash, so a project can look healthy while its margin is disappearing. | • Require progress, cost and cash on the same page per project. Physical progress alone hides margin erosion. • Standardise how percentage complete is calculated, since inconsistent measurement makes the whole portfolio view unreliable. • Set the exception triggers with numbers: margin slipping by more than a stated amount, delay beyond a stated period, unbilled work above a limit. • Show cross-project dependencies, particularly shared people and equipment, because that is where one delay becomes three. • Add a watch list with a defined entry and exit, so troubled projects get sustained attention rather than one mention. | Yes | Yes
33 | Company / Leadership | Direct company and project recovery plans and corrective priorities | Chief Executive Officer (CEO) | Trigger: When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. Action: The Chief Executive Officer (CEO) completes “Direct company and project recovery plans and corrective priorities” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. Output/Evidence: an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. Control/Handoff: Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. Continuity/Escalation: A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. Timing: Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. | The Chief Executive Officer (CEO) completes “Direct company and project recovery plans and corrective priorities” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. | an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. | Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. | A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. | Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | • In plain words: when the company or a project is off track, the CEO decides what the recovery plan is and what gets fixed first. • Starts when: performance breaches an agreed tolerance, a project enters recovery, or the ownership review directs corrective priorities. • How it runs: (1) the cause is established rather than assumed. (2) The responsible chief proposes a recovery plan with actions, owners and dates. (3) The CFO confirms the cost of recovery and the effect on the forecast. (4) The CEO approves the plan and sets the priority order. (5) Progress is reviewed at a shorter interval until recovery is achieved. • Proof it happened: an approved recovery plan with milestones, and the review records showing progress against it. • Where it usually breaks: recovery plans list activity rather than measurable milestones, so it is impossible to say whether recovery is working. | • Require a root-cause statement before the plan. A recovery plan built on the wrong cause simply consumes more money. • Insist on measurable milestones with dates, and state that activity lists are not accepted as recovery plans. • Increase the review frequency automatically while recovery is live, and say who has the authority to declare recovery complete. • Require the cost of recovery to be quantified and reflected in the forecast, so the financial effect is not deferred. • Add an escalation point: if recovery misses its own milestones twice, the matter goes up rather than round again. | Yes | Yes
34 | Company / Leadership | Approve executive hold, recovery, restart or closure decisions within authority | Chief Executive Officer (CEO) | Trigger: When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. Action: The Chief Executive Officer (CEO) completes “Approve executive hold, recovery, restart or closure decisions within authority” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. Output/Evidence: an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. Control/Handoff: Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. Continuity/Escalation: A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. Timing: Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. | The Chief Executive Officer (CEO) completes “Approve executive hold, recovery, restart or closure decisions within authority” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. | an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. | Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. | A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. | Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | • In plain words: the CEO decides whether to pause work, put it into recovery, restart it, or close it down, within the limits the owners have set. • Starts when: a project or activity is unsafe, unfunded, unprofitable, blocked, or the conditions for restarting are met. • How it runs: (1) the case for hold, restart or closure is submitted with evidence. (2) The CFO sets out the financial and contractual consequences. (3) The CLO advises on client and contractual exposure. (4) The CEO decides within authority, or refers it up if beyond. (5) The decision is issued with the conditions attached to it. • Proof it happened: a signed hold, restart or closure decision listing the conditions, and the notifications issued to those affected. • Where it usually breaks: work is held informally with no formal decision, so costs keep accruing and the client is never properly notified. | • Make the four decisions distinct in the SOP: hold, recover, restart, close. Each needs its own conditions and its own evidence. • Require restart conditions to be written at the moment of the hold, so restarting is a check rather than a fresh argument. • State the contractual and client notification steps for each, with who issues them and within what period. • Cover the cost side: what spending stops immediately on hold, what continues, and who controls demobilised resources. • State the authority limits in figures, and what must be referred to the Chairman. | Yes | Yes
35 | Company / Leadership | Report company performance, risks and decisions to the Chairman | Chief Executive Officer (CEO) | Trigger: When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. Action: The Chief Executive Officer (CEO) completes “Report company performance, risks and decisions to the Chairman” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. Output/Evidence: an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. Control/Handoff: Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. Continuity/Escalation: A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. Timing: Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | When the daily exception review, weekly operating review, monthly performance close, project gate or corrective-action deadline requires executive evaluation. | The Chief Executive Officer (CEO) completes “Report company performance, risks and decisions to the Chairman” using reconciled company and project dashboards, finance results, sales pipeline, technical/procurement/project status, people metrics, legal and risk matters, KPI exceptions and corrective-action evidence. | an executive performance decision, recovery mandate, project-portfolio direction, approved corrective action or Chairman performance report. | Functional chiefs certify their data, the CFO reconciles financial results, the CRO governs KPI definitions and action traceability, and the CEO records decisions without replacing the responsible chief's delivery accountability. | A formally appointed acting CEO may chair routine reviews; material loss, unsafe work, insolvency risk, contract default, client termination or persistent executive nonperformance escalates to the CEO and Chairman without waiting for the next review. | Review critical exceptions daily, operating performance weekly, company performance monthly and strategic performance quarterly; issue urgent recovery ownership within one working day. | • In plain words: the CEO gives the Chairman a straight account of how the company is performing, what the risks are and what has been decided. • Starts when: the scheduled reporting date arrives, or a material event occurs that the Chairman must know about immediately. • How it runs: (1) the CEO consolidates one company position with the CFO. (2) Figures are verified before submission. (3) The report covers performance, risk, decisions taken under CEO authority, and matters needing ownership decisions. (4) It is submitted to the calendar. (5) Ownership questions and directions are logged and answered. • Proof it happened: the submitted report with its date, the verified supporting data, and the record of ownership direction in response. • Where it usually breaks: the report presents good news fully and bad news late, which is what destroys ownership confidence when it eventually surfaces. | • Standardise the report format so it is comparable period to period, and require both plan and actual against every headline number. • Define immediate-notification events separately from the routine report: material loss, serious incident, regulator contact, loss of a major client, funding risk. • Require decisions taken under CEO authority to be listed, so the Chairman can see how delegated authority is being used. • State the submission deadline relative to the ownership meeting date, with enough time for papers to be read. • Add a section for matters requiring an ownership decision, phrased as a clear request, so meetings decide rather than discuss. | Yes | Yes
36 | Company / Leadership | Approve bid/no-bid decisions for major and strategic opportunities | Chief Executive Officer (CEO) | Trigger: When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. Action: The Chief Executive Officer (CEO) completes “Approve bid/no-bid decisions for major and strategic opportunities” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. Output/Evidence: an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. Control/Handoff: The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. Continuity/Escalation: No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. Timing: Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. | The Chief Executive Officer (CEO) completes “Approve bid/no-bid decisions for major and strategic opportunities” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. | an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. | The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. | No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. | Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | • In plain words: the CEO decides whether the company chases a major or strategically important opportunity, or lets it go. • Starts when: a strategic opportunity or major tender is identified and a bid or no-bid decision is needed. • How it runs: (1) the CMO presents the opportunity and the client position. (2) The CTO assesses the technical fit and capacity to deliver. (3) The CFO reviews the pricing basis, credit and cash implications. (4) The CLO flags contract and risk terms. (5) The CEO decides bid or no-bid and records the reason. • Proof it happened: a recorded bid or no-bid decision with the reason and conditions, and the resulting pursuit plan. • Where it usually breaks: the company bids by default and reviews the decision only after losing, so effort is spread across work it was never going to win. | • Set the criteria that trigger a formal CEO decision: value above a stated figure, a new client type, a new geography, or unusual contract terms. • Use a scored checklist covering strategic fit, capacity, margin, client credit and risk terms, and record the score with the decision. • Make no-bid a respectable, recorded outcome with its reason captured, so the pattern can be reviewed later. • Require capacity confirmation before bidding, so a win does not immediately create a delivery problem. • Add a win and loss review that feeds back into the criteria, which is how the decision quality actually improves. | Yes | Yes
37 | Company / Leadership | Approve integrated commercial strategy and exceptions within CEO authority | Chief Executive Officer (CEO) | Trigger: When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. Action: The Chief Executive Officer (CEO) completes “Approve integrated commercial strategy and exceptions within CEO authority” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. Output/Evidence: an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. Control/Handoff: The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. Continuity/Escalation: No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. Timing: Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. | The Chief Executive Officer (CEO) completes “Approve integrated commercial strategy and exceptions within CEO authority” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. | an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. | The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. | No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. | Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | • In plain words: the CEO sets the commercial approach across sales, pricing and contracting, and decides the exceptions that sit above functional limits. • Starts when: the commercial strategy is set or revised, or an exception is requested that exceeds a chief's authority. • How it runs: (1) the CMO proposes the commercial approach with market evidence. (2) The CTO retains quotation approval and the CFO retains credit and pricing control within their limits. (3) Exceptions above those limits are submitted with the reason and the risk. (4) The CEO approves within CEO authority. (5) Approved exceptions are recorded and monitored for pattern. • Proof it happened: an approved commercial strategy, and a log of approved exceptions with the reason and the value at risk. • Where it usually breaks: exceptions become routine, so the approved pricing and credit rules exist on paper while the real rules are whatever gets approved. | • Log every exception with the reason and the value, and report the volume of exceptions to the CEO. A high volume means the underlying rule is wrong and should be changed. • Confirm functional approvals remain with the CTO for quotations, the CFO for credit and the CLO for contract terms. The CEO decides above their limits and does not bypass them. • Set discount and payment-term boundaries in figures, with the approval level for each band. • Require an exception to state its expiry, so a one-off concession does not become a standing arrangement with a client. • Add a periodic review of granted exceptions against actual outcome, particularly on margin and collection. | Yes | Yes
38 | Company / Leadership | Review pipeline quality, conversion, backlog and strategic revenue exposure | Chief Executive Officer (CEO) | Trigger: When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. Action: The Chief Executive Officer (CEO) completes “Review pipeline quality, conversion, backlog and strategic revenue exposure” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. Output/Evidence: an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. Control/Handoff: The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. Continuity/Escalation: No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. Timing: Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. | The Chief Executive Officer (CEO) completes “Review pipeline quality, conversion, backlog and strategic revenue exposure” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. | an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. | The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. | No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. | Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | • In plain words: the CEO checks the health of the sales pipeline. Is there enough work coming, is it the right kind, is it converting, and how much of future revenue depends on a few clients. • Starts when: the pipeline review falls due, or backlog or conversion moves outside its normal range. • How it runs: (1) the CMO reports pipeline by stage, with age and probability. (2) Conversion rates and backlog cover are calculated on a consistent basis. (3) Concentration by client, sector and geography is set out. (4) The CEO reviews the exposure and directs where effort goes. (5) Actions are tracked to the next review. • Proof it happened: the pipeline and backlog report, the conversion analysis, and the recorded decisions on where to focus. • Where it usually breaks: the pipeline is measured only by total value, so it looks strong while being made up of stale, low-probability opportunities. | • Define the pipeline stages and the entry rule for each, so probability weighting means the same thing to everyone. • Require age analysis. Stale opportunities should be shown separately or removed, otherwise the pipeline total is fiction. • Report backlog as months of cover against the plan, not only as a value, since cover is what tells you about the coming period. • Set concentration limits or warning levels by client and sector, with an escalation when they are exceeded. • Name the system of record for pipeline data and forbid parallel spreadsheets, or the figures will never agree. | Yes | Yes
39 | Company / Leadership | Lead executive engagement and resolution for strategic client escalations | Chief Executive Officer (CEO) | Trigger: When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. Action: The Chief Executive Officer (CEO) completes “Lead executive engagement and resolution for strategic client escalations” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. Output/Evidence: an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. Control/Handoff: The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. Continuity/Escalation: No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. Timing: Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. | The Chief Executive Officer (CEO) completes “Lead executive engagement and resolution for strategic client escalations” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. | an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. | The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. | No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. | Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | • In plain words: when an important client is seriously unhappy, the CEO takes the lead in dealing with them and getting to a resolution. • Starts when: a strategic client escalates, or an issue passes a severity or value threshold, or a relationship is at risk. • How it runs: (1) the facts are established with the CMO and the delivery function before contact. (2) The CLO advises on contractual position and anything that should not be said. (3) The CEO engages the client at the right level. (4) A resolution plan with commitments and dates is agreed. (5) Delivery of those commitments is tracked and the client is kept informed. • Proof it happened: the escalation record, the agreed resolution plan with dates, and evidence of the commitments being met. • Where it usually breaks: commitments are made in the meeting to calm the client and never handed to anyone to deliver, so the same escalation returns worse. | • Define the escalation thresholds that bring the CEO in, so the CEO is not drawn into every routine complaint. • Require a fact and contract briefing before client contact, because commitments made without the contractual position are expensive. • Make every commitment given to a client a tracked action with an owner and a date, recorded the same day. • Set a same-day acknowledgement rule for critical escalations, separate from the time needed to resolve them. • Add a closure step with the client confirming resolution, and a review of the cause so it is fixed rather than just settled. | Yes | Yes
40 | Company / Leadership | Approve contract-award readiness after all functional clearances are complete | Chief Executive Officer (CEO) | Trigger: When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. Action: The Chief Executive Officer (CEO) completes “Approve contract-award readiness after all functional clearances are complete” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. Output/Evidence: an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. Control/Handoff: The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. Continuity/Escalation: No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. Timing: Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | When a strategic opportunity, major tender, commercial exception, executive client escalation or contract-award gate requires company commitment. | The Chief Executive Officer (CEO) completes “Approve contract-award readiness after all functional clearances are complete” using the CMO opportunity and client record, CTO technical/quotation approval, estimator cost basis, CFO credit and financial review, CLO contract advice, CPO supply assessment and COO delivery-capacity confirmation. | an approved pursuit decision, executive commercial boundary, strategic-client action, contract-award readiness decision or controlled exception record. | The CMO owns the client and CRM process, the CTO retains quotation approval, the CLO retains client-contract control, the CFO retains credit and financial control, the CPO retains PO/subcontract authority and the COO retains delivery planning; the CEO decides only the integrated commitment or exception within authority. | No tender, price, contract, credit, procurement or delivery commitment may bypass the responsible functional approval; matters above CEO authority or outside approved risk appetite escalate to the Chairman before submission or signature. | Complete bid and award decisions before the external deadline, acknowledge critical client escalations the same working day and record the approved commercial boundary before any commitment. | • In plain words: before the company signs a contract, the CEO confirms every function has done its checks and cleared it. • Starts when: an award is imminent and the functional clearances are complete, or a clearance is being sought as an exception. • How it runs: (1) the CLO clears the contract terms. (2) The CFO clears pricing, credit and cash terms. (3) The CTO clears the technical scope and the CPO clears the supply commitments. (4) The COO confirms delivery capacity. (5) The CEO confirms award readiness and the contract is signed by the authorised signatory. • Proof it happened: a completed clearance record showing each function's sign-off, the CEO award-readiness approval, and the executed contract. • Where it usually breaks: signature happens under client deadline pressure with clearances outstanding, and the risks are discovered during delivery. | • Use a single clearance checklist that must be complete before signature, with each function signing its own line and a date against it. • Set a rule for outstanding clearances: either the deadline is renegotiated, or the specific risk is accepted in writing by the CEO. Silence is not an option. • Separate award readiness from signature authority in the SOP, and name who is authorised to sign at each value band. • Require a check that the final signed version matches what was cleared, since late client changes are common. • Add the post-signature handover: who receives the contract, and how the delivery team is briefed on the obligations it contains. | Yes | Yes
41 | Company / Leadership | Approve the management budget before ownership submission | Chief Executive Officer (CEO) | Trigger: When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. Action: The Chief Executive Officer (CEO) completes “Approve the management budget before ownership submission” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. Output/Evidence: an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. Control/Handoff: The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. Continuity/Escalation: An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. Timing: Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. | The Chief Executive Officer (CEO) completes “Approve the management budget before ownership submission” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. | an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. | The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. | An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. | Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | • In plain words: the CEO reviews and approves the budget the management team has built, before it goes to the owners for final approval. • Starts when: the budget cycle reaches the point where departmental budgets have been consolidated. • How it runs: (1) the CFO consolidates the departmental budgets and tests the assumptions. (2) The CEO challenges each department's numbers against the operating plan. (3) Gaps are closed by changing plans, not by adjusting the numbers to fit. (4) The CEO approves the management budget. (5) It is submitted to the Chairman with a recommendation. • Proof it happened: the CEO-approved management budget with its assumptions, and the submission to ownership. • Where it usually breaks: the gap to target is closed by trimming numbers across the board rather than changing what the company will actually do. | • Require every budget change made during the challenge to be traceable to a plan change, so the budget stays deliverable rather than merely acceptable. • State that the management budget and the ownership submission are two separate approvals with two separate records. • Put the internal deadlines in the SOP, working back from the ownership approval date, and name who chases them. • List the mandatory pack contents: assumptions, headcount, capital requests, sensitivity and prior year comparison. • Say what departments may see of other departments' budgets, since this affects how openly the challenge can be run. | Yes | Yes
42 | Company / Leadership | Approve company forecasts, reforecasts and financial recovery assumptions | Chief Executive Officer (CEO) | Trigger: When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. Action: The Chief Executive Officer (CEO) completes “Approve company forecasts, reforecasts and financial recovery assumptions” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. Output/Evidence: an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. Control/Handoff: The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. Continuity/Escalation: An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. Timing: Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. | The Chief Executive Officer (CEO) completes “Approve company forecasts, reforecasts and financial recovery assumptions” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. | an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. | The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. | An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. | Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | • In plain words: during the year the CEO approves the updated view of where the numbers will land, and the assumptions behind any recovery in them. • Starts when: the monthly forecast cycle runs, or an event happens that makes the current forecast unrealistic. • How it runs: (1) the CFO prepares the forecast from actuals plus the latest departmental view. (2) Changed assumptions are stated explicitly against the last version. (3) Recovery assumptions are tested for realism, not accepted on optimism. (4) The CEO approves the forecast. (5) It is reported to the Chairman with the variance to budget explained. • Proof it happened: the approved forecast with a version and date, the assumption changes listed, and the variance explanation. • Where it usually breaks: recovery is assumed in the last quarter every time, so the forecast holds up until it suddenly cannot. | • Require each forecast to show what changed since the last version and why. A forecast without a bridge is impossible to review. • Set a realism test on recovery assumptions, such as evidence of secured work or a signed variation, rather than intent. • Track forecast accuracy over time by comparing each forecast against outcome, and report it. This is what disciplines forecasting. • Fix the cycle and the cut-off dates, and state who may change a submitted departmental forecast. • State the threshold at which a reforecast must be triggered mid-cycle instead of waiting for the monthly run. | Yes | Yes
43 | Company / Leadership | Review cash flow, working capital, collections and payment priorities | Chief Executive Officer (CEO) | Trigger: When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. Action: The Chief Executive Officer (CEO) completes “Review cash flow, working capital, collections and payment priorities” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. Output/Evidence: an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. Control/Handoff: The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. Continuity/Escalation: An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. Timing: Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. | The Chief Executive Officer (CEO) completes “Review cash flow, working capital, collections and payment priorities” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. | an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. | The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. | An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. | Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | • In plain words: the CEO keeps a close eye on the cash. What is coming in, what is going out, what customers owe, and who gets paid first when cash is tight. • Starts when: the weekly cash review falls due, daily during a tight period, or when a collection or payment problem escalates. • How it runs: (1) the CFO presents the cash position and a forward rolling forecast. (2) Overdue receivables are reviewed by client with the collection action stated. (3) Committed outflows are set against expected inflows. (4) The CEO sets the payment priorities where cash is constrained. (5) Payment release stays with Finance controls under the approved priorities. • Proof it happened: the cash review record, the receivables ageing with actions, and the approved payment priorities. • Where it usually breaks: collections are treated as a Finance chore rather than a company priority, so overdue debt grows while everyone reports being busy. | • Give collections a named owner outside Finance as well, usually the client-facing chief, because the relationship is what actually unlocks payment. • Require a rolling forward cash forecast in the pack, covering a stated number of weeks, updated weekly. • Set escalation triggers on receivables by age band, with defined actions such as stopping work or issuing a legal notice. • Keep the separation of duties explicit. The CEO sets priorities, Finance verifies and releases payment. The SOP should not blur this. • Define what puts the company into daily cash monitoring, and who declares it and stands it down. | Yes | Yes
44 | Company / Leadership | Authorise commitments and exceptions above functional limits within CEO authority | Chief Executive Officer (CEO) | Trigger: When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. Action: The Chief Executive Officer (CEO) completes “Authorise commitments and exceptions above functional limits within CEO authority” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. Output/Evidence: an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. Control/Handoff: The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. Continuity/Escalation: An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. Timing: Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. | The Chief Executive Officer (CEO) completes “Authorise commitments and exceptions above functional limits within CEO authority” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. | an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. | The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. | An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. | Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | • In plain words: when a commitment is bigger than a department chief may approve, it comes to the CEO, who can authorise it up to the limit the owners have set. • Starts when: a purchase, contract, payment or commitment exceeds the responsible chief's approval limit. • How it runs: (1) the requesting chief submits the request with the reason and the alternatives considered. (2) The CFO confirms the budget, the cash effect and that the process was followed. (3) The CPO confirms procurement was competitive where required. (4) The CEO approves, reduces or rejects within CEO authority. (5) Anything beyond CEO authority is submitted to the Chairman. • Proof it happened: the approved authorisation record showing the value, the reason and the authority relied on. • Where it usually breaks: approval is given after the commitment is already made, which turns the control into paperwork. | • State plainly that approval comes before commitment, and define how a genuine emergency is handled and ratified afterwards. • Require the request to show budget availability and whether it was competitively sourced, so the CEO is not approving in the dark. • Set the authority bands as figures, and forbid splitting a commitment into smaller parts to stay under a limit. Name who checks for that. • Keep one authorisation log with value, requester, reason and approver, so above-limit spending can be reviewed as a whole. • Add a periodic review of above-limit approvals. Frequent exceptions usually mean the limits themselves need resetting. | Yes | Yes
45 | Company / Leadership | Approve investment and funding business cases for Chairman consideration | Chief Executive Officer (CEO) | Trigger: When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. Action: The Chief Executive Officer (CEO) completes “Approve investment and funding business cases for Chairman consideration” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. Output/Evidence: an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. Control/Handoff: The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. Continuity/Escalation: An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. Timing: Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | When the budget cycle, monthly forecast, weekly cash review, above-limit commitment request or investment proposal requires executive financial direction. | The Chief Executive Officer (CEO) completes “Approve investment and funding business cases for Chairman consideration” using CFO-certified budgets, forecasts, cash-flow and working-capital reports, project profitability, funding options, risk analysis, business case, authority limits and relevant functional recommendations. | an approved management budget/forecast, cash or working-capital action, above-limit executive authorisation, investment recommendation or Chairman funding paper. | The CFO owns accounting, treasury, payment verification and financial accuracy; the CEO approves company priorities or authorised exceptions without releasing payments, and ownership-reserved funding and commitments are submitted to the Chairman. | An acting CEO may approve only within written temporary authority; payment release remains with Finance controls, and liquidity, fraud, covenant or solvency threats escalate immediately to the CEO and Chairman. | Review cash weekly and during critical periods daily, approve monthly forecasts to the close calendar, and decide complete above-limit requests within two working days. | • In plain words: when the company wants to invest in something significant or needs funding, the CEO prepares and approves the case before the Chairman sees it. • Starts when: an investment need is identified, or funding is required beyond what the approved budget covers. • How it runs: (1) the sponsoring function drafts the case with the options considered. (2) The CFO builds the financial model, funding options and return. (3) The CLO reviews the structure and any security. (4) The CEO tests the case and approves it for ownership submission. (5) The Chairman decides, and the outcome is recorded. • Proof it happened: the CEO-approved business case, the supporting financial model, and the ownership submission record. • Where it usually breaks: only one option is presented, with the do-nothing case left out, so ownership is asked to rubber-stamp rather than choose. | • Make more than one option compulsory, including the do-nothing option and its consequences. • Fix the appraisal method so cases are comparable: the same payback or return measure, the same assumptions on cost of money, stated in the template. • Require a sensitivity view showing what happens if the key assumption is wrong by a stated margin. • Name who is accountable for delivering the benefits after approval, not just for making the case. • Add a post-implementation review at a set interval, comparing actual against the case, and feed the findings into future submissions. | Yes | Yes
46 | Company / Leadership | Approve executive project-mobilisation readiness and strategic conditions | Chief Executive Officer (CEO) | Trigger: When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. Action: The Chief Executive Officer (CEO) completes “Approve executive project-mobilisation readiness and strategic conditions” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. Output/Evidence: an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. Control/Handoff: The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. Continuity/Escalation: Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. Timing: Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. | The Chief Executive Officer (CEO) completes “Approve executive project-mobilisation readiness and strategic conditions” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. | an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. | The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. | Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. | Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | • In plain words: before a newly won project starts, the CEO confirms the company is genuinely ready to mobilise and sets any conditions. • Starts when: a project is awarded and mobilisation approval is requested, or a mobilisation gate is reached. • How it runs: (1) the COO submits the mobilisation readiness position. (2) The CTO confirms the technical scope and design readiness, the CPO the supply chain, the CFO the funding and billing setup. (3) QHSE confirms the safety and site requirements. (4) The CEO approves mobilisation, with conditions where readiness is partial. (5) Conditions are tracked to closure with dates. • Proof it happened: an approved mobilisation decision listing the conditions, and the readiness evidence behind it. • Where it usually breaks: mobilisation is approved with conditions and the conditions are never closed, which is where early project losses come from. | • Use a mobilisation readiness checklist with a named owner per line: contract, scope, design, procurement, people, plant, safety, billing and insurance. • Treat conditional approval seriously. Every condition needs an owner and a closure date, and the project reports on them until they are shut. • State what may not start until specific conditions are closed, particularly anything involving safety or permits. • Require the billing and payment setup to be in place before mobilisation, since early cash discipline determines the project's cash profile. • Add a short post-mobilisation review at a set number of weeks, to catch the gaps the checklist missed. | Yes | Yes
47 | Company / Leadership | Review critical project progress, delay, margin and recovery requirements | Chief Executive Officer (CEO) | Trigger: When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. Action: The Chief Executive Officer (CEO) completes “Review critical project progress, delay, margin and recovery requirements” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. Output/Evidence: an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. Control/Handoff: The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. Continuity/Escalation: Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. Timing: Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. | The Chief Executive Officer (CEO) completes “Review critical project progress, delay, margin and recovery requirements” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. | an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. | The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. | Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. | Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | • In plain words: the CEO reviews the projects that matter most, focusing on delay, margin and what it will take to recover them. • Starts when: the critical project review falls due, or a project breaches a delay, cost or margin tolerance. • How it runs: (1) the COO reports progress, delay causes and the critical path. (2) The CFO reports margin, cash and the value of unbilled or disputed work. (3) The CTO reports technical and design issues driving delay. (4) The CEO decides the recovery actions and the priority for resources. (5) Actions are tracked at a shortened interval until resolved. • Proof it happened: the critical project review record, the margin and delay data behind it, and the recorded recovery decisions. • Where it usually breaks: delay is reported without its cause, so the same recovery actions are tried repeatedly with no effect. | • Define what makes a project critical: value, client, delay, margin slippage or safety exposure. Name the criteria rather than leaving it to selection. • Require a stated cause per delay, categorised, for example client-driven, design, procurement, resource or weather. That categorisation is what enables entitlement claims. • Link delay to entitlement in the SOP. Where the client caused it, the notice and claim steps must be triggered within the contractual time limit. • Show unbilled and disputed work per project, since that is often larger than the margin under discussion. • Set a weekly cadence while a project is critical, and a clear rule for exiting critical status. | Yes | Yes
48 | Company / Leadership | Resolve competing project-resource and organisational priorities | Chief Executive Officer (CEO) | Trigger: When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. Action: The Chief Executive Officer (CEO) completes “Resolve competing project-resource and organisational priorities” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. Output/Evidence: an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. Control/Handoff: The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. Continuity/Escalation: Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. Timing: Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. | The Chief Executive Officer (CEO) completes “Resolve competing project-resource and organisational priorities” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. | an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. | The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. | Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. | Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | • In plain words: when several projects need the same people or equipment at the same time, the CEO decides who gets them. • Starts when: a resource clash is escalated because two or more projects or functions need the same resource in the same period. • How it runs: (1) the competing needs are set out with dates and the impact of not getting the resource. (2) The COO provides the resource position across all projects. (3) The CFO shows the financial and contractual consequences of each option. (4) The CEO allocates and states the priority. (5) The affected projects update their plans and any client commitments. • Proof it happened: the recorded allocation decision with its reasons, and the updated project plans reflecting it. • Where it usually breaks: allocation is decided verbally and project plans are never updated, so two projects continue planning on the same crew. | • Require a single resource view across all projects as the basis for the decision. Without it, allocation is done on advocacy. • Ask for the impact of not getting the resource, in days and money, so competing claims can be compared on the same footing. • Make plan updates a mandatory step after allocation, with a deadline, and name who verifies it happened. • Set priority rules in advance, for example safety-critical work, contractual milestones with damages, then margin. This reduces case-by-case argument. • Log the clashes. Repeated clashes on the same resource are a capacity problem for the workforce plan, not a scheduling problem. | Yes | Yes
49 | Company / Leadership | Decide major delivery, quality, safety and client exceptions within authority | Chief Executive Officer (CEO) | Trigger: When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. Action: The Chief Executive Officer (CEO) completes “Decide major delivery, quality, safety and client exceptions within authority” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. Output/Evidence: an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. Control/Handoff: The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. Continuity/Escalation: Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. Timing: Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. | The Chief Executive Officer (CEO) completes “Decide major delivery, quality, safety and client exceptions within authority” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. | an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. | The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. | Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. | Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | • In plain words: the CEO decides the significant one-off calls on delivery, quality, safety and client matters that are too big for the functions to settle. • Starts when: a serious delivery, quality, safety or client exception is escalated beyond functional authority. • How it runs: (1) the exception is submitted with the facts, the options and the risk of each. (2) QHSE advises on safety and the CTO on technical acceptability, with neither overridden informally. (3) The CLO advises on contractual and legal exposure. (4) The CEO decides within authority. (5) The decision, its conditions and its rationale are recorded and communicated. • Proof it happened: the exception record with the decision, the conditions attached, and the technical or safety advice relied on. • Where it usually breaks: commercial pressure quietly overrides a technical or safety objection, and the objection never appears in the record. | • State that safety and technical objections cannot be overruled informally. If the CEO decides against advice, the advice and the reason must both be recorded. • Keep the stop-work right absolute and unambiguous. Imminent danger stops work immediately with no approval needed, and no one may reverse that without the safety clearance. • Define the escalation thresholds by value and severity, so functions know exactly what they must escalate. • Require a rationale in the record, since these decisions are the ones examined most closely after an incident or a dispute. • Add a review of recurring exceptions, because a pattern points to a process or capability problem to fix upstream. | Yes | Yes
50 | Company / Leadership | Approve executive handover, DLP and project-closeout gate decisions | Chief Executive Officer (CEO) | Trigger: When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. Action: The Chief Executive Officer (CEO) completes “Approve executive handover, DLP and project-closeout gate decisions” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. Output/Evidence: an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. Control/Handoff: The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. Continuity/Escalation: Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. Timing: Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | When a project award, mobilisation gate, critical project review, resource conflict, serious site exception or handover/closeout gate requires executive direction. | The Chief Executive Officer (CEO) completes “Approve executive handover, DLP and project-closeout gate decisions” using COO project recommendation, approved contract and IFC status, budget and cash information, procurement readiness, resource plan, QHSE status, client/consultant commitments, risk register and recovery alternatives. | an approved mobilisation direction, executive project priority, recovery/exception decision, handover gate decision or project-portfolio action record. | The COO owns project delivery, the CTO owns technical release, the CPO owns procurement commitments, the CFO owns financial controls, the CLO owns notices/contract advice and QHSE controls safety; the CEO resolves the integrated company decision within authority. | Operational command remains with the COO and Project Engineer; imminent danger requires immediate stop-work under QHSE authority, while material loss, client termination, contract default or project abandonment escalates to the CEO and Chairman. | Review critical projects weekly, decide complete mobilisation and stage-gate submissions within two working days, and respond immediately to serious safety, client or business-continuity threats. | • In plain words: the CEO signs off the end of a project. Handing it to the client, entering the defects period, and finally closing it out. • Starts when: a project reaches handover, enters or completes the defect liability period, or is ready for financial closeout. • How it runs: (1) the COO submits the completion and handover evidence. (2) The CTO confirms technical completion and the CLO the contractual position on completion. (3) The CFO confirms final account, retention and outstanding claims. (4) QHSE confirms documentation and any outstanding obligations. (5) The CEO approves the gate decision and any conditions carried forward. • Proof it happened: signed handover and closeout gate approvals, the completion certificate, and the final account and retention position. • Where it usually breaks: the project is treated as finished at handover, while retention, claims and defect obligations sit unmanaged for months. | • Separate the three gates in the SOP: handover, end of defects period, and financial closeout. They happen at different times and are often collapsed into one. • Require a live retention and claims register per project, with an owner, since money left on the table after handover is rarely chased by anyone. • Set who is responsible during the defects period and how defect costs are budgeted, because the delivery team has usually moved on. • Make the document handover explicit: as-built drawings, warranties, manuals and test records, with the client's acknowledgement. • Add a lessons-learned step tied to the closeout gate, and require the output to reach the functions that can act on it. | Yes | Yes
51 | Company / Leadership | Approve company organisation design and workforce priorities | Chief Executive Officer (CEO) | Trigger: When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. Action: The Chief Executive Officer (CEO) completes “Approve company organisation design and workforce priorities” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. Output/Evidence: an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. Control/Handoff: The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. Continuity/Escalation: Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. Timing: Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. | The Chief Executive Officer (CEO) completes “Approve company organisation design and workforce priorities” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. | an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. | The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. | Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. | Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | • In plain words: the CEO decides how the company is structured, what functions exist and how many people are needed where. • Starts when: the annual workforce plan is prepared, or an organisation change is proposed during the year. • How it runs: (1) the CPCO prepares the organisation and workforce plan against the operating plan. (2) Chiefs justify their headcount against workload and priorities. (3) The CFO confirms the cost fits the budget. (4) The CEO approves the structure and the workforce numbers. (5) The approved structure and headcount become the control for recruitment. • Proof it happened: an approved organisation chart with a version and date, and the approved headcount by function. • Where it usually breaks: hiring happens against need as it arises rather than against the approved plan, so the structure on paper and the real one drift apart. | • Make approved headcount the control for recruitment. No requisition proceeds without an approved position, and name who checks that. • Require the organisation chart to be version controlled and reissued after every approved change, with a single published copy. • Ask chiefs to justify headcount against workload measures rather than against last year's number. • Add a process for creating a position mid-year: who requests, who funds it, who approves, and how the chart is updated. • Include the consultation and notice obligations for any structure change that affects existing staff, with the CLO's input. | Yes | Yes
52 | Company / Leadership | Appoint functional chiefs and approve their annual objectives within authority | Chief Executive Officer (CEO) | Trigger: When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. Action: The Chief Executive Officer (CEO) completes “Appoint functional chiefs and approve their annual objectives within authority” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. Output/Evidence: an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. Control/Handoff: The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. Continuity/Escalation: Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. Timing: Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. | The Chief Executive Officer (CEO) completes “Appoint functional chiefs and approve their annual objectives within authority” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. | an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. | The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. | Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. | Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | • In plain words: the CEO appoints the heads of each function and agrees what each of them will be measured on for the year. • Starts when: a chief role is vacant or created, or the annual objective-setting cycle for chiefs comes round. • How it runs: (1) the role and its mandate are defined before recruitment starts. (2) The CPCO runs the selection process. (3) The CFO confirms the cost sits within approved limits and the CLO clears the employment terms. (4) The CEO appoints within authority and agrees the objectives. (5) The mandate and objectives are issued and filed. • Proof it happened: the appointment record, the signed role mandate, and the agreed objectives with measures and targets. • Where it usually breaks: the person starts before their objectives are agreed, and the first review has nothing to measure against. | • Require objectives to be agreed within a fixed number of days of start date, and treat it as an open item until they are signed. • Keep the role mandate distinct from the job advert. The mandate says what the role owns and decides, and it links to the process ownership register. • State the CEO's appointment authority in the SOP and what must go to the Chairman, including remuneration bands. • Add an induction requirement covering authority limits, governance obligations and the SOPs the role owns. • Cover the leaver side too: handover of process ownership and system access before the last working day. | Yes | Yes
53 | Company / Leadership | Approve executive succession, development and temporary-cover plans | Chief Executive Officer (CEO) | Trigger: When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. Action: The Chief Executive Officer (CEO) completes “Approve executive succession, development and temporary-cover plans” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. Output/Evidence: an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. Control/Handoff: The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. Continuity/Escalation: Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. Timing: Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. | The Chief Executive Officer (CEO) completes “Approve executive succession, development and temporary-cover plans” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. | an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. | The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. | Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. | Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | • In plain words: making sure every senior role has someone ready to step up, someone able to cover at short notice, and a development plan to get them there. • Starts when: the annual succession review falls due, a chief resigns, or short-term cover is needed for absence. • How it runs: (1) the CPCO assesses successors and readiness for each senior role. (2) Development gaps are identified with plans and dates. (3) Temporary cover arrangements are proposed for each role. (4) The CEO approves the succession plan and the cover arrangements. (5) The plan is reviewed and updated at least annually. • Proof it happened: an approved succession plan showing successors and readiness, the development plans, and the written temporary cover arrangements. • Where it usually breaks: the same one or two names appear as successor for several roles, which is not a plan but a single point of failure. | • Flag anyone named as successor for more than one critical role. That concentration should be treated as a risk to be resolved. • Record readiness in stages, for example ready now, ready in a year, ready with development, so the plan is honest about the gap. • Tie development plans to dates and to a budget, otherwise succession planning stays an annual paper exercise. • Keep temporary cover documented with authority limits, start and end dates, as with any delegation. • Set access rules on the document, since succession information is sensitive and can damage trust if it circulates. | Yes | Yes
54 | Company / Leadership | Approve compensation, policy and employment exceptions above CPCO authority | Chief Executive Officer (CEO) | Trigger: When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. Action: The Chief Executive Officer (CEO) completes “Approve compensation, policy and employment exceptions above CPCO authority” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. Output/Evidence: an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. Control/Handoff: The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. Continuity/Escalation: Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. Timing: Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. | The Chief Executive Officer (CEO) completes “Approve compensation, policy and employment exceptions above CPCO authority” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. | an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. | The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. | Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. | Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | • In plain words: pay, policy and employment decisions that go beyond what the people function can approve come to the CEO. • Starts when: a request exceeds CPCO authority, such as an off-scale salary, an unusual contract term or a policy exception. • How it runs: (1) the CPCO submits the request with the policy position and the precedent it would set. (2) The CFO confirms the cost and the budget effect. (3) The CLO confirms the legal position, particularly on contract terms and end of service. (4) The CEO approves, adjusts or rejects within authority. (5) The exception is recorded with its reason and any expiry. • Proof it happened: the approved exception record with the reason, cost and authority relied on, and the resulting contract or policy variation. • Where it usually breaks: exceptions are granted one by one until the published pay structure no longer reflects reality, and equal-pay problems follow. | • Log every exception with the reason and the cost, and review the log periodically. A pattern of exceptions means the policy or the pay bands need changing. • Require a precedent assessment in the submission: who else could reasonably ask for the same, and what that would cost. • Set the boundary in figures between CPCO authority, CEO authority and matters reserved to the Chairman. • Require CLO clearance on anything touching contract terms, end of service or statutory entitlements, since these carry legal exposure. • Add an expiry or review date to exceptions where possible, so a temporary arrangement does not become permanent by default. | Yes | Yes
55 | Company / Leadership | Review culture, engagement, executive performance and leadership conduct | Chief Executive Officer (CEO) | Trigger: When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. Action: The Chief Executive Officer (CEO) completes “Review culture, engagement, executive performance and leadership conduct” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. Output/Evidence: an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. Control/Handoff: The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. Continuity/Escalation: Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. Timing: Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | When the annual workforce plan, organisation change, executive appointment, succession review, policy exception or culture/performance issue requires CEO direction. | The Chief Executive Officer (CEO) completes “Review culture, engagement, executive performance and leadership conduct” using CPCO workforce and policy recommendation, department resource plans, approved budget, performance evidence, succession assessment, employee-risk information, CLO advice and authority limits. | an approved organisation/workforce decision, executive appointment objective, succession direction, compensation/policy exception or leadership culture action. | The CPCO owns People & Culture processes and records, functional chiefs own workforce performance and conduct, the CFO confirms budget and the CLO advises on employment/legal risk; the CEO decides only within approved authority. | Confidential people information remains access-controlled; executive appointment/removal above CEO authority and CEO-related matters escalate to the Chairman, while urgent welfare, misconduct or safety matters follow the approved investigation and protection process. | Complete annual workforce and succession reviews to the planning calendar, review executive performance quarterly and acknowledge material people or conduct risks within one working day. | • In plain words: the CEO takes a view on how the company feels to work in, how engaged people are, and how the senior team is behaving. • Starts when: the engagement or culture review falls due, the executive performance cycle runs, or a conduct concern is raised about a senior person. • How it runs: (1) the CPCO presents engagement, turnover, grievance and exit data. (2) Chiefs report on their own function's people position. (3) Conduct matters are handled confidentially with the CPCO and the CLO. (4) The CEO reviews and sets actions with owners. (5) Actions are tracked, and serious conduct matters are reported to the Chairman. • Proof it happened: the reviewed people and culture data, recorded actions with owners, and confidential records for any conduct matter. • Where it usually breaks: engagement is measured by survey and nothing visible changes, which makes the next survey both worse and less trusted. | • Require the survey to produce a small number of committed, published actions with owners. Measuring without acting damages trust faster than not measuring. • Bring in hard data alongside the survey: turnover by function, exit reasons, grievance volumes and absence. Sentiment alone is easy to dismiss. • Set the confidentiality and conflict rules for conduct matters involving a chief, including when the Chairman must be informed and when the CEO must step aside. • Fix the frequency of the survey and a shorter check in between, so the gap between measurement points is not a whole year. • State how leadership behaviour is assessed, not just results, and how that feeds executive reviews. | Yes | Yes
56 | Company / Leadership | Own the enterprise-risk review and executive risk-treatment priorities | Chief Executive Officer (CEO) | Trigger: When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. Action: The Chief Executive Officer (CEO) completes “Own the enterprise-risk review and executive risk-treatment priorities” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. Output/Evidence: an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. Control/Handoff: The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. Continuity/Escalation: No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. Timing: Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. | The Chief Executive Officer (CEO) completes “Own the enterprise-risk review and executive risk-treatment priorities” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. | an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. | The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. | No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. | Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | • In plain words: the CEO owns the company's view of its biggest risks and decides which ones get treated first. • Starts when: the risk review falls due, a new material risk emerges, or an incident shows a risk was understated. • How it runs: (1) each chief maintains the risks for their function with likelihood, impact and controls. (2) The consolidated enterprise register is prepared with movements since last time. (3) Risks are compared against the risk appetite the owners set. (4) The CEO agrees the treatment priorities and the owners of each. (5) Progress on treatment is reviewed at the next cycle, and material risks are reported to the Chairman. • Proof it happened: the enterprise risk register with owners and treatment plans, and the record of CEO decisions on priority. • Where it usually breaks: the register is completed for the meeting and then ignored, so it becomes a compliance artefact rather than a management tool. | • Require movement reporting: what is new, what has worsened, what has been closed. A static register is a sign nobody is using it. • Score risks against the risk appetite set by ownership, so exceeding appetite triggers escalation automatically rather than by judgement. • Give every material risk a named owner and a treatment plan with dates, and review treatment progress rather than just the score. • Add the top-risk deep dive: one or two risks examined properly each cycle instead of a shallow pass over all of them. • Connect incidents back to the register. Any incident should prompt a check on whether the related risk was rated correctly. | Yes | Yes
57 | Company / Leadership | Review high-risk contracts, claims, disputes and settlement strategies | Chief Executive Officer (CEO) | Trigger: When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. Action: The Chief Executive Officer (CEO) completes “Review high-risk contracts, claims, disputes and settlement strategies” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. Output/Evidence: an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. Control/Handoff: The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. Continuity/Escalation: No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. Timing: Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. | The Chief Executive Officer (CEO) completes “Review high-risk contracts, claims, disputes and settlement strategies” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. | an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. | The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. | No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. | Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | • In plain words: the CEO reviews the contracts, claims and disputes that could cost the company significantly, and decides whether to fight or settle. • Starts when: a high-risk contract is proposed, a claim is made by or against the company, or a dispute escalates. • How it runs: (1) the CLO presents the legal position, the exposure and the options. (2) The CFO quantifies the financial exposure and the provision needed. (3) The delivery function provides the factual record and the evidence. (4) The CEO agrees the strategy, including any settlement limits. (5) The matter is tracked on the register until closed, with material items reported to the Chairman. • Proof it happened: the claim or dispute register entry, the agreed strategy with any settlement authority, and the record of the outcome. • Where it usually breaks: contemporaneous records were never kept on the project, so the company has the better argument and no evidence for it. | • Make record keeping a project obligation, not a legal one. Site records, notices and correspondence are what decide claims, and they must be kept as work happens. • Set contractual notice deadlines as hard controls, since entitlement is commonly lost by missing a time bar rather than by being wrong. • Require a quantified exposure and a provision position for every material claim, agreed with the CFO. • State settlement authority in figures and who may agree what, and require legal review before any settlement is communicated. • Add a lessons step feeding into contract review, so the terms that caused the dispute are challenged next time. | Yes | Yes
58 | Company / Leadership | Approve executive responses to regulators and serious incidents | Chief Executive Officer (CEO) | Trigger: When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. Action: The Chief Executive Officer (CEO) completes “Approve executive responses to regulators and serious incidents” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. Output/Evidence: an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. Control/Handoff: The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. Continuity/Escalation: No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. Timing: Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. | The Chief Executive Officer (CEO) completes “Approve executive responses to regulators and serious incidents” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. | an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. | The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. | No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. | Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | • In plain words: when a regulator asks questions or something serious goes wrong, the CEO approves what the company says and does about it. • Starts when: a regulator makes contact, an inspection or investigation begins, or a serious incident occurs. • How it runs: (1) the matter is notified internally immediately and the facts are established. (2) The CLO leads on the legal position and what may be disclosed. (3) QHSE leads the investigation for safety incidents. (4) The CEO approves the response and who delivers it. (5) Commitments made to the regulator become tracked actions with deadlines. • Proof it happened: the notification record, the approved written response, and the closure evidence for every commitment made. • Where it usually breaks: different people speak to the regulator separately, giving inconsistent accounts that turn a manageable matter into a credibility problem. | • Name a single point of contact for each regulator and require all communication to route through them, with a log of every contact. • Require legal review before any written response leaves the company, and state that verbal commitments to a regulator are confirmed in writing afterwards. • Set immediate internal notification rules with a time limit, since delay in telling the CEO is the common failure. • Treat commitments made to a regulator as tracked actions with evidence of closure, because they will be checked at the next visit. • Add a preservation instruction for records and evidence as soon as an investigation is likely. | Yes | Yes
59 | Company / Leadership | Lead company crisis, emergency and business-continuity management | Chief Executive Officer (CEO) | Trigger: When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. Action: The Chief Executive Officer (CEO) completes “Lead company crisis, emergency and business-continuity management” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. Output/Evidence: an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. Control/Handoff: The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. Continuity/Escalation: No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. Timing: Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. | The Chief Executive Officer (CEO) completes “Lead company crisis, emergency and business-continuity management” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. | an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. | The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. | No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. | Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | • In plain words: when a crisis hits, the CEO takes command. Protect people first, contain the damage, keep the business running and keep everyone properly informed. • Starts when: a crisis or continuity event occurs, such as a serious injury, site failure, cyber attack, loss of a key facility or a sudden funding shock. • How it runs: (1) life safety and containment actions happen immediately, without waiting for approval. (2) The CEO convenes the crisis team and notifies the Chairman. (3) Roles, facts and a timed decision log are established. (4) Continuity plans are activated to keep critical operations running. (5) Communication is controlled through one authorised channel, and a review follows once the situation is stable. • Proof it happened: the crisis declaration, the timed decision log, the continuity activation record, and the post-incident review with actions. • Where it usually breaks: the plan exists but has never been rehearsed, so the first time it is used, contact details are stale and roles are unclear. | • Require a rehearsal at a stated interval, and treat an untested plan as an open risk. This is the single highest-value item in this area. • Keep the contact tree and out-of-hours numbers as a controlled annexure with a routine check that they are current. • Define roles by position rather than by name, with a deputy for each, so the plan works when someone is away. • State which operations are critical and the target time to restore each, so continuity decisions are pre-made rather than improvised. • Control communication tightly: one authorised spokesperson, holding statements prepared in advance, and a rule that nobody else comments. | Yes | Yes
60 | Company / Leadership | Review insurance, licence, compliance and remediation status | Chief Executive Officer (CEO) | Trigger: When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. Action: The Chief Executive Officer (CEO) completes “Review insurance, licence, compliance and remediation status” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. Output/Evidence: an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. Control/Handoff: The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. Continuity/Escalation: No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. Timing: Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | When the enterprise risk review, high-risk contract/claim, regulatory matter, serious incident, crisis or compliance deadline requires executive action. | The Chief Executive Officer (CEO) completes “Review insurance, licence, compliance and remediation status” using the enterprise risk register, CLO legal/compliance advice, QHSE incident evidence, CFO exposure analysis, insurance and licence status, investigation facts, business-continuity plan and functional recommendations. | an enterprise-risk direction, approved legal/claim strategy, regulatory response mandate, crisis decision or verified compliance-remediation action. | The CLO owns legal advice and contract/legal processes, QHSE owns safety investigation/control, the CFO quantifies exposure, functional chiefs implement remediation and the CEO reports ownership-reserved or reputation-critical matters to the Chairman. | No one may suppress a serious incident, illegality, fraud, licence threat or material claim; life-safety protection and legal-notification deadlines take priority, with immediate escalation to the CEO, Chairman and authorities where required. | Review enterprise risk monthly and quarterly; acknowledge serious incidents, regulatory threats, fraud or crisis events immediately and issue interim control direction the same working day. | • In plain words: the CEO checks the company's insurances are valid, its licences are current, and that anything found non-compliant is actually being fixed. • Starts when: the compliance review falls due, a policy or licence approaches renewal, or an audit or inspection raises a finding. • How it runs: (1) the CFO reports insurance cover, claims and renewal dates. (2) The CLO reports licence and registration status and expiry dates. (3) Open findings from audits and inspections are listed with owners and dates. (4) The CEO reviews and directs where closure is slipping. (5) Renewals and remediation are tracked to completion. • Proof it happened: the insurance and licence register with expiry dates, and the remediation log showing closure evidence. • Where it usually breaks: a licence or policy lapses because the renewal date sat in one person's diary rather than in a controlled register. | • Keep one controlled register of every licence, registration and insurance policy with expiry dates and a named owner for each renewal. • Set advance reminders well before expiry, sized to how long each renewal actually takes, and escalate when a renewal window is missed. • Check cover against real exposure at least annually, including contractual insurance requirements imposed by clients. • Require closure evidence for remediation items, and treat an overdue item as an escalation rather than a status update. • Add a check that project-specific insurance and permits are in place at mobilisation, linking this back to the mobilisation checklist. | Yes | Yes
61 | Company / Leadership | Sponsor the company operating system and SOP-governance programme | Chief Executive Officer (CEO) | Trigger: When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. Action: The Chief Executive Officer (CEO) completes “Sponsor the company operating system and SOP-governance programme” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. Output/Evidence: an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. Control/Handoff: The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. Continuity/Escalation: Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. Timing: Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. | The Chief Executive Officer (CEO) completes “Sponsor the company operating system and SOP-governance programme” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. | an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. | The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. | Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. | Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | • In plain words: the CEO backs the programme that gets the company working to written, agreed procedures rather than to habit and memory. • Starts when: the operating model is reviewed, the SOP approval cycle runs, or an audit shows procedures are missing or not followed. • How it runs: (1) the CRO owns the process architecture and the SOP framework. (2) Each process is assigned a single owner who drafts and maintains its SOP. (3) SOPs are reviewed, approved and issued under version control. (4) The CEO sponsors the programme, clears the blockers and holds chiefs to their commitments. (5) Compliance and effectiveness are measured, not assumed. • Proof it happened: the approved SOP framework, a register showing status and owner for every process, and issued controlled SOPs. • Where it usually breaks: SOPs get written and issued but nobody checks whether they are followed, so the library grows while behaviour stays the same. | • Build compliance checking into the programme from the start. An SOP nobody audits is documentation, not control. • Keep one register covering every process with its owner, its SOP status and its last review date, and report progress against it. • Set the approval and version rules once, centrally: numbering, effective date, review interval, and withdrawal of superseded versions. • Require training and acknowledgement on issue, so people can be held to a procedure they have actually been shown. • Give the programme a visible CEO commitment: standing agenda item, named deadlines per department, and consequences for slippage. | Yes | Yes
62 | Company / Leadership | Approve the FirstBit roadmap and material workflow changes within authority | Chief Executive Officer (CEO) | Trigger: When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. Action: The Chief Executive Officer (CEO) completes “Approve the FirstBit roadmap and material workflow changes within authority” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. Output/Evidence: an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. Control/Handoff: The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. Continuity/Escalation: Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. Timing: Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. | The Chief Executive Officer (CEO) completes “Approve the FirstBit roadmap and material workflow changes within authority” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. | an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. | The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. | Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. | Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | • In plain words: the CEO approves what changes are made to the FirstBit system and in what order, and any significant change to how work flows through it. • Starts when: the system roadmap is reviewed, a workflow change is requested, or a system problem requires a change of approach. • How it runs: (1) change requests are collected with the business reason and the benefit. (2) The CRO confirms the process impact and the CFO the financial control impact. (3) IT confirms feasibility, testing needs and continuity risk. (4) The CEO approves the roadmap and priorities within authority. (5) Changes are tested, approved and released with a rollback option available. • Proof it happened: the approved roadmap with priorities, change records with test evidence, and the release approvals. • Where it usually breaks: changes go live without proper testing or a way back, and a workflow that was working is broken for everyone at once. | • Make testing and a rollback plan mandatory before any release. State that no change goes live without both, whatever the pressure. • Require every change request to state the business benefit and who owns realising it, or the roadmap fills with preferences. • Separate routine changes from material ones, with different approval levels, so small fixes are not stuck behind CEO approval. • Require sign-off from the process owner as well as IT, since the workflow belongs to the business and not to the system team. • Add a post-release check after a set period, confirming the change worked and did not break something adjacent. | Yes | Yes
63 | Company / Leadership | Approve enterprise master-data, access and digital-control principles | Chief Executive Officer (CEO) | Trigger: When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. Action: The Chief Executive Officer (CEO) completes “Approve enterprise master-data, access and digital-control principles” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. Output/Evidence: an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. Control/Handoff: The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. Continuity/Escalation: Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. Timing: Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. | The Chief Executive Officer (CEO) completes “Approve enterprise master-data, access and digital-control principles” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. | an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. | The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. | Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. | Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | • In plain words: the CEO sets the rules on who can see and change company data, who owns each set of master records, and what controls must exist in the systems. • Starts when: a master-data or access change is proposed, a new system or role is introduced, or an audit finds a control weakness. • How it runs: (1) each master-data set is assigned a single owner. (2) Access levels are defined by role rather than by individual. (3) The CFO confirms the controls preserve segregation of duties, particularly around payments. (4) The CEO approves the principles and any exception. (5) Access is reviewed periodically and revoked promptly when people move or leave. • Proof it happened: the approved data ownership and access matrix, and the periodic access review records with the changes made. • Where it usually breaks: leavers and movers keep their old access, so over time a handful of people can do far more than anyone intended. | • Tie access revocation to the leaver and mover process with a same-day requirement, and require evidence it happened. • Define access by role, not by person, and require a periodic review where each chief confirms who in their function holds what. • Protect segregation of duties explicitly around payments, supplier creation and credit notes, and name who tests it. • Give every master-data set one owner responsible for accuracy, and state who may create or amend records. • Require dual approval for changes to critical master data such as supplier bank details, which is the most commonly exploited weakness of all. | Yes | Yes
64 | Company / Leadership | Review process performance, audit findings and improvement closure | Chief Executive Officer (CEO) | Trigger: When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. Action: The Chief Executive Officer (CEO) completes “Review process performance, audit findings and improvement closure” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. Output/Evidence: an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. Control/Handoff: The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. Continuity/Escalation: Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. Timing: Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. | The Chief Executive Officer (CEO) completes “Review process performance, audit findings and improvement closure” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. | an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. | The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. | Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. | Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | • In plain words: the CEO checks whether the company's processes are actually working, what audits have found, and whether the fixes have been completed. • Starts when: the process performance review falls due, an internal audit reports, or improvement actions pass their deadline. • How it runs: (1) the CRO reports process performance measures and compliance results. (2) Audit and inspection findings are listed with owner, action and due date. (3) Overdue and repeat findings are highlighted separately. (4) The CEO directs where closure is failing. (5) Closure is verified with evidence, not accepted on assertion. • Proof it happened: the process performance report, the findings log with status, and closure evidence for each completed action. • Where it usually breaks: findings are closed on the owner's word alone, so the same issue reappears at the next audit. | • Require independent verification before a finding is closed. The person who fixed it should not be the person who signs it off. • Report repeat findings separately and escalate them, since a repeat means the first fix addressed the symptom. • Set a small number of real process measures, such as cycle time, rework and first-time-right, rather than counting documents produced. • Show an ageing view of open findings, so slow closure is visible before it becomes an audit issue in itself. • Feed findings back to the process owner and the SOP, so the procedure is corrected and not just the instance. | Yes | Yes
65 | Company / Leadership | Approve innovation pilots and scale-up decisions within CEO authority | Chief Executive Officer (CEO) | Trigger: When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. Action: The Chief Executive Officer (CEO) completes “Approve innovation pilots and scale-up decisions within CEO authority” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. Output/Evidence: an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. Control/Handoff: The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. Continuity/Escalation: Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. Timing: Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | When the operating-model review, SOP approval cycle, FirstBit roadmap, master-data/control change, audit finding or innovation gate requires executive sponsorship. | The Chief Executive Officer (CEO) completes “Approve innovation pilots and scale-up decisions within CEO authority” using CRO process and system proposal, functional requirements, FirstBit workflow evidence, data/security assessment, audit results, change-impact analysis, business case, training/readiness plan and authority limits. | an approved operating-system direction, ERP/change sponsorship decision, data/control mandate, improvement action or pilot scale/defer/stop decision. | The CRO owns process architecture, SOP governance, workflow/master-data method and improvement evidence; IT owns technical continuity/access, the CPCO coordinates training and each functional chief owns adoption and business outcomes. | Material workflow, master-data, permission or control changes require approved testing and rollback; system bypass, data loss, unauthorised access or failed adoption escalates to the CEO and relevant functional chief, with ownership approval where investment exceeds authority. | Review operating-system performance monthly, approve planned changes at the relevant stage gate and acknowledge critical system/control failures the same working day. | • In plain words: the CEO decides which new ideas get tried as a small pilot, and which pilots are worth rolling out across the company. • Starts when: an innovation or improvement idea is proposed as a pilot, or a running pilot reaches its decision point. • How it runs: (1) the proposal states the problem, the approach, the cost and how success will be measured. (2) The CFO confirms the cost and the CRO the process impact. (3) The CEO approves the pilot with a scope, a budget and an end date. (4) Results are measured against the stated success criteria. (5) The CEO decides to scale, adjust or stop, and stopping is recorded as a valid outcome. • Proof it happened: the approved pilot scope with success criteria, the measured results, and the recorded scale or stop decision. • Where it usually breaks: pilots have no end date and no success measure, so they neither scale nor stop and quietly consume resource for years. | • Require a fixed end date and stated success criteria at approval. No pilot is approved open-ended. • Make stopping an explicit, respected outcome with its reasons recorded, so failure is cheap and learning is kept. • Cap pilot spend and scope so the risk is contained, with a separate approval needed to scale. • Ask what has to be true to scale: process changes, training, system changes and cost at full size. Scaling is where pilots usually fail. • Keep a register of pilots with status, so the same idea is not retried without reference to what happened last time. | Yes | Yes
66 | Company / Leadership | Prepare complete ownership submissions and reserved-matter recommendations | Chief Executive Officer (CEO) | Trigger: When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. Action: The Chief Executive Officer (CEO) completes “Prepare complete ownership submissions and reserved-matter recommendations” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. Output/Evidence: a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. Control/Handoff: The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. Continuity/Escalation: Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. Timing: Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. | The Chief Executive Officer (CEO) completes “Prepare complete ownership submissions and reserved-matter recommendations” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. | a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. | The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. | Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. | Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | • In plain words: when something has to go to the owners for decision, the CEO makes sure the paper is complete, honest and carries a clear recommendation. • Starts when: a matter reserved to ownership arises, or a scheduled ownership submission falls due. • How it runs: (1) the CEO establishes that the matter genuinely requires an ownership decision. (2) The relevant functions supply verified input, with the CFO on numbers and the CLO on legal. (3) The paper sets out the options, the recommendation and the consequences of each. (4) The CEO signs it as one authorised company position. (5) It is submitted to the calendar, and the decision is recorded and implemented. • Proof it happened: the submitted paper with its date, the verified supporting evidence, and the ownership decision record. • Where it usually breaks: papers arrive incomplete or too late to read properly, so the meeting either defers or decides on partial information. | • Set a standard submission template: purpose, background, options, recommendation, financial impact, legal view, risks, and the exact decision requested. • Fix the deadline relative to the meeting date and give the Chairman the right to defer any paper that arrives late or incomplete. • Require named functional verification on the paper, so the CEO is not the only person standing behind the numbers. • State that the paper presents a single company position. Unresolved internal disagreement is resolved before submission or disclosed openly, not smuggled in. • Add the implementation step: once decided, who converts it into actions and how completion is reported back. | Yes | Yes
67 | Company / Leadership | Represent the company with strategic stakeholders and institutional partners | Chief Executive Officer (CEO) | Trigger: When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. Action: The Chief Executive Officer (CEO) completes “Represent the company with strategic stakeholders and institutional partners” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. Output/Evidence: a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. Control/Handoff: The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. Continuity/Escalation: Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. Timing: Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. | The Chief Executive Officer (CEO) completes “Represent the company with strategic stakeholders and institutional partners” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. | a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. | The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. | Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. | Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | • In plain words: the CEO is the company's face with major clients, banks, partners, government bodies and other institutions. • Starts when: a strategic relationship needs attention, a significant meeting or negotiation arises, or an institutional matter is escalated. • How it runs: (1) the purpose and the company position are agreed before the engagement. (2) The CLO advises on anything that could bind the company, and the CFO on anything financial. (3) The CEO represents the company within the authority held. (4) Outcomes and any commitments made are recorded promptly. (5) Commitments become tracked actions with owners. • Proof it happened: the record of the engagement and its outcome, and the tracked actions for any commitment given. • Where it usually breaks: commitments made in a meeting never get written down, so the other party remembers them and the company does not. | • Require a short written record after any significant external engagement, listing anything that could be read as a commitment. • State clearly what the CEO may commit to and what needs prior approval, so a relationship meeting does not become an unintended contract. • Maintain a relationship map with a named owner per key stakeholder, so coverage does not depend on one person's contacts. • Require a pre-brief for negotiations, covering the position, the walk-away point and the legal constraints. • Add a gifts, hospitality and conflict-of-interest rule for these engagements, with a register. | Yes | Yes
68 | Company / Leadership | Approve corporate communications and executive reputation responses | Chief Executive Officer (CEO) | Trigger: When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. Action: The Chief Executive Officer (CEO) completes “Approve corporate communications and executive reputation responses” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. Output/Evidence: a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. Control/Handoff: The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. Continuity/Escalation: Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. Timing: Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. | The Chief Executive Officer (CEO) completes “Approve corporate communications and executive reputation responses” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. | a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. | The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. | Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. | Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | • In plain words: the CEO approves what the company says publicly, and how it responds when its reputation is at stake. • Starts when: a communication is planned, or an event occurs that draws media, client or public attention. • How it runs: (1) the CMO drafts the communication and identifies the audiences. (2) The CLO clears anything with legal or contractual exposure. (3) The CFO verifies any figures quoted. (4) The CEO approves the message and names who delivers it. (5) Release is controlled through the agreed channel, and reaction is monitored. • Proof it happened: the approved communication with its approval date, the legal clearance record, and the release log. • Where it usually breaks: speed is treated as the only priority, so an unreviewed statement goes out and creates a second problem alongside the first. | • Prepare holding statements in advance for foreseeable events, so a fast response does not mean an uncleared one. • Name one authorised spokesperson per situation and state plainly that nobody else comments, including on social media. • Require legal clearance for anything touching a live incident, dispute, client or employee matter, and require figures to be verified before release. • Set a target response time for reputation matters, with the approval route compressed but not skipped. • Keep a log of what was released, when and by whom, which matters if the sequence is later questioned. | Yes | Yes
69 | Company / Leadership | Maintain the CEO decision, risk, dependency and executive-action registers | Chief Executive Officer (CEO) | Trigger: When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. Action: The Chief Executive Officer (CEO) completes “Maintain the CEO decision, risk, dependency and executive-action registers” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. Output/Evidence: a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. Control/Handoff: The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. Continuity/Escalation: Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. Timing: Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. | The Chief Executive Officer (CEO) completes “Maintain the CEO decision, risk, dependency and executive-action registers” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. | a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. | The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. | Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. | Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | • In plain words: the CEO keeps the master record of decisions taken, risks being carried, things waiting on other people, and actions still open. • Starts when: a decision, risk, dependency or action arises, and continuously as each is updated or closed. • How it runs: (1) every executive decision is logged with its date, its basis and the authority relied on. (2) Risks and dependencies are recorded with owners. (3) Actions carry an owner and a deadline. (4) The registers are updated after each review and reissued. (5) Overdue items are escalated and closure requires evidence. • Proof it happened: maintained decision, risk, dependency and action registers, showing status, owner and closure evidence. • Where it usually breaks: each register lives in a different place and format, so nothing reconciles and the same item shows three different statuses. | • Hold the registers in one place with one format, and name the person responsible for keeping them current. • Record the authority relied on with every decision. That single field turns the register into an audit trail. • Make dependency tracking explicit, showing who is waiting on whom, since cross-department dependencies are the usual cause of quiet delay. • Require evidence for closure and forbid self-closure of significant items without a check. • Report an ageing view of overdue items at every executive review, so slippage is discussed rather than accumulated. | Yes | Yes
70 | Company / Leadership | Maintain CEO continuity, emergency delegation and acting-authority readiness | Chief Executive Officer (CEO) | Trigger: When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. Action: The Chief Executive Officer (CEO) completes “Maintain CEO continuity, emergency delegation and acting-authority readiness” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. Output/Evidence: a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. Control/Handoff: The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. Continuity/Escalation: Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. Timing: Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | When an ownership submission, strategic stakeholder matter, corporate communication, executive reporting deadline or CEO continuity event requires formal action. | The Chief Executive Officer (CEO) completes “Maintain CEO continuity, emergency delegation and acting-authority readiness” using reconciled executive reports, verified stakeholder facts, approved company position, CMO communication advice, CLO legal/reputation review, decision/action registers, authority limits and continuity arrangements. | a complete Chairman submission, authorised stakeholder position, approved corporate communication, controlled CEO decision/risk register or activated continuity record. | The CEO presents one authorised company position; the CMO coordinates communication, the CLO controls legal/reputation risk, the CFO verifies financial statements, the CRO/Document Controller preserve controlled records and functional chiefs deliver assigned actions. | Only a Chairman-approved acting CEO may represent or commit the company under CEO authority during absence; confidential, market-sensitive, legal or ownership matters remain restricted and unauthorised statements are escalated immediately. | Submit scheduled ownership reports to the approved calendar, approve urgent reputation responses before release and activate CEO continuity immediately when the CEO is unavailable. | • In plain words: making sure that if the CEO is suddenly unavailable, someone can lawfully act immediately and the business keeps moving. • Starts when: the arrangement is reviewed, the CEO plans an absence, or the CEO becomes unavailable without warning. • How it runs: (1) an acting CEO is nominated and approved by the Chairman. (2) The authority the acting CEO holds is written down, with what is excluded. (3) The CLO confirms the delegation is legally valid, including bank and signing authorities. (4) The arrangement is held ready, with start and end dates recorded when activated. (5) Normal authority is formally restored on the CEO's return. • Proof it happened: the approved acting-authority document, the activation and deactivation records with dates, and the notifications issued. • Where it usually breaks: the arrangement covers internal approvals but not bank mandates or client signing authority, so the acting CEO cannot do the things that actually matter. | • Check the delegation covers external authorities as well as internal ones: bank mandates, client contract signature and statutory filings. This is the gap that catches companies out. • Keep a pre-signed, dated document ready to activate, held by the Chairman and the CLO, rather than assembled during the emergency. • List what the acting CEO may not do, including reserved matters, strategy changes and commitments above a stated value. • Define activation and deactivation. Who declares unavailability, who notifies whom, and how full authority is formally handed back. • Require a periodic review of the arrangement, and a short handover note from the acting CEO on decisions taken during the period. | Yes | Yes
71 | Technical Engineering | Set Technical Engineering strategy, design standards and annual objectives | Chief Technical Officer (CTO) | Trigger: When the annual planning cycle, a material business change or an approved management review. Action: The Chief Technical Officer (CTO) completes “Set Technical Engineering strategy, design standards and annual objectives” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved technical plan, standards, resource decision or KPI action record. Control/Handoff: The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the annual planning cycle, a material business change or an approved management review. | The Chief Technical Officer (CTO) completes “Set Technical Engineering strategy, design standards and annual objectives” using the approved brief, source documents, calculations and controlled company systems. | an approved technical plan, standards, resource decision or KPI action record. | The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO decides where the engineering function is going, the design standards everyone must work to, and what the team is expected to achieve this year. • Starts when: the annual planning cycle opens, the business changes materially, or a management review directs a change of approach. • How it runs: (1) the CTO sets the technical strategy from the approved company plan. (2) Design standards, codes and software are agreed and written down. (3) Annual objectives and measures are set for the function. (4) The CEO approves where company-level commitment is needed. (5) The decisions are recorded in the controlled technical register and issued to the discipline owners. • Proof it happened: an approved technical plan with objectives and measures, the issued design standards, and the entry in the technical register. • Where it usually breaks: standards are agreed but never written into a single controlled document, so each discipline quietly works to its own version. | • Require one controlled standards document covering codes, software versions, drawing conventions and templates, with an owner and a review date. • Set the objectives in measurable terms: design delivered on programme, rework rate, authority approval at first submission, and RFI volume from site. • State which decisions the CTO may take alone and which need the CEO, so the strategy does not stall on unclear authority. • Require the standards to be reissued when a code or software version changes, with the old version withdrawn. • Add a yearly check that the discipline teams are actually working to the standard, not just that it exists. |  | Yes
72 | Technical Engineering | Assign technical process owners, discipline responsibilities and authority limits | Chief Technical Officer (CTO) | Trigger: When the annual planning cycle, a material business change or an approved management review. Action: The Chief Technical Officer (CTO) completes “Assign technical process owners, discipline responsibilities and authority limits” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved technical plan, standards, resource decision or KPI action record. Control/Handoff: The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the annual planning cycle, a material business change or an approved management review. | The Chief Technical Officer (CTO) completes “Assign technical process owners, discipline responsibilities and authority limits” using the approved brief, source documents, calculations and controlled company systems. | an approved technical plan, standards, resource decision or KPI action record. | The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO names who owns each technical process, what each discipline is responsible for, and how much each person can approve without asking. • Starts when: the function is reorganised, a new discipline or role is added, or a dispute shows that ownership is unclear. • How it runs: (1) the technical processes are listed and a single owner named for each. (2) Discipline boundaries are defined, including where two disciplines overlap. (3) Approval limits are set for checking, releasing and signing drawings. (4) The CTO approves and issues the assignment. (5) The technical register is updated and kept current as people change. • Proof it happened: a controlled list of technical processes with named owners, defined discipline responsibilities, and written approval limits. • Where it usually breaks: checking and approval authority is assumed from job title rather than written down, so unchecked drawings get released by whoever is available. | • Write approval authority per drawing action: who may prepare, who may check, who may approve and who may release. Never allow the same person to do all four. • Name a single owner per technical process and link it to the SOP that will govern it. • Define what happens when the named owner is absent, with a written deputy rather than an informal stand-in. • Include the overlap areas explicitly, particularly architecture against structure and structure against MEP, since that is where responsibility gaps appear. • Require the register to be updated on any staff change, and name who is responsible for updating it. |  | Yes
73 | Technical Engineering | Approve technical resource plan, competency requirements and external consultant use | Chief Technical Officer (CTO) | Trigger: When the annual planning cycle, a material business change or an approved management review. Action: The Chief Technical Officer (CTO) completes “Approve technical resource plan, competency requirements and external consultant use” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved technical plan, standards, resource decision or KPI action record. Control/Handoff: The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the annual planning cycle, a material business change or an approved management review. | The Chief Technical Officer (CTO) completes “Approve technical resource plan, competency requirements and external consultant use” using the approved brief, source documents, calculations and controlled company systems. | an approved technical plan, standards, resource decision or KPI action record. | The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO works out how many designers are needed, what skills they must have, and when to bring in outside consultants instead. • Starts when: the annual resource plan is prepared, workload changes significantly, or a project needs expertise the team does not have. • How it runs: (1) forecast design workload is set against current capacity. (2) Competency requirements are defined per discipline, including any certification needed. (3) Gaps are met by recruitment, training or external consultants. (4) The CFO confirms the cost and the CEO approves where above CTO authority. (5) Consultant appointments are made through the proper procurement and contract route. • Proof it happened: an approved technical resource plan, a competency matrix by discipline, and approved consultant appointments with scope and fee. • Where it usually breaks: consultants are engaged directly by the technical team without procurement or a contract, so scope, liability and insurance are undefined. | • Require every external consultant to go through Procurement with a written scope, fee, programme and liability position. No direct engagement by the design team. • Check professional indemnity insurance and licence validity before appointment, and record the expiry dates. • Keep a competency matrix per discipline, showing who is authorised to design, check and sign off what. • Base the capacity forecast on committed and probable work, and state the trigger point at which extra resource must be sought rather than absorbed. • State who owns the consultant's output and how it is checked before it enters the company's controlled design. |  | Yes
74 | Technical Engineering | Report Technical Engineering workload, KPIs, risks and corrective actions | Chief Technical Officer (CTO) | Trigger: When the annual planning cycle, a material business change or an approved management review. Action: The Chief Technical Officer (CTO) completes “Report Technical Engineering workload, KPIs, risks and corrective actions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved technical plan, standards, resource decision or KPI action record. Control/Handoff: The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the annual planning cycle, a material business change or an approved management review. | The Chief Technical Officer (CTO) completes “Report Technical Engineering workload, KPIs, risks and corrective actions” using the approved brief, source documents, calculations and controlled company systems. | an approved technical plan, standards, resource decision or KPI action record. | The CTO records the decision in the controlled technical register and aligns CEO, COO, CFO, CMO, CRO and discipline owners where affected. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO reports how much work the engineering team has, how it is performing, what is at risk, and what is being done about it. • Starts when: the scheduled management review falls due, or a workload or delivery risk needs raising earlier. • How it runs: (1) workload and deliverable status are collected per discipline. (2) Performance is measured against the agreed indicators. (3) Risks to design delivery are identified with their effect on projects. (4) The CTO reports to the CEO with corrective actions and owners. (5) Actions are tracked to the next review. • Proof it happened: the technical performance report for the period, the KPI data behind it, and the tracked corrective actions. • Where it usually breaks: reporting counts drawings issued rather than design delivered on time and right first time, so a busy team looks like a performing team. | • Choose indicators that reflect outcome, not activity: deliverables on programme, revisions caused by internal error, authority approvals at first submission, and site RFI volume by cause. • Report workload as capacity against committed deliverables, so overload is visible before it becomes delay. • Set an escalation trigger. Design slipping beyond a stated number of days on a critical project is reported immediately, not at the next review. • Require the report to name the projects at risk rather than reporting only totals. • Track corrective actions to closure with evidence, and show repeat issues separately. |  | Yes
75 | Technical Engineering | Accept qualified lead and verify the technical handover package | Chief Technical Officer (CTO) | Trigger: When Marketing & Sales submits a qualified lead, client brief and available site information. Action: The Chief Technical Officer (CTO) completes “Accept qualified lead and verify the technical handover package” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a verified technical lead file, feasibility decision, survey record or preliminary concept basis. Control/Handoff: Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When Marketing & Sales submits a qualified lead, client brief and available site information. | The Chief Technical Officer (CTO) completes “Accept qualified lead and verify the technical handover package” using the approved brief, source documents, calculations and controlled company systems. | a verified technical lead file, feasibility decision, survey record or preliminary concept basis. | Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: when Sales passes over a genuine enquiry, the CTO checks the handover is complete enough for engineering to actually start work on it. • Starts when: Marketing and Sales submits a qualified lead with the client brief and whatever site information exists. • How it runs: (1) the handover is checked against a defined minimum content list. (2) Anything missing is identified and the pack is returned to the CMO rather than partially accepted. (3) Once complete, a technical lead file is opened and registered. (4) The CTO assigns initial ownership within the technical team. (5) The acceptance is recorded with the date and what was received. • Proof it happened: a verified technical lead file with a register entry, the acceptance record, and the list of what was received. • Where it usually breaks: incomplete handovers are accepted to be helpful, and the design team then spends unpaid time chasing information Sales should have provided. | • Define the minimum handover content and make acceptance conditional on it: client brief, scope, site address and access, plot or title information, budget indication and programme expectation. • Give the CTO an explicit right to return an incomplete handover, and log returns so the pattern is visible to the CEO. • Put a response time on acceptance, so leads do not sit unacknowledged. • Register every accepted lead with a unique reference used by all disciplines from that point on. • State what technical effort may be spent before the client commits, since this is unpaid work and needs a limit. |  | Yes
76 | Technical Engineering | Approve preliminary site-visit and survey plan | Chief Technical Officer (CTO) | Trigger: When Marketing & Sales submits a qualified lead, client brief and available site information. Action: The Chief Technical Officer (CTO) completes “Approve preliminary site-visit and survey plan” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a verified technical lead file, feasibility decision, survey record or preliminary concept basis. Control/Handoff: Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When Marketing & Sales submits a qualified lead, client brief and available site information. | The Chief Technical Officer (CTO) completes “Approve preliminary site-visit and survey plan” using the approved brief, source documents, calculations and controlled company systems. | a verified technical lead file, feasibility decision, survey record or preliminary concept basis. | Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: before anyone visits the site, the CTO approves who goes, what they need to measure and record, and what they must come back with. • Starts when: a lead has been accepted and a site visit or survey is needed to progress the concept. • How it runs: (1) the survey scope is defined from the client brief and the likely design needs. (2) Access, permissions and safety requirements are confirmed. (3) The team, date and equipment are set. (4) The CTO approves the plan and any cost. (5) The survey output is checked against the plan before the visit is treated as complete. • Proof it happened: the approved site-visit and survey plan, the record of access permissions, and the survey output checked against the plan. • Where it usually breaks: the visit happens without a defined information list, so a second visit is needed later at the company's cost. | • Use a survey checklist per project type, so the team returns with everything needed rather than everything remembered. • Require access permission and any client or authority clearance to be confirmed in writing before travel. • Include safety requirements for the visit, particularly on live or occupied sites, and state who is responsible for them. • Add a completeness check on return, with a named checker, before the survey is closed and the team demobilised. • Record survey cost against the lead, so unpaid pre-award effort is visible. |  | Yes
77 | Technical Engineering | Decide preliminary feasibility, constraints and technical no-go conditions | Chief Technical Officer (CTO) | Trigger: When Marketing & Sales submits a qualified lead, client brief and available site information. Action: The Chief Technical Officer (CTO) completes “Decide preliminary feasibility, constraints and technical no-go conditions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a verified technical lead file, feasibility decision, survey record or preliminary concept basis. Control/Handoff: Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When Marketing & Sales submits a qualified lead, client brief and available site information. | The Chief Technical Officer (CTO) completes “Decide preliminary feasibility, constraints and technical no-go conditions” using the approved brief, source documents, calculations and controlled company systems. | a verified technical lead file, feasibility decision, survey record or preliminary concept basis. | Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO decides early whether the project is technically doable, what will constrain it, and whether there is any reason to walk away. • Starts when: the survey and brief are available and a feasibility view is needed before further design effort is spent. • How it runs: (1) site, regulatory and technical constraints are identified. (2) The brief is tested against those constraints. (3) Any condition that makes the project unviable is stated plainly as a no-go. (4) The CTO records the feasibility decision with the reasons. (5) The outcome goes back to the CMO and, where strategic, to the CEO. • Proof it happened: a recorded feasibility decision listing the constraints and any no-go conditions, issued to Sales. • Where it usually breaks: constraints are noted but no decision is recorded, so the pursuit continues by momentum and the constraint resurfaces after award. | • Make the no-go outcome a formal, recorded option with reasons, so declining is a decision rather than an argument. • List the standard constraint checks: plot ratio and setbacks, height limits, authority approvals, utility capacity, access, ground conditions and existing structure condition. • Require constraints to be carried forward into the design basis, so they are not rediscovered later in the project. • State who is told and how, including the client-facing message, so the constraint is managed commercially and not just technically. • Set an authority level for a no-go on a strategic client, since that is a commercial decision as much as a technical one. |  | Yes
78 | Technical Engineering | Approve preliminary concept and indicative budget basis for client alignment | Chief Technical Officer (CTO) | Trigger: When Marketing & Sales submits a qualified lead, client brief and available site information. Action: The Chief Technical Officer (CTO) completes “Approve preliminary concept and indicative budget basis for client alignment” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a verified technical lead file, feasibility decision, survey record or preliminary concept basis. Control/Handoff: Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When Marketing & Sales submits a qualified lead, client brief and available site information. | The Chief Technical Officer (CTO) completes “Approve preliminary concept and indicative budget basis for client alignment” using the approved brief, source documents, calculations and controlled company systems. | a verified technical lead file, feasibility decision, survey record or preliminary concept basis. | Incomplete handovers are returned to CMO; strategic, capacity, client or feasibility exceptions escalate to CEO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO approves the first design idea and the rough cost basis that will be shown to the client to get agreement in principle. • Starts when: feasibility is confirmed and a concept and indicative budget are needed for client alignment. • How it runs: (1) the Architect prepares the concept within the agreed constraints. (2) An indicative budget basis is prepared with the assumptions and exclusions stated. (3) The CTO reviews both for technical soundness and realism. (4) The CTO approves the concept and the budget basis for release. (5) It is issued to the client through the CMO with the assumptions attached. • Proof it happened: the approved concept package, the indicative budget basis with assumptions and exclusions, and the issue record. • Where it usually breaks: an indicative figure is given without written assumptions or exclusions, and the client treats it afterwards as a fixed price. | • Require every indicative budget to carry written assumptions, exclusions and a clear statement that it is indicative and subject to detailed design. • Fix the accuracy range in the SOP, expressed as a percentage, so both sides know what an indicative figure means. • Require the CTO's approval before anything reaches the client, and state that no member of the design team issues figures directly. • Keep a record of every indicative figure issued and its basis, since it will be quoted back later. • State what happens when the client's expectation and the indicative budget do not meet: who reopens the brief and how. |  | Yes
79 | Technical Engineering | Define paid detailed-design scope, deliverables, programme and fee basis | Chief Technical Officer (CTO) | Trigger: When the client elects to proceed beyond preliminary concept and commercial activation is required. Action: The Chief Technical Officer (CTO) completes “Define paid detailed-design scope, deliverables, programme and fee basis” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved design scope, programme, fee basis, activation decision and assigned deliverables. Control/Handoff: Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the client elects to proceed beyond preliminary concept and commercial activation is required. | The Chief Technical Officer (CTO) completes “Define paid detailed-design scope, deliverables, programme and fee basis” using the approved brief, source documents, calculations and controlled company systems. | an approved design scope, programme, fee basis, activation decision and assigned deliverables. | Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO defines exactly what the paid design service will cover, what will be delivered, by when, and on what fee basis. • Starts when: the client wants to move beyond concept and a paid detailed-design engagement needs to be defined. • How it runs: (1) deliverables are listed per discipline, with the number of revisions included. (2) The programme is built from real discipline durations, not from the client's preferred date. (3) The fee basis is set with the CFO's input. (4) Exclusions and assumptions are stated explicitly. (5) The CTO approves the scope, programme and fee basis before any quotation is prepared. • Proof it happened: an approved design scope and deliverables list, the programme, and the fee basis with exclusions recorded. • Where it usually breaks: revisions are not limited in the scope, so repeated client changes are absorbed free and the design fee is consumed by rework. | • State the number of revision cycles included and what happens beyond that, since uncontrolled revisions are the main cause of design fee loss. • List deliverables by discipline and by stage, with the format and the purpose of each, so completion can be judged objectively. • Build the programme from discipline durations and dependencies, and state what client information is needed and by when for the programme to hold. • Write the exclusions in plain terms: specialist consultants, authority fees, third-party surveys, and anything outside the listed disciplines. • Define the trigger for a scope variation and who is authorised to agree it with the client. |  | Yes
80 | Technical Engineering | Approve design quotation or agreement before client issue | Chief Technical Officer (CTO) | Trigger: When the client elects to proceed beyond preliminary concept and commercial activation is required. Action: The Chief Technical Officer (CTO) completes “Approve design quotation or agreement before client issue” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved design scope, programme, fee basis, activation decision and assigned deliverables. Control/Handoff: Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the client elects to proceed beyond preliminary concept and commercial activation is required. | The Chief Technical Officer (CTO) completes “Approve design quotation or agreement before client issue” using the approved brief, source documents, calculations and controlled company systems. | an approved design scope, programme, fee basis, activation decision and assigned deliverables. | Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO checks and approves the design quotation or agreement before it goes anywhere near the client. • Starts when: a design quotation or agreement has been prepared and client issue is intended. • How it runs: (1) the quotation is checked against the approved scope, deliverables and programme. (2) The CFO confirms the fee, payment terms and credit position. (3) The CLO reviews the agreement terms and liability position. (4) The CTO approves for issue. (5) It is issued through the CMO and the issued version is recorded. • Proof it happened: the approved quotation or agreement with the approval record, and the issue log showing the version sent. • Where it usually breaks: a revised version is sent to the client without going back through approval, so the company is exposed to terms nobody checked. | • Require every version issued to the client to be approved, including revisions made during negotiation. No exceptions for speed. • Keep a version log with what changed between versions, since clients frequently sign an earlier one. • Set the professional liability and limitation position with the CLO once, as standard wording, rather than negotiating it each time. • Confirm payment terms and any advance payment requirement before issue, with the CFO's sign-off. • State who is allowed to send the document to the client, so the controlled version is the one that arrives. |  | Yes
81 | Technical Engineering | Confirm client acceptance and Finance payment before design activation | Chief Technical Officer (CTO) | Trigger: When the client elects to proceed beyond preliminary concept and commercial activation is required. Action: The Chief Technical Officer (CTO) completes “Confirm client acceptance and Finance payment before design activation” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved design scope, programme, fee basis, activation decision and assigned deliverables. Control/Handoff: Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the client elects to proceed beyond preliminary concept and commercial activation is required. | The Chief Technical Officer (CTO) completes “Confirm client acceptance and Finance payment before design activation” using the approved brief, source documents, calculations and controlled company systems. | an approved design scope, programme, fee basis, activation decision and assigned deliverables. | Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: detailed design does not start until the client has formally accepted and Finance confirms the money has arrived. • Starts when: the client indicates acceptance of the design offer and activation of the work is requested. • How it runs: (1) written client acceptance is obtained, not verbal or implied. (2) Finance confirms the advance payment or agreed payment condition is met. (3) The CTO records both confirmations. (4) Only then is the design activated and resources assigned. (5) Any pressure to start earlier is escalated rather than absorbed. • Proof it happened: written client acceptance, the Finance payment confirmation, and the dated design activation record. • Where it usually breaks: design starts on a verbal go-ahead to keep the client happy, and the company carries unpaid work with no signed scope. | • Make the block explicit and unambiguous: no design activation without written acceptance and Finance confirmation. Name who verifies both. • Define what counts as written acceptance, for example a signed quotation, a purchase order or a signed agreement. • Provide a single exception route through the CEO, in writing, with a stated value limit, so the rule is not broken quietly instead. • Record the activation date, because it starts the design programme and any later delay claim depends on it. • Log every request to start early and its outcome, since the pattern is useful evidence for the CEO. |  | Yes
82 | Technical Engineering | Chair detailed-design kickoff and assign discipline deliverables | Chief Technical Officer (CTO) | Trigger: When the client elects to proceed beyond preliminary concept and commercial activation is required. Action: The Chief Technical Officer (CTO) completes “Chair detailed-design kickoff and assign discipline deliverables” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved design scope, programme, fee basis, activation decision and assigned deliverables. Control/Handoff: Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When the client elects to proceed beyond preliminary concept and commercial activation is required. | The Chief Technical Officer (CTO) completes “Chair detailed-design kickoff and assign discipline deliverables” using the approved brief, source documents, calculations and controlled company systems. | an approved design scope, programme, fee basis, activation decision and assigned deliverables. | Detailed design remains blocked until client acceptance and Finance payment confirmation are recorded. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO holds the meeting that starts detailed design properly, and gives each discipline its list of deliverables and dates. • Starts when: design has been activated and the disciplines need to be briefed and tasked. • How it runs: (1) the kickoff is held with all disciplines and the project lead present. (2) The brief, constraints, standards and programme are walked through. (3) Deliverables are assigned by discipline with named owners and dates. (4) Interfaces and dependencies between disciplines are identified. (5) The kickoff record and deliverable register are issued. • Proof it happened: the kickoff minutes with attendance, and the deliverable register showing owner and date per item. • Where it usually breaks: disciplines are briefed separately at different times, so interfaces are agreed twice or not at all. | • Require all disciplines in one kickoff, and treat it as a mandatory gate before discipline work starts. • Produce a deliverable register at the kickoff with owner, date and dependency for every item, and make it the tracking document for the whole design. • Cover the interfaces explicitly in the agenda, particularly openings, plant space, loads and routes. • State what client information is still awaited and the date it is needed, so the dependency is visible from day one. • Set the design review points at the kickoff, so they are diarised rather than arranged later under pressure. |  | Yes
83 | Technical Engineering | Approve project design basis, codes, assumptions and technical criteria | Chief Technical Officer (CTO) | Trigger: When discipline design reaches the scheduled review or release milestone. Action: The Chief Technical Officer (CTO) completes “Approve project design basis, codes, assumptions and technical criteria” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved coordinated design, QA record, specifications and controlled IFC status. Control/Handoff: No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When discipline design reaches the scheduled review or release milestone. | The Chief Technical Officer (CTO) completes “Approve project design basis, codes, assumptions and technical criteria” using the approved brief, source documents, calculations and controlled company systems. | an approved coordinated design, QA record, specifications and controlled IFC status. | No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO approves the technical rules for the project. Which codes apply, what assumptions are being made, and the criteria the design must meet. • Starts when: detailed design is starting, or an assumption or code requirement changes during design. • How it runs: (1) each discipline states its proposed codes, standards, loads and criteria. (2) Assumptions are written down where information is not yet available. (3) Authority and client-specific requirements are incorporated. (4) The CTO approves the design basis as a controlled document. (5) Any later change to it goes through a recorded revision. • Proof it happened: an approved design basis document with a version, listing codes, criteria and assumptions per discipline. • Where it usually breaks: assumptions are made in individual designers' heads rather than written down, so nobody can tell later whether a change invalidates the design. | • Make the design basis a single controlled document covering all disciplines, approved before substantive design work proceeds. • Require every assumption to be listed with the information it is standing in for and the date it must be confirmed by. • Put the design basis under revision control, since a code or load change mid-design affects work already done. • Include client and authority specific requirements, so they are not treated as late additions. • State who may approve a change to the design basis and how affected deliverables are identified and reworked. |  | Yes
84 | Technical Engineering | Direct multidisciplinary design coordination and clash closure | Chief Technical Officer (CTO) | Trigger: When discipline design reaches the scheduled review or release milestone. Action: The Chief Technical Officer (CTO) completes “Direct multidisciplinary design coordination and clash closure” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved coordinated design, QA record, specifications and controlled IFC status. Control/Handoff: No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When discipline design reaches the scheduled review or release milestone. | The Chief Technical Officer (CTO) completes “Direct multidisciplinary design coordination and clash closure” using the approved brief, source documents, calculations and controlled company systems. | an approved coordinated design, QA record, specifications and controlled IFC status. | No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO makes sure the disciplines design around each other rather than into each other, and that every clash gets resolved and closed. • Starts when: discipline designs reach a coordination point, or a clash or interface conflict is identified. • How it runs: (1) coordination reviews are held at planned points in the programme. (2) Clashes are logged with the disciplines involved. (3) Each clash is assigned to a responsible designer for resolution. (4) Resolutions are checked and the clash is closed with evidence. (5) Unresolved conflicts are decided by the CTO rather than left open. • Proof it happened: the coordination review records and a clash register showing each item, its owner, its resolution and its closure. • Where it usually breaks: clashes are discussed in meetings but never logged, so the same conflict reappears at IFC and then again on site. | • Make a written clash register mandatory, with owner, resolution and closure evidence per item. Verbal coordination does not survive a revision. • Set coordination review points in the programme rather than holding them when someone asks, and require all disciplines to attend. • Give the CTO a decision role with a time limit, so a disputed clash cannot sit between two disciplines. • Require the resolution to be reflected in every affected discipline drawing, with a check that it was. • Report open clash count and age at each design review, since it is the best early warning of an unbuildable design. |  | Yes
85 | Technical Engineering | Approve technical specifications, materials and approved-brand requirements | Chief Technical Officer (CTO) | Trigger: When discipline design reaches the scheduled review or release milestone. Action: The Chief Technical Officer (CTO) completes “Approve technical specifications, materials and approved-brand requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved coordinated design, QA record, specifications and controlled IFC status. Control/Handoff: No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When discipline design reaches the scheduled review or release milestone. | The Chief Technical Officer (CTO) completes “Approve technical specifications, materials and approved-brand requirements” using the approved brief, source documents, calculations and controlled company systems. | an approved coordinated design, QA record, specifications and controlled IFC status. | No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO approves what materials and equipment the design specifies, and which brands are acceptable. • Starts when: specifications are being prepared, or a material or brand change is proposed during design or procurement. • How it runs: (1) each discipline drafts its specification against the design basis and the standards. (2) Approved brand or equivalent requirements are set, with the client's and authority's requirements respected. (3) The CPO confirms availability, lead time and commercial implications. (4) The CTO approves the specification. (5) Any substitution later must come back for technical approval. • Proof it happened: the approved specification with the approved brand list, and the record of any approved substitution. • Where it usually breaks: substitutions are agreed on site for availability or price without technical approval, and the performance the design relied on is quietly lost. | • Write the substitution rule clearly: no material or brand change without technical approval, whatever the reason, with a named approver and a turnaround time. • Require lead time and availability input from Procurement before a specification is approved, so the design is procurable. • State how "or equivalent" is assessed, and what evidence a proposed equivalent must provide. • Check client and authority mandated brands or approvals separately, since these override internal preference. • Keep a specification register per project, so site and procurement always work from the current approved version. |  | Yes
86 | Technical Engineering | Approve construction-ready design after interdisciplinary QA review | Chief Technical Officer (CTO) | Trigger: When discipline design reaches the scheduled review or release milestone. Action: The Chief Technical Officer (CTO) completes “Approve construction-ready design after interdisciplinary QA review” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved coordinated design, QA record, specifications and controlled IFC status. Control/Handoff: No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When discipline design reaches the scheduled review or release milestone. | The Chief Technical Officer (CTO) completes “Approve construction-ready design after interdisciplinary QA review” using the approved brief, source documents, calculations and controlled company systems. | an approved coordinated design, QA record, specifications and controlled IFC status. | No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO gives final approval that the design is complete, coordinated and safe to build from. • Starts when: discipline designs reach the release milestone and the interdisciplinary QA review is complete. • How it runs: (1) each discipline confirms its deliverables are complete and internally checked. (2) The interdisciplinary QA review verifies coordination across disciplines. (3) Open clashes and comments are confirmed closed. (4) The CTO reviews the QA evidence and approves construction readiness. (5) Anything unresolved is either closed first or explicitly recorded as a caveat. • Proof it happened: the QA review record, the closed clash and comment registers, and the CTO's construction-ready approval. • Where it usually breaks: approval is given under programme pressure with comments still open, and site discovers them as RFIs and variations. | • State the entry conditions for approval and hold to them: internal checks complete, clashes closed, authority comments incorporated. Approval with open items should be an explicit, recorded exception. • Keep preparer, checker and approver as different people, and record all three names on the QA record. • Where a caveat has to be carried, record it, notify the COO, and track it to closure rather than letting it travel silently to site. • Use a QA checklist per discipline so the review is consistent regardless of who runs it. • Measure design errors found after release, by discipline, and feed that back into the review. |  | Yes
87 | Technical Engineering | Approve controlled IFC release and revision status | Chief Technical Officer (CTO) | Trigger: When discipline design reaches the scheduled review or release milestone. Action: The Chief Technical Officer (CTO) completes “Approve controlled IFC release and revision status” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved coordinated design, QA record, specifications and controlled IFC status. Control/Handoff: No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When discipline design reaches the scheduled review or release milestone. | The Chief Technical Officer (CTO) completes “Approve controlled IFC release and revision status” using the approved brief, source documents, calculations and controlled company systems. | an approved coordinated design, QA record, specifications and controlled IFC status. | No uncontrolled or unchecked drawing may be issued; unresolved discipline conflict returns to the responsible designer and escalates to CTO. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO controls which drawings are released as issued-for-construction and makes sure everyone knows which revision is current. • Starts when: an approved design is ready for construction release, or a revision to an already released drawing is needed. • How it runs: (1) approved drawings are marked with the correct status and revision. (2) The release is authorised by the CTO. (3) Document Control issues the package and records the transmittal. (4) Superseded revisions are formally withdrawn from use. (5) The revision register shows the current status of every drawing at any time. • Proof it happened: the authorised IFC release record, the transmittal from Document Control, and a revision register showing current and superseded status. • Where it usually breaks: a superseded drawing stays in use on site because the withdrawal was never communicated, and work is built to the wrong revision. | • Make withdrawal of the superseded revision an explicit step with confirmation from site, not an assumption that the new issue replaces it. • Require every drawing to carry status, revision and purpose of issue, and forbid any uncontrolled or unstamped drawing from leaving the office. • Route all issues through Document Control, so there is one transmittal record. Direct emails from designers to site should be prohibited. • Keep a live revision register accessible to site and procurement, so the current revision can always be checked. • Set a rule for urgent releases that keeps the record intact even when speed is needed. |  | Yes
88 | Technical Engineering | Approve authority, permit and NOC strategy and submission responsibility | Chief Technical Officer (CTO) | Trigger: When an authority submission, NOC, design change, deviation or critical clarification is required. Action: The Chief Technical Officer (CTO) completes “Approve authority, permit and NOC strategy and submission responsibility” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised submission, decision, revised design or closed technical-query record. Control/Handoff: Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When an authority submission, NOC, design change, deviation or critical clarification is required. | The Chief Technical Officer (CTO) completes “Approve authority, permit and NOC strategy and submission responsibility” using the approved brief, source documents, calculations and controlled company systems. | an authorised submission, decision, revised design or closed technical-query record. | Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO decides which authority approvals, permits and no-objection certificates the project needs, and who is responsible for getting each one. • Starts when: a project needs authority approval, or the approval requirements change during design. • How it runs: (1) the applicable authorities and required approvals are identified for the project type and location. (2) The submission sequence and dependencies between approvals are mapped. (3) Responsibility for each submission is assigned, whether internal or a consultant. (4) The CTO approves the strategy and the timeline. (5) Progress against it is tracked, since approvals usually sit on the critical path. • Proof it happened: an approved authority and permit strategy listing each approval, its owner, its dependency and its target date. • Where it usually breaks: approvals are treated as a design task rather than a programme item, so the dependency is discovered when construction cannot start. | • Put the approvals on the project programme with durations and dependencies, since they routinely control the start of construction. • Keep an approvals matrix per project type and authority, so the requirements are not researched from scratch each time. • Name one owner per approval, and state whether the fee is a company cost or a client cost, since this is a frequent dispute. • Record realistic authority turnaround times from experience and use those in planning, not best-case assumptions. • Add an escalation route for stalled approvals, including who engages the authority at a senior level. |  | Yes
89 | Technical Engineering | Review and authorise authority submission packages | Chief Technical Officer (CTO) | Trigger: When an authority submission, NOC, design change, deviation or critical clarification is required. Action: The Chief Technical Officer (CTO) completes “Review and authorise authority submission packages” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised submission, decision, revised design or closed technical-query record. Control/Handoff: Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When an authority submission, NOC, design change, deviation or critical clarification is required. | The Chief Technical Officer (CTO) completes “Review and authorise authority submission packages” using the approved brief, source documents, calculations and controlled company systems. | an authorised submission, decision, revised design or closed technical-query record. | Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: before anything goes to an authority, the CTO checks the submission package is complete and correct. • Starts when: a discipline has compiled an authority submission package and submission is due. • How it runs: (1) the package is checked against the authority's own checklist. (2) Drawings, calculations and forms are verified as consistent with each other. (3) The required stamps, licences and signatures are confirmed. (4) The CTO authorises the submission. (5) The submission is logged with its date and reference for tracking. • Proof it happened: the authorised submission package, the completeness check record, and the submission log with the authority's reference. • Where it usually breaks: packages are submitted incomplete to meet an internal date, and the rejection costs more time than the check would have taken. | • Use the authority's own checklist as the internal check, and require it to be signed before submission is authorised. • Log every submission with its date, reference and expected response date, so follow-up is systematic rather than personal. • Verify consistency between drawings, calculations and forms as a specific step, since mismatches are a common rejection reason. • Confirm the required licensed signatory or stamp is in place and valid before submission. • Track rejection reasons over time, because the same few causes usually account for most of them. |  | Yes
90 | Technical Engineering | Decide material design deviations, value engineering and technical changes | Chief Technical Officer (CTO) | Trigger: When an authority submission, NOC, design change, deviation or critical clarification is required. Action: The Chief Technical Officer (CTO) completes “Decide material design deviations, value engineering and technical changes” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised submission, decision, revised design or closed technical-query record. Control/Handoff: Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When an authority submission, NOC, design change, deviation or critical clarification is required. | The Chief Technical Officer (CTO) completes “Decide material design deviations, value engineering and technical changes” using the approved brief, source documents, calculations and controlled company systems. | an authorised submission, decision, revised design or closed technical-query record. | Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO decides on changes to an approved design, including cost-saving alternatives, and confirms they are technically acceptable. • Starts when: a deviation is proposed, value engineering is requested, or a change is needed after design approval. • How it runs: (1) the change is submitted with the technical reason and the alternative proposed. (2) The effect on other disciplines is assessed, not just the discipline proposing it. (3) Cost and programme impact go to the COO and CFO, and contractual impact to the CLO, before approval. (4) The CTO approves or rejects on technical grounds. (5) The approved change is issued as a controlled revision with the design basis updated. • Proof it happened: the approved change record showing the technical justification and the assessed impacts, and the resulting controlled revision. • Where it usually breaks: value engineering is accepted on price alone, and the knock-on effects on other disciplines appear later as rework on site. | • Require a cross-discipline impact assessment on every change before approval. Single-discipline sign-off is how value engineering creates rework. • Separate technical acceptability from commercial desirability. The CTO decides the first, the COO and CFO the second, and both must be recorded. • Require the design basis and every affected drawing to be updated as part of closing the change, with a check that it happened. • State who may commit a change to the client, and that a change is not live until it is issued as a controlled revision. • Keep a change register per project with cost, time and status, since it is the evidence base for variation claims. |  | Yes
91 | Technical Engineering | Control critical RFIs, technical clarifications and site design issues | Chief Technical Officer (CTO) | Trigger: When an authority submission, NOC, design change, deviation or critical clarification is required. Action: The Chief Technical Officer (CTO) completes “Control critical RFIs, technical clarifications and site design issues” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised submission, decision, revised design or closed technical-query record. Control/Handoff: Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When an authority submission, NOC, design change, deviation or critical clarification is required. | The Chief Technical Officer (CTO) completes “Control critical RFIs, technical clarifications and site design issues” using the approved brief, source documents, calculations and controlled company systems. | an authorised submission, decision, revised design or closed technical-query record. | Document Control preserves revision history; cost, time, legal and project impacts are handed to COO, CFO and CLO before approval where applicable. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: when site asks an urgent design question, the CTO makes sure it is answered properly, quickly and in a way that is recorded. • Starts when: a critical RFI, technical clarification or design issue is raised from site. • How it runs: (1) the query is registered with its priority and the effect of delay. (2) It is routed to the responsible discipline with a response deadline. (3) The answer is checked before issue, since an RFI response changes the design in practice. (4) Where the answer alters the design, a controlled revision follows rather than the RFI standing alone. (5) The register tracks response time and closure. • Proof it happened: the RFI register showing dates, owners, responses and closure, and any controlled revisions issued as a result. • Where it usually breaks: an RFI answer is sent by email and never turned into a drawing revision, so the as-built condition and the drawings no longer agree. | • Require any RFI response that changes the design to be followed by a controlled drawing revision. An email answer is not a design change. • Set response deadlines by priority and report overdue RFIs, since design delay to site quickly becomes a delay claim. • Have every response checked before issue by someone other than the author, given the weight these answers carry. • Analyse RFIs by cause and discipline, because a high volume from one area points to a design quality problem to fix. • State who may answer site directly and who may not, so unrecorded verbal instructions do not circulate. |  | Yes
92 | Technical Engineering | Validate final civil and MEP BOQ against coordinated design | Chief Technical Officer (CTO) | Trigger: When design is ready for pricing, project activation, handover or technical closeout. Action: The Chief Technical Officer (CTO) completes “Validate final civil and MEP BOQ against coordinated design” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a validated BOQ/quotation basis, signed technical handover or approved closeout package. Control/Handoff: CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When design is ready for pricing, project activation, handover or technical closeout. | The Chief Technical Officer (CTO) completes “Validate final civil and MEP BOQ against coordinated design” using the approved brief, source documents, calculations and controlled company systems. | a validated BOQ/quotation basis, signed technical handover or approved closeout package. | CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO checks that the quantities used for pricing actually match the coordinated design, for both civil and MEP. • Starts when: the BOQ is prepared for pricing, or the design changes after the BOQ was produced. • How it runs: (1) the estimators produce quantities from the current approved drawings. (2) The quantities are reconciled against the coordinated design and the specification. (3) Gaps, double counts and unpriced scope are identified. (4) The CTO validates the BOQ as consistent with the design. (5) The drawing revisions the BOQ was based on are recorded. • Proof it happened: the validated BOQ with its reconciliation record, and the list of drawing revisions it was measured from. • Where it usually breaks: the BOQ is measured from a superseded revision, so the price is right for a design that no longer exists. | • Record the exact drawing revisions the BOQ was measured from, and require a re-check whenever those revisions change. • Use a reconciliation step that hunts specifically for gaps between disciplines, which is where scope goes unpriced. • Require builders-work, testing, commissioning and authority allowances to be checked as present, since these are routinely omitted. • Set a tolerance for the reconciliation and an escalation when the variance exceeds it. • State who validates and that it is not the same person who measured. |  | Yes
93 | Technical Engineering | Approve consolidated technical quotation basis, exclusions and margin inputs | Chief Technical Officer (CTO) | Trigger: When design is ready for pricing, project activation, handover or technical closeout. Action: The Chief Technical Officer (CTO) completes “Approve consolidated technical quotation basis, exclusions and margin inputs” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a validated BOQ/quotation basis, signed technical handover or approved closeout package. Control/Handoff: CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When design is ready for pricing, project activation, handover or technical closeout. | The Chief Technical Officer (CTO) completes “Approve consolidated technical quotation basis, exclusions and margin inputs” using the approved brief, source documents, calculations and controlled company systems. | a validated BOQ/quotation basis, signed technical handover or approved closeout package. | CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: the CTO approves the technical basis of the price. What is included, what is excluded, and the assumptions the margin is calculated on. • Starts when: the consolidated quotation is being assembled from the civil and MEP estimates. • How it runs: (1) the discipline estimates are consolidated and checked for overlap and omission. (2) Exclusions, assumptions and qualifications are stated in one place. (3) The CTO confirms the technical basis and the risk allowances. (4) Margin inputs are provided to the CFO and CEO for the commercial decision. (5) The approved technical basis is recorded against the version quoted. • Proof it happened: the approved technical quotation basis with exclusions and assumptions, and the record of the margin inputs provided. • Where it usually breaks: exclusions live in the estimators' working files and never reach the client-facing offer, so the company is held to scope it never priced. | • Require the exclusions and assumptions to be carried into the client-facing offer word for word. An exclusion that stays internal is worthless. • Separate the technical basis from the commercial decision in the SOP. The CTO owns what is priced; the CEO and CFO own the margin. • Check for overlap and omission between civil and MEP as a specific step, particularly at builders-work and interfaces. • State risk and contingency allowances explicitly, so they are visible rather than hidden inside rates. • Lock the version. The approved technical basis relates to one quotation version, and any change requires re-approval. |  | Yes
94 | Technical Engineering | Conduct formal CTO-to-COO construction-ready handover | Chief Technical Officer (CTO) | Trigger: When design is ready for pricing, project activation, handover or technical closeout. Action: The Chief Technical Officer (CTO) completes “Conduct formal CTO-to-COO construction-ready handover” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a validated BOQ/quotation basis, signed technical handover or approved closeout package. Control/Handoff: CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When design is ready for pricing, project activation, handover or technical closeout. | The Chief Technical Officer (CTO) completes “Conduct formal CTO-to-COO construction-ready handover” using the approved brief, source documents, calculations and controlled company systems. | a validated BOQ/quotation basis, signed technical handover or approved closeout package. | CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: when design is finished, the CTO formally hands the project to the COO for construction, with everything the site team needs. • Starts when: the design is construction ready and the project is being activated for delivery. • How it runs: (1) the handover pack is assembled: IFC drawings, specifications, design basis, approvals, BOQ, assumptions and open items. (2) The COO reviews it and raises gaps. (3) Any open item is listed with an owner and a closure date rather than left implicit. (4) Both parties sign the handover record. (5) Design support obligations for the construction phase are agreed. • Proof it happened: a signed CTO to COO handover record listing what was transferred and what remains open. • Where it usually breaks: the handover is treated as sending a folder of drawings, so the assumptions and open items behind the design never reach the people building it. | • Require a signed handover with a defined pack list, and treat it as a gate: construction does not start until it is signed. • Make the open-items list mandatory, with owner and date for each, since these are what become site delays. • Include the design assumptions and constraints in the pack, not just the drawings. Site needs to know what the design depends on. • Agree the design support arrangement for the construction phase: response times for RFIs, site visit expectations and who provides them. • Add a short briefing session as part of the handover, because a pack alone does not transfer understanding. |  | Yes
95 | Technical Engineering | Approve technical closeout, as-built, final-inspection and lessons-learned package | Chief Technical Officer (CTO) | Trigger: When design is ready for pricing, project activation, handover or technical closeout. Action: The Chief Technical Officer (CTO) completes “Approve technical closeout, as-built, final-inspection and lessons-learned package” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a validated BOQ/quotation basis, signed technical handover or approved closeout package. Control/Handoff: CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. Continuity/Escalation: The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. Timing: To be confirmed. | When design is ready for pricing, project activation, handover or technical closeout. | The Chief Technical Officer (CTO) completes “Approve technical closeout, as-built, final-inspection and lessons-learned package” using the approved brief, source documents, calculations and controlled company systems. | a validated BOQ/quotation basis, signed technical handover or approved closeout package. | CTO confirms design, commercial and record completeness before handoff to CMO, Finance, Legal, COO/Projects or Document Control. | The Architect (Lead) may coordinate routine technical work as deputy, but reserved approvals, material deviations and commercial commitments escalate to the CEO with the relevant CXO. | To be confirmed. | • In plain words: at the end of the job, the CTO signs off the as-built records, the final technical inspection, and what the company learned from it. • Starts when: the project reaches technical completion and closeout is due. • How it runs: (1) as-built drawings are prepared from verified site red-lines. (2) The final technical inspection is carried out and defects listed. (3) Test records, warranties and manuals are collected and checked. (4) Lessons learned are captured with the causes, not just the symptoms. (5) The CTO approves the closeout package and it is archived under Document Control. • Proof it happened: the approved closeout package with as-builts, inspection and test records, warranties, and a lessons-learned record. • Where it usually breaks: as-builts are drawn from memory months later because red-lines were never kept, and lessons learned are written but never reach the next project. | • Require site red-lines to be maintained as work proceeds and verified before as-builts are drawn. Retrospective as-builts are guesswork. • Give lessons learned a route into practice: an owner, a target document to change, whether that is the design standard, the checklist or the specification. • Set the closeout pack contents as a checklist, including test records, warranties, manuals and authority completion certificates. • Make archiving explicit: what is retained, in what format, for how long, and who controls access. • Tie the closeout gate to the retention or final payment milestone, so there is a real incentive to complete it. |  | Yes
96 | Technical Engineering | Receive and validate client brief, lead record and technical handover | Architect (Lead) | Trigger: When the Architect receives an accepted technical lead or approved design instruction. Action: The Architect (Lead) completes “Receive and validate client brief, lead record and technical handover” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled brief, survey record, constraints register and verified design inputs. Control/Handoff: Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When the Architect receives an accepted technical lead or approved design instruction. | The Architect (Lead) completes “Receive and validate client brief, lead record and technical handover” using the approved brief, source documents, calculations and controlled company systems. | a controlled brief, survey record, constraints register and verified design inputs. | Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect takes over the client brief and the handover from the CTO and checks it is complete enough to design from. • Starts when: the CTO assigns an accepted lead or project to the architectural team. • How it runs: (1) the brief, lead record and handover pack are reviewed against what architecture actually needs. (2) Missing information is listed and requested rather than assumed. (3) The client's stated requirements are separated from the team's interpretation of them. (4) The Architect confirms acceptance to the CTO. (5) The project is set up in the drawing and deliverable registers. • Proof it happened: the acceptance record, the list of information requested, and the project set up in the registers. • Where it usually breaks: gaps in the brief get filled with assumptions that were never written down, and the client rejects the design for something nobody ever asked them about. | • Define the minimum brief content architecture needs before design starts, and make acceptance conditional on it. • Require any gap filled by assumption to be written into the design brief and confirmed by the client, not carried in someone's head. • Separate the client's words from the designer's interpretation in the record, since disputes turn on exactly this difference. • Set a time limit for accepting or returning a handover, so projects do not sit in limbo. • Register the project once, with one reference used by every discipline and every drawing from that point. |  | Yes
97 | Technical Engineering | Plan architectural site survey, measurement and information requirements | Architect (Lead) | Trigger: When the Architect receives an accepted technical lead or approved design instruction. Action: The Architect (Lead) completes “Plan architectural site survey, measurement and information requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled brief, survey record, constraints register and verified design inputs. Control/Handoff: Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When the Architect receives an accepted technical lead or approved design instruction. | The Architect (Lead) completes “Plan architectural site survey, measurement and information requirements” using the approved brief, source documents, calculations and controlled company systems. | a controlled brief, survey record, constraints register and verified design inputs. | Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect plans the site visit properly. What has to be measured, photographed and confirmed, and who will do it. • Starts when: a project is accepted and site information is needed before design can start. • How it runs: (1) the information the design will need is listed, working backwards from the deliverables. (2) Measurement scope and accuracy are set, including whether a specialist survey is required. (3) Access, permission and safety arrangements are confirmed. (4) The Architect agrees the plan with the CTO. (5) The team, date and equipment are fixed. • Proof it happened: the survey plan with its information checklist, the confirmed access permissions, and the assigned team and date. • Where it usually breaks: the survey is planned around what is easy to capture rather than what the design will need, and a second visit becomes unavoidable. | • Build the survey checklist backwards from the deliverables, so the visit collects what the drawings will require. • State when a professional measured survey is mandatory rather than optional, for example on existing buildings above a stated size or complexity. • Require written access permission and safety arrangements before travel, especially on occupied or live sites. • Set the accuracy and tolerance expected, since later coordination depends on it. • Log survey cost and time against the project, so repeat visits are visible. |  | Yes
98 | Technical Engineering | Record site conditions, photographs, dimensions, constraints and interfaces | Architect (Lead) | Trigger: When the Architect receives an accepted technical lead or approved design instruction. Action: The Architect (Lead) completes “Record site conditions, photographs, dimensions, constraints and interfaces” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled brief, survey record, constraints register and verified design inputs. Control/Handoff: Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When the Architect receives an accepted technical lead or approved design instruction. | The Architect (Lead) completes “Record site conditions, photographs, dimensions, constraints and interfaces” using the approved brief, source documents, calculations and controlled company systems. | a controlled brief, survey record, constraints register and verified design inputs. | Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: on site, the Architect records what is actually there. Dimensions, photographs, constraints and how the building meets its surroundings. • Starts when: the approved survey is carried out. • How it runs: (1) dimensions are taken against the checklist and recorded on marked-up plans. (2) Photographs are taken systematically, with location and direction identified. (3) Constraints, services and interfaces with neighbours or existing structures are noted. (4) Anything not accessible or not confirmed is recorded as an open item. (5) The survey record is checked for completeness and filed before the team demobilises. • Proof it happened: the survey record with marked-up dimensions, indexed photographs, a constraints list and the open items. • Where it usually breaks: photographs are taken without location references, so months later nobody can tell what they show or where they were taken. | • Require photographs to be indexed to a location key on the plan, with the view direction. Unreferenced photographs lose their value quickly. • Make the record what was actually found, with anything inaccessible listed as an open item rather than estimated silently. • Run the completeness check before the team leaves site, with a named checker. • Store the survey record in one controlled project location, so every discipline works from the same site information. • State how long site data stays valid before re-verification, since sites change during long design periods. |  | Yes
99 | Technical Engineering | Prepare controlled architectural design brief, assumptions and exclusions | Architect (Lead) | Trigger: When the Architect receives an accepted technical lead or approved design instruction. Action: The Architect (Lead) completes “Prepare controlled architectural design brief, assumptions and exclusions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled brief, survey record, constraints register and verified design inputs. Control/Handoff: Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When the Architect receives an accepted technical lead or approved design instruction. | The Architect (Lead) completes “Prepare controlled architectural design brief, assumptions and exclusions” using the approved brief, source documents, calculations and controlled company systems. | a controlled brief, survey record, constraints register and verified design inputs. | Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect writes down what is being designed, what has been assumed, and what is deliberately not included. • Starts when: the brief and survey are in hand and design is about to begin. • How it runs: (1) the client's requirements are restated in design terms, area by area or space by space. (2) Assumptions are listed where information is missing, each with the confirmation still needed. (3) Exclusions are stated so scope creep can be identified later. (4) The CTO approves the brief as a controlled document. (5) The client confirms it before substantive design work continues. • Proof it happened: a controlled architectural design brief with assumptions and exclusions, approved internally and confirmed by the client. • Where it usually breaks: the brief is never confirmed by the client, so every later change is presented as a correction rather than a variation. | • Require written client confirmation of the design brief before substantive design proceeds. It is the baseline every variation is measured against. • List assumptions individually with the information each is standing in for and the date it must be confirmed. • Write exclusions in plain language, including specialist scope such as interiors, landscape, kitchens and audio visual, where included or not. • Put the brief under version control, since it will change and the change history matters. • State clearly that a change to a confirmed brief is a variation, and name who is authorised to agree one. |  | Yes
100 | Technical Engineering | Identify planning, access, authority and project-specific design constraints | Architect (Lead) | Trigger: When the Architect receives an accepted technical lead or approved design instruction. Action: The Architect (Lead) completes “Identify planning, access, authority and project-specific design constraints” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled brief, survey record, constraints register and verified design inputs. Control/Handoff: Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When the Architect receives an accepted technical lead or approved design instruction. | The Architect (Lead) completes “Identify planning, access, authority and project-specific design constraints” using the approved brief, source documents, calculations and controlled company systems. | a controlled brief, survey record, constraints register and verified design inputs. | Missing client/site information is logged and returned through CTO/CMO; no unsupported assumption is treated as approved. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect finds out what the rules and the site will not allow, before the design commits to anything. • Starts when: the design brief is being prepared, or a new constraint emerges during design. • How it runs: (1) planning rules are checked: plot coverage, setbacks, height, use and parking. (2) Access, service connections and site constraints are established. (3) Authority-specific and project-specific requirements are identified. (4) Each constraint is recorded with its source, whether a regulation, a client requirement or a physical condition. (5) The constraints are carried into the design brief and the design basis. • Proof it happened: a constraints register showing each constraint, its source and its design implication. • Where it usually breaks: a constraint is verified verbally with someone at the authority and never recorded, so it cannot be relied on when the submission is rejected. | • Require every constraint to be recorded with its written source, whether a regulation clause, a client instruction or a survey finding. Verbal confirmations should be followed up in writing. • Keep a standing checklist of the planning parameters to verify per project type and authority. • State the date the constraint was verified, since regulations change and old checks go stale. • Carry constraints into the design basis rather than leaving them in a separate note, so designers work to them. • Add an escalation route for a constraint that makes the client's brief unachievable, since that is a commercial conversation, not just a design one. |  | Yes
101 | Technical Engineering | Develop preliminary site planning and space programme | Architect (Lead) | Trigger: When verified survey and client requirements are available for concept development. Action: The Architect (Lead) completes “Develop preliminary site planning and space programme” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled concept options, presentation record, client comments and concept-freeze status. Control/Handoff: CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When verified survey and client requirements are available for concept development. | The Architect (Lead) completes “Develop preliminary site planning and space programme” using the approved brief, source documents, calculations and controlled company systems. | controlled concept options, presentation record, client comments and concept-freeze status. | CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect works out roughly how the site will be used and how much space each function needs. • Starts when: the brief and constraints are established and concept design is starting. • How it runs: (1) the required functions and their areas are listed from the brief. (2) Site planning options are tested against the constraints: access, orientation, setbacks and services. (3) A space programme is built showing area per function and the total. (4) The programme is checked against the brief and the allowable built area. (5) The Architect issues the site planning and space programme for internal review. • Proof it happened: the site plan option with the space programme showing area by function, checked against the brief and the allowable area. • Where it usually breaks: the space programme is not reconciled against the permitted built area, so the design has to be cut back after the client has already fallen in love with it. | • Make reconciliation against the permitted built area a mandatory check before anything is shown to the client. • Require the space programme to show gross and net areas and the efficiency ratio, since that is where later disputes sit. • State the circulation, plant and service space allowances used, so they are not squeezed out later by MEP requirements. • Test at least the access and orientation options, and record why the chosen option was chosen. • Keep the space programme live as a controlled document, since it becomes the reference for area schedules later. |  | Yes
102 | Technical Engineering | Prepare alternative architectural concept options | Architect (Lead) | Trigger: When verified survey and client requirements are available for concept development. Action: The Architect (Lead) completes “Prepare alternative architectural concept options” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled concept options, presentation record, client comments and concept-freeze status. Control/Handoff: CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When verified survey and client requirements are available for concept development. | The Architect (Lead) completes “Prepare alternative architectural concept options” using the approved brief, source documents, calculations and controlled company systems. | controlled concept options, presentation record, client comments and concept-freeze status. | CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect prepares more than one way of solving the brief so the client has a real choice. • Starts when: the site planning and space programme are established and concept options are needed. • How it runs: (1) genuinely different options are developed, not variations of one idea. (2) Each option is tested against the brief, the constraints and the indicative budget. (3) The advantages and disadvantages of each are stated plainly. (4) An internal review selects the options worth presenting. (5) The Architect records why options were kept or dropped. • Proof it happened: the option set with a comparison against brief, constraints and budget, and the internal review record. • Where it usually breaks: options are cosmetic variants of the same scheme, so the client has no real choice and comes back later with a fundamentally different idea. | • State how many options are included in the fee and that they must be genuinely distinct, so option work is bounded and useful. • Require each option to be tested against the indicative budget, not just the brief. An unaffordable option wastes everyone's time. • Record why an option was dropped, since clients revisit discarded ideas months later. • Hold an internal review before client presentation, with the CTO, so weak options are not presented. • State what happens when the client asks for options beyond the included number. |  | Yes
103 | Technical Engineering | Prepare concept drawings, massing and material intent | Architect (Lead) | Trigger: When verified survey and client requirements are available for concept development. Action: The Architect (Lead) completes “Prepare concept drawings, massing and material intent” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled concept options, presentation record, client comments and concept-freeze status. Control/Handoff: CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When verified survey and client requirements are available for concept development. | The Architect (Lead) completes “Prepare concept drawings, massing and material intent” using the approved brief, source documents, calculations and controlled company systems. | controlled concept options, presentation record, client comments and concept-freeze status. | CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect draws up the chosen concept, its form and shape, and the intended look and materials. • Starts when: a concept direction is selected and a presentable package is needed. • How it runs: (1) concept plans, elevations and massing are prepared to a consistent standard. (2) Material and finish intent is indicated, with the level of commitment made clear. (3) Visuals are prepared where they are part of the agreed deliverable. (4) The package is checked against the brief and constraints before release. (5) The CTO approves the concept package for client presentation. • Proof it happened: the approved concept drawing package with the stated material intent, and the internal check record. • Where it usually breaks: visuals show finishes and features that were never priced, and the client expects every one of them in the finished building. | • Require a stated disclaimer on all visuals and material intent: indicative, subject to detailed design, specification and budget. Then hold to it. • Keep concept material intent aligned with the indicative budget, and flag any element that is aspirational rather than priced. • Set the concept deliverable list precisely: which drawings, which views, how many visuals, in what format. • Have the package checked against brief and constraints by someone other than the author before release. • Route all client issue through the agreed channel, so the version presented is the version approved. |  | Yes
104 | Technical Engineering | Present concept and feasibility basis to client and internal reviewers | Architect (Lead) | Trigger: When verified survey and client requirements are available for concept development. Action: The Architect (Lead) completes “Present concept and feasibility basis to client and internal reviewers” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled concept options, presentation record, client comments and concept-freeze status. Control/Handoff: CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When verified survey and client requirements are available for concept development. | The Architect (Lead) completes “Present concept and feasibility basis to client and internal reviewers” using the approved brief, source documents, calculations and controlled company systems. | controlled concept options, presentation record, client comments and concept-freeze status. | CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect presents the concept to the client and to internal reviewers, and explains what is feasible and what it rests on. • Starts when: the concept package is approved for presentation. • How it runs: (1) the internal review is held first, with the CTO and the commercial side present. (2) The presentation covers the brief, the constraints, the options and the budget basis. (3) Assumptions and exclusions are stated aloud, not buried in a footnote. (4) Client reactions, requirements and objections are recorded during the meeting. (5) Next steps and decisions required are agreed with dates. • Proof it happened: the presentation record with attendance, the recorded client feedback, and the agreed next steps. • Where it usually breaks: the presentation focuses on the appealing images and skips the constraints and the budget basis, so expectations are set that the project cannot meet. | • Make the internal review a required gate before any client presentation, attended by the CTO and the commercial owner. • Require the constraints, assumptions and budget basis to be presented explicitly as part of the agenda, not left to the appendix. • Record the meeting and issue the record to the client, so verbal agreements are captured while memories match. • Name who leads the presentation and who owns the commercial questions that come up in it. • Set the deadline for the client's decision, since concept stage drift consumes the design fee. |  | Yes
105 | Technical Engineering | Record client comments, design decisions and concept-freeze status | Architect (Lead) | Trigger: When verified survey and client requirements are available for concept development. Action: The Architect (Lead) completes “Record client comments, design decisions and concept-freeze status” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled concept options, presentation record, client comments and concept-freeze status. Control/Handoff: CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When verified survey and client requirements are available for concept development. | The Architect (Lead) completes “Record client comments, design decisions and concept-freeze status” using the approved brief, source documents, calculations and controlled company systems. | controlled concept options, presentation record, client comments and concept-freeze status. | CTO reviews feasibility and commercial implications; client decisions are recorded before detailed design proceeds. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect writes down what the client said, what was decided, and confirms the point at which the concept is frozen. • Starts when: the client responds to the concept, or a concept freeze is required to start detailed design. • How it runs: (1) client comments are logged individually with the response to each. (2) Design decisions are recorded with the date and who made them. (3) The revised concept is issued for confirmation. (4) The client confirms the freeze in writing. (5) From that point, changes are handled as variations, not as ongoing design. • Proof it happened: the comment log with responses, the recorded design decisions, and the written concept-freeze confirmation. • Where it usually breaks: no freeze is ever declared, so the concept keeps evolving while detailed design proceeds underneath it, and both have to be redone. | • Make the concept freeze a formal, dated, written milestone. Without it, detailed design has no stable base and the fee erodes. • State plainly that a change after freeze is a variation, and name who may accept one and on what commercial basis. • Log client comments individually with a response to each, so nothing is quietly dropped. • Set a limit on concept revision cycles included in the fee, consistent with the design agreement. • Require the frozen concept to be the documented input to detailed design, referenced by revision.
106 | Technical Engineering | Prepare coordinated architectural plans, elevations and sections | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Prepare coordinated architectural plans, elevations and sections” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Prepare coordinated architectural plans, elevations and sections” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect produces the proper working drawings. Plans, elevations and sections that all agree with each other. • Starts when: the concept is frozen and detailed design is under way. • How it runs: (1) drawings are produced to the company standard from the frozen concept. (2) Plans, elevations and sections are cross-checked for consistency. (3) Dimensions, levels and grids are coordinated with the structural grid. (4) Drawings are internally checked before they are shared with other disciplines. (5) The set is issued for coordination at the planned review point. • Proof it happened: the coordinated drawing set with the internal check records and the issue for coordination. • Where it usually breaks: plans get updated after a change but elevations and sections do not, so the set contradicts itself and site chooses whichever suits. | • Require a cross-consistency check between plans, elevations and sections at every revision, not only at the end. • Define the drawing standard once: scales, layers, title blocks, dimensioning and annotation conventions, and reference it here. • Fix grids, levels and datum jointly with the structural discipline before detailed drawings advance. • Have every drawing checked by a named person other than the preparer before it leaves architecture. • Keep a deliverable register showing the status and revision of every drawing, so coordination works from current information.
107 | Technical Engineering | Develop architectural details, schedules and specification requirements | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Develop architectural details, schedules and specification requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Develop architectural details, schedules and specification requirements” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect works out the parts of the building in detail, and writes the schedules and specification requirements that go with them. • Starts when: the general arrangement drawings are stable enough to detail. • How it runs: (1) the details needing design are identified, including junctions, waterproofing and interfaces. (2) Details are drawn from the standard details library where one exists, and newly designed where not. (3) Schedules for doors, windows and finishes are built from the drawings, not separately. (4) Specification requirements are drafted per element for the CTO's approval. (5) Details and schedules are checked against each other and against the drawings. • Proof it happened: the detail drawings, the element schedules, and the drafted specification requirements with the check records. • Where it usually breaks: schedules are maintained separately from the drawings, so a door changes on the plan and the schedule still shows the old one. | • Require schedules to be generated from or reconciled against the drawings at each revision. Independently maintained schedules always drift. • Build and maintain a standard details library, and state that project details start from it and deviations are justified. • List the details that are mandatory for every project, particularly waterproofing, thresholds, parapets and wet area junctions. • Route specification requirements through the CTO for approval, consistent with the approved brands and materials process. • Cross-check details against structure and MEP before issue, since junctions are where disciplines collide.
108 | Technical Engineering | Coordinate finishes, materials, colours and sample requirements | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Coordinate finishes, materials, colours and sample requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Coordinate finishes, materials, colours and sample requirements” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect settles the finishes, materials and colours, and manages the samples the client has to approve. • Starts when: finishes selection is due, or a material needs client or authority approval. • How it runs: (1) finishes are selected per space against the brief, the budget and technical suitability. (2) Availability and lead time are checked with Procurement. (3) Samples or boards are prepared for client approval. (4) Client approval is recorded per item, not as a general nod at a board. (5) The approved finishes schedule is issued and controlled. • Proof it happened: the approved finishes schedule with the recorded client approval per item, and the retained approved samples. • Where it usually breaks: finishes are approved from a board with no record of the exact product code, and what arrives on site is not what the client believed they chose. | • Require client approval to be recorded per item with the exact product reference, colour code and finish, not as approval of a board. • Retain the approved physical sample, labelled and dated, since it is the reference for accepting delivered material. • Check lead time and availability with Procurement before a finish is presented, so approved selections are actually obtainable. • Check technical suitability as well as appearance, particularly slip resistance, wet areas, fire rating and external durability. • Handle substitution through the same approval route as the original selection, with the client informed.
109 | Technical Engineering | Coordinate accessibility, fire-life-safety and planning design requirements | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Coordinate accessibility, fire-life-safety and planning design requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Coordinate accessibility, fire-life-safety and planning design requirements” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect makes sure the design meets the accessibility, fire safety and planning rules, not just the client's taste. • Starts when: the design is developed enough to test against regulations, and at every subsequent change. • How it runs: (1) the applicable accessibility, fire and planning requirements are identified for the building type. (2) The design is checked against each: escape routes, travel distances, ratings, access and facilities. (3) Specialist or authority input is obtained where required. (4) Non-compliances are corrected in the design, not noted for later. (5) Compliance evidence is recorded for the authority submission. • Proof it happened: a compliance check record against each requirement, with the evidence for the authority submission. • Where it usually breaks: compliance is checked once and then a plan change moves a wall, and nobody rechecks travel distances or accessible routes. | • Require a compliance recheck at every design change that affects layout, since one moved wall can break escape and accessibility compliance. • Keep a compliance checklist per building type, referencing the actual regulation clause for each item. • State when specialist fire or accessibility input is mandatory rather than discretionary. • Record the compliance evidence as it is produced, so the authority submission is assembled rather than reconstructed. • Treat a non-compliance as a design defect requiring correction and closure, with an owner and a date.
110 | Technical Engineering | Review constructability, tolerances, waterproofing and buildability interfaces | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Review constructability, tolerances, waterproofing and buildability interfaces” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Review constructability, tolerances, waterproofing and buildability interfaces” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect checks the design can actually be built, with the tolerances, waterproofing and interfaces that real construction needs. • Starts when: the design is developed and before construction-ready release, and whenever a detail changes materially. • How it runs: (1) the design is reviewed for buildability: access, sequence, tolerances and available trades. (2) Waterproofing and weather protection are reviewed as a continuous system, not detail by detail. (3) Interfaces between trades and materials are checked for movement, tolerance and durability. (4) Site or projects input is sought where useful. (5) Findings are corrected in the design and the closure is recorded. • Proof it happened: the constructability review record with the findings and their closure in the design. • Where it usually breaks: the review is done by the designer alone, so the problems that only site people see are found later on site as RFIs. | • Involve Projects or site experience in the constructability review. A designer reviewing their own buildability finds the least. • Review waterproofing as a continuous system across details, since leaks happen at the junctions between correct details. • Use a buildability checklist covering tolerances, access for installation, sequence and available local trade skills. • Make findings a tracked list with closure evidence, not meeting notes. • Feed recurring buildability issues back into the standard details, so the same problem is not designed in again.
111 | Technical Engineering | Maintain area schedules, room data and design deliverable registers | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Maintain area schedules, room data and design deliverable registers” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Maintain area schedules, room data and design deliverable registers” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect keeps the running records of areas, room data and which drawings exist at which revision. • Starts when: the project is set up, then continuously as the design develops. • How it runs: (1) the area schedule is maintained against the space programme and the permitted area. (2) Room data is recorded per space: finishes, services requirements and equipment. (3) The deliverable register lists every drawing with its status, revision and owner. (4) The registers are updated at each revision, not at the end. (5) They are reconciled against the drawings at defined checkpoints. • Proof it happened: current area schedules, room data sheets and a deliverable register reconciled against the issued drawings. • Where it usually breaks: the registers are updated in a burst before a deadline, so between deadlines nobody can tell what the current revision actually is. | • Require the deliverable register to be updated when a drawing changes, not periodically. It is the only reliable answer to what is current. • Reconcile area schedules against the permitted area and the space programme at each design stage, since area creep is expensive and slow to spot. • Name a single owner for the registers, with a deputy, so accuracy does not depend on whoever is available. • Keep room data as the source for the finishes and MEP requirements per space, so disciplines share one reference. • Report register status at design reviews: total deliverables, issued, in progress and overdue.
112 | Technical Engineering | Monitor architectural programme, deliverable status and overdue actions | Architect (Lead) | Trigger: When concept freeze and design activation are approved. Action: The Architect (Lead) completes “Monitor architectural programme, deliverable status and overdue actions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated architectural drawings, schedules, details, specifications and status records. Control/Handoff: Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When concept freeze and design activation are approved. | The Architect (Lead) completes “Monitor architectural programme, deliverable status and overdue actions” using the approved brief, source documents, calculations and controlled company systems. | coordinated architectural drawings, schedules, details, specifications and status records. | Architect checks compliance and constructability; discipline dependencies are recorded and escalated before issue. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect tracks whether architectural work is on programme, and chases what is late. • Starts when: design is under way, then at each planned progress checkpoint. • How it runs: (1) actual deliverable status is compared with the programme. (2) Overdue items are identified with the reason and the effect on other disciplines. (3) Dependencies on client or third party information are flagged where they are the cause. (4) Recovery actions are agreed with owners and dates. (5) Anything affecting the project milestone is escalated to the CTO rather than absorbed. • Proof it happened: the progress report against programme, the overdue list with causes, and the recovery actions with owners. • Where it usually breaks: slippage is absorbed quietly in the hope of catching up, and the CTO learns about it when the milestone is already missed. | • Set an escalation trigger in days, so slippage is reported at a defined point rather than when someone decides it is serious. • Report the cause with the delay, distinguishing internal capacity, client information and third party dependencies. The remedies are different. • Track the effect on downstream disciplines, since architectural delay usually stalls structure and MEP. • Log client information requests with the date needed, so external causes are evidenced and not argued about later. • Keep the reporting short and frequent rather than detailed and monthly.
113 | Technical Engineering | Coordinate architectural design with structural requirements | Architect (Lead) | Trigger: When architectural, structural and MEP information reaches a coordination milestone. Action: The Architect (Lead) completes “Coordinate architectural design with structural requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed coordination comments, clash decisions, interface drawings and updated discipline packages. Control/Handoff: Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural, structural and MEP information reaches a coordination milestone. | The Architect (Lead) completes “Coordinate architectural design with structural requirements” using the approved brief, source documents, calculations and controlled company systems. | closed coordination comments, clash decisions, interface drawings and updated discipline packages. | Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect and the structural designer make sure the building's shape and its structure agree. • Starts when: structural design begins, and at every change to grids, levels or loads. • How it runs: (1) grids, levels and datum are agreed jointly and fixed. (2) Structural element sizes and positions are reflected in the architectural drawings. (3) Openings, recesses and slab edges are coordinated in both directions. (4) Conflicts are logged and resolved through the clash process rather than informally. (5) Both disciplines confirm alignment at the defined coordination points. • Proof it happened: the coordination record confirming agreed grids, levels and element positions in both discipline sets. • Where it usually breaks: a column grows in the structural design and the architectural plan is never updated, so the room loses space nobody accounted for. | • Fix grids, levels and datum jointly and formally, and treat any change as a coordinated revision affecting both disciplines. • Require structural element sizes to be reflected in architectural drawings at each structural revision, with a check that it happened. • Coordinate openings in both directions, so neither discipline adds one unilaterally. • Log conflicts in the shared clash register rather than resolving them verbally between two designers. • Set the coordination checkpoints in the programme, so alignment is verified at known points.
114 | Technical Engineering | Coordinate architectural design with HVAC, plumbing and electrical routes | Architect (Lead) | Trigger: When architectural, structural and MEP information reaches a coordination milestone. Action: The Architect (Lead) completes “Coordinate architectural design with HVAC, plumbing and electrical routes” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed coordination comments, clash decisions, interface drawings and updated discipline packages. Control/Handoff: Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural, structural and MEP information reaches a coordination milestone. | The Architect (Lead) completes “Coordinate architectural design with HVAC, plumbing and electrical routes” using the approved brief, source documents, calculations and controlled company systems. | closed coordination comments, clash decisions, interface drawings and updated discipline packages. | Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect makes sure there is somewhere for the ducts, pipes and cables to go, and enough ceiling space to fit them. • Starts when: MEP design develops, and at each change to layouts, ceilings or plant. • How it runs: (1) MEP routes and required space are overlaid on the architectural drawings. (2) Ceiling voids, risers, shafts and plant rooms are checked for adequacy. (3) Access for installation and maintenance is verified, not just physical fit. (4) Conflicts go into the clash register with an owner. (5) Resolutions are reflected in both the architectural and MEP sets. • Proof it happened: the coordination record and clash closure showing routes, voids and plant space agreed by both disciplines. • Where it usually breaks: the ceiling void is agreed on paper with no allowance for crossings and insulation, so ducts and drainage cannot both fit and the ceiling drops. | • Set the required ceiling void, riser and plant space allowances early, including an allowance for crossings, insulation and installation clearance. • Verify maintenance and replacement access as a distinct check, since physical fit alone creates buildings that cannot be serviced. • Require MEP routes to be overlaid on the architectural background at defined checkpoints, using a shared coordinate system. • Resolve conflicts through the clash register with closure reflected in both sets. • Confirm the final ceiling levels only after MEP coordination is closed, not before.
115 | Technical Engineering | Coordinate openings, builders work, plant spaces and ceiling interfaces | Architect (Lead) | Trigger: When architectural, structural and MEP information reaches a coordination milestone. Action: The Architect (Lead) completes “Coordinate openings, builders work, plant spaces and ceiling interfaces” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed coordination comments, clash decisions, interface drawings and updated discipline packages. Control/Handoff: Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural, structural and MEP information reaches a coordination milestone. | The Architect (Lead) completes “Coordinate openings, builders work, plant spaces and ceiling interfaces” using the approved brief, source documents, calculations and controlled company systems. | closed coordination comments, clash decisions, interface drawings and updated discipline packages. | Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect coordinates the holes, chases and plant spaces the services need through the building fabric. • Starts when: MEP routes are developed enough to define openings and builders work. • How it runs: (1) MEP provides required openings, sleeves and builders work with sizes and positions. (2) Architecture checks them against the layout, finishes and appearance. (3) Structure confirms they are acceptable where they pass through structural elements. (4) The agreed openings are shown on the architectural and structural drawings. (5) A builders-work schedule is produced so nothing is left to be cut on site. • Proof it happened: the agreed builders-work and openings schedule reflected in the architectural and structural drawings. • Where it usually breaks: openings are missed at design stage and cut on site afterwards, which damages structure, finishes and the programme. | • Produce a builders-work schedule as a required deliverable before construction release. Openings cut later cost far more than openings designed. • Require structural confirmation for every opening through a structural element, with no exceptions on site. • Set a cut-off point after which new openings become a formal change, since late additions are the main cause of structural damage. • Coordinate plant space with access, ventilation and noise requirements, not only footprint. • Cross-check the schedule against the MEP drawings before issue, since these lists drift apart easily.
116 | Technical Engineering | Lead clash review, design-comment allocation and closure | Architect (Lead) | Trigger: When architectural, structural and MEP information reaches a coordination milestone. Action: The Architect (Lead) completes “Lead clash review, design-comment allocation and closure” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed coordination comments, clash decisions, interface drawings and updated discipline packages. Control/Handoff: Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural, structural and MEP information reaches a coordination milestone. | The Architect (Lead) completes “Lead clash review, design-comment allocation and closure” using the approved brief, source documents, calculations and controlled company systems. | closed coordination comments, clash decisions, interface drawings and updated discipline packages. | Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect runs the clash review, decides which discipline owns each comment, and drives them all to closure. • Starts when: a coordination review is due, or clashes are raised between disciplines. • How it runs: (1) the disciplines' current drawings are brought together for review. (2) Clashes and design comments are logged individually. (3) Each item is allocated to a responsible discipline with a closure date. (4) Resolutions are verified in the updated drawings, not just reported. (5) Items that cannot be resolved between disciplines go to the CTO for decision. • Proof it happened: the clash and comment register showing owner, resolution, verification and closure per item. • Where it usually breaks: items are marked closed on the strength of a reply rather than a checked drawing, so they reappear at IFC. | • Close a clash only against a verified updated drawing, never against a verbal or written assurance. • Allocate every item to one discipline with a date, and report open items by age at each review. • Escalate to the CTO after a stated period, so an item cannot sit between two disciplines indefinitely. • Use one register across all disciplines rather than separate lists, so the total picture is visible. • Require a final clash status report as an entry condition for construction-ready approval.
117 | Technical Engineering | Review specialist-consultant and vendor design interfaces | Architect (Lead) | Trigger: When architectural, structural and MEP information reaches a coordination milestone. Action: The Architect (Lead) completes “Review specialist-consultant and vendor design interfaces” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed coordination comments, clash decisions, interface drawings and updated discipline packages. Control/Handoff: Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural, structural and MEP information reaches a coordination milestone. | The Architect (Lead) completes “Review specialist-consultant and vendor design interfaces” using the approved brief, source documents, calculations and controlled company systems. | closed coordination comments, clash decisions, interface drawings and updated discipline packages. | Each discipline owns its corrections; unresolved scope, geometry, performance or programme conflict escalates to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: where specialists or vendors design part of the building, the Architect checks their work fits the rest of it. • Starts when: a specialist consultant or vendor design is received, such as facade, kitchen, lift or audio visual. • How it runs: (1) the interface and the responsibility boundary are defined before the specialist starts. (2) The submitted design is reviewed against the architectural intent, dimensions and specification. (3) Interfaces with structure and MEP are checked, including loads and services requirements. (4) Comments are issued and closure tracked. (5) The accepted specialist design is incorporated into the coordinated set with the source recorded. • Proof it happened: the interface definition, the review comments and their closure, and the incorporation of the accepted design into the coordinated drawings. • Where it usually breaks: the specialist design is accepted as the specialist's responsibility and never coordinated, so its structural and services requirements surface during installation. | • Define the responsibility boundary in writing before the specialist starts, including who checks what and who carries the design liability. • Require the specialist's structural and services requirements to be coordinated with those disciplines, not accepted in isolation. • Set a review turnaround time, since specialist submissions usually sit on the procurement critical path. • Record which parts of the coordinated design originate from the specialist, so later changes reach the right party. • Check that the specialist design does not quietly alter the approved architectural appearance or the specification.
118 | Technical Engineering | Compile architectural authority and NOC submission package | Architect (Lead) | Trigger: When an architectural authority/NOC submission or comment response becomes due. Action: The Architect (Lead) completes “Compile architectural authority and NOC submission package” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled submission, response matrix, revised drawings and approval evidence. Control/Handoff: CTO authorises submission; Document Control records issue and receipt; rejected or overdue matters are escalated. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When an architectural authority/NOC submission or comment response becomes due. | The Architect (Lead) completes “Compile architectural authority and NOC submission package” using the approved brief, source documents, calculations and controlled company systems. | a controlled submission, response matrix, revised drawings and approval evidence. | CTO authorises submission; Document Control records issue and receipt; rejected or overdue matters are escalated. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect puts together the architectural package the authority needs to approve the project. • Starts when: an architectural authority or no-objection submission is required. • How it runs: (1) the authority's requirements and checklist for the submission are confirmed. (2) Drawings are prepared or adapted to the authority's format and scale requirements. (3) Forms, calculations, ownership documents and licence details are collected. (4) The package is checked against the authority's checklist. (5) It goes to the CTO for authorisation before submission. • Proof it happened: the compiled submission package with the completed checklist and the CTO's authorisation. • Where it usually breaks: the package is built to the internal drawing standard rather than the authority's format, and it is rejected for presentation rather than substance. | • Keep an authority requirements sheet per authority and project type, covering format, scale, sheet size, stamps and required documents. • Require the authority's own checklist to be completed and signed internally before the package is authorised. • Confirm who holds the licence or stamp required for submission and that it is valid. • Record the submission date, reference and expected response, so follow-up does not depend on individual memory. • Keep the submitted set under revision control, since the approved set becomes the reference for construction and any later amendment.
119 | Technical Engineering | Respond to architectural authority comments and resubmission requirements | Architect (Lead) | Trigger: When an architectural authority/NOC submission or comment response becomes due. Action: The Architect (Lead) completes “Respond to architectural authority comments and resubmission requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled submission, response matrix, revised drawings and approval evidence. Control/Handoff: CTO authorises submission; Document Control records issue and receipt; rejected or overdue matters are escalated. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When an architectural authority/NOC submission or comment response becomes due. | The Architect (Lead) completes “Respond to architectural authority comments and resubmission requirements” using the approved brief, source documents, calculations and controlled company systems. | a controlled submission, response matrix, revised drawings and approval evidence. | CTO authorises submission; Document Control records issue and receipt; rejected or overdue matters are escalated. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: when the authority comes back with comments, the Architect answers them and resubmits. • Starts when: the authority issues comments, a rejection or a request for further information. • How it runs: (1) the comments are logged individually with the clause or requirement behind each. (2) The design response is prepared, involving other disciplines where the comment affects them. (3) Where a comment forces a design change, the change goes through the normal change process. (4) The response and revised package go to the CTO for authorisation. (5) The resubmission is logged and tracked. • Proof it happened: the authority comment log with the response to each, and the authorised resubmission with its date and reference. • Where it usually breaks: comments are answered by revising the submission drawings only, and the construction drawings are never updated to match. | • Require every authority-driven design change to be carried into the construction drawing set, not only the submission set. Two diverging sets is a serious risk. • Log comments individually with the response and the resulting drawing revision, so nothing is answered in general terms. • Involve the affected disciplines before responding, since authority comments frequently have structural or MEP consequences. • Track resubmission cycles per project and their causes, because repeat cycles are usually the same avoidable issues. • Report to the CTO and the project when a comment affects cost or programme, rather than treating it as purely technical.
120 | Technical Engineering | Close authority comments and update the approved architectural design basis | Architect (Lead) | Trigger: When an architectural authority/NOC submission or comment response becomes due. Action: The Architect (Lead) completes “Close authority comments and update the approved architectural design basis” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled submission, response matrix, revised drawings and approval evidence. Control/Handoff: CTO authorises submission; Document Control records issue and receipt; rejected or overdue matters are escalated. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When an architectural authority/NOC submission or comment response becomes due. | The Architect (Lead) completes “Close authority comments and update the approved architectural design basis” using the approved brief, source documents, calculations and controlled company systems. | a controlled submission, response matrix, revised drawings and approval evidence. | CTO authorises submission; Document Control records issue and receipt; rejected or overdue matters are escalated. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: once the authority is satisfied, the Architect closes out the comments and updates the approved design record. • Starts when: the authority approves, or the last comment is resolved. • How it runs: (1) each comment is confirmed closed against the authority's response. (2) The approved drawings and conditions are recorded, including any condition attached to the approval. (3) The design basis and the drawing set are updated to the approved position. (4) Approval conditions are handed to Projects, since many are construction obligations. (5) The approval and its documents are archived under Document Control. • Proof it happened: the closed comment log, the approval with its conditions recorded, and the updated design basis. • Where it usually breaks: the approval arrives with conditions attached and nobody extracts them, so obligations surface at completion when the authority inspects. | • Require approval conditions to be extracted into a tracked list with owners and dates, and handed to Projects formally. This is the step most often missed. • Update the design basis and drawing set to the approved position, and record which revision the approval relates to. • Confirm every comment closed against the authority's own response rather than internal opinion. • Archive the approval, drawings and correspondence together, since completion certification depends on them. • State what happens if construction later deviates from the approved drawings, and who must be told.
121 | Technical Engineering | Perform final architectural IFC completeness and coordination check | Architect (Lead) | Trigger: When architectural design is ready for construction issue, site support or closeout. Action: The Architect (Lead) completes “Perform final architectural IFC completeness and coordination check” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. Control/Handoff: Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural design is ready for construction issue, site support or closeout. | The Architect (Lead) completes “Perform final architectural IFC completeness and coordination check” using the approved brief, source documents, calculations and controlled company systems. | an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. | Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: before drawings go out for construction, the Architect does the last full check that the set is complete and consistent. • Starts when: the architectural set is proposed for construction-ready release. • How it runs: (1) the deliverable register is checked against the set for missing drawings. (2) Plans, elevations, sections, details and schedules are cross-checked for consistency. (3) Coordination with structure and MEP is confirmed closed. (4) Authority conditions and design changes are confirmed incorporated. (5) The completed check goes to the CTO with the release recommendation. • Proof it happened: the completed IFC check record, signed by a named checker, supporting the release. • Where it usually breaks: the check is a sign-off rather than a check, so missing details and superseded references travel into the construction set. | • Use a written IFC checklist signed by a named checker who did not prepare the drawings, and retain it as evidence. • Check the set against the deliverable register for completeness, not just the drawings that happen to exist. • Confirm clash closure and authority incorporation as explicit entry conditions for release. • Check that referenced details, schedules and specifications exist and are current, since dead references are common. • Record any item released with a known open point, notify Projects, and track it to closure.
122 | Technical Engineering | Issue controlled architectural package and revision index to Document Control | Architect (Lead) | Trigger: When architectural design is ready for construction issue, site support or closeout. Action: The Architect (Lead) completes “Issue controlled architectural package and revision index to Document Control” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. Control/Handoff: Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural design is ready for construction issue, site support or closeout. | The Architect (Lead) completes “Issue controlled architectural package and revision index to Document Control” using the approved brief, source documents, calculations and controlled company systems. | an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. | Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect hands the controlled drawing package and its revision list to Document Control for issue. • Starts when: the CTO has authorised the construction-ready release, or a revision is being issued. • How it runs: (1) drawings are finalised with correct number, revision, status and purpose of issue. (2) The revision index is prepared listing every drawing and its current revision. (3) The package and index go to Document Control, which issues and records the transmittal. (4) Superseded revisions are formally withdrawn. (5) The architectural registers are updated to match what was issued. • Proof it happened: the transmittal record from Document Control, the revision index issued with it, and the updated registers. • Where it usually breaks: designers send drawings directly to site to save time, so Document Control's record is incomplete and nobody knows what site actually holds. | • Prohibit direct issue from designers to site or vendors. Everything goes through Document Control so one record exists. • Require a revision index with every issue, listing the current revision of every drawing, so recipients can verify what they hold. • Make withdrawal of superseded revisions an explicit step with confirmation from the recipient. • State the required naming and numbering convention, and make compliance a condition of issue. • Reconcile the architectural register against Document Control's record periodically, since these two diverge quietly.
123 | Technical Engineering | Conduct architectural technical handover to Projects | Architect (Lead) | Trigger: When architectural design is ready for construction issue, site support or closeout. Action: The Architect (Lead) completes “Conduct architectural technical handover to Projects” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. Control/Handoff: Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural design is ready for construction issue, site support or closeout. | The Architect (Lead) completes “Conduct architectural technical handover to Projects” using the approved brief, source documents, calculations and controlled company systems. | an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. | Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: the Architect briefs the Projects team on the design, what it assumes, and what still needs watching. • Starts when: the design is released for construction and the project is being activated for delivery. • How it runs: (1) the handover pack is assembled: drawings, schedules, specification, approvals, conditions and open items. (2) A briefing is held with the Projects team, not just a file transfer. (3) Critical details, tolerances and sequence-sensitive elements are highlighted. (4) Open items and design assumptions are listed with owners. (5) The handover is recorded and signed by both sides. • Proof it happened: the signed architectural handover record with the pack list, the open items and the briefing attendance. • Where it usually breaks: the design intent behind the critical details is never explained, so site builds them in the easiest way and the performance is lost. | • Require a briefing session as part of the handover, not just a document transfer. Design intent does not travel in a folder. • Highlight the critical details and tolerances explicitly, including waterproofing and anything sequence sensitive. • List open items and assumptions with owners and dates, and confirm Projects accepts them. • Include the authority approval conditions in the pack, since they are construction obligations. • Agree the design support arrangement: RFI response times, site visit frequency and who attends.
124 | Technical Engineering | Respond to site RFIs and review architectural shop drawings and material submittals | Architect (Lead) | Trigger: When architectural design is ready for construction issue, site support or closeout. Action: The Architect (Lead) completes “Respond to site RFIs and review architectural shop drawings and material submittals” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. Control/Handoff: Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural design is ready for construction issue, site support or closeout. | The Architect (Lead) completes “Respond to site RFIs and review architectural shop drawings and material submittals” using the approved brief, source documents, calculations and controlled company systems. | an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. | Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: during construction the Architect answers site questions and checks the contractor's shop drawings and material submissions. • Starts when: site raises an RFI, or a shop drawing or material submittal is received for review. • How it runs: (1) the item is registered with its date and required response time. (2) The review is done against the approved design, specification and approved brands. (3) Comments are issued as approved, approved with comment or rejected, with reasons. (4) Where the answer changes the design, a controlled revision follows the response. (5) The register tracks turnaround and closure. • Proof it happened: the RFI and submittal register with dates, decisions and comments, and any controlled revisions arising. • Where it usually breaks: submittals are approved under time pressure without checking against the specification, and the substitution enters the building with the approval on record. | • Require submittals to be checked against the approved specification and brand list, with the reviewer named. A rushed approval transfers the risk to the company. • Use clear decision categories with reasons, and state that approval does not relieve the contractor of their obligations. • Follow any RFI answer that changes the design with a controlled drawing revision. • Set and report turnaround times, since design response delay becomes a contractor claim. • Track the volume and cause of RFIs by area, and feed the pattern back into design quality.
125 | Technical Engineering | Review architectural as-built records, close design punch items and capture lessons learned | Architect (Lead) | Trigger: When architectural design is ready for construction issue, site support or closeout. Action: The Architect (Lead) completes “Review architectural as-built records, close design punch items and capture lessons learned” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. Control/Handoff: Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. Continuity/Escalation: A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. Timing: To be confirmed. | When architectural design is ready for construction issue, site support or closeout. | The Architect (Lead) completes “Review architectural as-built records, close design punch items and capture lessons learned” using the approved brief, source documents, calculations and controlled company systems. | an IFC/handover package, RFI/submittal response, inspection record or reviewed as-built file. | Only approved revisions are issued to Projects; material site deviation and repeated design failure escalate to CTO. | A nominated qualified discipline lead may coordinate routine actions; unresolved client, authority, scope, interface or programme risk escalates to CTO. | To be confirmed. | • In plain words: at the end the Architect checks the as-built records, closes the outstanding design snags, and captures what should be done differently next time. • Starts when: the project reaches completion and architectural closeout is due. • How it runs: (1) contractor red-lines are reviewed and verified against site reality. (2) As-built architectural drawings are confirmed as complete and consistent. (3) Design-related punch items are inspected and closed with evidence. (4) Lessons learned are recorded with the cause and the document that should change. (5) The closeout package goes to the CTO and into the archive. • Proof it happened: verified as-built architectural drawings, the closed punch list with evidence, and a lessons-learned record with actions. • Where it usually breaks: lessons learned are written down and filed, and the standard details and checklists they were meant to improve are never touched. | • Give each lesson learned a target document and an owner, whether the standard detail, the specification or the checklist. A lesson that changes nothing is not a lesson. • Require as-builts to be verified against site rather than accepted from the contractor's mark-ups alone. • Separate design-caused punch items from workmanship items, since only the first belongs to architecture and the distinction matters commercially. • Set the closeout pack contents as a checklist, including approved samples, finishes schedules and authority documents. • Tie closeout completion to the design fee retention milestone, so it actually gets finished.
126 | Technical Engineering | Receive approved architectural inputs, mark-ups and drawing instructions | Civil Draftsman | Trigger: When an approved drafting instruction or project setup requirement is issued. Action: The Civil Draftsman completes “Receive approved architectural inputs, mark-ups and drawing instructions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled CAD setup, reference file and compliant drawing template. Control/Handoff: The Architect verifies design inputs; unclear or conflicting instructions are returned before drafting starts. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When an approved drafting instruction or project setup requirement is issued. | The Civil Draftsman completes “Receive approved architectural inputs, mark-ups and drawing instructions” using the approved brief, source documents, calculations and controlled company systems. | a controlled CAD setup, reference file and compliant drawing template. | The Architect verifies design inputs; unclear or conflicting instructions are returned before drafting starts. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman takes the Architect's approved mark-ups and instructions and checks they are clear enough to draw from before starting. • Starts when: the Architect issues inputs, mark-ups or a drawing instruction to the drafting team. • How it runs: (1) the inputs are checked for legibility, revision and completeness. (2) Anything ambiguous or contradictory is queried before drawing, not interpreted. (3) The revision being drawn from is recorded on the task. (4) The scope and target date are confirmed. (5) The task is logged in the drafting workload list. • Proof it happened: the logged drafting task showing the input revision drawn from, with the queries raised and answered. • Where it usually breaks: the Draftsman guesses at an unclear mark-up rather than asking, and the error is only found after the drawing has been checked, issued and used. | • Require the input revision to be recorded against every drafting task. This is the only way to prove which information a drawing was drawn from. • State plainly that unclear or contradictory mark-ups must be queried, never interpreted, and make the query route quick enough that people use it. • Set a minimum standard for what an acceptable mark-up looks like, so drafting is not asked to work from unusable input. • Log every task with target date and status, so workload and priority are visible rather than negotiated informally. • Reject and return incomplete inputs rather than starting on partial information.
127 | Technical Engineering | Set up project CAD files, coordinates, layers, title blocks and drawing standards | Civil Draftsman | Trigger: When an approved drafting instruction or project setup requirement is issued. Action: The Civil Draftsman completes “Set up project CAD files, coordinates, layers, title blocks and drawing standards” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled CAD setup, reference file and compliant drawing template. Control/Handoff: The Architect verifies design inputs; unclear or conflicting instructions are returned before drafting starts. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When an approved drafting instruction or project setup requirement is issued. | The Civil Draftsman completes “Set up project CAD files, coordinates, layers, title blocks and drawing standards” using the approved brief, source documents, calculations and controlled company systems. | a controlled CAD setup, reference file and compliant drawing template. | The Architect verifies design inputs; unclear or conflicting instructions are returned before drafting starts. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman sets up the project drawing files correctly at the start. Coordinates, layers, title blocks and standards. • Starts when: a new project is assigned to drafting. • How it runs: (1) the project folder and file structure are created to the standard. (2) The project coordinate system, units and datum are set and agreed with the other disciplines. (3) The approved title block is applied with the correct project information. (4) Layer and drawing standards are applied from the template, not built from scratch. (5) The setup is checked before production drawing begins. • Proof it happened: the project CAD setup record showing coordinates, units, title block and standards applied and checked. • Where it usually breaks: each discipline sets up its own coordinates, so overlaying drawings later requires manual shifting and things end up in the wrong place. | • Fix one project coordinate system, unit and datum for all disciplines at setup, and record it. Overlay coordination is impossible without this. • Require setup from the approved template rather than by copying a previous project, since old projects carry old errors. • Have the setup checked by a second person before production starts. Fixing setup later means redoing drawings. • Standardise the file and folder naming, so files can be found by someone other than the author. • Record the software version used, since version differences break references and printing.
128 | Technical Engineering | Maintain approved drawing templates, symbols and standard details | Civil Draftsman | Trigger: When an approved drafting instruction or project setup requirement is issued. Action: The Civil Draftsman completes “Maintain approved drawing templates, symbols and standard details” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled CAD setup, reference file and compliant drawing template. Control/Handoff: The Architect verifies design inputs; unclear or conflicting instructions are returned before drafting starts. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When an approved drafting instruction or project setup requirement is issued. | The Civil Draftsman completes “Maintain approved drawing templates, symbols and standard details” using the approved brief, source documents, calculations and controlled company systems. | a controlled CAD setup, reference file and compliant drawing template. | The Architect verifies design inputs; unclear or conflicting instructions are returned before drafting starts. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman looks after the company's drawing templates, symbols and standard details so every project starts from the same base. • Starts when: a template or standard detail needs creating, updating or reissuing. • How it runs: (1) the change or addition needed is identified, often from a project or a lessons-learned action. (2) The update is drafted. (3) The Architect or CTO approves it, since standard details carry technical liability. (4) The approved version is issued into the library with a version number. (5) The superseded version is removed from use. • Proof it happened: the version-controlled template and detail library with the approval record for each change. • Where it usually breaks: people keep private copies of templates and details, so the library becomes advisory and every project drifts. | • Hold the library in one controlled location, read only, with no private copies. A library people can edit locally is not a standard. • Require technical approval from the Architect or CTO for any standard detail change, since these details carry liability across every project. • Version the library and record what changed, so a project can identify which version it used. • Feed lessons learned and recurring site issues into the library deliberately, with an owner and a review cycle. • Remove superseded details from the library rather than leaving them alongside the current ones.
129 | Technical Engineering | Prepare existing-condition and measured-survey drawings | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare existing-condition and measured-survey drawings” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare existing-condition and measured-survey drawings” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman turns the site survey information into drawings showing what is actually there now. • Starts when: survey or measured data is available and existing-condition drawings are required. • How it runs: (1) the survey record and photographs are reviewed against the checklist. (2) Existing conditions are drawn to the standard, with levels and dimensions as recorded. (3) Assumed or unverified information is marked as such on the drawing. (4) The drawing is checked back against the survey record. (5) It is issued to the Architect for verification. • Proof it happened: the existing-condition drawings with the survey source recorded and the areas marked as unverified. • Where it usually breaks: gaps in the survey are drawn as if they were measured, so the design is built on dimensions nobody actually took. | • Require unverified or assumed information to be marked on the drawing itself, not just mentioned in an email. Everyone downstream reads the drawing. • Record the survey source and date on the drawing, since site conditions change and old surveys mislead. • Check the drawing back against the survey record by a named checker before issue. • Set a route for reporting survey gaps back for a return visit, rather than filling them by assumption. • Keep existing conditions on a separate layer or drawing from the proposed design, so the difference is always clear.
130 | Technical Engineering | Prepare location, site and setting-out drawings | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare location, site and setting-out drawings” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare location, site and setting-out drawings” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman prepares the drawings that tell site where the building actually sits and how to set it out. • Starts when: location, site or setting-out drawings are required for approval or construction. • How it runs: (1) the site boundary, plot details and access are drawn from the survey and title information. (2) The building position is dimensioned from fixed, verifiable references, not from other buildings. (3) Grid references, levels and datum are shown. (4) Setback and boundary dimensions are checked against the planning constraints. (5) The drawing is checked and issued for verification. • Proof it happened: the setting-out drawing with dimensions from fixed references, checked against boundary and setback requirements. • Where it usually breaks: setting out is dimensioned from a feature that later moves or turns out to be inaccurate, so the whole building is out of position. | • Require setting out to be dimensioned from permanent, verifiable references with stated coordinates, never from temporary or assumed features. • Check setbacks and boundary dimensions against the planning constraints as a mandatory step, since this is an unrecoverable error on site. • Show the datum and its physical reference point on the drawing. • Require independent checking of setting out by a second person, given the consequence of an error. • State that site must confirm setting out against the drawing before construction, with a written record.
131 | Technical Engineering | Prepare architectural floor plans | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare architectural floor plans” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare architectural floor plans” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman draws the floor plans, properly and to the company standard. • Starts when: approved design information is available for the floor plans. • How it runs: (1) plans are drawn from the approved mark-ups at the correct scale. (2) Dimensions, grids and levels are added consistently across floors. (3) Room names, numbers and areas are shown to match the schedules. (4) Cross-references to sections and details are added. (5) The plan is self-checked, then submitted for the Architect's check. • Proof it happened: the floor plans with the input revision recorded, the self-check completed and the checker's comments closed. • Where it usually breaks: room numbers and areas on the plan do not match the schedules, so two documents give different answers to the same question. | • Require room numbers, names and areas to match the schedules at each revision, with a reconciliation check. • Set the dimensioning convention once, including what dimensions are to structure and what to finish, since this ambiguity causes real site errors. • Keep grids and levels identical across all floors and disciplines. • Require cross-references to be verified as existing and current before issue, since dead references are common. • Use a self-check list before submitting for checking, so the checker is not doing the drafting.
132 | Technical Engineering | Prepare architectural elevations and sections | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare architectural elevations and sections” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare architectural elevations and sections” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman draws the elevations and sections, and makes sure they agree with the plans. • Starts when: the floor plans are stable enough to generate elevations and sections. • How it runs: (1) elevations and sections are generated or drawn from the current plans. (2) Levels, heights and floor-to-floor dimensions are checked against the plans and structural information. (3) Materials and finishes are annotated as instructed. (4) Section marks and references are matched with the plans. (5) The set is cross-checked for consistency, then submitted for checking. • Proof it happened: the elevations and sections with a recorded cross-consistency check against the plans. • Where it usually breaks: the plan changes and the elevations do not follow, so heights, openings and levels contradict each other in the issued set. | • Make a plan-to-elevation-to-section consistency check compulsory at every revision, not only at IFC. This is the single most common drawing defect. • Require levels and floor-to-floor heights to be verified against the structural information, not carried from concept. • Keep section marks and their references synchronised, so a section mark always leads to a drawing that exists. • State when elevations must be model generated rather than drawn separately, since separate drawings drift. • Record the plan revision the elevations were generated from.
133 | Technical Engineering | Prepare enlarged plans and construction details | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare enlarged plans and construction details” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare enlarged plans and construction details” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman draws the enlarged plans and the close-up construction details that show how things are actually built. • Starts when: the Architect issues detail mark-ups, or standard details need adapting to the project. • How it runs: (1) the details required are drawn from the standard library where one applies. (2) Project-specific details are drawn from the Architect's mark-ups at a readable scale. (3) Materials, thicknesses, falls and fixings are annotated as instructed. (4) Detail references are matched to the plans and sections. (5) The detail is checked, including whether it matches what the plans actually show. • Proof it happened: the detail drawings with the standard detail source or the mark-up they came from recorded, and the check record. • Where it usually breaks: a detail is drawn correctly but does not match the condition on the plan it is referenced from, so site builds a junction that does not exist. | • Start from the standard detail library and record when a project detail departs from it, so deviations are visible and approved. • Require detail-to-plan consistency checking, since a correct detail in the wrong place is still a defect. • Set minimum scales and annotation requirements per detail type, so details are readable on site. • Keep a project detail index, so site and estimators can find the detail that applies to a location. • Require technical annotation such as falls, thicknesses and fixings to come from the Architect rather than drafting judgement.
134 | Technical Engineering | Prepare door, window, finish and room schedules | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare door, window, finish and room schedules” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare door, window, finish and room schedules” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman builds the door, window, finish and room schedules from the drawings. • Starts when: the drawings are developed enough to schedule, and at each revision affecting them. • How it runs: (1) items are counted and coded from the current drawings, not from the previous project's schedule. (2) The schedule is built to the standard format with all required attributes. (3) Types are reconciled against the plans and the details. (4) Quantities and types are cross-checked before issue. (5) The schedule is submitted for the Architect's check with the drawing revision recorded. • Proof it happened: the schedules with the source drawing revision recorded and the reconciliation check completed. • Where it usually breaks: the schedule is updated separately from the drawings, so the count on the plan and the count in the schedule stop agreeing. | • Require the schedule to be reconciled against the drawings at each revision, with the drawing revision recorded on the schedule. Estimators and Procurement price from these. • Set the standard attributes per schedule type, so nothing essential is left blank. • Use one coding system across drawings, schedules and the BOQ, so items can be traced between them. • Have the count independently verified, since schedule quantity errors flow straight into procurement. • State who is entitled to change a schedule, since these documents are used by several departments.
135 | Technical Engineering | Prepare external works and civil interface drawings | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare external works and civil interface drawings” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare external works and civil interface drawings” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman draws the external works and how the building meets the site: roads, drainage, levels and boundaries. • Starts when: external works or civil interface drawings are required. • How it runs: (1) site levels, falls and drainage routes are drawn from the survey and the design instruction. (2) Boundary treatment, paving, parking and access are drawn. (3) The interface with the building, thresholds and external levels is coordinated. (4) External services and utility connections are coordinated with the MEP information. (5) The drawing is checked for level continuity and issued for checking. • Proof it happened: the external works drawings with levels and drainage coordinated, and the check record. • Where it usually breaks: external and internal levels are drawn by different people at different times, so thresholds do not work and water runs the wrong way. | • Require external and internal levels to be checked for continuity at thresholds as a specific step. This is a recurring and visible site failure. • Show falls and drainage direction explicitly, with invert levels where applicable. • Coordinate utility connection points with the MEP information and the authority requirements. • Confirm boundary positions against the survey and title information rather than assuming. • State who owns external works design where it sits between architecture and civil, so it is not left to drafting to decide.
136 | Technical Engineering | Prepare presentation and authority drawing sheets | Civil Draftsman | Trigger: When approved survey, concept or detailed-design information is released for drafting. Action: The Civil Draftsman completes “Prepare presentation and authority drawing sheets” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: accurate civil/architectural drawings and schedules ready for technical review. Control/Handoff: Draftsman performs self-check; Architect checks content before any authority or IFC issue. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When approved survey, concept or detailed-design information is released for drafting. | The Civil Draftsman completes “Prepare presentation and authority drawing sheets” using the approved brief, source documents, calculations and controlled company systems. | accurate civil/architectural drawings and schedules ready for technical review. | Draftsman performs self-check; Architect checks content before any authority or IFC issue. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman prepares the drawing sheets in the special format needed for client presentations and authority submissions. • Starts when: a presentation or authority submission package is required. • How it runs: (1) the required format is confirmed: sheet size, scale, stamps and content. (2) Sheets are composed from the current approved drawings, not from working files. (3) Authority-specific content is added: forms, notes, calculations and stamps. (4) The package is checked against the authority or client checklist. (5) It is submitted to the Architect and CTO for authorisation. • Proof it happened: the submission-ready sheets with the completed format checklist and the authorisation before issue. • Where it usually breaks: presentation sheets are built from an older working file, so the authority receives a version that does not match the current design. | • Require submission sheets to be built from the current approved revision, with that revision recorded. Submitting a superseded version is a serious and common error. • Keep an authority format sheet per authority: sheet size, scale, stamps, notes and required documents. • Complete the format checklist before authorisation, since rejections on format waste weeks. • Keep a copy of exactly what was submitted, since the approved set becomes the construction reference. • State who holds the stamp or licence used and confirm its validity before submission.
137 | Technical Engineering | Overlay and coordinate structural drawing backgrounds | Civil Draftsman | Trigger: When new structural/MEP backgrounds or approved review comments are received. Action: The Civil Draftsman completes “Overlay and coordinate structural drawing backgrounds” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated overlays, updated drawings and closed drafting comments. Control/Handoff: Unresolved clash or design ambiguity is logged and escalated to Architect/CTO rather than assumed. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When new structural/MEP backgrounds or approved review comments are received. | The Civil Draftsman completes “Overlay and coordinate structural drawing backgrounds” using the approved brief, source documents, calculations and controlled company systems. | coordinated overlays, updated drawings and closed drafting comments. | Unresolved clash or design ambiguity is logged and escalated to Architect/CTO rather than assumed. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman overlays the structural drawings on the architectural ones to see whether they agree. • Starts when: structural information is received or revised and coordination is due. • How it runs: (1) the structural background is inserted using the shared coordinate system, never manually aligned. (2) Column, wall and slab positions are compared against the architectural layout. (3) Level and thickness differences are identified. (4) Discrepancies are listed and reported to the Architect rather than corrected by drafting. (5) The agreed resolution is drawn in once instructed. • Proof it happened: the overlay with the discrepancy list reported to the Architect and the instructed corrections drawn in. • Where it usually breaks: drafting quietly adjusts the architecture to fit the structure without telling anyone, so a room shrinks and no decision was ever taken. | • State clearly that drafting reports discrepancies and never resolves them. Silent corrections change the design without a decision. • Require overlays to use the shared coordinate reference, with manual alignment prohibited. • Record the structural revision used for each overlay, so the coordination has a date and a basis. • Set the coordination checkpoints in the programme rather than doing overlays when someone remembers. • Log discrepancies into the shared clash register so they are tracked to closure.
138 | Technical Engineering | Overlay and coordinate MEP routes, openings and builders-work information | Civil Draftsman | Trigger: When new structural/MEP backgrounds or approved review comments are received. Action: The Civil Draftsman completes “Overlay and coordinate MEP routes, openings and builders-work information” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated overlays, updated drawings and closed drafting comments. Control/Handoff: Unresolved clash or design ambiguity is logged and escalated to Architect/CTO rather than assumed. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When new structural/MEP backgrounds or approved review comments are received. | The Civil Draftsman completes “Overlay and coordinate MEP routes, openings and builders-work information” using the approved brief, source documents, calculations and controlled company systems. | coordinated overlays, updated drawings and closed drafting comments. | Unresolved clash or design ambiguity is logged and escalated to Architect/CTO rather than assumed. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman overlays the services routes and shows the openings and builders work the drawings need. • Starts when: MEP information is received or revised and coordination is due. • How it runs: (1) MEP backgrounds are inserted on the shared coordinates. (2) Routes, risers and plant space are checked against the architectural layout and ceiling voids. (3) Required openings and builders work are drawn where instructed. (4) Clashes and space shortfalls are listed and reported. (5) Agreed resolutions and the builders-work information are drawn in and the schedule updated. • Proof it happened: the coordinated overlay, the reported clash list, and the builders-work information reflected in the drawings and schedule. • Where it usually breaks: openings are drawn on the architectural plan but never added to the builders-work schedule, so nobody forms them and they are cut later. | • Require every opening drawn to be reflected in the builders-work schedule, with a reconciliation check between the two. • Confirm the MEP revision used for the overlay, since MEP information changes frequently. • Report space shortfalls in ceiling voids and risers rather than drawing services into space that does not exist. • Prohibit drafting from moving services or openings without instruction. • Keep the builders-work schedule as a controlled deliverable with an owner, since several parties depend on it.
139 | Technical Engineering | Incorporate approved design-review and clash-resolution comments | Civil Draftsman | Trigger: When new structural/MEP backgrounds or approved review comments are received. Action: The Civil Draftsman completes “Incorporate approved design-review and clash-resolution comments” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated overlays, updated drawings and closed drafting comments. Control/Handoff: Unresolved clash or design ambiguity is logged and escalated to Architect/CTO rather than assumed. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When new structural/MEP backgrounds or approved review comments are received. | The Civil Draftsman completes “Incorporate approved design-review and clash-resolution comments” using the approved brief, source documents, calculations and controlled company systems. | coordinated overlays, updated drawings and closed drafting comments. | Unresolved clash or design ambiguity is logged and escalated to Architect/CTO rather than assumed. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman puts the approved review and clash comments into the drawings, properly and completely. • Starts when: checked drawings are returned with comments, or clash resolutions are approved. • How it runs: (1) comments are listed individually against the drawing and location. (2) Each is incorporated as instructed, and queried where it is unclear or conflicts with another comment. (3) The affected plans, elevations, sections, details and schedules are all updated, not just the drawing commented on. (4) Each comment is marked incorporated with the revision it went into. (5) The updated drawing goes back for verification. • Proof it happened: the comment list showing each item incorporated with its revision, and the verification by the checker. • Where it usually breaks: the commented drawing is updated but the related sections, details and schedules are not, so the change is only half made. | • Require the impact of every comment to be traced to all affected drawings and schedules, not only the sheet it was written on. Half-applied changes are worse than none. • Track incorporation per comment with the revision it entered, so closure is evidenced. • Require the checker to verify incorporation rather than accepting a report that it was done. • Set a route for querying a comment that conflicts with another or with the design, rather than choosing one. • Report comment volume and repeat comment types, since they show where drafting standards or briefing need work.
140 | Technical Engineering | Prepare IFC drawing sheets from approved design information | Civil Draftsman | Trigger: When a drawing reaches review, authority, tender or IFC issue status. Action: The Civil Draftsman completes “Prepare IFC drawing sheets from approved design information” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a checked drawing set, revision index, issue record and controlled transmittal. Control/Handoff: Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When a drawing reaches review, authority, tender or IFC issue status. | The Civil Draftsman completes “Prepare IFC drawing sheets from approved design information” using the approved brief, source documents, calculations and controlled company systems. | a checked drawing set, revision index, issue record and controlled transmittal. | Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman prepares the final construction-ready sheets from approved information only. • Starts when: the design is approved for construction-ready issue. • How it runs: (1) the drawing list for the package is confirmed against the deliverable register. (2) Sheets are prepared with the correct status, purpose of issue and revision. (3) All references, schedules and details are confirmed to exist and be current. (4) Notes, legends and general notes are checked as applicable to this project. (5) The set goes to the Architect and CTO for the final check and authorisation. • Proof it happened: the construction-ready sheet set with the drawing list, the status and revision correct, and the authorisation record. • Where it usually breaks: general notes and legends are carried over from a previous project, so the construction set contains instructions that do not belong to this building. | • Require general notes, legends and abbreviations to be reviewed as project specific at IFC. Inherited notes from other projects create real site confusion. • Check the package against the deliverable register for completeness, not against what happens to be finished. • Verify every cross-reference, schedule and detail reference exists and is current before authorisation. • Set the status and purpose-of-issue wording once and use it consistently, so site can tell construction information from preliminary. • Prohibit any construction-ready sheet built from unapproved or draft information.
141 | Technical Engineering | Maintain drawing numbers, revisions, status and issue purpose | Civil Draftsman | Trigger: When a drawing reaches review, authority, tender or IFC issue status. Action: The Civil Draftsman completes “Maintain drawing numbers, revisions, status and issue purpose” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a checked drawing set, revision index, issue record and controlled transmittal. Control/Handoff: Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When a drawing reaches review, authority, tender or IFC issue status. | The Civil Draftsman completes “Maintain drawing numbers, revisions, status and issue purpose” using the approved brief, source documents, calculations and controlled company systems. | a checked drawing set, revision index, issue record and controlled transmittal. | Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman keeps the drawing numbers, revisions and status right, so everyone knows what is current. • Starts when: a drawing is created, revised or reissued. • How it runs: (1) drawings are numbered to the standard convention with no local variation. (2) The revision is incremented on every reissue, with the reason recorded in the revision block. (3) The status and purpose of issue are set correctly. (4) The register is updated at the time of the change. (5) The numbering and revisions are reconciled against Document Control's record at defined points. • Proof it happened: the drawing register with numbers, revisions, status and issue purpose, reconciled with Document Control. • Where it usually breaks: a drawing is changed without incrementing the revision, so two different drawings exist with the same number and nobody can tell which is right. | • Prohibit any change to an issued drawing without a new revision. Two drawings with the same number is the worst outcome in drawing control. • Require the revision block to state what changed and why, so recipients can see the impact without comparing sheets. • Reconcile the drafting register against Document Control periodically, since these records drift apart. • Fix the numbering convention centrally and prohibit project-specific variations. • Make the register the single answer to what is current, and name its owner and deputy.
142 | Technical Engineering | Issue corrected drawings for Architect and CTO checking | Civil Draftsman | Trigger: When a drawing reaches review, authority, tender or IFC issue status. Action: The Civil Draftsman completes “Issue corrected drawings for Architect and CTO checking” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a checked drawing set, revision index, issue record and controlled transmittal. Control/Handoff: Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When a drawing reaches review, authority, tender or IFC issue status. | The Civil Draftsman completes “Issue corrected drawings for Architect and CTO checking” using the approved brief, source documents, calculations and controlled company systems. | a checked drawing set, revision index, issue record and controlled transmittal. | Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman sends the corrected drawings to the Architect and CTO to be checked before anything is issued. • Starts when: drawings are complete and ready for checking, or corrections have been made. • How it runs: (1) the self-check is completed and recorded. (2) The drawings are submitted for checking with the comment closure list attached. (3) The Architect checks and either approves or returns with comments. (4) The CTO authorises where required by the approval limits. (5) Only checked and authorised drawings move to issue. • Proof it happened: the checking record showing preparer, checker and approver as different people, with the comment closure attached. • Where it usually breaks: deadline pressure leads to drawings being issued on the drafter's own confidence, and the check is recorded afterwards as a formality. | • Keep preparer, checker and approver as three different people, with no exception for deadline pressure. A retrospective check is not a check. • Require a completed self-check before submission, so checkers are not doing basic drafting corrections. • Set checking turnaround times, since checking bottlenecks are what create the pressure to skip them. • State which drawings need CTO authorisation and which the Architect can approve, consistent with the authority matrix. • Record who checked and approved on the drawing itself, not only in a separate log.
143 | Technical Engineering | Update drawing register and transmit approved files to Document Control | Civil Draftsman | Trigger: When a drawing reaches review, authority, tender or IFC issue status. Action: The Civil Draftsman completes “Update drawing register and transmit approved files to Document Control” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a checked drawing set, revision index, issue record and controlled transmittal. Control/Handoff: Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When a drawing reaches review, authority, tender or IFC issue status. | The Civil Draftsman completes “Update drawing register and transmit approved files to Document Control” using the approved brief, source documents, calculations and controlled company systems. | a checked drawing set, revision index, issue record and controlled transmittal. | Document Control is the formal issue channel; superseded files are withdrawn and unauthorised issue is prohibited. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman updates the drawing register and sends the approved files to Document Control for issue. • Starts when: drawings are checked and authorised for issue. • How it runs: (1) the register is updated with the revision, status and date. (2) The files are prepared in the required formats to the naming convention. (3) The transmittal list is prepared showing every drawing and its revision. (4) Document Control issues and records the transmittal. (5) Superseded revisions are withdrawn and the withdrawal recorded. • Proof it happened: the Document Control transmittal record with the drawing list and revisions, and the register updated to match. • Where it usually breaks: files are sent straight to site or a vendor by the drafter to save time, so the official record does not match what people actually hold. | • Route all issue through Document Control with no direct sending from drafting, so one record of who holds what exists. • Include a revision list with every transmittal, so recipients can verify their holdings. • Make withdrawal of superseded revisions an explicit step with recipient confirmation, since old drawings on site cause rework. • State the required file formats and naming for issue, including whether editable files are released and to whom. • Reconcile the drafting register and the Document Control record at defined checkpoints.
144 | Technical Engineering | Prepare architectural and civil as-built drawings from verified red-lines | Civil Draftsman | Trigger: When verified red-lines or technical-closeout inputs are received. Action: The Civil Draftsman completes “Prepare architectural and civil as-built drawings from verified red-lines” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: review-ready as-built drawings and archived editable/source records. Control/Handoff: Projects verifies site information; Architect approves design representation; Document Control closes the record. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When verified red-lines or technical-closeout inputs are received. | The Civil Draftsman completes “Prepare architectural and civil as-built drawings from verified red-lines” using the approved brief, source documents, calculations and controlled company systems. | review-ready as-built drawings and archived editable/source records. | Projects verifies site information; Architect approves design representation; Document Control closes the record. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: at the end the Draftsman turns the verified site red-lines into as-built drawings showing what was really built. • Starts when: verified red-line mark-ups are received at project closeout. • How it runs: (1) the red-lines are checked as verified and signed before drawing, since unverified mark-ups are not a basis for as-builts. (2) The drawings are updated to the as-built position. (3) Changes are cross-checked across plans, sections, details and schedules. (4) The as-built status and revision are applied. (5) The set is checked, authorised and issued to Document Control for archive and handover. • Proof it happened: the as-built drawing set with the verified red-line source recorded, the check record and the archive transmittal. • Where it usually breaks: as-builts are produced from unverified contractor mark-ups, so the record the client keeps for the building's life is wrong. | • Require red-lines to be verified and signed by Projects before as-built drawing starts. As-builts drawn from unverified mark-ups are worse than no as-builts. • Apply the changes across all related drawings and schedules, not only the plans. • Set the as-built status and revision convention, so an as-built cannot be confused with a construction drawing. • Tie as-built completion to the handover and retention milestone, since this work is otherwise abandoned once the site closes. • Include the concealed services and actual routes, which is what the client will need years later.
145 | Technical Engineering | Archive controlled editable files, references and superseded drawing history | Civil Draftsman | Trigger: When verified red-lines or technical-closeout inputs are received. Action: The Civil Draftsman completes “Archive controlled editable files, references and superseded drawing history” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: review-ready as-built drawings and archived editable/source records. Control/Handoff: Projects verifies site information; Architect approves design representation; Document Control closes the record. Continuity/Escalation: A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. Timing: To be confirmed. | When verified red-lines or technical-closeout inputs are received. | The Civil Draftsman completes “Archive controlled editable files, references and superseded drawing history” using the approved brief, source documents, calculations and controlled company systems. | review-ready as-built drawings and archived editable/source records. | Projects verifies site information; Architect approves design representation; Document Control closes the record. | A nominated competent drafting resource provides backup; no drawing is issued without Architect/CTO check and controlled Document Control release. | To be confirmed. | • In plain words: the Draftsman archives the editable files, references and the history of superseded drawings so the project can be picked up again years later. • Starts when: the project closes out, or at defined archive points during the project. • How it runs: (1) the editable files, references, fonts and linked files are collected so the drawings will open correctly later. (2) The file set is checked to open and print from the archive copy. (3) The superseded revision history is retained, not deleted. (4) The archive is indexed against the drawing register. (5) It is transferred to the controlled archive under Document Control with the retention period recorded. • Proof it happened: the indexed archive with editable files and references, verified to open, and the transfer record to Document Control. • Where it usually breaks: only the finished drawings are archived without their linked files and references, so nothing can be edited when the client returns for an extension. | • Require the archive to include all linked references, fonts and support files, and to be tested by opening from the archive copy. An archive that will not open is not an archive. • Retain the superseded revision history, since claims and disputes turn on what was issued when. • Index the archive against the drawing register, so a drawing can be found without the original author. • State the retention period and where it is held, consistent with the company records policy. • Record the software and version used, since files become unopenable across versions.
146 | Technical Engineering | Review architectural brief, site survey and available geotechnical information | Structural Designer | Trigger: When architectural/site information is available for structural definition. Action: The Structural Designer completes “Review architectural brief, site survey and available geotechnical information” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved structural basis, system decision, test request and input register. Control/Handoff: Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When architectural/site information is available for structural definition. | The Structural Designer completes “Review architectural brief, site survey and available geotechnical information” using the approved brief, source documents, calculations and controlled company systems. | an approved structural basis, system decision, test request and input register. | Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: before designing anything, the Structural Designer reads the architectural brief and the site information to see what the structure has to do and what the ground can take. • Starts when: a project is assigned to structural design. • How it runs: (1) the architectural drawings, brief and survey are reviewed for what affects structure. (2) Available geotechnical information is reviewed for bearing capacity, water table and soil type. (3) Gaps in the information are listed, particularly where a soil investigation is missing. (4) Anything that looks structurally unworkable in the architecture is raised early with the Architect. (5) Acceptance is confirmed to the CTO with the open information items. • Proof it happened: the input review record listing the information used, the gaps identified and the early concerns raised. • Where it usually breaks: design starts on assumed ground conditions because the soil report is late, and the foundations have to be redesigned when the real report arrives. | • State plainly whether design may start on assumed ground conditions, and if so, that the assumption is recorded on the drawings and the design is provisional until the soil report arrives. • Set a minimum input list structural needs before starting, and make acceptance conditional on it. • Require early flagging of architectural arrangements that are structurally difficult, since raising them after concept freeze is expensive. • Record which architectural revision the structural design is based on. • Escalate a missing soil investigation as a project risk, not just a design inconvenience.
147 | Technical Engineering | Establish structural design criteria, codes, loads and assumptions | Structural Designer | Trigger: When architectural/site information is available for structural definition. Action: The Structural Designer completes “Establish structural design criteria, codes, loads and assumptions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved structural basis, system decision, test request and input register. Control/Handoff: Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When architectural/site information is available for structural definition. | The Structural Designer completes “Establish structural design criteria, codes, loads and assumptions” using the approved brief, source documents, calculations and controlled company systems. | an approved structural basis, system decision, test request and input register. | Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer writes down the rules the design will follow. Which codes, what loads, and what has been assumed. • Starts when: the inputs are accepted and design is about to begin. • How it runs: (1) the applicable design codes and the authority's requirements are confirmed. (2) Dead, live, wind and seismic loads are established for the building type and location. (3) Material grades, cover and durability requirements are set. (4) Assumptions are listed with what each depends on. (5) The criteria are approved by the CTO as a controlled document before design proceeds. • Proof it happened: an approved structural design criteria document stating codes, loads, materials and assumptions, with its version. • Where it usually breaks: the design criteria are never written down as a single document, so each element gets designed to whatever the designer had in mind at the time. | • Require design criteria to be one approved, version-controlled document before element design starts. Undocumented criteria cannot be checked or defended. • State the code edition and the authority requirements explicitly, since code versions differ and authorities are specific. • List loads by category with their source, including any client-specified or equipment loads. • Require CTO approval of the criteria, since they set the liability position for the whole structure. • Treat any later change to the criteria as a formal revision with a re-check of affected elements.
148 | Technical Engineering | Develop preliminary structural system and framing options | Structural Designer | Trigger: When architectural/site information is available for structural definition. Action: The Structural Designer completes “Develop preliminary structural system and framing options” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved structural basis, system decision, test request and input register. Control/Handoff: Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When architectural/site information is available for structural definition. | The Structural Designer completes “Develop preliminary structural system and framing options” using the approved brief, source documents, calculations and controlled company systems. | an approved structural basis, system decision, test request and input register. | Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer works out what kind of structure suits the building and compares the sensible ways of framing it. • Starts when: the design criteria are approved and a structural system has to be chosen. • How it runs: (1) framing options are developed against the architectural layout and the ground conditions. (2) Each is assessed for depth, cost, buildability, programme and local trade availability. (3) The impact on floor-to-floor heights and services routes is checked with Architecture and MEP. (4) The preferred system is recommended with reasons. (5) The CTO approves the system before detailed design. • Proof it happened: the framing options comparison and the approved structural system with the reason for selection. • Where it usually breaks: a system is chosen on structural efficiency alone, without checking whether local contractors can build it or whether it eats the ceiling void. | • Assess options on cost, buildability, programme and local trade capability, not structural efficiency alone. The cheapest structure to design is often the most expensive to build. • Check the effect on floor-to-floor height and services routes with Architecture and MEP before the system is fixed. • Require CTO approval of the system, since changing it later means redesigning everything. • Record why the selected option was chosen and why others were not. • Give the indicative structural quantity per option to Estimation, so the commercial impact is visible at the point of choice.
149 | Technical Engineering | Identify required tests, investigations and missing structural inputs | Structural Designer | Trigger: When architectural/site information is available for structural definition. Action: The Structural Designer completes “Identify required tests, investigations and missing structural inputs” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved structural basis, system decision, test request and input register. Control/Handoff: Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When architectural/site information is available for structural definition. | The Structural Designer completes “Identify required tests, investigations and missing structural inputs” using the approved brief, source documents, calculations and controlled company systems. | an approved structural basis, system decision, test request and input register. | Missing geotechnical/load information is escalated to CTO and design proceeds only with documented assumptions. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer identifies the tests and investigations that must be done, and what information is still missing. • Starts when: gaps in the structural inputs are identified, or a test is needed to confirm an assumption. • How it runs: (1) the required investigations are specified: soil, existing structure, material or load testing. (2) The scope and purpose of each are written so the result answers the design question. (3) The requirement is raised to Projects or the client with the reason and the consequence of not doing it. (4) The status of each open input is tracked. (5) Results are reviewed and the design assumptions are updated or confirmed. • Proof it happened: the open inputs and required tests register, with the requests raised and the results reviewed against the assumptions. • Where it usually breaks: the test is requested once and never followed up, so the design is completed and issued on assumptions that were meant to be temporary. | • Track open structural inputs as a live register with owners and dates, and report it at design reviews. Temporary assumptions become permanent when nobody chases them. • State the consequence of not doing a required test in the request, so the client's decision is informed. • Specify the test scope so the result answers the design question rather than being generically useful. • Mark drawings issued on unconfirmed assumptions, and state who must be told when the assumption changes. • Escalate to the CTO where a refused or delayed investigation creates a safety or liability exposure.
150 | Technical Engineering | Prepare structural analysis model and calculation basis | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Prepare structural analysis model and calculation basis” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Prepare structural analysis model and calculation basis” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer builds the analysis model and sets out the basis of the calculations. • Starts when: the structural system is approved and analysis is required. • How it runs: (1) the model geometry is built from the coordinated architectural and structural grids. (2) Supports, restraints, load cases and combinations are applied per the design criteria. (3) The model is sanity checked: equilibrium, reactions, deflections and obviously wrong results. (4) The calculation basis is documented so the model can be understood by someone else. (5) The model and basis are recorded under version control. • Proof it happened: the analysis model with a documented calculation basis, the sanity check record and the version reference. • Where it usually breaks: nobody sanity checks the model output against simple hand calculations, so a modelling error is carried through the whole design. | • Require hand calculation sanity checks on key elements and total reactions. Software output is not evidence that the model is right. • Document the calculation basis so another engineer can understand the model, including support assumptions and load combinations. • Version control the model and record which model version each drawing was designed from. • State the software and version used, since results differ between versions and codes. • Require the model geometry to come from the coordinated grids rather than being drawn independently.
151 | Technical Engineering | Design foundations and substructure elements | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Design foundations and substructure elements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Design foundations and substructure elements” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer designs the foundations and everything below ground. • Starts when: the loads are established and the ground information is available. • How it runs: (1) the foundation type is selected against the soil report and the loads. (2) Elements are sized and designed with the settlement and bearing checks. (3) Water table, ground water protection and durability requirements are addressed. (4) Interfaces with drainage, service entries and the retaining structures are coordinated. (5) The design is independently checked before it goes to drawings. • Proof it happened: the foundation design calculations with the soil report reference, the checks performed and the independent check record. • Where it usually breaks: the foundation is designed from a soil report for a nearby plot or an old investigation, and the actual ground turns out to be different. | • Require the specific project soil investigation to be referenced by report number and date. A report from an adjacent plot is not a substitute. • Address water table and ground water protection explicitly, since below ground leaks are the most expensive defects to fix. • Coordinate service entries, drainage and pit locations with MEP before foundation design is finalised. • Require independent checking of foundation design, given the consequence of failure. • State what must happen when excavation reveals ground conditions different from the report, including who has authority to stop work.
152 | Technical Engineering | Design slabs, beams, columns and load-bearing elements | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Design slabs, beams, columns and load-bearing elements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Design slabs, beams, columns and load-bearing elements” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer designs the frame that holds the building up. Slabs, beams, columns and load-bearing walls. • Starts when: the framing system and loads are established. • How it runs: (1) elements are sized and designed against the criteria and load combinations. (2) Deflection, crack width and serviceability are checked, not just strength. (3) Element sizes are issued to Architecture so the drawings reflect reality. (4) Openings and penetrations required by MEP are designed in rather than accommodated later. (5) The design is independently checked and the calculations recorded. • Proof it happened: element design calculations covering strength and serviceability, the independent check record, and the sizes issued to Architecture. • Where it usually breaks: sizes change during design and Architecture is not told, so the drawings show columns that no longer exist at that size. | • Require element size changes to be issued to Architecture and MEP as a controlled notification, with confirmation the drawings were updated. • Check serviceability and deflection explicitly, since strength-only design produces buildings that crack and bounce. • Design MEP openings and penetrations into elements rather than approving them later on site. • Require independent checking with the checker named on the calculation record. • Keep a schedule of element sizes as the single reference used by drafting, estimation and site.
153 | Technical Engineering | Design structural steel or specialist structural elements where applicable | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Design structural steel or specialist structural elements where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Design structural steel or specialist structural elements where applicable” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: where the building uses steel or a specialist structure, the Structural Designer designs it and defines what the fabricator must do. • Starts when: the structural system includes steel or a specialist element such as a truss, a canopy or a pre-engineered building. • How it runs: (1) members are designed with the connection philosophy stated, not left to the fabricator by default. (2) Fabrication, welding, bolting and corrosion protection requirements are specified. (3) The design responsibility boundary with the fabricator or specialist is defined in writing. (4) Erection sequence and temporary stability are considered. (5) The design is independently checked and the specification issued. • Proof it happened: the steel or specialist design with the connection philosophy, the specification, and the written responsibility boundary with the fabricator. • Where it usually breaks: the connection design is left to the fabricator with no philosophy or criteria given, so the connections do not match the assumptions in the analysis. | • Define the design responsibility boundary with the fabricator in writing before procurement, including who designs connections and who checks them. • State the connection philosophy and the design forces, so fabricator connections match the analysis assumptions. • Specify fabrication, welding, inspection and corrosion protection requirements, and who witnesses them. • Address erection sequence and temporary stability, since collapses happen during erection more than in service. • Require fabricator shop drawings and their design submissions to be reviewed against the stated criteria, with the reviewer named.
154 | Technical Engineering | Design retaining walls, tanks and external structural elements where applicable | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Design retaining walls, tanks and external structural elements where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Design retaining walls, tanks and external structural elements where applicable” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer designs the retaining walls, tanks and external structures that hold back soil or water. • Starts when: the project includes retaining structures, water-retaining structures or external structural elements. • How it runs: (1) the earth, water and surcharge loads are established, including any construction loading. (2) Stability is checked for overturning, sliding and bearing, not only the wall section. (3) Water tightness, joints and waterproofing requirements are specified for retaining structures. (4) Drainage behind the wall and any relief measures are designed. (5) The design is independently checked and the construction requirements recorded. • Proof it happened: the retaining and water-retaining structure design with stability checks, waterproofing and drainage requirements, independently checked. • Where it usually breaks: drainage behind the retaining wall is treated as a construction detail and left out, so water pressure builds up against a wall that was never designed for it. | • Require drainage and relief behind retaining structures to be designed and drawn, not left as a site detail. Its omission is a frequent cause of failure. • Check overturning, sliding and bearing stability as distinct checks, with the results recorded. • Include construction stage and surcharge loading, since walls are often most vulnerable before backfill. • Specify water tightness, joint and waterproofing requirements for water-retaining structures with the testing regime. • State the inspection and hold points for backfilling and waterproofing, since these are concealed once complete.
155 | Technical Engineering | Prepare reinforcement, structural details and connection requirements | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Prepare reinforcement, structural details and connection requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Prepare reinforcement, structural details and connection requirements” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer works out the reinforcement and how the parts of the structure connect to each other. • Starts when: element design is complete and reinforcement and details are required for drawings. • How it runs: (1) reinforcement is designed per element with cover, lap and anchorage requirements. (2) Standard structural details are used where they apply, and specific details designed where they do not. (3) Congestion and buildability at junctions are checked, since drawn reinforcement must physically fit. (4) Connection and joint requirements are specified. (5) Details are checked against the calculations and issued to drafting. • Proof it happened: the reinforcement and detail design with cover, lap and anchorage stated, checked against the calculations. • Where it usually breaks: reinforcement is designed on paper without checking congestion at the junctions, so the steel cannot physically be placed and site improvises. | • Require a congestion and buildability check at heavily reinforced junctions. Reinforcement that cannot be placed gets changed on site by whoever is holding the bars. • State cover, lap length and anchorage on the drawings rather than relying on a general note, since site works from what is in front of them. • Use the standard structural detail library, and record where a project detail departs from it. • Check details against the calculations by a named checker, since a detail error is a structural error. • Provide the reinforcement information Estimation needs, and confirm the drawing revision it was taken from.
156 | Technical Engineering | Prepare structural member, reinforcement and design schedules | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Prepare structural member, reinforcement and design schedules” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Prepare structural member, reinforcement and design schedules” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer prepares the schedules listing every structural member and its reinforcement. • Starts when: element and reinforcement design is complete enough to schedule. • How it runs: (1) member schedules are built from the design, listing size, grade and location. (2) Reinforcement schedules are prepared with bar marks, sizes, shapes and quantities. (3) The schedules are reconciled against the drawings and the calculations. (4) The drawing revision the schedule was built from is recorded. (5) The schedules are checked and issued with the drawings. • Proof it happened: the member and reinforcement schedules reconciled against the drawings, with the source revision recorded and the check completed. • Where it usually breaks: the schedule and the drawing disagree on a bar size or count, and site orders steel from whichever they happened to read. | • Require schedule-to-drawing reconciliation at every revision, with the source revision recorded. Site and Procurement order material from these schedules. • Use one bar marking and member coding system across drawings, schedules and the BOQ. • Require quantities to be independently verified, since a scheduling error becomes a material order error. • State the rounding, wastage and lap allowances used, or explicitly that they are excluded, so Estimation knows what it is pricing. • Name who may revise a schedule after issue and how the change reaches site.
157 | Technical Engineering | Maintain controlled structural calculations and design-check records | Structural Designer | Trigger: When the structural basis and required inputs are approved. Action: The Structural Designer completes “Maintain controlled structural calculations and design-check records” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: controlled analysis, calculations, drawings, details and schedules. Control/Handoff: Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When the structural basis and required inputs are approved. | The Structural Designer completes “Maintain controlled structural calculations and design-check records” using the approved brief, source documents, calculations and controlled company systems. | controlled analysis, calculations, drawings, details and schedules. | Qualified checking is completed before release; unsafe, unstable or noncompliant condition is immediately escalated to CTO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer keeps the calculations and check records in order, so the design can be defended years later. • Starts when: calculations are produced, revised or checked. • How it runs: (1) calculations are prepared to a consistent format with the criteria, assumptions and references stated. (2) Each calculation set is identified by element, revision and date. (3) The independent check is recorded with the checker's name, comments and closure. (4) Superseded calculations are retained, not discarded. (5) The set is filed under control with the drawings it supports. • Proof it happened: the controlled calculation file with revisions, the named check records and the retained superseded versions. • Where it usually breaks: calculations live on the designer's own drive with no revision or check record, so when a problem arises nobody can show how the structure was designed. | • Hold calculations in one controlled location with revision and check records. Calculations on a personal drive are not evidence and disappear with the person. • Require the checker's name, comments and closure to be recorded, since an unrecorded check does not exist. • Retain superseded calculations, as claims and investigations turn on what was designed when. • Link calculations to the drawings and revisions they support, so a drawing can be traced to its basis. • Set the retention period in line with the company records policy and the applicable liability period.
158 | Technical Engineering | Coordinate structural grids, levels and geometry with Architecture | Structural Designer | Trigger: When structural design reaches a coordination or checking milestone. Action: The Structural Designer completes “Coordinate structural grids, levels and geometry with Architecture” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: resolved grids, openings, loads, comments and structural check evidence. Control/Handoff: Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design reaches a coordination or checking milestone. | The Structural Designer completes “Coordinate structural grids, levels and geometry with Architecture” using the approved brief, source documents, calculations and controlled company systems. | resolved grids, openings, loads, comments and structural check evidence. | Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer and the Architect agree the grids, levels and geometry, and keep them agreed. • Starts when: structural design begins, and at every change to grids, levels or geometry. • How it runs: (1) grids, levels and datum are agreed jointly and fixed as a controlled reference. (2) Structural geometry is checked against the architectural layout. (3) Element positions and sizes are issued to Architecture and confirmed as reflected. (4) Discrepancies go to the clash register rather than being resolved informally. (5) Both disciplines confirm alignment at the coordination checkpoints. • Proof it happened: the coordination record confirming grids, levels and geometry agreed by both disciplines, with the revisions referenced. • Where it usually breaks: a level is changed by one discipline for a good local reason and the other is not told, so the two sets are working to different datums. | • Fix grids, levels and datum as a controlled shared reference, and require any change to be a coordinated revision confirmed by both disciplines. • Require element sizes and positions to be confirmed as reflected in the architectural drawings, not just sent. • Route discrepancies through the shared clash register with an owner and a date. • Set coordination checkpoints in the programme, so alignment is verified at known points rather than at IFC. • Record the revision of each discipline at each coordination point.
159 | Technical Engineering | Coordinate structural openings, sleeves, plant loads and MEP requirements | Structural Designer | Trigger: When structural design reaches a coordination or checking milestone. Action: The Structural Designer completes “Coordinate structural openings, sleeves, plant loads and MEP requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: resolved grids, openings, loads, comments and structural check evidence. Control/Handoff: Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design reaches a coordination or checking milestone. | The Structural Designer completes “Coordinate structural openings, sleeves, plant loads and MEP requirements” using the approved brief, source documents, calculations and controlled company systems. | resolved grids, openings, loads, comments and structural check evidence. | Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer deals with the holes, sleeves and equipment loads the services need from the structure. • Starts when: MEP openings, sleeves or plant loads are proposed or revised. • How it runs: (1) requested openings and sleeves are assessed against the element design. (2) Acceptable positions and sizes are defined, with strengthening designed where needed. (3) Plant and equipment loads are incorporated into the design, including their locations. (4) Anything unacceptable is refused with the reason and an alternative offered. (5) The agreed openings and loads are recorded on the drawings and in the builders-work information. • Proof it happened: the approved openings and sleeves record with any strengthening designed, and the plant loads incorporated in the calculations. • Where it usually breaks: openings appear on site without structural approval because someone judged them small enough, and the element is quietly weakened. | • State absolutely that no opening or penetration is made in a structural element without written structural approval, with no size exemption decided on site. • Define permitted opening zones and sizes per element type, so routine requests do not need individual design. • Require plant and equipment loads with their positions in writing from MEP, since assumed loads are often wrong. • Design strengthening where openings are accepted, and show it on the drawings. • Set a cut-off after which new openings become a formal change with cost and programme impact.
160 | Technical Engineering | Review structural constructability, sequence and temporary-condition risks | Structural Designer | Trigger: When structural design reaches a coordination or checking milestone. Action: The Structural Designer completes “Review structural constructability, sequence and temporary-condition risks” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: resolved grids, openings, loads, comments and structural check evidence. Control/Handoff: Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design reaches a coordination or checking milestone. | The Structural Designer completes “Review structural constructability, sequence and temporary-condition risks” using the approved brief, source documents, calculations and controlled company systems. | resolved grids, openings, loads, comments and structural check evidence. | Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer checks the structure can actually be built safely, including the stages before it is finished. • Starts when: the design is developed and before construction-ready release, and at any change to sequence or method. • How it runs: (1) the construction sequence assumed by the design is stated. (2) Temporary conditions are considered: propping, formwork, backfill, lifting and partially complete stability. (3) Buildability is reviewed with Projects input where available. (4) Requirements and limits are stated on the drawings, such as when props may be removed. (5) Findings are addressed in the design and recorded. • Proof it happened: the constructability review record with the assumed sequence, the temporary condition requirements, and their statement on the drawings. • Where it usually breaks: the design assumes a sequence that is never communicated, so site builds in a different order and the structure is unstable at a stage nobody designed for. | • Require the assumed construction sequence and any temporary condition limits to be stated on the drawings. Site cannot follow an assumption it was never told. • Name who is responsible for temporary works design, and state that the permanent works designer is not it unless expressly appointed. • State propping, striking and backfill requirements with the conditions for removal, since early removal causes real failures. • Involve Projects in the review, since sequence problems are visible to builders before designers. • Require the contractor's proposed method to be reviewed against the design assumptions where it differs.
161 | Technical Engineering | Complete independent structural check and close review comments | Structural Designer | Trigger: When structural design reaches a coordination or checking milestone. Action: The Structural Designer completes “Complete independent structural check and close review comments” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: resolved grids, openings, loads, comments and structural check evidence. Control/Handoff: Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design reaches a coordination or checking milestone. | The Structural Designer completes “Complete independent structural check and close review comments” using the approved brief, source documents, calculations and controlled company systems. | resolved grids, openings, loads, comments and structural check evidence. | Architecture and MEP confirm interfaces; unresolved stability, buildability or change impact escalates to CTO/COO. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: someone other than the designer checks the whole structural design, and the comments are closed properly. • Starts when: the design is complete and requires independent checking before release. • How it runs: (1) an independent checker is assigned who did not do the design. (2) The check covers criteria, loads, model, calculations, details and schedules. (3) Comments are logged individually with a category and a required action. (4) The designer responds and revises, and the checker verifies each closure. (5) The CTO approves release once the check is closed. • Proof it happened: the independent check record with each comment, its resolution and the checker's verified closure, plus the CTO's approval. • Where it usually breaks: the check is done by the same team under time pressure and closure is recorded on the designer's own word rather than verified. | • Require the checker to be independent of the design and to verify each closure personally. Self-verified closure is not a check. • State the scope of the check explicitly, covering criteria, model, calculations, details and schedules, so it does not become a drawing glance. • Categorise comments by severity, so safety-critical items cannot be closed as minor. • Make a closed check an entry condition for construction-ready release, with the CTO approving. • Record checker qualification for structures above a stated size or risk, since competence is part of the defence.
162 | Technical Engineering | Prepare structural authority submission drawings and calculations | Structural Designer | Trigger: When structural design is ready for authority or construction release. Action: The Structural Designer completes “Prepare structural authority submission drawings and calculations” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled authority/IFC structural package with calculations and revision evidence. Control/Handoff: CTO authorises release; Document Control records issue; rejection returns through a controlled comment matrix. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design is ready for authority or construction release. | The Structural Designer completes “Prepare structural authority submission drawings and calculations” using the approved brief, source documents, calculations and controlled company systems. | a controlled authority/IFC structural package with calculations and revision evidence. | CTO authorises release; Document Control records issue; rejection returns through a controlled comment matrix. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer prepares the drawings and calculations the authority needs to approve the structure. • Starts when: a structural authority submission is required. • How it runs: (1) the authority's structural requirements and checklist are confirmed. (2) Submission drawings are prepared in the required format and scale. (3) Calculations are compiled in the required form, with the code references and the soil report. (4) Stamps, licences and forms are arranged. (5) The package is checked against the checklist and authorised by the CTO before submission. • Proof it happened: the authority submission package with the completed checklist, the calculations included, and the CTO's authorisation. • Where it usually breaks: the calculations submitted do not correspond to the drawings submitted, because one was updated after the other. | • Require the submitted calculations and drawings to be from the same revision, with a cross-check recorded. Mismatched submissions are rejected and delay approval. • Keep an authority requirements sheet for structural submissions, including calculation format, code references and required reports. • Confirm the stamp or licence needed and its validity before submission. • Record the submission date and reference and track the expected response. • Keep the submitted set as a controlled record, since the approved structure is the reference for construction and any amendment.
163 | Technical Engineering | Respond to structural authority comments and revise controlled design | Structural Designer | Trigger: When structural design is ready for authority or construction release. Action: The Structural Designer completes “Respond to structural authority comments and revise controlled design” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled authority/IFC structural package with calculations and revision evidence. Control/Handoff: CTO authorises release; Document Control records issue; rejection returns through a controlled comment matrix. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design is ready for authority or construction release. | The Structural Designer completes “Respond to structural authority comments and revise controlled design” using the approved brief, source documents, calculations and controlled company systems. | a controlled authority/IFC structural package with calculations and revision evidence. | CTO authorises release; Document Control records issue; rejection returns through a controlled comment matrix. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: when the authority comments on the structure, the Structural Designer answers and revises the design under control. • Starts when: the authority issues structural comments or a rejection. • How it runs: (1) comments are logged individually with the code clause or requirement behind each. (2) Responses are prepared, with recalculation where the comment affects the design. (3) Design changes go through the normal check and approval route, not directly into the submission. (4) Affected disciplines are told where the change affects them. (5) The revised package is authorised and resubmitted, and the drawings updated to match. • Proof it happened: the comment log with responses, the revised and rechecked calculations, and the authorised resubmission. • Where it usually breaks: the submission is revised to satisfy the authority but the construction drawings and calculations are never brought in line. | • Require every authority-driven change to be carried into the construction drawings, schedules and calculations, not only the submission set. • Send changed elements back through the independent check, since an authority-driven fix is still a design change. • Notify Architecture and MEP where a structural change affects their design, as depth and position changes usually do. • Track resubmission cycles and their causes, since repeats are usually avoidable. • Report cost and programme impact to the project rather than treating the change as purely technical.
164 | Technical Engineering | Release checked structural IFC package with calculation and revision evidence | Structural Designer | Trigger: When structural design is ready for authority or construction release. Action: The Structural Designer completes “Release checked structural IFC package with calculation and revision evidence” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a controlled authority/IFC structural package with calculations and revision evidence. Control/Handoff: CTO authorises release; Document Control records issue; rejection returns through a controlled comment matrix. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When structural design is ready for authority or construction release. | The Structural Designer completes “Release checked structural IFC package with calculation and revision evidence” using the approved brief, source documents, calculations and controlled company systems. | a controlled authority/IFC structural package with calculations and revision evidence. | CTO authorises release; Document Control records issue; rejection returns through a controlled comment matrix. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer releases the construction-ready structural package with the evidence that it was checked. • Starts when: the structural design is checked, coordinated and approved for construction issue. • How it runs: (1) the package is checked complete against the deliverable register. (2) Drawings, schedules and calculations are confirmed consistent at the same revision. (3) Coordination and clash closure are confirmed. (4) The check evidence and calculation references are attached. (5) The CTO authorises and the package goes to Document Control for issue. • Proof it happened: the released structural package with the revision index, the check evidence and the calculation reference, issued through Document Control. • Where it usually breaks: drawings are issued for construction while the calculations behind them are still being revised, so the built structure has no matching design record. | • Require drawings, schedules and calculations to be at consistent revisions at release, with the calculation reference recorded on the issue. The design record must match what was built. • Make check closure and clash closure explicit entry conditions for release. • Issue through Document Control only, with a revision index and withdrawal of superseded revisions. • Record any item released with a known open point, notify Projects and track it to closure. • State the status and purpose of issue clearly, so preliminary information cannot be mistaken for construction information.
165 | Technical Engineering | Respond to structural RFIs, design clarifications and approved variations | Structural Designer | Trigger: When a structural RFI, submittal, inspection, variation or closeout requirement is received. Action: The Structural Designer completes “Respond to structural RFIs, design clarifications and approved variations” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review record, inspection evidence or accepted as-built update. Control/Handoff: Material structural deviation requires CTO and Project Engineer control before site implementation. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When a structural RFI, submittal, inspection, variation or closeout requirement is received. | The Structural Designer completes “Respond to structural RFIs, design clarifications and approved variations” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review record, inspection evidence or accepted as-built update. | Material structural deviation requires CTO and Project Engineer control before site implementation. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: during construction the Structural Designer answers site questions and handles approved changes to the structure. • Starts when: site raises a structural RFI, a clarification is needed, or a variation affecting the structure is approved. • How it runs: (1) the query is registered with its date and the response time required. (2) The answer is prepared against the design and recalculated where necessary. (3) Where the answer changes the design, it goes through checking and a controlled revision follows. (4) Cost and programme implications are reported to the project, not just the technical answer. (5) The register tracks the response and closure. • Proof it happened: the structural RFI and variation register with the responses, any recalculation, and the controlled revisions issued. • Where it usually breaks: a quick answer is given by phone or on site to keep work moving, and the drawings and calculations never catch up with what was actually built. | • Require every verbal or site instruction affecting structure to be confirmed in writing the same day and followed by a controlled revision. This is the most common source of undocumented structural change. • Send any answer that changes the design back through checking before it is issued. • Report cost and programme impact with the technical answer, since site is often unaware of the commercial consequence. • Set and monitor response times, since structural delay stops work and generates claims. • Track RFI causes, as repeated queries in one area usually indicate a drawing or detailing weakness.
166 | Technical Engineering | Review structural shop drawings, material submittals and critical work inspections | Structural Designer | Trigger: When a structural RFI, submittal, inspection, variation or closeout requirement is received. Action: The Structural Designer completes “Review structural shop drawings, material submittals and critical work inspections” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review record, inspection evidence or accepted as-built update. Control/Handoff: Material structural deviation requires CTO and Project Engineer control before site implementation. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When a structural RFI, submittal, inspection, variation or closeout requirement is received. | The Structural Designer completes “Review structural shop drawings, material submittals and critical work inspections” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review record, inspection evidence or accepted as-built update. | Material structural deviation requires CTO and Project Engineer control before site implementation. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: the Structural Designer checks the contractor's shop drawings and materials, and inspects the critical work before it is covered up. • Starts when: shop drawings or material submittals are received, or a critical inspection point is reached on site. • How it runs: (1) submittals are reviewed against the design, the specification and the criteria. (2) Comments are issued with clear decisions and reasons. (3) Critical inspection and hold points are agreed, particularly reinforcement before concrete and connections before covering. (4) Inspections are carried out and recorded with photographs. (5) Non-conformances are raised with the required corrective action and tracked to closure. • Proof it happened: the submittal review records, the witnessed inspection records with photographs, and the closed non-conformance reports. • Where it usually breaks: concrete is poured before the reinforcement inspection because the schedule is tight, and there is no way to verify what is inside the element. | • Set mandatory hold points where work cannot proceed without inspection, particularly reinforcement before concrete. Once covered, verification is impossible. • Name who has authority to release a hold point and state that site pressure is not a reason to waive it. • Require photographic records of concealed work, indexed to element and date. • Review submittals against the specified criteria with the reviewer named, and state that approval does not transfer the contractor's obligations. • Track non-conformances to closure with evidence, and escalate structural non-conformances to the CTO.
167 | Technical Engineering | Review structural as-built information and close outstanding technical actions | Structural Designer | Trigger: When a structural RFI, submittal, inspection, variation or closeout requirement is received. Action: The Structural Designer completes “Review structural as-built information and close outstanding technical actions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review record, inspection evidence or accepted as-built update. Control/Handoff: Material structural deviation requires CTO and Project Engineer control before site implementation. Continuity/Escalation: A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. Timing: To be confirmed. | When a structural RFI, submittal, inspection, variation or closeout requirement is received. | The Structural Designer completes “Review structural as-built information and close outstanding technical actions” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review record, inspection evidence or accepted as-built update. | Material structural deviation requires CTO and Project Engineer control before site implementation. | A qualified structural reviewer provides backup; any stability, safety or compliance concern immediately escalates to CTO and affected site work remains on hold. | To be confirmed. | • In plain words: at the end the Structural Designer checks the as-built structural record and closes any outstanding technical issues. • Starts when: the project reaches structural completion or closeout. • How it runs: (1) as-built structural information and any deviations from design are reviewed. (2) Deviations are assessed for structural acceptability and formally accepted or corrected. (3) Outstanding technical actions, non-conformances and open RFIs are closed. (4) The final calculation and drawing record is confirmed to match the built structure. (5) Lessons learned are recorded against the criteria, details or checklists that should change. • Proof it happened: the reviewed as-built structural record with deviations assessed and accepted, the closed technical actions, and the lessons learned. • Where it usually breaks: deviations that happened on site are recorded but never assessed, so nobody has confirmed the structure as built is actually adequate. | • Require every as-built deviation to be assessed and formally accepted or corrected by a named engineer. An unassessed deviation is an open liability. • Confirm the final calculations and drawings match the built structure, since that record is what a future engineer will rely on. • Close open non-conformances and RFIs before structural closeout is signed, with a list of any exceptions and their owners. • Direct lessons learned to the design criteria, standard details or checklists, with an owner. • Archive the calculations, drawings, inspection records and deviations together for the retention period.
168 | Technical Engineering | Receive approved architectural brief and MEP scope | HVAC & Plumbing Draftsman | Trigger: When the approved brief and available utility/site information are received. Action: The HVAC & Plumbing Draftsman completes “Receive approved architectural brief and MEP scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an MEP basis, survey record, missing-input list and authority criteria. Control/Handoff: Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the approved brief and available utility/site information are received. | The HVAC & Plumbing Draftsman completes “Receive approved architectural brief and MEP scope” using the approved brief, source documents, calculations and controlled company systems. | an MEP basis, survey record, missing-input list and authority criteria. | Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the HVAC and Plumbing Draftsman takes the approved architectural brief and the MEP scope and checks what is actually being asked for before starting. • Starts when: the architectural brief and MEP scope are issued to the mechanical team. • How it runs: (1) the brief, drawings and scope are reviewed for what affects mechanical services. (2) What is in and out of the scope is confirmed, including who supplies what. (3) Missing information is listed, particularly ceiling voids, plant space and client equipment. (4) Anything unworkable is raised early with the Architect and the CTO. (5) Acceptance is confirmed with the open items recorded. • Proof it happened: the scope acceptance record listing the information used, the scope boundary confirmed and the open items. • Where it usually breaks: mechanical scope boundaries with the client, the kitchen supplier or the specialist vendor are assumed rather than confirmed, and the gap appears at commissioning. | • Require the scope boundary to be confirmed in writing, naming who supplies, installs and connects each item. Kitchen, medical and process equipment gaps are the classic omission. • Set a minimum input list mechanical needs before starting, including ceiling void heights, plant space and client equipment data. • Record the architectural revision the mechanical design is based on. • Raise unworkable arrangements such as insufficient plant space before concept freeze, since later they cannot be fixed. • Log open items in a tracked register rather than an email thread.
169 | Technical Engineering | Survey existing HVAC, plumbing and drainage services where applicable | HVAC & Plumbing Draftsman | Trigger: When the approved brief and available utility/site information are received. Action: The HVAC & Plumbing Draftsman completes “Survey existing HVAC, plumbing and drainage services where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an MEP basis, survey record, missing-input list and authority criteria. Control/Handoff: Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the approved brief and available utility/site information are received. | The HVAC & Plumbing Draftsman completes “Survey existing HVAC, plumbing and drainage services where applicable” using the approved brief, source documents, calculations and controlled company systems. | an MEP basis, survey record, missing-input list and authority criteria. | Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: where services already exist, the Draftsman surveys what is there and what condition it is in. • Starts when: the project involves existing HVAC, plumbing or drainage services. • How it runs: (1) available existing drawings and records are collected, and treated as indicative until verified. (2) A site survey records routes, sizes, equipment and their condition. (3) Live services, isolation points and capacities are identified. (4) Anything that could not be traced or accessed is marked as unverified. (5) The survey is drawn up and issued for verification. • Proof it happened: the existing services survey with photographs, the identified isolation points, and the unverified areas marked. • Where it usually breaks: old drawings are trusted without a site check, so a concealed live pipe is only found when it is cut. | • State that existing drawings are indicative only and must be verified on site. This is a safety matter, not a drawing accuracy matter. • Require isolation points and live service positions to be identified and recorded before any work near them. • Mark unverified and inaccessible areas clearly on the survey drawings. • Record existing equipment condition and remaining capacity, since reusing undersized plant is a common mistake. • Photograph and index the survey, since access is often unavailable later.
170 | Technical Engineering | Establish HVAC and plumbing design criteria, assumptions and authority requirements | HVAC & Plumbing Draftsman | Trigger: When the approved brief and available utility/site information are received. Action: The HVAC & Plumbing Draftsman completes “Establish HVAC and plumbing design criteria, assumptions and authority requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an MEP basis, survey record, missing-input list and authority criteria. Control/Handoff: Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the approved brief and available utility/site information are received. | The HVAC & Plumbing Draftsman completes “Establish HVAC and plumbing design criteria, assumptions and authority requirements” using the approved brief, source documents, calculations and controlled company systems. | an MEP basis, survey record, missing-input list and authority criteria. | Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman writes down the rules for the mechanical design. Which codes and standards, what conditions to design for, and what the authority requires. • Starts when: the scope is accepted and design is about to begin. • How it runs: (1) applicable codes, standards and authority requirements are confirmed. (2) Design conditions are set: outdoor and indoor temperatures, humidity, fresh air rates and occupancy. (3) Assumptions are listed with what each depends on. (4) The criteria are set out as a single document. (5) The CTO approves them before design proceeds. • Proof it happened: the approved mechanical design criteria document stating codes, conditions, rates and assumptions, with its version. • Where it usually breaks: the design conditions are never written down, so different rooms end up designed to different assumptions and the plant is sized on a mixture. | • Require design criteria to be one approved, version-controlled document before load calculations start. Plant sizing cannot be defended without it. • State the code edition, authority requirements and any client standard explicitly. • List the design conditions and fresh air rates by space type, so they are applied consistently. • Require CTO approval, since criteria drive equipment capacity and therefore cost. • Treat any change to criteria as a formal revision with recalculation of the affected loads.
171 | Technical Engineering | Identify missing utility data, tests, capacities and specialist inputs | HVAC & Plumbing Draftsman | Trigger: When the approved brief and available utility/site information are received. Action: The HVAC & Plumbing Draftsman completes “Identify missing utility data, tests, capacities and specialist inputs” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an MEP basis, survey record, missing-input list and authority criteria. Control/Handoff: Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the approved brief and available utility/site information are received. | The HVAC & Plumbing Draftsman completes “Identify missing utility data, tests, capacities and specialist inputs” using the approved brief, source documents, calculations and controlled company systems. | an MEP basis, survey record, missing-input list and authority criteria. | Assumed capacity or condition is documented; missing critical data escalates to CTO before final design. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman identifies what is still missing, such as utility capacities, tests and specialist information. • Starts when: gaps in the mechanical inputs are identified. • How it runs: (1) missing information is listed: water pressure and supply capacity, drainage connection levels, power availability, client equipment loads. (2) Required tests or utility confirmations are specified with their purpose. (3) The requirement is raised to Projects or the client with the consequence of not having it. (4) Each open input is tracked with an owner and a date. (5) Assumptions are updated or confirmed when the information arrives. • Proof it happened: the open inputs register with the requests raised, the responses received and the assumptions updated. • Where it usually breaks: incoming water pressure is assumed, and the whole distribution design has to change when the real figure comes in low. | • Require utility capacities such as incoming water pressure and drainage invert levels to be confirmed by the utility in writing, not assumed. These change the entire distribution design. • Track open inputs as a live register with owners and dates, reported at design reviews. • State the consequence of missing information in the request, so the client can weigh the risk. • Mark drawings issued on unconfirmed assumptions and state who must be told when they change. • Escalate refused or delayed inputs that create a design or safety exposure.
172 | Technical Engineering | Prepare cooling-load and ventilation calculations | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Prepare cooling-load and ventilation calculations” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Prepare cooling-load and ventilation calculations” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman calculates how much cooling and fresh air each space needs. • Starts when: the design criteria are approved and the architectural layout is stable enough to calculate from. • How it runs: (1) spaces are entered with their areas, orientation, construction and occupancy. (2) Building fabric values are taken from the architectural information rather than assumed. (3) Internal gains from people, lighting and equipment are applied per the criteria. (4) Ventilation rates are calculated per space type. (5) The results are sanity checked against benchmark figures, then checked and recorded. • Proof it happened: the cooling load and ventilation calculations with the inputs stated, the architectural revision used, and the check record. • Where it usually breaks: loads are calculated with generous safety margins added at every step, so the plant ends up substantially oversized and cycles badly. | • State where safety margins may be applied and how much, once only. Compounded margins at every step are the reason plant is routinely oversized. • Require fabric values to come from the architectural design rather than default assumptions. • Sanity check the result against benchmark figures per space type, and query anything well outside the range. • Record the architectural revision the loads were calculated from, since layout changes invalidate them. • Require recalculation when the layout, occupancy or facade changes materially, and define what counts as material.
173 | Technical Engineering | Select preliminary HVAC systems and equipment capacities | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Select preliminary HVAC systems and equipment capacities” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Select preliminary HVAC systems and equipment capacities” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman selects the type of HVAC system and the equipment capacities to suit the building. • Starts when: the loads are calculated and a system has to be selected. • How it runs: (1) system options are considered against the loads, the building use and the available plant space. (2) Each is assessed for capital cost, running cost, maintenance access and spares availability locally. (3) Equipment capacities are selected with the manufacturer data referenced. (4) Plant space, weight, power and drainage needs are issued to Architecture, Structure and Electrical. (5) The CTO approves the system before layout work proceeds. • Proof it happened: the system selection record with the options compared, the selected capacities with their data source, and the CTO's approval. • Where it usually breaks: equipment is selected on price and capacity only, and nobody checks whether it can physically be got into the plant room or serviced once installed. | • Require an access, replacement and maintenance check for every major item: how it gets in, how it comes out, and whether it can be serviced in place. • Assess running cost and local spares and service availability, not capital cost alone. • Issue plant weight, power, water and drainage requirements to Structure, Electrical and Architecture as a controlled notification. • Reference manufacturer data for every selection, since generic capacities do not survive procurement. • Require CTO approval of the system, as it fixes cost, space and the operating model.
174 | Technical Engineering | Prepare HVAC zoning, ductwork and air-distribution layouts | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Prepare HVAC zoning, ductwork and air-distribution layouts” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Prepare HVAC zoning, ductwork and air-distribution layouts” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws the zoning and the ductwork that gets air to each space. • Starts when: the system is approved and air distribution layouts are required. • How it runs: (1) zones are set by use, orientation and occupancy pattern. (2) Duct routes are drawn within the available ceiling voids and coordinated with structure. (3) Diffusers and grilles are positioned against the reflected ceiling plan and the room use. (4) Access for dampers, filters and cleaning is provided. (5) The layout is checked against the loads and the ceiling void, then submitted for checking. • Proof it happened: the ductwork and air distribution layouts with zoning, coordinated against the ceiling void and structure, with the check record. • Where it usually breaks: duct routes are drawn assuming a ceiling void that the structure and other services do not leave, so ducts are flattened or rerouted on site. | • Require the available ceiling void to be confirmed against the structural and architectural design before duct routes are drawn, and require a shortfall to be reported rather than absorbed. • Show access requirements for dampers, filters and cleaning on the drawings, since these are omitted and then impossible. • Coordinate diffuser positions with the reflected ceiling plan and the lighting layout. • Prohibit reducing duct sizes on site to fit, and state the route for requesting a redesign. • Record the zoning logic, since it drives controls and later fit-out changes.
175 | Technical Engineering | Prepare refrigerant, chilled-water or condensate piping layouts where applicable | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Prepare refrigerant, chilled-water or condensate piping layouts where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Prepare refrigerant, chilled-water or condensate piping layouts where applicable” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws the refrigerant, chilled water or condensate pipework serving the equipment. • Starts when: the selected system requires refrigerant, chilled water or condensate piping. • How it runs: (1) routes are drawn between plant and units within the manufacturer's limits on length and lift. (2) Condensate is drawn with continuous fall to a proper discharge point, never to a route that relies on chance. (3) Insulation, supports and expansion provisions are specified. (4) Routes are coordinated with structure, other services and access. (5) The layout is checked against the manufacturer's requirements and submitted for checking. • Proof it happened: the piping layouts with the manufacturer limits confirmed, the condensate falls shown, and the check record. • Where it usually breaks: condensate drainage is drawn without a proper fall or discharge point, and the first hot week produces water damage in the ceiling. | • Require condensate routes, falls and a legitimate discharge point to be drawn and dimensioned. Condensate is the single most common cause of water damage in fit-out. • Confirm refrigerant pipe length, lift and equivalent length against the manufacturer's limits, and record the confirmation. • Specify insulation, vapour barrier and support spacing, since condensation on pipework causes the same damage. • Coordinate routes for access to valves, filters and drain points. • State pressure testing and leak testing requirements with the hold points before concealment.
176 | Technical Engineering | Size ducts, pipes and major HVAC components | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Size ducts, pipes and major HVAC components” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Size ducts, pipes and major HVAC components” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman calculates the correct sizes for ducts, pipes and the main HVAC components. • Starts when: the layouts are developed enough to size, and at every layout change. • How it runs: (1) flow rates are taken from the load and ventilation calculations. (2) Ducts and pipes are sized to the criteria for velocity, pressure drop and noise. (3) Total system resistance is calculated to select fans and pumps. (4) The sizes are checked against the space actually available. (5) Sizing is checked, recorded and reflected on the drawings and schedules. • Proof it happened: the sizing calculations with the criteria and flow sources stated, and the sizes reflected consistently on drawings and schedules. • Where it usually breaks: sizes are changed on the drawings to fit the space without recalculating, so the system is quietly undersized and never achieves its design flow. | • Prohibit changing a duct or pipe size on a drawing without recalculating and updating the record. A size changed to fit is an undersized system. • Require velocity, pressure drop and noise criteria to be stated and applied, since noise complaints are usually a sizing decision. • Calculate total system resistance for fan and pump selection rather than relying on nominal figures. • Keep sizes consistent between calculations, drawings and schedules with a reconciliation check at each revision. • Record the calculation source for each sized run, so a query can be answered without redoing the work.
177 | Technical Engineering | Prepare HVAC schematics, details and equipment schedules | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Prepare HVAC schematics, details and equipment schedules” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Prepare HVAC schematics, details and equipment schedules” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman prepares the HVAC schematics, details and the equipment schedules that say exactly what is being bought. • Starts when: the system design is stable enough to schematise and schedule. • How it runs: (1) schematics are drawn showing the system arrangement, controls intent and interlocks. (2) Installation details are prepared for typical and specific conditions. (3) Equipment schedules are built listing capacity, electrical data, weight, dimensions and performance. (4) Schedules are reconciled against the drawings and the calculations. (5) The set is checked and issued with the drawing revision recorded. • Proof it happened: the schematics, details and equipment schedules reconciled against the drawings and calculations, with the check record. • Where it usually breaks: the equipment schedule omits the electrical data and weight, so Electrical and Structure design around figures they had to guess. | • Fix the minimum attributes for equipment schedules, including electrical load, weight, dimensions, connection sizes and performance point. Electrical and Structure design from these. • Require schematics to show the controls intent and interlocks, since commissioning disputes come from unstated intent. • Reconcile schedules against drawings and calculations at every revision, recording the source revision. • Use one equipment tagging system across drawings, schedules, the BOQ and commissioning records. • State whether performance figures are at design conditions or nominal, since procurement substitutes on nominal figures.
178 | Technical Engineering | Coordinate ventilation, exhaust and fresh-air requirements | HVAC & Plumbing Draftsman | Trigger: When the MEP basis, architectural spaces and performance requirements are approved. Action: The HVAC & Plumbing Draftsman completes “Coordinate ventilation, exhaust and fresh-air requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: HVAC calculations, layouts, schematics, schedules and coordination information. Control/Handoff: The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When the MEP basis, architectural spaces and performance requirements are approved. | The HVAC & Plumbing Draftsman completes “Coordinate ventilation, exhaust and fresh-air requirements” using the approved brief, source documents, calculations and controlled company systems. | HVAC calculations, layouts, schematics, schedules and coordination information. | The design is checked for capacity, access, maintainability and interdisciplinary fit before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman makes sure fresh air gets in and stale or dangerous air gets out, in the right amounts and to the right places. • Starts when: ventilation and exhaust requirements are being designed or revised. • How it runs: (1) fresh air and exhaust rates are set per space against the code and the criteria. (2) Kitchen, toilet, car park, plant room and generator ventilation are addressed specifically. (3) Intake and discharge positions are coordinated so exhaust is not drawn back into intakes. (4) Smoke and fire ventilation requirements are checked with the fire strategy. (5) The design is checked against the code and the authority requirements. • Proof it happened: the ventilation and exhaust design with the rates per space, the intake and discharge positions coordinated, and the code compliance check. • Where it usually breaks: an exhaust discharge is positioned near a fresh air intake or an openable window, and the building recirculates its own kitchen or car park air. | • Require intake and discharge separation to be checked against the code and against openable windows and occupied terraces. Short-circuiting exhaust into intake is a health issue, not an inconvenience. • Address kitchen, car park, generator and battery ventilation as specific cases with their own requirements. • Check smoke and fire ventilation against the fire strategy, and name who owns that interface. • State the rates per space type on the drawings or schedules, so commissioning can verify against a stated target. • Require authority-specific ventilation requirements to be confirmed before layout, since they often govern.
179 | Technical Engineering | Prepare water-demand and storage calculations | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Prepare water-demand and storage calculations” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Prepare water-demand and storage calculations” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman calculates how much water the building needs and how much storage it must hold. • Starts when: the design criteria are approved and the fixture schedule is known. • How it runs: (1) fixture units and demand are calculated from the occupancy and the fixture schedule. (2) Peak demand and simultaneous use are established per the code. (3) Storage requirements are calculated including any authority or fire reserve. (4) The available incoming supply and pressure are compared with demand. (5) The calculations are checked and the tank and pump requirements issued to Structure and Architecture. • Proof it happened: the water demand and storage calculations with the fixture basis, the incoming supply confirmed, and the requirements issued. • Where it usually breaks: storage volume is calculated but the tank weight and space are never issued to Structure and Architecture until the slab is designed. | • Issue tank volume, footprint, weight and access requirements to Structure and Architecture as a controlled notification, with confirmation of receipt. Full tanks are heavy and late notice means redesign. • State whether fire reserve is included in the storage volume, since double counting or omission both cause failures. • Compare demand against the confirmed incoming supply and pressure, not the assumed one. • Record the fixture schedule revision the demand was calculated from. • Require recalculation when occupancy or fixture count changes, and define the threshold that triggers it.
180 | Technical Engineering | Prepare domestic water-supply layouts and schematics | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Prepare domestic water-supply layouts and schematics” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Prepare domestic water-supply layouts and schematics” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws how clean water reaches every fixture in the building. • Starts when: the demand and storage calculations are complete and layouts are required. • How it runs: (1) the supply route from the incoming connection through storage and pumping is drawn. (2) Distribution to risers and fixtures is drawn with valves and isolation points. (3) Hot water generation, distribution and any recirculation are drawn. (4) Access to valves, meters and equipment is coordinated. (5) The layout and schematic are checked against the calculations and submitted for checking. • Proof it happened: the water supply layouts and schematics with isolation points shown, checked against the demand calculations. • Where it usually breaks: isolation valves are not planned by zone, so years later a single leak means shutting off water to the whole building. | • Require isolation valves to be planned by zone, floor and riser, and shown on the drawings and schematics. This decides whether the building can be maintained without a full shutdown. • Show access panels and valve access positions coordinated with Architecture, since valves behind tiles are unusable. • Address hot water recirculation and dead legs explicitly, both for comfort and for water hygiene. • Show meter positions and any authority requirements for them. • State pressure testing and disinfection requirements with hold points before concealment.
181 | Technical Engineering | Prepare soil, waste and vent drainage layouts | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Prepare soil, waste and vent drainage layouts” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Prepare soil, waste and vent drainage layouts” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws how waste water and soil leave the building, and how the system breathes. • Starts when: drainage layouts are required. • How it runs: (1) fixture discharge and drainage loads are established. (2) Pipe routes are drawn with the required falls, and invert levels are stated. (3) Vent pipework is designed so the system works without siphoning or smells. (4) Access points, cleanouts and manholes are positioned for real access. (5) The connection point and its level are confirmed against the authority or site drainage, then the layout is checked. • Proof it happened: the drainage layouts with falls and invert levels, the vent design, the access points, and the confirmed connection level. • Where it usually breaks: the final connection invert level is assumed, and the drainage cannot achieve fall to it, so pumping has to be added late. | • Require the outfall or connection invert level to be confirmed in writing before drainage layouts are finalised. Everything upstream depends on it and pumping added late is costly. • State falls and invert levels on the drawings, not just pipe sizes, since site cannot infer them. • Design venting explicitly and show it, as siphoning and smell complaints are venting failures. • Position cleanouts and manholes where they can actually be reached, coordinated with Architecture. • State testing requirements and the hold point before pipework is covered or backfilled.
182 | Technical Engineering | Prepare storm-water drainage layouts where applicable | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Prepare storm-water drainage layouts where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Prepare storm-water drainage layouts where applicable” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: where needed, the Draftsman draws how rainwater is collected and taken away. • Starts when: the project requires storm water drainage. • How it runs: (1) the design rainfall intensity is taken from the local standard or the authority requirement. (2) Catchment areas are established from the roof and external areas. (3) Outlets, gutters, downpipes and below-ground routes are sized and drawn. (4) Overflow provision is designed for the case where an outlet blocks. (5) The discharge point is confirmed with the authority and the design checked. • Proof it happened: the storm water design with the rainfall intensity source, catchment areas, sizing, overflow provision and the confirmed discharge point. • Where it usually breaks: no overflow route is provided, so one blocked outlet in a storm puts standing water on a roof that was not designed to hold it. | • Require overflow provision for blocked outlets to be designed and drawn. A roof holding water it was not designed for is a structural risk. • Record the rainfall intensity used and its source, since this figure governs all sizing. • Confirm the discharge point and any authority restriction on discharge rate before design. • Coordinate external routes and levels with the civil and external works design. • Specify silt traps, gullies and maintenance access, since blocked systems fail at the worst moment.
183 | Technical Engineering | Prepare pump, tank, heater and plumbing-equipment schedules | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Prepare pump, tank, heater and plumbing-equipment schedules” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Prepare pump, tank, heater and plumbing-equipment schedules” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman prepares the schedules for pumps, tanks, heaters and the other plumbing equipment. • Starts when: plumbing equipment selection is complete enough to schedule. • How it runs: (1) equipment is scheduled with duty, head, capacity and performance point. (2) Electrical load, weight, dimensions and connection sizes are included. (3) Duty and standby arrangements and control intent are stated. (4) The schedule is reconciled against the drawings, schematics and calculations. (5) It is checked and issued with the revision recorded. • Proof it happened: the plumbing equipment schedules with duty and electrical data, reconciled against the drawings and calculations. • Where it usually breaks: pump duty and head are scheduled without the system resistance calculation behind them, so the pump supplied cannot deliver the flow. | • Require the duty point of every pump to be supported by a system resistance calculation, referenced on the schedule. Nominal duties produce pumps that cannot deliver. • Include electrical load, weight, dimensions and connection sizes as mandatory attributes. • State duty and standby arrangements and the control intent, since these are assumed differently by everyone. • Reconcile with drawings and calculations at each revision, recording the source revision. • Use one equipment tag across drawings, schedules, the BOQ and commissioning.
184 | Technical Engineering | Size plumbing pipes, drainage and water-service components | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Size plumbing pipes, drainage and water-service components” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Size plumbing pipes, drainage and water-service components” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman calculates the correct sizes for water pipes, drainage and the incoming service. • Starts when: layouts are developed enough to size, and at every layout change. • How it runs: (1) demand or discharge is established per run from the fixture information. (2) Pipes are sized to the criteria for velocity, pressure loss and noise. (3) Residual pressure at the least favourable fixture is checked, since that is what the user experiences. (4) Drainage is sized with the required falls and gradients. (5) Sizing is checked and reflected consistently on drawings and schedules. • Proof it happened: the sizing calculations with the criteria stated, the worst-case pressure check, and the sizes reflected on the drawings. • Where it usually breaks: pressure is checked only at the main, not at the highest and furthest fixture, so the top floor has poor flow from day one. | • Require the residual pressure check at the least favourable fixture, not at the incoming main. This is what the occupant actually experiences. • Prohibit changing a pipe size on the drawing without recalculating and updating the record. • State velocity and noise criteria, since water noise in occupied spaces is a sizing decision. • Size drainage with the falls stated, and check them against the available level difference. • Keep sizes consistent between calculations, drawings and schedules with a reconciliation at each revision.
185 | Technical Engineering | Prepare plumbing risers, details and fixture schedules | HVAC & Plumbing Draftsman | Trigger: When water, drainage, fixture and architectural information is available. Action: The HVAC & Plumbing Draftsman completes “Prepare plumbing risers, details and fixture schedules” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: plumbing calculations, layouts, risers, details and equipment/fixture schedules. Control/Handoff: The design is checked for capacity, gradients, access and authority requirements before issue. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When water, drainage, fixture and architectural information is available. | The HVAC & Plumbing Draftsman completes “Prepare plumbing risers, details and fixture schedules” using the approved brief, source documents, calculations and controlled company systems. | plumbing calculations, layouts, risers, details and equipment/fixture schedules. | The design is checked for capacity, gradients, access and authority requirements before issue. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws the vertical pipework, the installation details and the fixture schedules. • Starts when: layouts and sizing are stable enough for risers, details and fixture scheduling. • How it runs: (1) risers are drawn showing every branch, floor level, valve and connection. (2) Riser positions and shaft sizes are coordinated with Architecture and Structure. (3) Installation details are prepared for typical conditions and for the difficult ones. (4) Fixtures are scheduled with the approved product references and connection requirements. (5) The set is reconciled against the layouts, checked and issued. • Proof it happened: the riser diagrams, details and fixture schedules reconciled against the layouts, with the check record. • Where it usually breaks: the riser shaft is sized for the pipes only, with no room for insulation, supports or the person who has to work in it. | • Require shaft and riser sizing to include insulation, supports, access and working space, confirmed with Architecture. Pipes-only sizing makes shafts unbuildable. • Show every branch, valve and floor level on the riser diagram, since site and maintenance work from it. • Schedule fixtures with the approved product reference and connection requirements, matched to the architectural finishes approval. • Reconcile fixture counts against the architectural schedules at each revision. • Provide access panel positions and sizes to Architecture as a controlled requirement.
186 | Technical Engineering | Coordinate HVAC and plumbing plant spaces, routes, ceilings and access | HVAC & Plumbing Draftsman | Trigger: When HVAC/plumbing design reaches coordination, authority or IFC milestone. Action: The HVAC & Plumbing Draftsman completes “Coordinate HVAC and plumbing plant spaces, routes, ceilings and access” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed MEP interfaces, submission responses and controlled IFC package. Control/Handoff: Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When HVAC/plumbing design reaches coordination, authority or IFC milestone. | The HVAC & Plumbing Draftsman completes “Coordinate HVAC and plumbing plant spaces, routes, ceilings and access” using the approved brief, source documents, calculations and controlled company systems. | closed MEP interfaces, submission responses and controlled IFC package. | Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman coordinates plant rooms, service routes, ceilings and access with the other disciplines. • Starts when: coordination is due, or when any discipline changes something that affects services. • How it runs: (1) plant room layouts are checked for equipment, access, maintenance space and removal routes. (2) Service routes are coordinated in the ceiling void with a services priority order agreed. (3) Access panel requirements are issued to Architecture. (4) Clashes and space shortfalls are logged in the shared register rather than resolved informally. (5) Coordination is confirmed at the checkpoints with the revisions recorded. • Proof it happened: the coordinated layouts and plant room drawings, the clash register entries, and the access requirements issued. • Where it usually breaks: services are coordinated on paper but the plant room has no route to get a chiller in or out, so replacement means breaking the wall. | • Require an equipment access and removal route check for every plant room, drawn on the layout. Replacement access is forgotten until the first failure. • Agree a services priority order in the ceiling void, since without it coordination is negotiated case by case. • Issue access panel positions and sizes to Architecture as a controlled requirement with confirmation. • Log clashes and space shortfalls in the shared register with owners and dates. • Set coordination checkpoints in the programme and record the discipline revisions at each one.
187 | Technical Engineering | Coordinate MEP openings, sleeves and builders-work requirements | HVAC & Plumbing Draftsman | Trigger: When HVAC/plumbing design reaches coordination, authority or IFC milestone. Action: The HVAC & Plumbing Draftsman completes “Coordinate MEP openings, sleeves and builders-work requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed MEP interfaces, submission responses and controlled IFC package. Control/Handoff: Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When HVAC/plumbing design reaches coordination, authority or IFC milestone. | The HVAC & Plumbing Draftsman completes “Coordinate MEP openings, sleeves and builders-work requirements” using the approved brief, source documents, calculations and controlled company systems. | closed MEP interfaces, submission responses and controlled IFC package. | Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman defines the holes, sleeves and building work the services need, and gets them approved. • Starts when: openings, sleeves or builders-work requirements are identified or revised. • How it runs: (1) required openings and sleeves are marked with size, level and position. (2) They are submitted for structural approval, which is required before they are drawn as final. (3) Approved openings are included in the builders-work schedule with their reference. (4) Fire stopping and waterproofing requirements at penetrations are specified. (5) The schedule and drawings are reconciled and issued. • Proof it happened: the approved openings and sleeves record with structural approval, reflected in the builders-work schedule and the drawings. • Where it usually breaks: services are installed and the holes are cut afterwards without approval, weakening elements and destroying fire compartments. | • State that no penetration is formed or cut without structural approval and, where it crosses a fire compartment, an approved fire stopping detail. This is a life safety control. • Require every drawn opening to appear in the builders-work schedule, with a reconciliation between the two. • Specify fire stopping and waterproofing details per penetration type, with inspection before concealment. • Set a cut-off date after which new openings become a formal change with cost and programme impact. • Name the owner of the builders-work schedule, since several parties rely on it.
188 | Technical Engineering | Prepare HVAC and plumbing authority submission and comment responses | HVAC & Plumbing Draftsman | Trigger: When HVAC/plumbing design reaches coordination, authority or IFC milestone. Action: The HVAC & Plumbing Draftsman completes “Prepare HVAC and plumbing authority submission and comment responses” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed MEP interfaces, submission responses and controlled IFC package. Control/Handoff: Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When HVAC/plumbing design reaches coordination, authority or IFC milestone. | The HVAC & Plumbing Draftsman completes “Prepare HVAC and plumbing authority submission and comment responses” using the approved brief, source documents, calculations and controlled company systems. | closed MEP interfaces, submission responses and controlled IFC package. | Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman prepares the mechanical submission for the authority and answers its comments. • Starts when: a mechanical authority submission is required, or comments are received. • How it runs: (1) the authority's requirements and checklist are confirmed. (2) Drawings and calculations are prepared in the required format with the required stamps. (3) The package is checked against the checklist and authorised by the CTO before submission. (4) Comments are logged individually and responses prepared, with recalculation where needed. (5) Changes go through checking, the drawings are updated to match, and the package is resubmitted. • Proof it happened: the submission package with the checklist, the comment log with responses, and the authorised resubmission with matching drawings. • Where it usually breaks: the submission is revised to satisfy the authority but the construction drawings are never brought in line with what was approved. | • Require every authority-driven change to be carried into the construction drawings, schedules and calculations, not only the submission set. • Keep an authority requirements sheet per authority covering format, calculations and required approvals. • Cross-check that submitted drawings and calculations are from the same revision. • Confirm the stamp or licence required and its validity before submission. • Track submission dates, responses and repeat cycles, since repeats are usually avoidable.
189 | Technical Engineering | Release checked HVAC and plumbing IFC package and revision index | HVAC & Plumbing Draftsman | Trigger: When HVAC/plumbing design reaches coordination, authority or IFC milestone. Action: The HVAC & Plumbing Draftsman completes “Release checked HVAC and plumbing IFC package and revision index” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed MEP interfaces, submission responses and controlled IFC package. Control/Handoff: Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When HVAC/plumbing design reaches coordination, authority or IFC milestone. | The HVAC & Plumbing Draftsman completes “Release checked HVAC and plumbing IFC package and revision index” using the approved brief, source documents, calculations and controlled company systems. | closed MEP interfaces, submission responses and controlled IFC package. | Architect/Structural Designer confirm interfaces; CTO authorises issue; Document Control preserves revision history. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman releases the construction-ready mechanical package with a clear index of what is included. • Starts when: the mechanical design is checked, coordinated and approved for construction issue. • How it runs: (1) the package is checked complete against the deliverable register. (2) Drawings, schematics, schedules and calculations are confirmed consistent at the same revision. (3) Coordination and clash closure are confirmed. (4) The check evidence is attached and the CTO authorises. (5) Document Control issues the package with the revision index and withdraws superseded revisions. • Proof it happened: the released package with its revision index, the check and coordination evidence, issued through Document Control. • Where it usually breaks: drawings are issued for construction while the equipment schedules are still being revised, so site installs to one revision and procures to another. | • Require drawings, schematics, schedules and calculations to be at consistent revisions at release. Site installing to one revision while procurement buys to another is a real and costly failure. • Make check closure and clash closure explicit entry conditions for release. • Issue only through Document Control with a revision index and confirmed withdrawal of superseded revisions. • Record any release with a known open point, notify Projects and track it to closure. • State the status and purpose of issue clearly so preliminary information is not treated as construction information.
190 | Technical Engineering | Respond to HVAC and plumbing RFIs and review technical submittals | HVAC & Plumbing Draftsman | Trigger: When a site RFI, submittal, inspection, testing or closeout request is received. Action: The HVAC & Plumbing Draftsman completes “Respond to HVAC and plumbing RFIs and review technical submittals” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review, test/inspection support record or accepted as-built update. Control/Handoff: Site deviation is not accepted without recorded technical decision and cost/time impact coordination. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When a site RFI, submittal, inspection, testing or closeout request is received. | The HVAC & Plumbing Draftsman completes “Respond to HVAC and plumbing RFIs and review technical submittals” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review, test/inspection support record or accepted as-built update. | Site deviation is not accepted without recorded technical decision and cost/time impact coordination. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: during construction the Draftsman answers mechanical questions from site and reviews what the contractor proposes to install. • Starts when: a mechanical RFI is raised, or a technical submittal or material approval is received. • How it runs: (1) the query or submittal is registered with its date and required response time. (2) Submittals are reviewed against the design, the specification and the schedules. (3) Decisions are issued with reasons, and equivalence is assessed properly where a substitution is proposed. (4) Where the response changes the design, a controlled revision follows. (5) The register tracks responses and closure. • Proof it happened: the RFI and submittal register with the reviewed decisions, the equivalence assessments, and any controlled revisions issued. • Where it usually breaks: a substitution is approved on the headline capacity alone, and the differences in noise, footprint, power or spares only appear at installation. | • Require substitutions to be assessed on all relevant attributes, including performance at design conditions, noise, weight, footprint, electrical load, controls compatibility and local service support. Headline capacity is not equivalence. • State that reviewing a submittal does not relieve the contractor of its obligations, and record the reviewer. • Follow any design-changing answer with a controlled revision the same cycle. • Set and monitor response times, since mechanical delays hold up multiple trades. • Track RFI causes, as clusters indicate weak drawings or unclear specification.
191 | Technical Engineering | Support HVAC and plumbing testing, commissioning and inspection requirements | HVAC & Plumbing Draftsman | Trigger: When a site RFI, submittal, inspection, testing or closeout request is received. Action: The HVAC & Plumbing Draftsman completes “Support HVAC and plumbing testing, commissioning and inspection requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review, test/inspection support record or accepted as-built update. Control/Handoff: Site deviation is not accepted without recorded technical decision and cost/time impact coordination. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When a site RFI, submittal, inspection, testing or closeout request is received. | The HVAC & Plumbing Draftsman completes “Support HVAC and plumbing testing, commissioning and inspection requirements” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review, test/inspection support record or accepted as-built update. | Site deviation is not accepted without recorded technical decision and cost/time impact coordination. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: the Draftsman supports the testing and commissioning that proves the systems actually work. • Starts when: installation reaches testing, or commissioning documentation is required. • How it runs: (1) the testing and commissioning requirements are set out with the acceptance criteria and design figures. (2) Pressure, leak and flushing tests are witnessed at the defined hold points. (3) Air and water balancing results are reviewed against the design flows. (4) Shortfalls are investigated and corrective action agreed rather than accepted. (5) Results are recorded and handed over with the system documentation. • Proof it happened: the witnessed test and commissioning records compared against the design figures, with any shortfalls and corrective actions closed. • Where it usually breaks: balancing results are signed off as complete without being compared against the design flows, so the building is handed over out of balance. | • Require commissioning results to be compared against the design flows and rates item by item, with variances explained. A signed commissioning sheet with no comparison proves nothing. • Set hold points for pressure, leak and flushing tests before concealment, and name who may release them. • State the acceptance tolerance in advance, so it is not negotiated during handover. • Require the witness to be named on each record, and retain the raw readings. • Include controls and interlock testing, since these are the most commonly skipped and the most complained about later.
192 | Technical Engineering | Review HVAC and plumbing as-built drawings and close technical actions | HVAC & Plumbing Draftsman | Trigger: When a site RFI, submittal, inspection, testing or closeout request is received. Action: The HVAC & Plumbing Draftsman completes “Review HVAC and plumbing as-built drawings and close technical actions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review, test/inspection support record or accepted as-built update. Control/Handoff: Site deviation is not accepted without recorded technical decision and cost/time impact coordination. Continuity/Escalation: A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. Timing: To be confirmed. | When a site RFI, submittal, inspection, testing or closeout request is received. | The HVAC & Plumbing Draftsman completes “Review HVAC and plumbing as-built drawings and close technical actions” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review, test/inspection support record or accepted as-built update. | Site deviation is not accepted without recorded technical decision and cost/time impact coordination. | A nominated competent MEP resource provides backup; unresolved performance, authority or coordination risk escalates to CTO. | To be confirmed. | • In plain words: at the end the Draftsman checks the mechanical as-built drawings and closes any technical loose ends. • Starts when: the project reaches mechanical completion or closeout. • How it runs: (1) contractor as-built information and red-lines are reviewed as verified before being accepted. (2) Concealed routes, valve positions and equipment locations are checked as recorded, since these are what maintenance will need. (3) Deviations from design are assessed and accepted or corrected. (4) Outstanding RFIs, non-conformances and open actions are closed. (5) The as-built set, commissioning records and manuals are handed to Document Control with the lessons learned recorded. • Proof it happened: the reviewed as-built set with concealed routes recorded, deviations assessed, actions closed, and the handover package archived. • Where it usually breaks: concealed pipework and valve positions are not recorded accurately, so the first maintenance job means opening ceilings to find out what is where. | • Require concealed routes, valve positions and access panel locations to be recorded accurately on the as-builts. This is the information the building needs for its whole life. • Require red-lines to be verified by Projects before as-built drawing starts. • Assess every deviation and accept or correct it formally rather than only recording it. • Tie as-built and manual completion to the handover and retention milestone, since this work is abandoned once the site closes. • Hand over commissioning records, manuals and warranties as one package with an index, not as scattered files.
193 | Technical Engineering | Receive approved architectural brief and electrical scope | Electrical Draftsman | Trigger: When the approved brief and available electrical/utility information are received. Action: The Electrical Draftsman completes “Receive approved architectural brief and electrical scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an electrical basis, survey record, load-input list and authority criteria. Control/Handoff: Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When the approved brief and available electrical/utility information are received. | The Electrical Draftsman completes “Receive approved architectural brief and electrical scope” using the approved brief, source documents, calculations and controlled company systems. | an electrical basis, survey record, load-input list and authority criteria. | Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Electrical Draftsman takes the approved architectural brief and the electrical scope and checks what is actually being asked for before starting. • Starts when: the architectural brief and electrical scope are issued to the electrical team. • How it runs: (1) the brief, drawings and scope are reviewed for what affects electrical and ELV work. (2) Scope boundaries are confirmed, including which specialist systems are in and which belong to a vendor. (3) Missing information is listed, particularly client equipment loads and IT requirements. (4) Anything unworkable, such as no space for a substation or riser, is raised early. (5) Acceptance is confirmed with the open items recorded. • Proof it happened: the scope acceptance record listing the information used, the scope boundary confirmed and the open items. • Where it usually breaks: specialist systems such as fire alarm, CCTV or access control are assumed to be someone else's scope, and nobody designs the interfaces between them. | • Require the scope boundary for every specialist system to be confirmed in writing: fire alarm, CCTV, access control, BMS, data. Interfaces between them are what get missed. • Set a minimum input list before starting, including client equipment loads, IT requirements and any tenant provision. • Record the architectural revision the electrical design is based on. • Raise space shortfalls for substation, generator, risers and panel rooms before concept freeze. • Log open items in a tracked register with owners and dates.
194 | Technical Engineering | Survey existing electrical and ELV services where applicable | Electrical Draftsman | Trigger: When the approved brief and available electrical/utility information are received. Action: The Electrical Draftsman completes “Survey existing electrical and ELV services where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an electrical basis, survey record, load-input list and authority criteria. Control/Handoff: Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When the approved brief and available electrical/utility information are received. | The Electrical Draftsman completes “Survey existing electrical and ELV services where applicable” using the approved brief, source documents, calculations and controlled company systems. | an electrical basis, survey record, load-input list and authority criteria. | Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: where electrical services already exist, the Draftsman surveys what is there, what it feeds and what condition it is in. • Starts when: the project involves existing electrical or ELV installations. • How it runs: (1) available records, panel schedules and previous drawings are collected and treated as indicative. (2) A site survey records panels, feeders, routes and equipment, with the safety precautions observed. (3) Existing capacity, spare ways and load are established from measurement rather than assumption. (4) Untraced circuits and inaccessible areas are marked as unverified. (5) The survey is drawn up and issued for verification. • Proof it happened: the existing services survey with panel schedules, measured load and spare capacity, and the unverified areas marked. • Where it usually breaks: existing spare capacity is taken from the panel schedule rather than measured, and the new load trips the incoming supply. | • Require existing capacity to be established from measured load, not from the panel schedule. Recorded schedules are almost always out of date. • State the safety requirements for surveying live installations, including who may open panels and what protective equipment is required. • Mark untraced circuits and inaccessible areas as unverified on the survey. • Record existing equipment age and condition, since reusing old switchgear carries risk and spares issues. • Photograph and index panels and their labelling, since access is rarely available later.
195 | Technical Engineering | Establish electrical design criteria, assumptions and authority requirements | Electrical Draftsman | Trigger: When the approved brief and available electrical/utility information are received. Action: The Electrical Draftsman completes “Establish electrical design criteria, assumptions and authority requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an electrical basis, survey record, load-input list and authority criteria. Control/Handoff: Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When the approved brief and available electrical/utility information are received. | The Electrical Draftsman completes “Establish electrical design criteria, assumptions and authority requirements” using the approved brief, source documents, calculations and controlled company systems. | an electrical basis, survey record, load-input list and authority criteria. | Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman writes down the rules for the electrical design. Which codes and standards, what supply arrangement, and what the authority and utility require. • Starts when: the scope is accepted and design is about to begin. • How it runs: (1) applicable codes, standards and utility regulations are confirmed. (2) The supply arrangement, voltages, earthing system and fault level are established. (3) Design assumptions are listed with what each depends on. (4) The criteria are set out as one document. (5) The CTO approves them before design proceeds. • Proof it happened: the approved electrical design criteria document stating codes, supply arrangement, earthing system and assumptions, with its version. • Where it usually breaks: the utility's fault level and supply arrangement are assumed, and equipment ratings and protection settings all have to be revisited when the real figures arrive. | • Require the utility supply arrangement, voltage and prospective fault level to be confirmed by the utility in writing. Equipment ratings and protection design depend entirely on these. • State the earthing system type explicitly, since it governs protection, bonding and safety design. • Require the criteria to be one approved, version-controlled document before load assessment starts. • Require CTO approval, as criteria drive switchgear ratings and therefore cost. • Treat any change to criteria as a formal revision with reassessment of the affected design.
196 | Technical Engineering | Identify missing utility data, loads and specialist-system inputs | Electrical Draftsman | Trigger: When the approved brief and available electrical/utility information are received. Action: The Electrical Draftsman completes “Identify missing utility data, loads and specialist-system inputs” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an electrical basis, survey record, load-input list and authority criteria. Control/Handoff: Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When the approved brief and available electrical/utility information are received. | The Electrical Draftsman completes “Identify missing utility data, loads and specialist-system inputs” using the approved brief, source documents, calculations and controlled company systems. | an electrical basis, survey record, load-input list and authority criteria. | Unknown supply capacity or specialist requirement is logged and escalated to CTO before final design. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman identifies what information is still missing, such as utility capacity, client loads and specialist system requirements. • Starts when: gaps in the electrical inputs are identified. • How it runs: (1) missing information is listed: available utility capacity, client and tenant equipment loads, IT and specialist system requirements. (2) The requirement is raised to Projects or the client with the consequence of not having it. (3) Utility applications and confirmations are initiated where they have long lead times. (4) Each open input is tracked with an owner and a date. (5) Assumptions are updated or confirmed when the information arrives. • Proof it happened: the open inputs register with the requests raised, the utility applications initiated, and the assumptions updated. • Where it usually breaks: the utility application is left late, and the supply approval becomes the item that holds up the whole project. | • Require the utility supply application to be initiated as early as the load estimate allows, and tracked as a programme item. Supply approval is a long lead item that regularly delays completion. • Require client and tenant equipment loads to be obtained in writing with the actual ratings, not allowances. • Track open inputs as a live register with owners and dates, reported at design reviews. • Mark drawings issued on unconfirmed assumptions and state who must be told when they change. • Escalate refused or delayed inputs that create a design or programme exposure.
197 | Technical Engineering | Prepare connected-load, demand and diversity assessment | Electrical Draftsman | Trigger: When approved loads, spaces and equipment requirements are available. Action: The Electrical Draftsman completes “Prepare connected-load, demand and diversity assessment” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: load calculations, SLDs, schedules, layouts and distribution requirements. Control/Handoff: The design is checked for capacity, protection, routing, access and coordination before issue. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When approved loads, spaces and equipment requirements are available. | The Electrical Draftsman completes “Prepare connected-load, demand and diversity assessment” using the approved brief, source documents, calculations and controlled company systems. | load calculations, SLDs, schedules, layouts and distribution requirements. | The design is checked for capacity, protection, routing, access and coordination before issue. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman works out how much electrical power the building needs, allowing for the fact that not everything runs at once. • Starts when: the design criteria are approved and load information is available. • How it runs: (1) connected loads are listed by area and system from the mechanical, architectural and client information. (2) Diversity factors are applied per load type with the basis stated. (3) Maximum demand is calculated with an allowance for future growth as agreed. (4) The result is checked against benchmark figures per building type. (5) The assessment is checked and used for the utility application and equipment sizing. • Proof it happened: the load and demand assessment with the loads listed, diversity basis stated, future allowance agreed, and the check record. • Where it usually breaks: diversity is applied by habit rather than by load type, so the demand figure is either inflated, which wastes capacity charges, or too low, which caps the building. | • Require diversity factors to be stated per load type with the basis recorded. Applying a single habitual factor either wastes paid-for capacity or caps the building permanently. • Require the future growth allowance to be agreed with the client in writing, since it is paid for in capacity charges. • Sanity check demand against benchmark figures per building type and query outliers. • Record the source revision of the mechanical and client load information used. • Require reassessment when major loads change, and define the threshold that triggers it.
198 | Technical Engineering | Prepare power-distribution concept and single-line diagrams | Electrical Draftsman | Trigger: When approved loads, spaces and equipment requirements are available. Action: The Electrical Draftsman completes “Prepare power-distribution concept and single-line diagrams” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: load calculations, SLDs, schedules, layouts and distribution requirements. Control/Handoff: The design is checked for capacity, protection, routing, access and coordination before issue. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When approved loads, spaces and equipment requirements are available. | The Electrical Draftsman completes “Prepare power-distribution concept and single-line diagrams” using the approved brief, source documents, calculations and controlled company systems. | load calculations, SLDs, schedules, layouts and distribution requirements. | The design is checked for capacity, protection, routing, access and coordination before issue. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman sets out how power flows through the building, from the incoming supply down to each distribution board, on a single diagram. • Starts when: the demand assessment is complete and the distribution concept is required. • How it runs: (1) the distribution strategy is set: supply intake, main boards, sub-boards and essential supplies. (2) The single-line diagram is drawn showing every board, feeder, rating and protective device. (3) Protection coordination and discrimination between levels are addressed. (4) Essential, emergency and UPS-supported sections are shown distinctly. (5) The diagram is checked and approved by the CTO before detailed design proceeds. • Proof it happened: the approved single-line diagram with boards, feeders, ratings and protective devices, and the discrimination basis. • Where it usually breaks: protection is selected board by board without checking discrimination, so a fault on one small circuit trips the main incoming breaker and blacks out the building. | • Require protection discrimination to be checked between all levels of distribution and recorded. Without it a minor fault takes out the whole building, which is the failure users actually experience. • Show essential, emergency and UPS-supported distribution distinctly on the diagram, since these are confused during installation. • Require the single-line diagram to be approved before detailed layouts, as it fixes the whole distribution design. • State fault levels and equipment ratings on the diagram, so procurement cannot substitute lower ratings. • Keep the diagram as the controlling document, and require it to be revised whenever distribution changes.
199 | Technical Engineering | Prepare MDB, SMDB and DB schedules | Electrical Draftsman | Trigger: When approved loads, spaces and equipment requirements are available. Action: The Electrical Draftsman completes “Prepare MDB, SMDB and DB schedules” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: load calculations, SLDs, schedules, layouts and distribution requirements. Control/Handoff: The design is checked for capacity, protection, routing, access and coordination before issue. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When approved loads, spaces and equipment requirements are available. | The Electrical Draftsman completes “Prepare MDB, SMDB and DB schedules” using the approved brief, source documents, calculations and controlled company systems. | load calculations, SLDs, schedules, layouts and distribution requirements. | The design is checked for capacity, protection, routing, access and coordination before issue. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman prepares the schedules that say exactly what each distribution board contains and feeds. • Starts when: the distribution concept is approved and boards need scheduling. • How it runs: (1) each board is scheduled with its rating, incoming feed, busbar and enclosure requirements. (2) Every circuit is listed with its load, cable size, protective device and description. (3) Spare ways and spare capacity are provided as agreed. (4) Schedules are reconciled against the single-line diagram and the layouts. (5) They are checked and issued with the revision recorded. • Proof it happened: the board schedules with circuits, ratings, cable sizes and devices, reconciled against the single-line diagram. • Where it usually breaks: circuit descriptions are generic, such as sockets, so nobody in operation can tell which circuit serves which area without switching things off to find out. | • Require circuit descriptions to identify the actual area or equipment served, not generic labels. This is what operations depend on for the life of the building. • Set a minimum spare way and spare capacity requirement per board and require it to be shown, since it is the first thing sacrificed. • Reconcile schedules against the single-line diagram and layouts at every revision. • State protective device type and rating explicitly, and prohibit substitution without technical review. • Use one board and circuit reference system across drawings, schedules, labelling and testing records.
200 | Technical Engineering | Prepare power, socket and equipment-connection layouts | Electrical Draftsman | Trigger: When approved loads, spaces and equipment requirements are available. Action: The Electrical Draftsman completes “Prepare power, socket and equipment-connection layouts” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: load calculations, SLDs, schedules, layouts and distribution requirements. Control/Handoff: The design is checked for capacity, protection, routing, access and coordination before issue. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When approved loads, spaces and equipment requirements are available. | The Electrical Draftsman completes “Prepare power, socket and equipment-connection layouts” using the approved brief, source documents, calculations and controlled company systems. | load calculations, SLDs, schedules, layouts and distribution requirements. | The design is checked for capacity, protection, routing, access and coordination before issue. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws where the power points, sockets and equipment connections go. • Starts when: board schedules are developed and power layouts are required. • How it runs: (1) socket and outlet positions are set from the room use, furniture layout and client requirements. (2) Fixed equipment connections are drawn from the mechanical and specialist schedules. (3) Mounting heights and coordination with finishes and joinery are addressed. (4) Circuits are allocated and reflected in the board schedules. (5) The layout is checked against the schedules and submitted for checking. • Proof it happened: the power and equipment connection layouts with positions, mounting heights and circuit references, checked against the board schedules. • Where it usually breaks: outlets are drawn to a standard spacing without the furniture layout, so half of them end up behind cabinets and the used positions have none. | • Require outlet positions to be coordinated against the furniture and equipment layout, not placed at standard spacing. Outlets behind joinery are the most visible and most avoidable defect. • State mounting heights on the drawings and coordinate them with finishes and skirting details. • Require every fixed equipment connection to be traced to the mechanical or specialist schedule that specifies it. • Show the circuit reference at each outlet group, so site wires to the schedule rather than by judgement. • Set a cut-off after which added outlets become a formal change with cost and programme impact.
201 | Technical Engineering | Prepare cable, containment and routing requirements | Electrical Draftsman | Trigger: When approved loads, spaces and equipment requirements are available. Action: The Electrical Draftsman completes “Prepare cable, containment and routing requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: load calculations, SLDs, schedules, layouts and distribution requirements. Control/Handoff: The design is checked for capacity, protection, routing, access and coordination before issue. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When approved loads, spaces and equipment requirements are available. | The Electrical Draftsman completes “Prepare cable, containment and routing requirements” using the approved brief, source documents, calculations and controlled company systems. | load calculations, SLDs, schedules, layouts and distribution requirements. | The design is checked for capacity, protection, routing, access and coordination before issue. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman decides cable sizes and how cables are supported and routed through the building. • Starts when: circuits are defined and cable and containment design is required. • How it runs: (1) cables are sized for current capacity, voltage drop, fault withstand and installation method. (2) Grouping, ambient temperature and derating factors are applied. (3) Containment routes and sizes are drawn with spare capacity allowed. (4) Segregation between power, ELV and data is provided per the standard. (5) Sizing and routes are checked and reflected consistently on drawings and schedules. • Proof it happened: the cable sizing calculations with derating factors applied, and the containment layouts with routes, sizes and spare capacity. • Where it usually breaks: cables are sized for current capacity only, with voltage drop ignored on long runs, so distant equipment underperforms and nobody connects it to the cable size. | • Require voltage drop to be checked on every long run and recorded, not just current capacity. Voltage drop failures show up as equipment underperforming with no obvious cause. • Require grouping and ambient derating factors to be stated and applied, since ignoring them is a fire risk. • Specify containment spare capacity as a percentage and require it to be shown, since future cabling always needs it. • Require segregation between power, ELV and data per the standard, shown on the drawings. • Prohibit changing a cable size on site to suit availability, and state the technical review route.
202 | Technical Engineering | Prepare earthing, bonding and lightning-protection layouts where applicable | Electrical Draftsman | Trigger: When approved loads, spaces and equipment requirements are available. Action: The Electrical Draftsman completes “Prepare earthing, bonding and lightning-protection layouts where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: load calculations, SLDs, schedules, layouts and distribution requirements. Control/Handoff: The design is checked for capacity, protection, routing, access and coordination before issue. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When approved loads, spaces and equipment requirements are available. | The Electrical Draftsman completes “Prepare earthing, bonding and lightning-protection layouts where applicable” using the approved brief, source documents, calculations and controlled company systems. | load calculations, SLDs, schedules, layouts and distribution requirements. | The design is checked for capacity, protection, routing, access and coordination before issue. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman designs the earthing and bonding that keeps people safe, and lightning protection where it is needed. • Starts when: earthing, bonding or lightning protection design is required. • How it runs: (1) the earthing system is designed to suit the supply arrangement, with the target earth resistance stated. (2) The earth electrode arrangement and test points are drawn. (3) Main and supplementary bonding of services, structure and metalwork is drawn. (4) Where required, lightning protection is designed with air terminations, down conductors and bonding. (5) The design is checked against the standard and the testing requirements are stated. • Proof it happened: the earthing, bonding and lightning protection layouts with the target resistance, test points, and the compliance check. • Where it usually breaks: earth electrodes and bonding connections are installed where they cannot be inspected or tested again, so compliance can never be re-verified. | • Require accessible, labelled test points for earthing and lightning protection, shown on the drawings. Compliance must be re-verifiable for the life of the building, not just at handover. • State the target earth resistance and the test method, since acceptance depends on a measured figure. • Require bonding of all incoming services, structural steel and major metalwork to be drawn, not left as a note. • Coordinate earth electrode and down conductor positions with Structure and Civil before construction. • Set testing hold points before concealment or backfill, and name who witnesses them.
203 | Technical Engineering | Prepare lighting layouts and control-zone requirements | Electrical Draftsman | Trigger: When architectural layouts and approved system scope are available. Action: The Electrical Draftsman completes “Prepare lighting layouts and control-zone requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated lighting, ELV and life-safety layouts, schematics and schedules. Control/Handoff: Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When architectural layouts and approved system scope are available. | The Electrical Draftsman completes “Prepare lighting layouts and control-zone requirements” using the approved brief, source documents, calculations and controlled company systems. | coordinated lighting, ELV and life-safety layouts, schematics and schedules. | Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman draws the lighting and how it is switched and controlled. • Starts when: lighting design is required and the architectural ceiling layout is available. • How it runs: (1) target light levels per space are set from the standard and the criteria. (2) Fittings are selected and laid out, coordinated with the reflected ceiling plan. (3) Calculations confirm the levels and uniformity achieved. (4) Control zones, switching and any dimming or sensing are defined. (5) The layout and controls schedule are checked and issued. • Proof it happened: the lighting layouts with the calculation results, the fitting schedule, and the control zone definitions. • Where it usually breaks: the lighting layout is coordinated with the ceiling but not with the mechanical grilles and sprinklers, so fittings shift on site and the calculated levels no longer apply. | • Require the lighting layout to be coordinated against ceiling, mechanical and fire services before issue, since fittings moved on site invalidate the calculations. • Record the target light level and the calculation result per space type, so handover disputes have a reference. • Define control zones with the switching intent, as this is where occupants most often complain. • State whether emergency function is integral to any fitting, so it is not lost in substitution. • Require recalculation when fittings are substituted, and prohibit substitution on wattage alone.
204 | Technical Engineering | Prepare emergency and exit-lighting layouts | Electrical Draftsman | Trigger: When architectural layouts and approved system scope are available. Action: The Electrical Draftsman completes “Prepare emergency and exit-lighting layouts” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated lighting, ELV and life-safety layouts, schematics and schedules. Control/Handoff: Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When architectural layouts and approved system scope are available. | The Electrical Draftsman completes “Prepare emergency and exit-lighting layouts” using the approved brief, source documents, calculations and controlled company systems. | coordinated lighting, ELV and life-safety layouts, schematics and schedules. | Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman designs the lighting that keeps people able to see and escape when the power fails. • Starts when: emergency and exit lighting design is required. • How it runs: (1) escape routes, exits and required coverage points are established from the fire strategy and the code. (2) Emergency fittings and exit signs are positioned to cover routes, stairs, changes of level and final exits. (3) The duration, illumination level and supply arrangement are specified. (4) Sign positions and viewing distances are checked for actual visibility. (5) The design is checked for code compliance and the testing regime stated. • Proof it happened: the emergency and exit lighting layouts with the coverage, duration and supply stated, and the code compliance check. • Where it usually breaks: exit signs are drawn in code-compliant positions but are not visible in practice once doors, ducts or signage are installed in front of them. | • Require exit sign positions to be checked for actual line of sight against the final architectural and mechanical arrangement. A compliant position that cannot be seen is a life safety failure. • Cross-check coverage against the approved fire strategy and escape route plan, and name who owns that interface. • State the required duration, illumination level and supply arrangement on the drawings. • Specify the testing regime and the record required, since this is an ongoing statutory obligation. • Require any layout change affecting escape routes to trigger a recheck of emergency lighting.
205 | Technical Engineering | Prepare fire-alarm layouts and interfaces where within approved scope | Electrical Draftsman | Trigger: When architectural layouts and approved system scope are available. Action: The Electrical Draftsman completes “Prepare fire-alarm layouts and interfaces where within approved scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated lighting, ELV and life-safety layouts, schematics and schedules. Control/Handoff: Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When architectural layouts and approved system scope are available. | The Electrical Draftsman completes “Prepare fire-alarm layouts and interfaces where within approved scope” using the approved brief, source documents, calculations and controlled company systems. | coordinated lighting, ELV and life-safety layouts, schematics and schedules. | Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: where it is in scope, the Draftsman draws the fire alarm system and how it connects to everything it has to control. • Starts when: fire alarm design or interface definition is required within the approved scope. • How it runs: (1) the detection and alarm requirements are established from the code, the fire strategy and the authority. (2) Devices, sounders and panels are laid out with the zoning defined. (3) Interfaces are defined with every system the alarm must act on: ventilation shutdown, smoke control, lifts, access control, dampers. (4) Cause and effect is set out so the intended behaviour is explicit. (5) The design is checked against the code and prepared for authority approval. • Proof it happened: the fire alarm layouts with zoning, the cause and effect schedule, and the interface definitions with the affected systems. • Where it usually breaks: the alarm system is designed correctly but the cause and effect is never written down, so what should happen on activation is decided during commissioning. | • Require a written cause and effect schedule as a design deliverable, approved before installation. Without it, fire system behaviour is invented at commissioning and cannot be verified against intent. • Define every interface explicitly, including ventilation shutdown, smoke control, dampers, lifts, access control and door release, and name the owner of each. • Cross-check zoning against the approved fire strategy and the authority requirement. • Require authority approval status to be recorded, since fire systems are directly licensable. • Require integrated testing against the cause and effect schedule, not device-by-device testing alone.
206 | Technical Engineering | Prepare data, telephone, CCTV and access-control layouts where within approved scope | Electrical Draftsman | Trigger: When architectural layouts and approved system scope are available. Action: The Electrical Draftsman completes “Prepare data, telephone, CCTV and access-control layouts where within approved scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated lighting, ELV and life-safety layouts, schematics and schedules. Control/Handoff: Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When architectural layouts and approved system scope are available. | The Electrical Draftsman completes “Prepare data, telephone, CCTV and access-control layouts where within approved scope” using the approved brief, source documents, calculations and controlled company systems. | coordinated lighting, ELV and life-safety layouts, schematics and schedules. | Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: where it is in scope, the Draftsman draws the data, telephone, CCTV and access control layouts. • Starts when: ELV system design is required within the approved scope. • How it runs: (1) requirements are confirmed with the client or the IT and security stakeholder rather than assumed. (2) Outlet, camera and reader positions are laid out against the room use and coverage needs. (3) Equipment room, rack and containment provision is coordinated. (4) Cable types, lengths and any distance limits are checked. (5) The layouts are checked and issued with the vendor scope boundary noted. • Proof it happened: the ELV layouts with the confirmed requirements, coverage positions, equipment room provision and the vendor boundary. • Where it usually breaks: camera and reader positions are drawn without confirming the coverage the client actually wants, so the system is installed and then moved. | • Require CCTV coverage and access control intent to be confirmed by the client or security stakeholder in writing before layout, since these are use decisions not technical ones. • State the vendor scope boundary clearly on the drawings: what is designed, what is supplied and who commissions. • Check cable distance limits and equipment room proximity, as these are frequently exceeded. • Coordinate equipment room space, cooling and power with Mechanical and the power design. • Record the coordination with IT infrastructure requirements, since data and security often share containment.
207 | Technical Engineering | Prepare ELV schematics, schedules and equipment requirements | Electrical Draftsman | Trigger: When architectural layouts and approved system scope are available. Action: The Electrical Draftsman completes “Prepare ELV schematics, schedules and equipment requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated lighting, ELV and life-safety layouts, schematics and schedules. Control/Handoff: Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When architectural layouts and approved system scope are available. | The Electrical Draftsman completes “Prepare ELV schematics, schedules and equipment requirements” using the approved brief, source documents, calculations and controlled company systems. | coordinated lighting, ELV and life-safety layouts, schematics and schedules. | Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman prepares the ELV schematics, schedules and equipment requirements. • Starts when: ELV design is stable enough to schematise and schedule. • How it runs: (1) schematics are drawn showing system architecture, head-end equipment and connections. (2) Equipment schedules are built with quantities, types, power and space requirements. (3) Power and cooling requirements are issued to the power and mechanical designs. (4) Integration requirements between systems are stated. (5) The set is reconciled against the layouts, checked and issued. • Proof it happened: the ELV schematics and schedules reconciled against the layouts, with the power and cooling requirements issued. • Where it usually breaks: ELV equipment power and cooling requirements are never issued to the power and mechanical designs, so the equipment room has neither enough supply nor enough cooling. | • Require ELV equipment power and cooling loads to be issued to the electrical and mechanical designs as a controlled notification with confirmation. Equipment rooms are routinely under-supplied and under-cooled. • State integration requirements between ELV systems, since integration is where the cost and the disputes sit. • Include quantities, types, rack space and power in the schedules as mandatory attributes. • Reconcile schedules against layouts at each revision with the source revision recorded. • Use one device tagging system across drawings, schedules, the BOQ and commissioning.
208 | Technical Engineering | Coordinate generator, UPS and specialist-power systems where applicable | Electrical Draftsman | Trigger: When architectural layouts and approved system scope are available. Action: The Electrical Draftsman completes “Coordinate generator, UPS and specialist-power systems where applicable” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: coordinated lighting, ELV and life-safety layouts, schematics and schedules. Control/Handoff: Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When architectural layouts and approved system scope are available. | The Electrical Draftsman completes “Coordinate generator, UPS and specialist-power systems where applicable” using the approved brief, source documents, calculations and controlled company systems. | coordinated lighting, ELV and life-safety layouts, schematics and schedules. | Only systems within approved competence/scope are designed; specialist and authority interfaces are recorded. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: where the building has a generator, UPS or other specialist power, the Draftsman coordinates it into the design. • Starts when: generator, UPS or specialist power systems are part of the project. • How it runs: (1) which loads must be supported and for how long is established and agreed. (2) Capacity is sized against those loads with the starting and transient characteristics considered. (3) Location requirements are coordinated: ventilation, exhaust, fuel, noise, vibration, access and weight. (4) Changeover arrangements, controls and interlocks are designed and stated. (5) The design is checked, and the authority and environmental requirements are addressed. • Proof it happened: the specialist power design with the supported load schedule, capacity basis, location requirements issued, and the changeover arrangement. • Where it usually breaks: the list of loads on the generator grows during the project without resizing, so the standby supply cannot carry what is connected to it. | • Require the essential load schedule to be a controlled document, with any addition triggering a resize check. Load creep onto standby supply is the standard failure and it is only discovered in an outage. • Issue location requirements covering ventilation, exhaust, fuel, noise, vibration, weight and access to Architecture, Structure and Mechanical. • State the changeover arrangement, timing and interlocks explicitly, since these are commissioning disputes otherwise. • Address authority, environmental and noise consent requirements before location is fixed. • Require load bank or on-load testing at commissioning, not a no-load start test.
209 | Technical Engineering | Coordinate electrical containment, ceiling and MEP interfaces | Electrical Draftsman | Trigger: When electrical design reaches coordination, authority or IFC milestone. Action: The Electrical Draftsman completes “Coordinate electrical containment, ceiling and MEP interfaces” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed interfaces, submission responses and controlled electrical IFC package. Control/Handoff: Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When electrical design reaches coordination, authority or IFC milestone. | The Electrical Draftsman completes “Coordinate electrical containment, ceiling and MEP interfaces” using the approved brief, source documents, calculations and controlled company systems. | closed interfaces, submission responses and controlled electrical IFC package. | Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman coordinates electrical containment with ceilings and the other services so everything fits. • Starts when: coordination is due, or when any discipline changes something affecting electrical routes. • How it runs: (1) containment routes are checked against the ceiling void, structure and mechanical services. (2) The agreed services priority order is applied rather than negotiated case by case. (3) Access to boards, junction boxes and pull points is coordinated with Architecture. (4) Clashes and space shortfalls are logged in the shared register. (5) Coordination is confirmed at the checkpoints with the revisions recorded. • Proof it happened: the coordinated containment layouts, the clash register entries, and the access requirements issued. • Where it usually breaks: electrical is coordinated last, so containment takes whatever space is left and cable pulling becomes impossible in practice. | • Require containment to be coordinated with the same standing as mechanical services, using the agreed priority order. Electrical coordinated last means containment that cannot be pulled. • Require bending radius, pull point and cable pulling access to be considered in routing, not just fit. • Issue access panel and board access requirements to Architecture as a controlled requirement. • Log clashes and space shortfalls in the shared register with owners and dates. • Set coordination checkpoints in the programme and record the discipline revisions at each one.
210 | Technical Engineering | Coordinate builders-work openings, equipment loads and plant connections | Electrical Draftsman | Trigger: When electrical design reaches coordination, authority or IFC milestone. Action: The Electrical Draftsman completes “Coordinate builders-work openings, equipment loads and plant connections” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed interfaces, submission responses and controlled electrical IFC package. Control/Handoff: Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When electrical design reaches coordination, authority or IFC milestone. | The Electrical Draftsman completes “Coordinate builders-work openings, equipment loads and plant connections” using the approved brief, source documents, calculations and controlled company systems. | closed interfaces, submission responses and controlled electrical IFC package. | Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman defines the openings, equipment loads and connections that the building works and other trades need to provide. • Starts when: builders-work, equipment load or plant connection requirements are identified or revised. • How it runs: (1) required openings, sleeves and cutouts are marked with size, level and position. (2) They are submitted for structural approval before being drawn as final. (3) Equipment weights and fixing requirements are issued to Structure, and connection requirements to Mechanical. (4) Fire stopping at penetrations is specified. (5) The builders-work schedule is reconciled with the drawings and issued. • Proof it happened: the approved openings record with structural approval, the equipment loads and connection requirements issued, and the reconciled builders-work schedule. • Where it usually breaks: cable penetrations through fire compartments are formed without approved fire stopping, so the compartmentation is defeated by the electrical installation. | • State that no penetration through a fire compartment is formed without an approved fire stopping detail and inspection before concealment. Electrical penetrations are the commonest cause of defeated compartmentation. • Require structural approval for every opening before it is drawn as final, with no size exemption decided on site. • Issue equipment weights and fixing requirements to Structure as a controlled notification with confirmation. • Require every drawn opening to appear in the builders-work schedule, with a reconciliation between the two. • Set a cut-off after which new openings become a formal change.
211 | Technical Engineering | Prepare electrical authority calculations, forms and submission drawings | Electrical Draftsman | Trigger: When electrical design reaches coordination, authority or IFC milestone. Action: The Electrical Draftsman completes “Prepare electrical authority calculations, forms and submission drawings” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed interfaces, submission responses and controlled electrical IFC package. Control/Handoff: Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When electrical design reaches coordination, authority or IFC milestone. | The Electrical Draftsman completes “Prepare electrical authority calculations, forms and submission drawings” using the approved brief, source documents, calculations and controlled company systems. | closed interfaces, submission responses and controlled electrical IFC package. | Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman prepares the calculations, forms and drawings the electrical authority requires. • Starts when: an electrical authority or utility submission is required. • How it runs: (1) the authority's and utility's requirements, forms and checklists are confirmed. (2) The required calculations are prepared in the required format. (3) Submission drawings are prepared with the required content and stamps. (4) The package is checked against the checklist and authorised by the CTO. (5) It is submitted through the defined route with the submission recorded. • Proof it happened: the submission package with the checklist, the calculations in the required format, and the authorised submission record. • Where it usually breaks: the submission is prepared to a general standard rather than the authority's specific format, and it is returned unread for format reasons. | • Keep an authority and utility requirements sheet per jurisdiction covering forms, calculation formats, drawing content and required stamps. Rejections here are almost always format rejections. • Confirm who is licensed to sign or stamp the submission, and that the licence is valid. • Require the checklist to be completed and evidenced before submission is authorised. • Cross-check that submitted drawings and calculations are from the same revision. • Track submission dates and approval status as programme items, since supply approval gates energisation.
212 | Technical Engineering | Respond to authority and interdisciplinary review comments | Electrical Draftsman | Trigger: When electrical design reaches coordination, authority or IFC milestone. Action: The Electrical Draftsman completes “Respond to authority and interdisciplinary review comments” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed interfaces, submission responses and controlled electrical IFC package. Control/Handoff: Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When electrical design reaches coordination, authority or IFC milestone. | The Electrical Draftsman completes “Respond to authority and interdisciplinary review comments” using the approved brief, source documents, calculations and controlled company systems. | closed interfaces, submission responses and controlled electrical IFC package. | Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman answers the comments that come back from the authority and from the other disciplines. • Starts when: authority comments or interdisciplinary review comments are received. • How it runs: (1) each comment is logged individually with its source and date. (2) The response and any design change required are determined, with recalculation where needed. (3) Changes go through the normal checking rather than being made directly on the submission set. (4) Construction drawings, schedules and calculations are updated to match. (5) The resubmission is authorised and the closure recorded. • Proof it happened: the comment log with responses, the updated design at consistent revisions, and the authorised resubmission. • Where it usually breaks: authority comments are answered on the submission drawings only, and the construction set still shows the arrangement that was rejected. | • Require every comment-driven change to be carried into the construction drawings, schedules and calculations, with a reconciliation before resubmission. • Log comments individually with the response and the closure evidence, since partial closure is invisible in an email thread. • Route all changes through normal checking, and prohibit direct edits to a submission set. • Record repeat comment themes, as they indicate an avoidable design or format weakness. • Escalate comments that require a design change with cost or programme impact rather than absorbing them.
213 | Technical Engineering | Release checked electrical and ELV IFC package and revision index | Electrical Draftsman | Trigger: When electrical design reaches coordination, authority or IFC milestone. Action: The Electrical Draftsman completes “Release checked electrical and ELV IFC package and revision index” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: closed interfaces, submission responses and controlled electrical IFC package. Control/Handoff: Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When electrical design reaches coordination, authority or IFC milestone. | The Electrical Draftsman completes “Release checked electrical and ELV IFC package and revision index” using the approved brief, source documents, calculations and controlled company systems. | closed interfaces, submission responses and controlled electrical IFC package. | Architect/MEP disciplines confirm interfaces; CTO authorises issue; Document Control controls revisions. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman releases the construction-ready electrical and ELV package with a clear index of what is in it. • Starts when: the electrical design is checked, coordinated and approved for construction issue. • How it runs: (1) the package is checked complete against the deliverable register. (2) Single-line diagram, schedules, layouts and calculations are confirmed consistent at the same revision. (3) Coordination and clash closure are confirmed. (4) The check evidence is attached and the CTO authorises. (5) Document Control issues the package with the revision index and withdraws superseded revisions. • Proof it happened: the released package with its revision index, the check and coordination evidence, issued through Document Control. • Where it usually breaks: layouts are issued while the board schedules are still changing, so site installs circuits that do not match the schedule they are tested against. | • Require the single-line diagram, board schedules, layouts and calculations to be at consistent revisions at release. A mismatch here produces circuits that fail testing against their own schedule. • Make check closure and clash closure explicit entry conditions for release. • Issue only through Document Control with a revision index and confirmed withdrawal of superseded revisions. • Record any release with a known open point, notify Projects and track it to closure. • State the status and purpose of issue clearly so preliminary information is not built from.
214 | Technical Engineering | Respond to electrical RFIs and review technical submittals | Electrical Draftsman | Trigger: When an electrical RFI, submittal, inspection, testing or closeout request is received. Action: The Electrical Draftsman completes “Respond to electrical RFIs and review technical submittals” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review, test/inspection support record or accepted as-built update. Control/Handoff: Safety, supply-capacity or authority deviation is immediately escalated and site work remains controlled. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When an electrical RFI, submittal, inspection, testing or closeout request is received. | The Electrical Draftsman completes “Respond to electrical RFIs and review technical submittals” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review, test/inspection support record or accepted as-built update. | Safety, supply-capacity or authority deviation is immediately escalated and site work remains controlled. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: during construction the Draftsman answers electrical questions from site and reviews what the contractor proposes to install. • Starts when: an electrical RFI is raised, or a technical submittal or material approval is received. • How it runs: (1) the query or submittal is registered with its date and required response time. (2) Submittals are reviewed against the design, specification and schedules. (3) Decisions are issued with reasons, and proposed substitutions are assessed against all relevant characteristics. (4) Where the response changes the design, a controlled revision follows. (5) The register tracks responses and closure. • Proof it happened: the RFI and submittal register with reviewed decisions, the substitution assessments, and any controlled revisions issued. • Where it usually breaks: a protective device is substituted on rating alone, and the discrimination and fault withstand of the whole distribution is quietly compromised. | • Require any protective device or switchgear substitution to be assessed for fault rating, discrimination and compatibility, not rating alone. This substitution silently undoes the protection design. • Require cable substitutions to be reassessed for current capacity and voltage drop under the actual installation method. • State that reviewing a submittal does not relieve the contractor of its obligations, and record the reviewer. • Follow any design-changing answer with a controlled revision the same cycle. • Track RFI causes, as clusters point to weak drawings or unclear specification.
215 | Technical Engineering | Support electrical testing, commissioning and inspection requirements | Electrical Draftsman | Trigger: When an electrical RFI, submittal, inspection, testing or closeout request is received. Action: The Electrical Draftsman completes “Support electrical testing, commissioning and inspection requirements” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review, test/inspection support record or accepted as-built update. Control/Handoff: Safety, supply-capacity or authority deviation is immediately escalated and site work remains controlled. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When an electrical RFI, submittal, inspection, testing or closeout request is received. | The Electrical Draftsman completes “Support electrical testing, commissioning and inspection requirements” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review, test/inspection support record or accepted as-built update. | Safety, supply-capacity or authority deviation is immediately escalated and site work remains controlled. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: the Draftsman supports the testing and inspection that proves the electrical installation is safe and works. • Starts when: installation reaches testing, or commissioning documentation is required. • How it runs: (1) the required tests and acceptance criteria are set out, including insulation, continuity, earth resistance and functional tests. (2) Inspection hold points are set before concealment and before energisation. (3) Test results are reviewed against the criteria and the design figures. (4) Failures are investigated and retested rather than accepted with a note. (5) Results are recorded and handed over with the system documentation. • Proof it happened: the witnessed test and inspection records against the stated criteria, with failures retested and closed. • Where it usually breaks: energisation happens before the earthing and protection testing is complete and witnessed, which is a safety exposure as well as a records gap. | • Make completed and witnessed earthing, insulation and protection testing a mandatory pre-condition of energisation, with a named authoriser. This is a life safety control, not paperwork. • Set inspection hold points before concealment, since concealed work cannot be verified afterwards. • Require results to be compared against the stated criteria and design figures, with variances explained. • Require failures to be retested and the retest recorded, not annotated and passed. • Include functional and interface testing, particularly fire alarm cause and effect and changeover operation.
216 | Technical Engineering | Review electrical and ELV as-built drawings and close technical actions | Electrical Draftsman | Trigger: When an electrical RFI, submittal, inspection, testing or closeout request is received. Action: The Electrical Draftsman completes “Review electrical and ELV as-built drawings and close technical actions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an authorised response, review, test/inspection support record or accepted as-built update. Control/Handoff: Safety, supply-capacity or authority deviation is immediately escalated and site work remains controlled. Continuity/Escalation: A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. Timing: To be confirmed. | When an electrical RFI, submittal, inspection, testing or closeout request is received. | The Electrical Draftsman completes “Review electrical and ELV as-built drawings and close technical actions” using the approved brief, source documents, calculations and controlled company systems. | an authorised response, review, test/inspection support record or accepted as-built update. | Safety, supply-capacity or authority deviation is immediately escalated and site work remains controlled. | A nominated competent electrical resource provides backup; safety, supply-capacity, authority or life-safety risk immediately escalates to CTO. | To be confirmed. | • In plain words: at the end the Draftsman checks the electrical and ELV as-built drawings and closes the technical loose ends. • Starts when: the project reaches electrical completion or closeout. • How it runs: (1) contractor as-built information and red-lines are reviewed as verified before acceptance. (2) Final board schedules, circuit references and concealed routes are checked as recorded. (3) Panel labelling is confirmed to match the as-built schedules. (4) Deviations from design are assessed and accepted or corrected, and open actions closed. (5) The as-built set, test records and manuals are handed to Document Control with the lessons learned recorded. • Proof it happened: the reviewed as-built set with final board schedules and circuit references, deviations assessed, actions closed, and the handover package archived. • Where it usually breaks: the as-built board schedules do not match the labelling on the panels, so operations cannot trust either and works blind for the life of the building. | • Require as-built board schedules, circuit references and panel labelling to be reconciled against each other, with the check recorded. A mismatch here disables safe operation permanently. • Require concealed cable routes and junction box positions to be recorded, as they cannot be found later. • Require red-lines to be verified by Projects before as-built drawing starts. • Assess every deviation and accept or correct it formally rather than only recording it. • Hand over test records, manuals, warranties and settings, including protection settings, as one indexed package.
217 | Technical Engineering | Receive and register civil tender package and submission deadline | Civil Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The Civil Estimator completes “Receive and register civil tender package and submission deadline” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The Civil Estimator completes “Receive and register civil tender package and submission deadline” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Civil Estimator receives the tender package, records what has been received and notes the deadline that everything else works back from. • Starts when: a civil tender package is received from the client or through Business Development. • How it runs: (1) the package is registered with what was received, the version and the date. (2) The submission deadline, format and delivery route are recorded. (3) The documents are checked against the list of what was meant to be issued. (4) Missing documents are requested immediately rather than after work starts. (5) An internal timeline is set working back from the deadline, and the bid decision is confirmed with the CTO. • Proof it happened: the tender register entry with the documents received, the deadline and format recorded, and the internal timeline. • Where it usually breaks: the package is registered but the addenda that follow are not, so the estimate is priced on superseded drawings. | • Require every addendum, clarification and reissued drawing to be registered against the tender with a date. Pricing on superseded documents is the single most damaging estimating error. • Record the submission deadline, format, delivery route and any portal requirement at registration, since format failures lose compliant bids. • Require the received document list to be checked against the issued list, and missing items requested the same day. • Require a recorded bid or no-bid decision by the CTO before estimating effort is spent. • Set the internal milestones back from the deadline, including a cut-off for late vendor quotations.
218 | Technical Engineering | Review civil, architectural and structural tender scope | Civil Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The Civil Estimator completes “Review civil, architectural and structural tender scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The Civil Estimator completes “Review civil, architectural and structural tender scope” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator reads the civil, architectural and structural scope properly to understand what is actually being priced. • Starts when: the tender package is registered and the bid decision is confirmed. • How it runs: (1) the drawings, specifications, BOQ and contract conditions are reviewed together, not separately. (2) What is included, excluded and provisional is identified. (3) Specification requirements that carry cost, such as materials, testing and standards, are noted. (4) Contract conditions affecting price, such as programme, liquidated damages and payment terms, are flagged to the CTO. (5) The scope understanding is recorded as the basis of the estimate. • Proof it happened: the scope review record listing inclusions, exclusions, cost-driving specification requirements and the contract conditions flagged. • Where it usually breaks: the BOQ is priced without reading the specification, so a required material standard or testing regime that costs real money is never priced. | • Require the specification to be read against every priced BOQ item, since the BOQ description alone routinely omits the cost-driving requirement. • Require contract conditions affecting price, including programme, damages, retention and payment terms, to be flagged to the CTO before pricing. • Record the scope understanding as the written basis of the estimate, so what was priced can be proven later. • Identify provisional and nominated items separately, since they are treated differently commercially. • Note where the BOQ and drawings disagree, and raise it rather than choosing one.
219 | Technical Engineering | Identify missing civil information, contradictions and commercial risks | Civil Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The Civil Estimator completes “Identify missing civil information, contradictions and commercial risks” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The Civil Estimator completes “Identify missing civil information, contradictions and commercial risks” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator finds what is missing, what contradicts itself and what could cost the company money. • Starts when: the scope review identifies gaps, conflicts or risks. • How it runs: (1) missing information is listed, including soil data, levels, utility positions and specifications. (2) Contradictions between drawings, BOQ and specification are recorded with the affected quantity. (3) Commercial risks are identified, such as unclear scope boundaries, onerous conditions and unpriceable items. (4) Each item is assessed for its cost exposure. (5) The list is passed to the query process and the significant risks raised with the CTO. • Proof it happened: the gaps, contradictions and commercial risk list with the cost exposure assessed and the significant items escalated. • Where it usually breaks: contradictions are noticed and quietly resolved by the estimator's own judgement, so the company carries a risk the client never accepted. | • Prohibit resolving a contradiction by internal judgement without raising it. An unraised contradiction transfers the risk to the company silently. • Require each gap and risk to carry an estimated cost exposure, so the CTO can decide what to qualify and what to price. • Require soil, level and utility information gaps to be treated as high exposure, since they drive earthworks and foundation cost. • Set a threshold above which a risk must be escalated to the CTO before submission. • Keep the list as a live document through the tender, not a one-off exercise.
220 | Technical Engineering | Prepare civil tender queries, assumptions and clarification log | Civil Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The Civil Estimator completes “Prepare civil tender queries, assumptions and clarification log” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The Civil Estimator completes “Prepare civil tender queries, assumptions and clarification log” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator writes the formal questions to the client and records the assumptions made where no answer comes. • Starts when: gaps and contradictions require client clarification. • How it runs: (1) queries are drafted clearly, each tied to the affected document and item. (2) They are submitted through the route and by the deadline the tender allows. (3) Responses are logged against the queries and their pricing effect assessed. (4) Where no response is received, a stated assumption is recorded with its cost basis. (5) The assumptions are carried into the submission as qualifications rather than left internal. • Proof it happened: the query and clarification log with responses, the pricing effects, and the assumptions recorded and qualified. • Where it usually breaks: assumptions are made to keep pricing moving but never appear in the submission, so the company is bound to a price based on assumptions the client never saw. | • Require every unanswered query to become a stated assumption in the submitted offer. An internal assumption that is not qualified becomes a free obligation. • Submit queries by the tender's query deadline, and record submission evidence, since late queries are not answered. • Log each response against its query with the pricing effect, and reprice affected items rather than noting the answer. • Require the CTO to approve which assumptions are qualified and which are absorbed. • Keep one log per tender, so the same question is not asked twice or answered inconsistently.
221 | Technical Engineering | Attend civil tender site visit and record pricing constraints | Civil Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The Civil Estimator completes “Attend civil tender site visit and record pricing constraints” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The Civil Estimator completes “Attend civil tender site visit and record pricing constraints” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator visits the site and records the real conditions that affect price. • Starts when: a tender site visit is arranged or required. • How it runs: (1) access, ground conditions, existing structures and services are observed and photographed. (2) Constraints affecting cost are recorded: working hours, storage space, crane access, neighbouring properties, distance to disposal. (3) Anything different from the tender documents is noted specifically. (4) Attendance is recorded where the tender requires it. (5) The observations are converted into pricing assumptions and cost allowances. • Proof it happened: the site visit record with photographs, the constraints noted, the differences from the documents, and the resulting pricing allowances. • Where it usually breaks: the visit happens but the observations are never turned into priced allowances, so known constraints such as restricted access are seen and then forgotten. | • Require every site observation with cost impact to be converted into a specific priced allowance or a stated qualification. A visit that changes nothing in the price was wasted. • Use a standard constraints checklist covering access, working hours, storage, crane access, disposal distance and neighbours. • Photograph and date the conditions, since disputes about pre-existing conditions arise after award. • Record differences from the tender documents formally, as these are the basis of later claims. • Retain the attendance record where the tender makes the visit a compliance requirement.
222 | Technical Engineering | Prepare civil and earthworks quantity takeoff | Civil Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The Civil Estimator completes “Prepare civil and earthworks quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The Civil Estimator completes “Prepare civil and earthworks quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the earthworks and civil quantities from the drawings. • Starts when: drawings and levels are sufficient to measure civil and earthworks quantities. • How it runs: (1) the drawing revisions to be measured from are confirmed and recorded. (2) Excavation, filling, disposal and compaction quantities are measured against the levels. (3) Cut and fill are balanced so disposal and import are not double counted. (4) Measurement is done to the stated method of measurement rather than by habit. (5) The takeoff is checked, and the basis and assumptions recorded. • Proof it happened: the civil and earthworks takeoff stating the drawing revisions measured from, the method of measurement, and the check record. • Where it usually breaks: cut and fill are measured independently, so both disposal of surplus and import of fill are priced when the site actually balances. | • Require a cut and fill balance to be produced and reconciled before disposal and import are priced. Double counting both is a large and common error. • Record the drawing revision and the level datum every quantity was measured from. • State the method of measurement applied, since net and gross conventions change quantities materially. • Require bulking and compaction factors to be stated and applied consistently, not assumed per item. • Require disposal distance and any tipping or permit charge to be confirmed rather than estimated.
223 | Technical Engineering | Prepare architectural and finishing quantity takeoff | Civil Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The Civil Estimator completes “Prepare architectural and finishing quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The Civil Estimator completes “Prepare architectural and finishing quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the architectural and finishing quantities. • Starts when: architectural drawings and finishes schedules are sufficient to measure. • How it runs: (1) the drawing and finishes schedule revisions are confirmed and recorded. (2) Floor, wall and ceiling finishes are measured by area and type against the finishes schedule. (3) Doors, windows, joinery and specialist items are measured against their schedules. (4) Openings and deductions are handled per the method of measurement. (5) The takeoff is checked against the schedules and the assumptions recorded. • Proof it happened: the architectural takeoff reconciled against the finishes and door schedules, with the drawing revisions and method stated. • Where it usually breaks: finishes are measured from the drawings but not reconciled with the finishes schedule, so a specified premium finish in a few rooms is priced as the standard one. | • Require the takeoff to be reconciled item by item against the finishes and door schedules. Premium finishes in a small number of rooms are the classic missed cost. • Record the drawing and schedule revisions measured from, since finishes change late and often. • State the deduction convention for openings, as it materially changes finish quantities. • Measure specialist and imported items separately, since their lead time and cost risk differ. • Flag any finish specified without an approved product reference, as it cannot be priced reliably.
224 | Technical Engineering | Prepare structural concrete and reinforcement quantity takeoff | Civil Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The Civil Estimator completes “Prepare structural concrete and reinforcement quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The Civil Estimator completes “Prepare structural concrete and reinforcement quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the concrete and the reinforcement steel. • Starts when: structural drawings and schedules are sufficient to measure. • How it runs: (1) the structural drawing and bar bending schedule revisions are confirmed. (2) Concrete volumes are measured by element and grade. (3) Reinforcement is measured from the schedules where available, or calculated with the assumption stated where not. (4) Formwork is measured by contact area and complexity, not as a single rate. (5) The takeoff is checked and steel ratios are sanity checked against benchmarks. • Proof it happened: the structural takeoff with concrete by grade, reinforcement by diameter, formwork by type, and the ratio sanity check. • Where it usually breaks: reinforcement is estimated with a single overall ratio, so a heavily reinforced element such as a raft or a transfer beam is significantly underpriced. | • Require reinforcement ratios to be applied per element type, not as one overall figure. Rafts, transfer beams and retaining walls are far heavier and this is where estimates lose money. • Sanity check steel per cubic metre against benchmarks per element and query outliers before submission. • Measure concrete by grade, since grade differences carry real cost. • Measure formwork by contact area and complexity, including special finishes and heights. • State whether laps, wastage and couplers are included, since these are quietly omitted.
225 | Technical Engineering | Prepare masonry, waterproofing and roofing quantity takeoff | Civil Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The Civil Estimator completes “Prepare masonry, waterproofing and roofing quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The Civil Estimator completes “Prepare masonry, waterproofing and roofing quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures masonry, waterproofing and roofing. • Starts when: the relevant drawings and specifications are sufficient to measure. • How it runs: (1) masonry is measured by type, thickness and height with the deductions applied. (2) Waterproofing is measured by system and location, with upstands, laps and protection included. (3) Roofing is measured by system with insulation, falls, edges and outlets included. (4) Ancillary items are measured, including lintels, ties, movement joints, flashings and terminations. (5) The takeoff is checked against the specification requirements. • Proof it happened: the masonry, waterproofing and roofing takeoff by system with ancillaries measured, checked against the specification. • Where it usually breaks: waterproofing is measured as a flat area with no allowance for upstands, terminations and protection, which is where most of the actual cost and most of the failures sit. | • Require waterproofing and roofing to be measured as a system including upstands, terminations, laps, protection and outlets. Flat area pricing understates both cost and risk. • Require the specified system and its warranty requirements to be identified, since approved applicator requirements change price. • Measure masonry ancillaries explicitly: lintels, ties, movement joints and reinforcement. • Include testing requirements such as flood testing where specified. • Flag any interface detail that is unresolved, as these are the failure points and the claim points.
226 | Technical Engineering | Prepare external works and provisional-item quantity takeoff | Civil Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The Civil Estimator completes “Prepare external works and provisional-item quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The Civil Estimator completes “Prepare external works and provisional-item quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the external works and the items priced provisionally. • Starts when: external works drawings are available or provisional items require pricing. • How it runs: (1) external works are measured: roads, paving, drainage, boundary walls, landscaping and external services. (2) Provisional and approximate quantity items are identified and priced with the basis stated. (3) Items dependent on information not yet available are qualified rather than guessed. (4) Utility connection and authority requirements are checked and allowed for. (5) The takeoff is checked with the provisional basis recorded. • Proof it happened: the external works takeoff and the provisional item pricing with the basis stated and the qualifications recorded. • Where it usually breaks: provisional items are priced with a lump sum that has no stated basis, so after award there is no way to defend or adjust the figure. | • Require every provisional and lump sum item to state the quantity, rate and assumption behind it. A figure with no basis cannot be defended or adjusted after award. • Identify external utility connection charges and authority fees explicitly, since these are large and routinely missed. • Qualify items that depend on unavailable information rather than pricing a guess. • Measure external drainage and services separately from the building, as their rates differ. • State what is excluded from external works, since the boundary with the client's scope is often unclear.
227 | Technical Engineering | Reconcile civil takeoff against BOQ, drawings and specifications | Civil Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The Civil Estimator completes “Reconcile civil takeoff against BOQ, drawings and specifications” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The Civil Estimator completes “Reconcile civil takeoff against BOQ, drawings and specifications” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator checks the measured quantities against the BOQ, the drawings and the specification so the three agree. • Starts when: the takeoffs are complete and require reconciliation before pricing. • How it runs: (1) measured quantities are compared with the BOQ quantities item by item. (2) Variances beyond the agreed tolerance are investigated rather than accepted. (3) BOQ items with no drawing basis and drawing items with no BOQ line are both identified. (4) Specification requirements are checked as reflected in the priced items. (5) The reconciliation is recorded, and material variances are raised as queries or qualifications. • Proof it happened: the reconciliation record showing measured against BOQ quantities, the variances investigated, and the missing items identified. • Where it usually breaks: a large variance between measured and BOQ quantity is accepted as a measurement difference, when it is actually a scope item nobody has priced. | • Set a variance tolerance above which a difference between measured and BOQ quantity must be investigated and explained in writing. Large unexplained variances are usually missing scope. • Require identification of both BOQ items with no drawing basis and drawn work with no BOQ line, since each is a different commercial risk. • Require a specification compliance check across the priced items, not just quantity agreement. • Record the reconciliation as evidence, since it is the defence if quantities are disputed after award. • Escalate material variances to the CTO for a decision on query or qualification.
228 | Technical Engineering | Prepare civil supplier and subcontractor RFQ packages | Civil Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The Civil Estimator completes “Prepare civil supplier and subcontractor RFQ packages” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The Civil Estimator completes “Prepare civil supplier and subcontractor RFQ packages” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator prepares the enquiry packages sent out to suppliers and subcontractors. • Starts when: market pricing is required for materials or subcontracted work. • How it runs: (1) packages are defined by trade with clear scope boundaries between them. (2) Each package includes the drawings, specification extracts, quantities and the conditions to be priced. (3) The required return format is stated so quotations can be compared. (4) The return deadline is set against the tender timeline. (5) Packages are issued through Procurement and the issue recorded. • Proof it happened: the RFQ packages with the scope defined, documents included, return format and deadline stated, issued through Procurement. • Where it usually breaks: package boundaries overlap or leave gaps, so an item is either priced twice or by nobody, and it only shows up during comparison. | • Require package boundaries to be mapped so that every scope item sits in exactly one package. Overlaps and gaps between trade packages are the standard cause of missed scope. • State the required return format and breakdown, since quotations that cannot be compared waste the whole exercise. • Include the specification extracts and conditions to be priced, not the drawings alone. • Set return deadlines with a margin before the submission, and state that late quotations may not be used. • Issue through Procurement so the vendor list and the commercial relationship stay controlled.
229 | Technical Engineering | Coordinate civil market quotations through Procurement | Civil Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The Civil Estimator completes “Coordinate civil market quotations through Procurement” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The Civil Estimator completes “Coordinate civil market quotations through Procurement” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator works with Procurement to get the market quotations back in time. • Starts when: RFQ packages have been issued and quotations are due. • How it runs: (1) issued enquiries are tracked against expected returns. (2) Vendor questions are answered consistently, with the same answer given to all bidders. (3) Non-responders are chased and alternatives approached where coverage is thin. (4) A minimum number of comparable quotations per package is pursued. (5) Received quotations are registered with their date and validity. • Proof it happened: the quotation tracker showing enquiries issued, responses received, coverage per package, and the validity dates recorded. • Where it usually breaks: a package ends up with only one quotation, and the estimate is built on a single price with nothing to test it against. | • Set a minimum number of comparable quotations per package, and require a recorded exception where it cannot be met. A single-source price is an unverified price. • Require vendor questions to be answered to all bidders alike, so quotations remain comparable and the process stays fair. • Record quotation validity dates, since expired validity is a real exposure on long tenders. • Track coverage per package as a progress measure, not just quotations received overall. • Keep Procurement as the channel for vendor contact, so relationships and terms stay controlled.
230 | Technical Engineering | Prepare civil quotation comparison and compliance review | Civil Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The Civil Estimator completes “Prepare civil quotation comparison and compliance review” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The Civil Estimator completes “Prepare civil quotation comparison and compliance review” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator compares the quotations properly and checks whether each one actually covers what was asked for. • Starts when: quotations have been received for a package. • How it runs: (1) quotations are normalised to the same scope, quantities and conditions before comparison. (2) Compliance with the specification and the required conditions is assessed for each. (3) Exclusions, qualifications and payment terms are listed for each bidder. (4) The comparison is made on total cost of compliance, not headline price. (5) A recommendation is prepared with the basis stated. • Proof it happened: the comparison sheet with the quotations normalised, the compliance assessed, the exclusions listed, and the recommendation basis. • Where it usually breaks: the lowest headline price is carried into the estimate without adding back what that bidder excluded, so the estimate is built on a price that does not cover the scope. | • Require quotations to be normalised to identical scope and conditions before comparison, with exclusions added back. Comparing headline prices carries a shortfall straight into the estimate. • Require a specification compliance assessment per quotation, since non-compliant offers are cheaper for a reason. • List payment terms, validity and delivery period in the comparison, as these carry real cost. • State the recommendation basis, so the selection can be defended and reused. • Require the comparison to be checked by someone other than the preparer for significant packages.
231 | Technical Engineering | Resolve civil vendor exclusions, deviations and unpriced scope | Civil Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The Civil Estimator completes “Resolve civil vendor exclusions, deviations and unpriced scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The Civil Estimator completes “Resolve civil vendor exclusions, deviations and unpriced scope” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator deals with the gaps left by vendor exclusions and deviations so no scope goes unpriced. • Starts when: vendor exclusions, deviations or unpriced scope are identified in the comparison. • How it runs: (1) every exclusion and deviation is listed against the scope it affects. (2) Each gap is closed by pricing it in-house, obtaining an alternative quotation, or qualifying it in the offer. (3) Deviations from the specification are assessed for acceptability rather than assumed acceptable. (4) The resolution of each item is recorded. (5) A closure check confirms that no scope remains unpriced or unqualified. • Proof it happened: the exclusions and deviations register with each item priced, requoted or qualified, and the closure check confirming no unpriced scope. • Where it usually breaks: exclusions are noted in the comparison but never carried into either the price or the qualifications, so the gap is discovered only after award. | • Require a closure check confirming every exclusion is either priced, requoted or qualified in the offer. Unclosed exclusions are the most reliable source of post-award loss. • Require specification deviations to be assessed for acceptability by the technical team, not accepted commercially. • Record the resolution route for each item, so the estimate basis is auditable. • Set a cut-off before submission after which exclusions must be qualified rather than repriced. • Escalate any gap that cannot be closed within the tender period to the CTO for a decision.
232 | Technical Engineering | Prepare civil labour, material, plant and subcontract rate build-ups | Civil Estimator | Trigger: When verified quantities and market inputs are available. Action: The Civil Estimator completes “Prepare civil labour, material, plant and subcontract rate build-ups” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The Civil Estimator completes “Prepare civil labour, material, plant and subcontract rate build-ups” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator builds up the rates from labour, material, plant and subcontract costs rather than using round figures. • Starts when: rate build-ups are required for pricing. • How it runs: (1) labour costs are built from actual wage rates, allowances and statutory costs. (2) Material costs are taken from quotations with wastage and delivery included. (3) Plant costs are built from rates, utilisation and operating costs. (4) Subcontract rates are taken from the compared quotations. (5) Build-ups are checked against historical rates achieved and the source of each input recorded. • Proof it happened: the rate build-ups showing labour, material, plant and subcontract components with the source of each input recorded. • Where it usually breaks: labour rates are used without the statutory and welfare costs on top, so every labour-intensive item is underpriced by a consistent margin. | • Require labour rates to be built up fully including statutory, welfare, accommodation, transport and non-productive time. A bare wage rate underprices every labour item consistently. • Require the source of every input to be recorded, so a rate can be re-examined without rebuilding it. • Maintain a reviewed rate library with a stated review date, since stale rates are a silent risk. • Benchmark build-ups against rates actually achieved on completed projects, and explain differences. • State plant utilisation assumptions, since idle time is where plant pricing fails.
233 | Technical Engineering | Apply civil productivity, wastage and logistics assumptions | Civil Estimator | Trigger: When verified quantities and market inputs are available. Action: The Civil Estimator completes “Apply civil productivity, wastage and logistics assumptions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The Civil Estimator completes “Apply civil productivity, wastage and logistics assumptions” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator applies realistic assumptions about how fast work goes, how much material is wasted and how the site logistics work. • Starts when: productivity, wastage and logistics assumptions are required for pricing. • How it runs: (1) productivity rates are set per activity from records rather than by habit. (2) The conditions affecting productivity are considered: access, height, congestion, weather, working hours. (3) Wastage allowances are set per material type. (4) Logistics are priced: haulage, handling, storage, vertical transport, disposal. (5) The assumptions are recorded so the estimate can be checked and reused. • Proof it happened: the assumptions record stating productivity per activity, the conditions considered, wastage per material and the logistics allowances. • Where it usually breaks: standard productivity rates are used regardless of the actual site conditions, so a congested or high-rise site is priced as though it were an open one. | • Require productivity to be adjusted for the actual site conditions recorded at the site visit, including access, height, congestion and working hour restrictions. Standard rates on a constrained site are the commonest structural underpricing. • Set wastage allowances per material type rather than one global figure. • Price logistics explicitly, including vertical transport and off-site storage where space is limited. • Record the assumptions so the estimate can be audited and the outcome fed back after the project. • Base productivity on recorded outputs from completed work, and review the figures periodically.
234 | Technical Engineering | Price preliminaries, temporary works and project constraints | Civil Estimator | Trigger: When verified quantities and market inputs are available. Action: The Civil Estimator completes “Price preliminaries, temporary works and project constraints” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The Civil Estimator completes “Price preliminaries, temporary works and project constraints” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator prices the cost of running the site itself and the temporary works needed to build it. • Starts when: preliminaries and temporary works require pricing. • How it runs: (1) the site organisation is priced: staff, offices, utilities, security, welfare, transport, over the actual programme duration. (2) Temporary works are identified and priced: shoring, propping, scaffolding, hoarding, access, dewatering. (3) Project constraints are priced: restricted hours, phasing, occupied areas, traffic management. (4) Insurances, permits, bonds and testing requirements are allowed for. (5) The preliminaries are checked against the programme and the value of the work. • Proof it happened: the priced preliminaries and temporary works tied to the programme duration, with constraints and statutory costs allowed for. • Where it usually breaks: preliminaries are priced as a percentage of the works value rather than from the actual programme, so a long-duration low-value project is badly underpriced. | • Require preliminaries to be built from the programme duration and the site organisation, not as a percentage of works value. Percentage preliminaries fail badly on long, low-value projects. • Require temporary works to be identified with the technical team, since shoring, propping and dewatering are engineering costs, not allowances. • Price constraints explicitly, including restricted hours, phasing, occupied areas and traffic management. • List statutory and contractual costs separately: insurances, bonds, permits, testing and authority fees. • Require repricing if the programme duration changes, since preliminaries are time-driven.
235 | Technical Engineering | Prepare civil risk, opportunity, exclusion and contingency register | Civil Estimator | Trigger: When verified quantities and market inputs are available. Action: The Civil Estimator completes “Prepare civil risk, opportunity, exclusion and contingency register” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The Civil Estimator completes “Prepare civil risk, opportunity, exclusion and contingency register” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator records the risks, the opportunities, what is excluded and how much contingency is carried. • Starts when: the estimate is being assembled and risk requires quantifying. • How it runs: (1) risks are listed with their likely cost impact and likelihood. (2) Opportunities are listed where cost could be lower than priced. (3) Exclusions are listed in the wording that will appear in the offer. (4) Contingency is set against the identified risks with the basis stated, not as a blanket percentage. (5) The register is reviewed with the CTO before submission. • Proof it happened: the risk, opportunity, exclusion and contingency register with the cost impacts, the contingency basis, and the CTO review. • Where it usually breaks: contingency is a flat percentage with no link to the identified risks, so it is arbitrary and gets negotiated away without anyone knowing what was given up. | • Require contingency to be built from the identified risks with the basis stated per item. A flat percentage cannot be defended in negotiation and is given away without knowing the exposure. • Require exclusions to be written in the exact wording that will appear in the offer, so nothing is lost in transfer. • Quantify risks with cost impact and likelihood, since unquantified risks cannot be traded in negotiation. • Require the register to be reviewed and approved by the CTO before submission. • Carry the register into the project handover after award, since it is the basis of the cost baseline.
236 | Technical Engineering | Develop civil value-engineering and alternative pricing options | Civil Estimator | Trigger: When verified quantities and market inputs are available. Action: The Civil Estimator completes “Develop civil value-engineering and alternative pricing options” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The Civil Estimator completes “Develop civil value-engineering and alternative pricing options” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator looks for cheaper ways of achieving the same result and prices them as options. • Starts when: value engineering or alternative pricing is required or opportunities are identified. • How it runs: (1) high-cost items are identified from the priced estimate. (2) Alternatives are developed with the technical team rather than by the estimator alone. (3) Each option is priced with its saving and its technical implications stated. (4) Options are checked for compliance with the specification and the authority requirements. (5) Options are presented separately from the compliant base offer. • Proof it happened: the value engineering options with the savings quantified, the technical implications stated, the compliance checked, and the base offer kept separate. • Where it usually breaks: alternatives are offered without technical verification, so a saving is promised on something that does not actually comply or perform. | • Require every alternative to be technically verified and signed off by the technical team before it is offered. An unverified saving becomes a loss after award. • Require a compliant base offer to be submitted separately from any alternative, since mixing them makes the bid non-compliant. • State the technical and operational implications of each option, not the saving alone. • Check alternatives against specification and authority approval requirements before offering. • Record which options the client accepted, so the awarded scope is unambiguous.
237 | Technical Engineering | Prepare priced civil BOQ and commercial summary | Civil Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The Civil Estimator completes “Prepare priced civil BOQ and commercial summary” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The Civil Estimator completes “Prepare priced civil BOQ and commercial summary” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator produces the priced BOQ and the commercial summary that shows how the price is made up. • Starts when: pricing is complete and the offer needs assembling. • How it runs: (1) rates are applied to the BOQ in the required format and all items are confirmed priced. (2) The commercial summary is built showing direct cost, preliminaries, risk, overhead and margin separately. (3) Cash flow implications and payment terms are considered. (4) The submission format and required documents are checked against the tender requirements. (5) The package is assembled with the qualifications and assumptions included. • Proof it happened: the priced BOQ in the required format and the commercial summary showing the cost build-up, with the qualifications included. • Where it usually breaks: a BOQ item is left unpriced or priced as included, and the tender is disqualified or the scope is delivered for nothing. | • Require an automated check that every BOQ line carries a rate before submission, and prohibit blank or included entries unless the tender permits them. This alone causes disqualifications and free scope. • Show direct cost, preliminaries, risk, overhead and margin separately in the summary, since a single figure cannot be negotiated intelligently. • Check the submission format and required documents against the tender checklist before assembly. • Include qualifications and assumptions in the submitted document itself, not in a covering email. • Record the final priced version and lock it, so what was submitted is unambiguous.
238 | Technical Engineering | Complete civil estimate self-check and reconciliation | Civil Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The Civil Estimator completes “Complete civil estimate self-check and reconciliation” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The Civil Estimator completes “Complete civil estimate self-check and reconciliation” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator checks their own work before it goes to the CTO. • Starts when: the estimate is assembled and requires self-checking before review. • How it runs: (1) all items are confirmed priced with no blanks or placeholders left. (2) Quantities, rates and extensions are checked, including the arithmetic and the totals. (3) Unit rates are sanity checked against benchmarks and outliers investigated. (4) The estimate is reconciled against the takeoff, the quotations and the assumptions register. (5) The self-check is evidenced against a checklist and any corrections recorded. • Proof it happened: the completed self-check checklist with the reconciliations, the sanity checks and the corrections made. • Where it usually breaks: the self-check confirms the arithmetic but never sanity checks the rates, so an order of magnitude error in a single rate passes through unnoticed. | • Require a rate sanity check against benchmarks per item type, with outliers investigated and explained. Arithmetic checks do not catch a rate that is out by a factor of ten. • Require a checklist to be completed and evidenced, not a general statement that the estimate was checked. • Reconcile the estimate against the takeoff, the accepted quotations and the assumptions register. • Check for blanks, placeholders and unpriced provisional items as a specific step. • Record corrections made at self-check, since recurring corrections point to a process weakness.
239 | Technical Engineering | Submit civil estimate for CTO review and approved margin integration | Civil Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The Civil Estimator completes “Submit civil estimate for CTO review and approved margin integration” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The Civil Estimator completes “Submit civil estimate for CTO review and approved margin integration” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the estimate goes to the CTO for review, and the approved margin is added. • Starts when: the self-check is complete and the estimate is ready for review. • How it runs: (1) the estimate is submitted with the assumptions, risks, qualifications and exclusions. (2) The CTO reviews the basis, the risk position and the competitiveness. (3) The margin is set within the approved authority, and any deviation is escalated to the CEO. (4) Comments are addressed and the estimate updated. (5) The approved price and its basis are recorded before submission. • Proof it happened: the CTO review record with the comments addressed, the approved margin within authority, and the approved final price recorded. • Where it usually breaks: the margin is adjusted downwards to win the job without recording what risk was accepted to justify it, so nobody can see afterwards what was traded away. | • Require any margin reduction to be recorded with the reason and the risk accepted, and approved within the authority matrix. Undocumented margin cuts remove the ability to learn or to hold anyone accountable. • State the approval limits for margin and price approval, and the escalation route above them. • Require review of the risk and qualification position, not the price alone. • Record the approved price and its basis as the version that was submitted. • Require any post-approval change to be re-approved rather than adjusted before sending.
240 | Technical Engineering | Revise civil offer for client clarification and negotiation | Civil Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The Civil Estimator completes “Revise civil offer for client clarification and negotiation” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The Civil Estimator completes “Revise civil offer for client clarification and negotiation” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: when the client comes back with questions or negotiates, the Estimator revises the offer properly. • Starts when: client clarifications, negotiations or revised requirements are received. • How it runs: (1) the request or negotiation position is recorded with its date. (2) Scope, quantity or condition changes are identified and repriced rather than discounted. (3) The effect on risk, qualifications and assumptions is reassessed. (4) The revision is approved within the authority before issue, including any margin change. (5) The revised offer is issued with a version number and the changes recorded. • Proof it happened: the revision record showing the request, the repricing, the reassessed risk position, the approval and the versioned revised offer. • Where it usually breaks: a price reduction is given in negotiation without removing scope or accepting a stated risk, so the reduction comes straight out of margin. | • Require every price reduction in negotiation to be matched to a scope change, a risk acceptance or a recorded margin decision. Otherwise reductions silently consume margin. • Require reassessment of qualifications and assumptions at each revision, since these are often dropped inadvertently. • Version-control every revised offer, and state clearly which version supersedes which. • Require approval within authority for each revision, not just the original submission. • Record what the client asked for verbally, so the final agreed scope is documented.
241 | Technical Engineering | Handover final civil estimate, assumptions and cost baseline after award | Civil Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The Civil Estimator completes “Handover final civil estimate, assumptions and cost baseline after award” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The Civil Estimator completes “Handover final civil estimate, assumptions and cost baseline after award” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The MEP Estimator may support tender administration but not civil technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: after award the Estimator hands the estimate, the assumptions and the cost baseline to the project team. • Starts when: the project is awarded. • How it runs: (1) the final priced estimate is confirmed as the awarded version. (2) The cost baseline is prepared in the form the project team will control cost against. (3) Assumptions, exclusions, qualifications and risk allowances are handed over explicitly. (4) A handover meeting covers what was priced, what was assumed and where the exposure sits. (5) The handover is recorded and the estimate archived as the baseline. • Proof it happened: the handover record with the awarded estimate, the cost baseline issued, the assumptions and risks transferred, and the archived baseline. • Where it usually breaks: the price is handed over but the assumptions behind it are not, so the project team manages against a number without knowing what it was based on. | • Require the assumptions, exclusions, qualifications and risk allowances to be handed over with the price, in a documented meeting. A price without its basis cannot be managed. • Require the cost baseline to be issued in the format the project team controls cost against, not as the tender workbook. • Name the point at which cost responsibility transfers from Estimating to Projects. • Archive the awarded estimate as a locked baseline, with later changes tracked as variations. • Require actual cost feedback after completion to be returned to Estimating, since this is the only way rates improve.
242 | Technical Engineering | Receive and register MEP tender package and submission deadline | MEP Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The MEP Estimator completes “Receive and register MEP tender package and submission deadline” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The MEP Estimator completes “Receive and register MEP tender package and submission deadline” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the MEP Estimator receives the services tender package, records what arrived and notes the deadline everything works back from. • Starts when: an MEP tender package is received from the client or through Business Development. • How it runs: (1) the package is registered with the documents received, their revisions and the date. (2) The submission deadline, format and delivery route are recorded. (3) The documents are checked for the items MEP pricing depends on: schedules, single line diagrams, specifications and load data. (4) Missing documents are requested immediately. (5) The internal timeline is set back from the deadline and the bid decision confirmed with the CTO. • Proof it happened: the tender register entry listing the documents and revisions received, the deadline and format, and the internal timeline. • Where it usually breaks: the drawings are registered but the equipment schedules and specification sections are not checked, and MEP cannot be priced from drawings alone. | • Require the registration check to name the MEP-specific documents pricing depends on: equipment schedules, single line diagrams, load calculations and specification sections. Drawings alone are not a priceable package. • Register every addendum and reissued schedule with a date, since equipment schedules change repeatedly during tender. • Record deadline, format, portal requirement and delivery route at registration. • Require a recorded bid or no-bid decision by the CTO before estimating effort is committed. • Set an internal cut-off for specialist vendor quotations, which take longer to return than civil ones.
243 | Technical Engineering | Review HVAC, plumbing, electrical and ELV tender scope | MEP Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The MEP Estimator completes “Review HVAC, plumbing, electrical and ELV tender scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The MEP Estimator completes “Review HVAC, plumbing, electrical and ELV tender scope” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator reads the HVAC, plumbing, electrical and ELV scope to understand what is actually being priced across four disciplines. • Starts when: the tender package is registered and the bid decision is confirmed. • How it runs: (1) each discipline's drawings, schedules, specification and BOQ are reviewed together. (2) The scope split between MEP, civil and the client's direct suppliers is established. (3) Specified equipment makes, standards and approval requirements are identified. (4) Contract conditions carrying cost, including testing, commissioning, warranties and training, are flagged. (5) The scope understanding is recorded as the basis of the estimate. • Proof it happened: the scope review record per discipline with the scope boundaries, the specified equipment requirements and the flagged contract conditions. • Where it usually breaks: the boundary between MEP scope and the client's direct suppliers is assumed rather than established, so equipment is either priced twice or not at all. | • Require the scope boundary between MEP, civil and the client's direct suppliers to be established in writing, and queried where unclear. Assumed boundaries produce both double pricing and missing equipment. • Require specified makes and approved vendor lists to be identified, since these remove the ability to price cheaper equivalents. • Flag testing, commissioning, warranty, spares and training obligations, which are substantial in MEP and routinely underpriced. • Review each discipline separately but reconcile the interfaces, since interface scope is where gaps sit. • Record the scope understanding as the written basis of the estimate.
244 | Technical Engineering | Identify missing MEP information, contradictions and commercial risks | MEP Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The MEP Estimator completes “Identify missing MEP information, contradictions and commercial risks” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The MEP Estimator completes “Identify missing MEP information, contradictions and commercial risks” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator finds the missing services information, the contradictions and the commercial risks. • Starts when: the scope review identifies gaps, conflicts or risks. • How it runs: (1) missing information is listed: load data, equipment schedules, utility capacities, incoming supply details, authority requirements. (2) Contradictions between drawings, schedules, BOQ and specification are recorded with the affected quantity. (3) Commercial risks are identified: unclear boundaries, single-source equipment, long lead items, onerous performance obligations. (4) Cost exposure is assessed per item. (5) The list feeds the query process and the significant items go to the CTO. • Proof it happened: the gaps, contradictions and risk list with cost exposure assessed and the significant items escalated. • Where it usually breaks: a missing incoming supply capacity or utility confirmation is treated as a detail, when it can change the entire distribution and generation design. | • Treat missing incoming supply capacity, utility confirmation and load data as high exposure items, since each can change the whole services design after award. • Prohibit resolving a schedule against drawing contradiction internally without raising it, as the difference is usually real scope. • Require single-source and long lead equipment to be identified as commercial risks at this stage, not at procurement. • Require performance obligations, such as guaranteed capacities or efficiencies, to be flagged, since these carry liability beyond price. • Keep the list live through the tender rather than as a one-off review.
245 | Technical Engineering | Prepare MEP tender queries, assumptions and clarification log | MEP Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The MEP Estimator completes “Prepare MEP tender queries, assumptions and clarification log” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The MEP Estimator completes “Prepare MEP tender queries, assumptions and clarification log” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator writes the formal client questions and records the assumptions where no answer arrives. • Starts when: gaps and contradictions require client clarification. • How it runs: (1) queries are drafted per discipline, each tied to the document and item affected. (2) They are submitted through the tender route by the query deadline. (3) Responses are logged and their pricing effect assessed and applied. (4) Where no answer is received, a stated assumption is recorded with its cost basis. (5) The assumptions are carried into the offer as qualifications. • Proof it happened: the query and clarification log with responses, pricing effects, and the assumptions recorded and qualified in the offer. • Where it usually breaks: assumptions about equipment selection are made to keep pricing moving but never qualified, so the company is bound to supply something it never priced. | • Require every equipment selection assumption to be qualified in the offer with the make, model or performance basis priced. An unqualified selection assumption becomes an obligation to supply whatever the client expected. • Require every unanswered query to become a stated assumption in the submitted offer. • Submit queries by the tender query deadline with evidence of submission. • Log each response with the item repriced, not just the answer recorded. • Require the CTO to approve which assumptions are qualified and which are absorbed.
246 | Technical Engineering | Attend MEP tender site visit and record services constraints | MEP Estimator | Trigger: When a controlled tender/quotation package and deadline are received. Action: The MEP Estimator completes “Attend MEP tender site visit and record services constraints” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: a registered tender file, scope review, query log, site-visit record and pricing plan. Control/Handoff: Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When a controlled tender/quotation package and deadline are received. | The MEP Estimator completes “Attend MEP tender site visit and record services constraints” using the approved brief, source documents, calculations and controlled company systems. | a registered tender file, scope review, query log, site-visit record and pricing plan. | Estimator returns missing information through CTO/CMO and records all assumptions before takeoff/pricing. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator visits the site and records the conditions that affect services installation and cost. • Starts when: a tender site visit is arranged or required. • How it runs: (1) existing services, incoming supply positions, plant room space and riser provision are observed and photographed. (2) Access constraints for equipment delivery and installation are recorded, including door sizes, lift capacity and route restrictions. (3) Conditions differing from the tender documents are noted. (4) Attendance is recorded where required. (5) Observations are converted into pricing assumptions and allowances. • Proof it happened: the site visit record with photographs, the access and space constraints, the differences from the documents, and the resulting allowances. • Where it usually breaks: equipment delivery and installation access is not checked, so large plant is priced without the craneage, dismantling or route works needed to get it in. | • Require the equipment delivery and installation route to be checked and recorded for every major item, including door sizes, lift capacity, floor loading and craneage. Access is the most expensive thing missed on MEP site visits. • Record existing services, incoming supply positions and available plant room and riser space, with photographs. • Convert every constraint with cost impact into a specific allowance or qualification. • Note differences from the tender documents formally, as these support later claims. • Use a standard MEP constraints checklist so the visit does not depend on who attends.
247 | Technical Engineering | Prepare HVAC equipment, ductwork and piping quantity takeoff | MEP Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The MEP Estimator completes “Prepare HVAC equipment, ductwork and piping quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The MEP Estimator completes “Prepare HVAC equipment, ductwork and piping quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the HVAC equipment, ductwork and piping. • Starts when: HVAC drawings and equipment schedules are sufficient to measure. • How it runs: (1) the drawing and schedule revisions measured from are recorded. (2) Equipment is counted and priced against the schedule, by capacity and specification. (3) Ductwork is measured by size, material, gauge and insulation, with fittings counted. (4) Piping is measured by size and material, with valves, fittings, insulation and supports counted. (5) The takeoff is checked against the schedules and the assumptions recorded. • Proof it happened: the HVAC takeoff with equipment against the schedule, duct and pipe by size and material, and fittings and accessories counted. • Where it usually breaks: ductwork and piping are measured by length only, so fittings, supports, insulation and accessories, which carry much of the cost and labour, are omitted. | • Require fittings, supports, valves, insulation and accessories to be measured and counted, not covered by a percentage on length. These carry a large share of installed cost and most of the labour. • Require duct measurement to state material, gauge and pressure class, since these change price substantially. • Price equipment against the schedule item by item, with the specified capacity and any approved equivalents stated. • Record the drawing and schedule revisions measured from, since HVAC schedules change late. • Sanity check duct weight per area and pipe metres per unit against benchmarks.
248 | Technical Engineering | Prepare plumbing, drainage and water-system quantity takeoff | MEP Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The MEP Estimator completes “Prepare plumbing, drainage and water-system quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The MEP Estimator completes “Prepare plumbing, drainage and water-system quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the plumbing, drainage and water systems. • Starts when: plumbing drawings and fixture schedules are sufficient to measure. • How it runs: (1) the drawing and schedule revisions are recorded. (2) Fixtures and fittings are counted against the schedule by type and specification. (3) Water piping is measured by size and material with valves, fittings, insulation and supports. (4) Drainage is measured by size and material with fittings, traps, cleanouts and vents. (5) Water heating, storage, pumps and treatment are priced against the schedule and the takeoff checked. • Proof it happened: the plumbing takeoff with fixtures against the schedule, piping and drainage by size and material, and equipment priced against the schedule. • Where it usually breaks: sanitaryware is priced at a standard rate when the schedule specifies premium or imported items, which can differ several times over in cost. | • Require every fixture to be priced against the schedule specification and product reference, not a standard rate. Sanitaryware cost varies several times over between standard and specified items. • Require pumps, water heating, storage and treatment equipment to be priced against the schedule with capacities stated. • Measure drainage fittings, traps, cleanouts and vents explicitly rather than as a percentage. • State the pipe material and jointing method priced, since these change labour significantly. • Flag any fixture specified without a product reference, as it cannot be priced reliably.
249 | Technical Engineering | Prepare fire-protection quantity takeoff where included in scope | MEP Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The MEP Estimator completes “Prepare fire-protection quantity takeoff where included in scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The MEP Estimator completes “Prepare fire-protection quantity takeoff where included in scope” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: where fire protection is in scope, the Estimator measures it. • Starts when: fire protection is confirmed as within the MEP scope for the tender. • How it runs: (1) the scope is confirmed, including whether detection, suppression, pumps and tanks are included. (2) Sprinkler and suppression pipework, heads and devices are measured by area and hazard classification. (3) Pumps, tanks and control equipment are priced against the schedule. (4) Detection and alarm devices are counted with the cause and effect requirements noted. (5) Authority approval and third party certification requirements are identified and allowed for. • Proof it happened: the fire protection takeoff with the scope confirmed, quantities by hazard classification, and the approval and certification allowances. • Where it usually breaks: authority approval, third party inspection and certification costs are not priced, and these are mandatory and significant in fire systems. | • Require authority approval, third party inspection, certification and approved contractor requirements to be priced explicitly. In fire systems these are mandatory, significant and routinely omitted. • Require the hazard classification and design standard applied to be stated, since it drives density, pipe sizes and pump duty. • Confirm in writing whether detection, suppression, pumps, tanks and cause and effect programming are in scope. • Allow for testing and witnessed commissioning, which fire systems require formally. • Flag where a specified system requires a licensed or approved specialist, as that limits pricing options.
250 | Technical Engineering | Prepare electrical power and lighting quantity takeoff | MEP Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The MEP Estimator completes “Prepare electrical power and lighting quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The MEP Estimator completes “Prepare electrical power and lighting quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the electrical power and lighting works. • Starts when: electrical drawings, panel schedules and lighting layouts are sufficient to measure. • How it runs: (1) the drawing and schedule revisions are recorded. (2) Distribution equipment is priced against the panel schedules and single line diagram, by rating and specification. (3) Cabling is measured by size, type and route length, with containment, glands and terminations counted. (4) Lighting and accessories are counted against the schedules by type. (5) Earthing, protection and testing requirements are allowed for and the takeoff checked. • Proof it happened: the electrical takeoff with equipment against the schedules, cabling by size and type with containment and terminations, and the testing allowances. • Where it usually breaks: cable is measured on the straight line distance rather than the actual route with drops, risers and slack, so cable quantities are consistently short. | • Require cable to be measured on the actual route including risers, drops, terminations and slack, with the routing basis stated. Straight line measurement understates cable consistently. • Require containment, glands, terminations and accessories to be counted, since these carry heavy labour content. • Price distribution equipment against the panel schedules and single line diagram by rating, not by count. • Allow for testing, earthing and protection verification as priced items. • Sanity check cable metres and light fittings per area against benchmarks.
251 | Technical Engineering | Prepare ELV, containment and specialist-system quantity takeoff | MEP Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The MEP Estimator completes “Prepare ELV, containment and specialist-system quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The MEP Estimator completes “Prepare ELV, containment and specialist-system quantity takeoff” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator measures the low voltage systems, the containment and the specialist systems. • Starts when: ELV and specialist system drawings and specifications are sufficient to measure. • How it runs: (1) each system is identified separately: data, security, access control, CCTV, public address, BMS and others. (2) Devices are counted against the schedules by type and specification. (3) Cabling and containment are measured by system with the route basis stated. (4) Head end equipment, servers, software, licensing and configuration are priced. (5) Integration, programming, testing and training requirements are allowed for. • Proof it happened: the ELV takeoff by system with devices counted, cabling measured, head end equipment priced, and the integration and licensing allowances. • Where it usually breaks: devices and cabling are priced but software licensing, programming, integration and training are not, and on ELV systems these can exceed the hardware cost. | • Require software licensing, programming, integration, configuration, testing and training to be priced as separate items on every ELV system. On BMS and security systems these can exceed the hardware cost. • Require each system to be priced separately rather than as one ELV allowance, since scope and risk differ per system. • State the integration requirements between systems, as integration scope is the commonest ELV dispute. • Identify proprietary systems and approved integrators, which limit pricing and later competition. • Allow for post-handover support obligations where the specification requires them.
252 | Technical Engineering | Reconcile MEP takeoff against BOQ, drawings and specifications | MEP Estimator | Trigger: When the controlled tender drawings, BOQ and specifications are available. Action: The MEP Estimator completes “Reconcile MEP takeoff against BOQ, drawings and specifications” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: traceable discipline takeoff sheets and reconciled quantities. Control/Handoff: Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the controlled tender drawings, BOQ and specifications are available. | The MEP Estimator completes “Reconcile MEP takeoff against BOQ, drawings and specifications” using the approved brief, source documents, calculations and controlled company systems. | traceable discipline takeoff sheets and reconciled quantities. | Estimator self-checks quantities and retains drawing/BOQ references; material uncertainty is raised before pricing closes. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator checks the measured MEP quantities against the BOQ, the drawings and the specification. • Starts when: the discipline takeoffs are complete and require reconciliation before pricing. • How it runs: (1) measured quantities are compared with the BOQ item by item per discipline. (2) Variances beyond tolerance are investigated. (3) BOQ items with no drawing basis and drawn work with no BOQ line are identified. (4) Equipment schedules are reconciled against the priced equipment list. (5) The reconciliation is recorded and material variances raised as queries or qualifications. • Proof it happened: the reconciliation per discipline showing measured against BOQ, the variances investigated, the equipment schedule reconciled, and the missing items identified. • Where it usually breaks: the equipment schedule is not reconciled against the priced list, so a scheduled item is never priced and appears only after award. | • Require an item by item reconciliation of the equipment schedule against the priced equipment list, since a scheduled but unpriced item is a direct loss after award. • Set a variance tolerance above which measured against BOQ differences must be investigated and explained. • Require identification of both BOQ items with no drawing basis and drawn work with no BOQ line. • Reconcile per discipline and then across interfaces, since interface scope falls between disciplines. • Record the reconciliation as the defence if quantities are disputed after award.
253 | Technical Engineering | Prepare MEP supplier and specialist-subcontractor RFQ packages | MEP Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The MEP Estimator completes “Prepare MEP supplier and specialist-subcontractor RFQ packages” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The MEP Estimator completes “Prepare MEP supplier and specialist-subcontractor RFQ packages” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator prepares the enquiry packages for MEP suppliers and specialist subcontractors. • Starts when: market pricing is required for MEP equipment or specialist work. • How it runs: (1) packages are defined by system with clear boundaries between them. (2) Each package includes drawings, specification extracts, schedules, quantities and the conditions to be priced. (3) Technical requirements are stated clearly: capacities, standards, approvals, testing and warranties. (4) The required return format and the deadline are stated. (5) Packages are issued through Procurement and recorded. • Proof it happened: the RFQ packages by system with the technical requirements stated, the return format and deadline, issued through Procurement. • Where it usually breaks: the enquiry states the equipment but not the performance requirement, so vendors price the cheapest item that carries the name rather than one that meets the duty. | • Require every equipment enquiry to state the performance duty, the applicable standard and the testing and warranty requirement, not the equipment name alone. Otherwise vendors price the cheapest item that fits the description. • Map package boundaries so every item sits in exactly one package. • State the required return format and breakdown so quotations are comparable. • Allow longer return periods for specialist and imported equipment, and record the deadline. • Issue through Procurement so the vendor list and terms stay controlled.
254 | Technical Engineering | Coordinate MEP market quotations through Procurement | MEP Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The MEP Estimator completes “Coordinate MEP market quotations through Procurement” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The MEP Estimator completes “Coordinate MEP market quotations through Procurement” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator works with Procurement to get the MEP quotations back in time. • Starts when: RFQ packages have been issued and quotations are due. • How it runs: (1) issued enquiries are tracked against expected returns per system. (2) Vendor technical questions are answered consistently and to all bidders alike. (3) Non-responders are chased and alternatives approached where coverage is thin. (4) A minimum number of comparable quotations per system is pursued. (5) Quotations are registered with their date, validity and delivery period. • Proof it happened: the quotation tracker showing coverage per system, the responses received, and the validity and delivery periods recorded. • Where it usually breaks: a specified sole source vendor delays or declines, and the estimate is completed on an assumed price with nothing behind it. | • Require an escalation to the CTO where a specified or sole source vendor does not quote, rather than pricing an assumed figure. An assumed equipment price is the largest single risk in an MEP estimate. • Set a minimum number of comparable quotations per system with a recorded exception where it cannot be met. • Record quotation validity and delivery periods, since long lead equipment prices expire and delivery drives programme. • Answer vendor technical questions to all bidders alike to keep quotations comparable. • Track coverage per system, not quotations received in total.
255 | Technical Engineering | Prepare MEP quotation comparison and technical-commercial compliance review | MEP Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The MEP Estimator completes “Prepare MEP quotation comparison and technical-commercial compliance review” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The MEP Estimator completes “Prepare MEP quotation comparison and technical-commercial compliance review” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator compares MEP quotations on both technical compliance and price. • Starts when: quotations have been received for a system package. • How it runs: (1) quotations are normalised to the same scope, quantities and conditions. (2) Technical compliance is assessed against the specified duty, standards and approvals. (3) Exclusions, qualifications, delivery periods and payment terms are listed per bidder. (4) The comparison is made on total cost of a compliant offer, including what must be added back. (5) A recommendation is prepared with the technical and commercial basis stated. • Proof it happened: the comparison with the quotations normalised, the technical compliance assessed per bidder, the exclusions listed, and the recommendation basis. • Where it usually breaks: a cheaper quotation is accepted on price without checking the offered equipment meets the specified duty, so the saving disappears when the equipment is rejected. | • Require a technical compliance assessment against the specified duty and standard for every quotation before price comparison. Cheaper MEP equipment is usually cheaper because it does not comply. • Require quotations to be normalised with exclusions added back before comparison. • Include delivery period, validity and payment terms in the comparison, since delivery affects programme cost. • Require technical review of any offered equivalent by the engineering team, not by the estimator alone. • State the recommendation basis so the selection can be defended and reused after award.
256 | Technical Engineering | Resolve MEP vendor exclusions, deviations and unpriced scope | MEP Estimator | Trigger: When takeoff and RFQ packages are ready for market enquiry. Action: The MEP Estimator completes “Resolve MEP vendor exclusions, deviations and unpriced scope” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: comparable supplier/subcontractor quotations, compliance review and clarification record. Control/Handoff: Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When takeoff and RFQ packages are ready for market enquiry. | The MEP Estimator completes “Resolve MEP vendor exclusions, deviations and unpriced scope” using the approved brief, source documents, calculations and controlled company systems. | comparable supplier/subcontractor quotations, compliance review and clarification record. | Procurement controls enquiry routing; estimator normalises quotations and escalates missing/deviating scope. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator closes the gaps left by MEP vendor exclusions and deviations. • Starts when: vendor exclusions, deviations or unpriced scope are identified in the comparison. • How it runs: (1) every exclusion and deviation is listed against the scope it affects. (2) Each gap is closed by pricing in-house, requoting, or qualifying it in the offer. (3) Technical deviations are assessed for acceptability by the engineering team. (4) Commonly excluded items are checked specifically: unloading, storage, builders work, testing, commissioning, start-up and training. (5) A closure check confirms no scope remains unpriced. • Proof it happened: the exclusions and deviations register with each item priced, requoted or qualified, and the closure check. • Where it usually breaks: vendors exclude commissioning, start-up and training as standard, and these get left out of the estimate entirely. | • Require a specific check on the items MEP vendors habitually exclude: offloading, storage, builders work, testing, commissioning, start-up, training and spares. These are excluded as standard and omitted as a result. • Require a closure check confirming every exclusion is priced, requoted or qualified in the offer. • Require technical deviations to be assessed by the engineering team, not accepted commercially. • Record the resolution route per item so the estimate basis is auditable. • Escalate any gap that cannot be closed within the tender period to the CTO.
257 | Technical Engineering | Prepare MEP labour, material, equipment and subcontract rate build-ups | MEP Estimator | Trigger: When verified quantities and market inputs are available. Action: The MEP Estimator completes “Prepare MEP labour, material, equipment and subcontract rate build-ups” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The MEP Estimator completes “Prepare MEP labour, material, equipment and subcontract rate build-ups” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator builds up MEP rates from labour, material, equipment and subcontract costs. • Starts when: rate build-ups are required for MEP pricing. • How it runs: (1) labour is built from actual rates by trade and skill level, including statutory and non-productive time. (2) Material costs come from quotations with wastage, delivery and offloading included. (3) Equipment costs come from quotations with delivery, unloading, positioning and start-up allowed for. (4) Subcontract rates come from the compared quotations. (5) Build-ups are checked against rates achieved historically and each input source recorded. • Proof it happened: the rate build-ups with labour by trade, material, equipment and subcontract components, and each input source recorded. • Where it usually breaks: equipment is priced at the supply cost with no allowance for delivery, offloading, positioning, connection and start-up, which are substantial on large plant. | • Require equipment pricing to include delivery, offloading, positioning, connection, start-up and vendor attendance as identified costs. Supply price alone understates installed cost significantly on plant. • Require labour to be built up by trade and skill level with statutory, welfare and non-productive time included. • Record the source of every input so a rate can be re-examined without rebuilding it. • Maintain a reviewed MEP rate library with a stated review date. • Benchmark against rates achieved on completed projects and explain differences.
258 | Technical Engineering | Apply MEP productivity, access, testing and logistics assumptions | MEP Estimator | Trigger: When verified quantities and market inputs are available. Action: The MEP Estimator completes “Apply MEP productivity, access, testing and logistics assumptions” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The MEP Estimator completes “Apply MEP productivity, access, testing and logistics assumptions” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator applies realistic assumptions about installation speed, access, testing and logistics. • Starts when: productivity and logistics assumptions are required for MEP pricing. • How it runs: (1) productivity is set per activity from records, per trade and system. (2) Access conditions are considered: ceiling voids, shafts, height, congestion, occupied areas, working hours. (3) Testing and commissioning effort is estimated per system rather than as a lump. (4) Logistics are priced: delivery, storage, vertical transport, handling of large plant. (5) The assumptions are recorded for checking and reuse. • Proof it happened: the assumptions record stating productivity per activity, the access conditions, the testing and commissioning effort, and the logistics allowances. • Where it usually breaks: coordination and rework time in congested ceiling voids and shafts is not allowed for, and it is the single biggest productivity loss in services installation. | • Require an explicit allowance for coordination and rework in congested ceiling voids, shafts and plant rooms. Services congestion is the biggest productivity loss in MEP installation and standard rates ignore it. • Require productivity to be adjusted for the access conditions recorded at the site visit. • Estimate testing and commissioning effort per system, since a lump sum allowance is invariably short. • Price handling of large plant separately, including vertical transport and route works. • Record the assumptions so the outcome can be fed back to Estimating after the project.
259 | Technical Engineering | Price builders-work, authority, testing and commissioning allowances | MEP Estimator | Trigger: When verified quantities and market inputs are available. Action: The MEP Estimator completes “Price builders-work, authority, testing and commissioning allowances” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The MEP Estimator completes “Price builders-work, authority, testing and commissioning allowances” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator prices the builders work, the authority costs and the testing and commissioning. • Starts when: builders work, authority and commissioning allowances require pricing. • How it runs: (1) builders work is measured or allowed for: openings, chases, plinths, supports, making good, and whether it sits in MEP scope is confirmed. (2) Authority requirements are identified and priced: submissions, inspections, approvals, connection charges, permits. (3) Testing is priced per system, including third party testing where required. (4) Commissioning is priced including specialist attendance, balancing, witnessing and documentation. (5) Handover requirements are allowed for: as-builts, manuals, training and spares. • Proof it happened: the priced builders work, authority costs, testing and commissioning by system, and the handover deliverable allowances. • Where it usually breaks: authority connection charges and inspection fees are assumed to sit with the client, and nobody confirms it until the bill arrives. | • Require written confirmation of who bears authority connection charges, inspection fees and permit costs, and qualify it in the offer where unconfirmed. These are large sums assumed to sit elsewhere. • Require the builders work scope split between MEP and civil to be confirmed rather than assumed. • Price commissioning per system including specialist attendance, balancing, witnessing and documentation. • Allow for handover deliverables: as-built drawings, operation manuals, training and spares, since these are contractual. • Include third party testing and certification where the specification requires it.
260 | Technical Engineering | Prepare MEP risk, opportunity, exclusion and contingency register | MEP Estimator | Trigger: When verified quantities and market inputs are available. Action: The MEP Estimator completes “Prepare MEP risk, opportunity, exclusion and contingency register” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The MEP Estimator completes “Prepare MEP risk, opportunity, exclusion and contingency register” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator records the MEP risks, opportunities, exclusions and contingency. • Starts when: the estimate is being assembled and risk requires quantifying. • How it runs: (1) risks are listed with cost impact and likelihood, including equipment price movement, long lead delivery, sole source dependency and performance obligations. (2) Opportunities are listed. (3) Exclusions are listed in the wording that will appear in the offer. (4) Contingency is set against identified risks with the basis stated. (5) The register is reviewed with the CTO before submission. • Proof it happened: the risk, opportunity, exclusion and contingency register with the cost impacts, the contingency basis, and the CTO review. • Where it usually breaks: equipment price and currency movement over a long tender and procurement period is not treated as a risk, so a validity expiry becomes a straight loss. | • Require equipment price validity, currency movement and long lead delivery to be treated as quantified risks, with a stated validity period in the offer. Expired equipment quotations become a direct loss. • Require contingency to be built from the identified risks with the basis stated per item. • Require exclusions to be written in the exact wording that will appear in the offer. • List performance and guarantee obligations as risks, since these carry liability beyond price. • Carry the register into the project handover after award.
261 | Technical Engineering | Develop MEP value-engineering and alternative-system pricing options | MEP Estimator | Trigger: When verified quantities and market inputs are available. Action: The MEP Estimator completes “Develop MEP value-engineering and alternative-system pricing options” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. Control/Handoff: CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When verified quantities and market inputs are available. | The MEP Estimator completes “Develop MEP value-engineering and alternative-system pricing options” using the approved brief, source documents, calculations and controlled company systems. | auditable rates, allowances, preliminaries, risks, exclusions and value-engineering options. | CTO reviews technical/commercial basis; CFO/CEO approvals apply to margin, risk and authority exceptions. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator prices alternative systems and equipment that achieve the same result for less. • Starts when: value engineering or alternative system pricing is required or opportunities are identified. • How it runs: (1) high-cost systems and equipment are identified from the priced estimate. (2) Alternatives are developed with the engineering team, covering equipment, system type and distribution strategy. (3) Each option is priced with its saving, its performance implications and its operating cost effect stated. (4) Options are checked against the specification, the authority requirements and any warranty conditions. (5) Options are presented separately from the compliant base offer. • Proof it happened: the value engineering options with savings quantified, performance and operating cost implications stated, compliance checked, and the base offer kept separate. • Where it usually breaks: a cheaper system is offered on capital cost alone, with no mention that it costs more to run or has a shorter life. | • Require every alternative to state its effect on operating cost, maintenance and expected life alongside the capital saving. A capital-only comparison misleads the client and damages the relationship after handover. • Require technical verification and sign-off by the engineering team before any alternative is offered. • Submit a compliant base offer separately from alternatives, since mixing them makes the bid non-compliant. • Check alternatives against specification, authority approval and warranty conditions. • Record which options the client accepted so the awarded scope is unambiguous.
262 | Technical Engineering | Prepare priced MEP BOQ and commercial summary | MEP Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The MEP Estimator completes “Prepare priced MEP BOQ and commercial summary” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The MEP Estimator completes “Prepare priced MEP BOQ and commercial summary” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator produces the priced MEP BOQ and the commercial summary. • Starts when: pricing is complete and the offer needs assembling. • How it runs: (1) rates are applied in the required format and every item is confirmed priced per discipline. (2) The commercial summary shows direct cost, preliminaries, risk, overhead and margin separately, and by discipline where required. (3) Equipment, installation and commissioning are shown distinctly where the tender requires it. (4) The submission format and required documents are checked against the tender requirements. (5) The package is assembled with the qualifications, assumptions and equipment schedule included. • Proof it happened: the priced MEP BOQ in the required format with the commercial summary and the submitted equipment schedule, qualifications and assumptions. • Where it usually breaks: the offer is submitted without the equipment schedule showing what was actually priced, so the client assumes a higher specification than was allowed for. | • Require a schedule of the equipment actually priced, with makes, models or performance basis, to be submitted with the offer. Without it the client assumes a higher specification than was priced. • Require an automated check that every BOQ line carries a rate, and prohibit blank or included entries unless permitted. • Show direct cost, preliminaries, risk, overhead and margin separately, and by discipline where required. • Check the submission format and required documents against the tender checklist. • Lock and record the final submitted version so what was sent is unambiguous.
263 | Technical Engineering | Complete MEP estimate self-check and reconciliation | MEP Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The MEP Estimator completes “Complete MEP estimate self-check and reconciliation” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The MEP Estimator completes “Complete MEP estimate self-check and reconciliation” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the Estimator checks their own MEP estimate before it goes to the CTO. • Starts when: the estimate is assembled and requires self-checking before review. • How it runs: (1) all items are confirmed priced with no blanks or placeholders. (2) Quantities, rates, extensions and totals are checked. (3) Rates are sanity checked against benchmarks per system and outliers investigated. (4) The estimate is reconciled against the takeoff, the equipment schedule, the accepted quotations and the assumptions register. (5) The self-check is evidenced against a checklist with corrections recorded. • Proof it happened: the completed self-check checklist with the reconciliations, the benchmark checks and the corrections made. • Where it usually breaks: the estimate is checked against the takeoff but not against the equipment schedule, so a scheduled item omitted at takeoff stage is never caught. | • Require the self-check to reconcile against the equipment schedule as well as the takeoff, since an item missed at takeoff will not be found by checking the takeoff again. • Require a benchmark sanity check per system, such as cost per area or per unit capacity, with outliers explained. • Require a completed checklist as evidence, not a statement that the estimate was checked. • Check specifically for blanks, placeholders and unpriced provisional items. • Record corrections made, since recurring corrections indicate a process weakness.
264 | Technical Engineering | Submit MEP estimate for CTO review and approved margin integration | MEP Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The MEP Estimator completes “Submit MEP estimate for CTO review and approved margin integration” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The MEP Estimator completes “Submit MEP estimate for CTO review and approved margin integration” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: the MEP estimate goes to the CTO for review and the approved margin is added. • Starts when: the self-check is complete and the estimate is ready for review. • How it runs: (1) the estimate is submitted with the assumptions, equipment basis, risks, qualifications and exclusions. (2) The CTO reviews the technical basis, the risk position and the competitiveness. (3) The margin is set within the approved authority, and deviations are escalated to the CEO. (4) Comments are addressed and the estimate updated. (5) The approved price and its basis are recorded before submission. • Proof it happened: the CTO review record with the comments addressed, the approved margin within authority, and the approved final price recorded. • Where it usually breaks: the review focuses on the price and not on the equipment basis, so a non-compliant equipment selection is approved and only discovered at submission review by the client. | • Require the CTO review to cover the equipment and technical basis explicitly, not the price alone. A non-compliant selection approved at this stage becomes a rejected submission or a loss after award. • Require any margin reduction to be recorded with the reason and the risk accepted, and approved within authority. • State the approval limits for margin and price, and the escalation route above them. • Record the approved price and basis as the submitted version. • Require re-approval for any change made after approval rather than adjusting before sending.
265 | Technical Engineering | Revise MEP offer for client clarification and negotiation | MEP Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The MEP Estimator completes “Revise MEP offer for client clarification and negotiation” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The MEP Estimator completes “Revise MEP offer for client clarification and negotiation” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: when the client clarifies or negotiates, the Estimator revises the MEP offer properly. • Starts when: client clarifications, negotiations or revised requirements are received. • How it runs: (1) the request or negotiation position is recorded with its date. (2) Scope, equipment, quantity or condition changes are identified and repriced rather than discounted. (3) The effect on risk, qualifications, assumptions and equipment validity is reassessed. (4) The revision is approved within authority before issue, including any margin change. (5) The revised offer is issued with a version number and the changes recorded. • Proof it happened: the revision record with the request, the repricing, the reassessed risk and validity position, the approval and the versioned offer. • Where it usually breaks: the offer is revised weeks later without rechecking equipment quotation validity, so the revised price is based on prices that have expired. | • Require equipment quotation validity to be rechecked at every revision, since MEP negotiations run long and expired prices carried into a revised offer become a direct loss. • Require every price reduction to be matched to a scope change, a risk acceptance or a recorded margin decision. • Reassess qualifications and assumptions at each revision, as these get dropped inadvertently. • Version-control every revised offer and state which version supersedes which. • Require approval within authority for each revision, not only the original submission.
266 | Technical Engineering | Handover final MEP estimate, assumptions and cost baseline after award | MEP Estimator | Trigger: When the estimate reaches internal review, client submission, negotiation or award. Action: The MEP Estimator completes “Handover final MEP estimate, assumptions and cost baseline after award” using the approved brief, source documents, calculations and controlled company systems. Output/Evidence: an approved priced BOQ, quotation package, revision record and post-award cost handover. Control/Handoff: CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. Continuity/Escalation: The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. Timing: To be confirmed. | When the estimate reaches internal review, client submission, negotiation or award. | The MEP Estimator completes “Handover final MEP estimate, assumptions and cost baseline after award” using the approved brief, source documents, calculations and controlled company systems. | an approved priced BOQ, quotation package, revision record and post-award cost handover. | CTO approves technical basis; CMO controls client issue; Finance/CEO approve commercial exceptions; final basis is handed to COO/QS. | The Civil Estimator may support tender administration but not MEP technical judgement; missing scope, pricing, margin or contract risk escalates to CTO and CFO/CEO within authority. | To be confirmed. | • In plain words: after award the Estimator hands the MEP estimate, assumptions and cost baseline to the project team. • Starts when: the project is awarded. • How it runs: (1) the final priced estimate is confirmed as the awarded version. (2) The cost baseline is prepared in the form the project team will control cost against. (3) The equipment basis, assumptions, exclusions, qualifications and risk allowances are handed over explicitly. (4) A handover meeting covers what was priced, what equipment was allowed for, the long lead items and where the exposure sits. (5) The handover is recorded and the estimate archived as the baseline. • Proof it happened: the handover record with the awarded estimate, the cost baseline, the equipment basis and assumptions transferred, and the archived baseline. • Where it usually breaks: the long lead equipment list is not flagged at handover, so procurement starts late and the delivery period drives the programme. | • Require the long lead equipment list with delivery periods to be handed over as a distinct item, since late procurement of long lead plant is the commonest MEP programme failure. • Require the equipment basis, assumptions, exclusions, qualifications and risk allowances to be handed over with the price in a documented meeting. • Issue the cost baseline in the format the project team controls cost against. • Name the point at which cost responsibility transfers from Estimating to Projects. • Require actual cost and equipment performance feedback after completion to be returned to Estimating.
267 | Projects | Set Projects strategy, delivery standards and annual operating objectives | Chief Operations Officer (COO) | Trigger: When the annual plan, a portfolio change or an executive review requires an operating decision. Action: The Chief Operations Officer (COO) completes “Set Projects strategy, delivery standards and annual operating objectives” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved Projects plan, governance decision, KPI action or portfolio record. Control/Handoff: The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the annual plan, a portfolio change or an executive review requires an operating decision. | The Chief Operations Officer (COO) completes “Set Projects strategy, delivery standards and annual operating objectives” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved Projects plan, governance decision, KPI action or portfolio record. | The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO decides how the Projects department will deliver work, what standard is expected, and what it must achieve over the year. • Starts when: the annual planning cycle runs, or company strategy or delivery performance changes enough to require new direction. • How it runs: (1) delivery performance and capability are reviewed against the previous year. (2) The delivery approach and standards are set: how projects are planned, controlled and reported. (3) Objectives are set with measures for safety, quality, programme, cost and client satisfaction. (4) The plan is aligned with the CEO's strategy and approved. (5) The objectives are issued to the project teams and built into their targets. • Proof it happened: the approved Projects strategy and delivery standards with measurable annual objectives issued to the teams. • Where it usually breaks: objectives are set at department level but never broken down to individual projects, so nobody on a site can say what they are being measured against. | • Require department objectives to be broken down to project level with named owners. A department target nobody on site can name changes no behaviour. • Set the delivery standards as named documents, such as the planning standard, reporting standard and quality standard, rather than as principles. • Include measures for safety, quality, programme, cost and client satisfaction, so the standard cannot be met by hitting programme alone. • Fix a review point during the year where objectives can be formally changed rather than quietly dropped. • Require the previous year's delivery performance and lessons learned to be an input, so the objectives respond to what actually happened.
268 | Projects | Approve Projects organisation, delegated authority and accountability structure | Chief Operations Officer (COO) | Trigger: When the annual plan, a portfolio change or an executive review requires an operating decision. Action: The Chief Operations Officer (COO) completes “Approve Projects organisation, delegated authority and accountability structure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved Projects plan, governance decision, KPI action or portfolio record. Control/Handoff: The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the annual plan, a portfolio change or an executive review requires an operating decision. | The Chief Operations Officer (COO) completes “Approve Projects organisation, delegated authority and accountability structure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved Projects plan, governance decision, KPI action or portfolio record. | The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO sets up the Projects structure and states who can decide what and how far. • Starts when: the department is being organised, or the structure or authority needs changing. • How it runs: (1) the roles needed for the portfolio are defined, with the reporting lines. (2) Accountability is assigned per role, particularly the project accountability of the Project Engineer. (3) Authority limits are set per role for cost, variations, procurement and site decisions. (4) The structure and limits are approved within the company authority framework. (5) The structure and limits are issued so every role knows its boundary. • Proof it happened: the approved Projects organisation chart with accountability per role and the delegated authority limits issued. • Where it usually breaks: authority limits are set for cost but not for site decisions such as sequence changes or accepting substitutions, so those decisions get taken by whoever is present. | • Set authority limits for technical and site decisions, not just cost: sequence changes, material substitutions, temporary works, work stoppage and acceptance of non-conforming work. These decisions cost more than most purchase approvals. • State that nobody may raise their own limit, and name the route for a temporary increase with an end date. • Name a single accountable person per project, since shared accountability produces none. • Reissue the limits whenever the structure changes so the two documents cannot drift apart. • State what happens when someone acts beyond authority, including ratification or reversal and who decides.
269 | Projects | Prioritise the project portfolio and allocate delivery capacity | Chief Operations Officer (COO) | Trigger: When the annual plan, a portfolio change or an executive review requires an operating decision. Action: The Chief Operations Officer (COO) completes “Prioritise the project portfolio and allocate delivery capacity” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved Projects plan, governance decision, KPI action or portfolio record. Control/Handoff: The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the annual plan, a portfolio change or an executive review requires an operating decision. | The Chief Operations Officer (COO) completes “Prioritise the project portfolio and allocate delivery capacity” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved Projects plan, governance decision, KPI action or portfolio record. | The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO decides which projects get the people, plant and attention, and in what order. • Starts when: new work is awarded, capacity is short, or the portfolio position changes. • How it runs: (1) the committed portfolio and its delivery requirements are reviewed. (2) Available capacity is assessed: staff, supervision, labour, plant and subcontract capability. (3) Projects are prioritised against criteria: contractual obligation, client importance, risk, margin and cash. (4) Capacity is allocated per project, and shortfalls are named rather than absorbed. (5) The allocation is issued and the constraint escalated to the CEO where capacity cannot meet commitments. • Proof it happened: the portfolio priority list with the capacity allocation per project and the shortfalls recorded and escalated. • Where it usually breaks: capacity is allocated on paper beyond what actually exists, so every project is told it has resources and they compete for the same crews. | • Require allocation against verified available capacity, with any shortfall named and escalated rather than absorbed. Allocating capacity that does not exist guarantees every project underperforms. • State the prioritisation criteria in the SOP: contractual obligation, client importance, risk, margin and cash impact. • Require the allocation to be reviewed on a fixed cycle, since capacity and priority both move. • Record where a project was deliberately de-prioritised, so the resulting delay is not later treated as a delivery failure. • Require key resources, such as supervision and critical plant, to be allocated by name rather than by number.
270 | Projects | Establish portfolio KPIs, risk thresholds and exception-reporting rules | Chief Operations Officer (COO) | Trigger: When the annual plan, a portfolio change or an executive review requires an operating decision. Action: The Chief Operations Officer (COO) completes “Establish portfolio KPIs, risk thresholds and exception-reporting rules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved Projects plan, governance decision, KPI action or portfolio record. Control/Handoff: The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the annual plan, a portfolio change or an executive review requires an operating decision. | The Chief Operations Officer (COO) completes “Establish portfolio KPIs, risk thresholds and exception-reporting rules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved Projects plan, governance decision, KPI action or portfolio record. | The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO sets the numbers that are tracked, the risk limits, and the point at which something must be reported upwards. • Starts when: the governance framework is being set or the existing measures are no longer giving early warning. • How it runs: (1) the portfolio KPIs are set: progress against baseline, productivity, cost against budget, safety, quality and client measures. (2) Thresholds are set per KPI for acceptable, warning and unacceptable. (3) Risk thresholds are set for cost, programme, safety and quality exposure. (4) Exception rules state what must be reported, by whom, to whom and within what time. (5) The framework is issued and built into the reporting format. • Proof it happened: the approved KPI and threshold set with the exception reporting rules issued and reflected in the reporting templates. • Where it usually breaks: exceptions are defined but no time limit is set, so a breach is reported at the next monthly meeting when it is already too late to act. | • Attach a reporting time limit to every exception, stated in hours or working days from detection. An exception reported at the next monthly meeting has already become a fact rather than a decision. • Set numeric thresholds per KPI for acceptable, warning and unacceptable, since a KPI without a threshold triggers nothing. • Include leading measures such as productivity and lookahead reliability, not only lagging measures such as progress achieved. • Name who reports and who receives each exception type, so the route does not depend on judgement. • Review the thresholds periodically, as thresholds that are always breached stop being used.
271 | Projects | Report portfolio delivery, resource and corrective-action status to the CEO | Chief Operations Officer (COO) | Trigger: When the annual plan, a portfolio change or an executive review requires an operating decision. Action: The Chief Operations Officer (COO) completes “Report portfolio delivery, resource and corrective-action status to the CEO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved Projects plan, governance decision, KPI action or portfolio record. Control/Handoff: The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the annual plan, a portfolio change or an executive review requires an operating decision. | The Chief Operations Officer (COO) completes “Report portfolio delivery, resource and corrective-action status to the CEO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved Projects plan, governance decision, KPI action or portfolio record. | The COO records the decision in the project-control system and aligns CEO, CTO, CFO, CPO, CLO, CPCO and delivery owners where affected. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO reports to the CEO on how the portfolio is delivering, what resources are needed and what is being done about problems. • Starts when: the reporting cycle falls due, or a material portfolio issue arises between cycles. • How it runs: (1) project reports are consolidated into a portfolio view. (2) Delivery status is reported against baseline with the reasons for variance. (3) Resource position and constraints are reported, including where capacity blocks delivery. (4) Corrective actions are reported with owners, dates and their effect. (5) Decisions or support needed from the CEO are stated explicitly. • Proof it happened: the portfolio report to the CEO with status against baseline, the resource position, the corrective actions with owners and dates, and the decisions requested. • Where it usually breaks: the report describes status without stating what decision is needed, so it is read as information and no decision is taken. | • Require every report to state the decisions or support required from the CEO explicitly, with a recommendation. A status-only report produces no decision. • Require variance against baseline to carry the reason and the recovery action, not the variance figure alone. • Report resource constraints as blockers with named consequences, so capacity decisions can be made rather than deferred. • Track corrective actions to closure across reports, so the same action does not reappear for months. • Fix the report format so periods can be compared, and prohibit changing measures without recording why.
272 | Projects | Review the CTO construction-ready handover package for completeness | Chief Operations Officer (COO) | Trigger: When the CTO submits a construction-ready package and commercial and financial gates are visible. Action: The Chief Operations Officer (COO) completes “Review the CTO construction-ready handover package for completeness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. Control/Handoff: No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the CTO submits a construction-ready package and commercial and financial gates are visible. | The Chief Operations Officer (COO) completes “Review the CTO construction-ready handover package for completeness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. | No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: before a project starts on site, the COO checks that the package handed over by the CTO is actually complete enough to build from. • Starts when: the CTO submits a construction-ready handover package for a project. • How it runs: (1) the package is checked against a defined completeness checklist. (2) The technical content is checked: IFC drawings, specifications, approvals, permits and technical assumptions. (3) The commercial content is checked: contract, BOQ, cost baseline, exclusions and qualifications. (4) The financial content is checked: budget, cash flow, payment terms and margin position. (5) Gaps are listed with their delivery impact and returned to the CTO for closure. • Proof it happened: the completed handover review checklist with the gaps listed, their delivery impact assessed, and the closure requirements issued. • Where it usually breaks: the review checks that documents exist rather than whether they are complete and consistent, so a project starts with drawings that are missing key approvals. | • Require the review to test completeness and consistency, not the presence of documents. A file that contains a drawing register is not evidence that the drawings are approved and buildable. • Publish the handover checklist so the CTO knows what must be delivered before submitting, rather than discovering it at review. • Require authority permits and approval conditions to be listed individually with their status, since a missing permit stops work entirely. • Require the estimate assumptions, exclusions and qualifications to be part of the package, since the cost baseline cannot be managed without them. • Record each gap with its delivery impact, so acceptance decisions are informed.
273 | Projects | Accept, conditionally accept or reject the technical-commercial-financial handover | Chief Operations Officer (COO) | Trigger: When the CTO submits a construction-ready package and commercial and financial gates are visible. Action: The Chief Operations Officer (COO) completes “Accept, conditionally accept or reject the technical-commercial-financial handover” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. Control/Handoff: No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the CTO submits a construction-ready package and commercial and financial gates are visible. | The Chief Operations Officer (COO) completes “Accept, conditionally accept or reject the technical-commercial-financial handover” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. | No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO formally decides whether to take the project on as handed over, take it with conditions, or send it back. • Starts when: the handover package review is complete. • How it runs: (1) the review findings are assessed against the delivery risk they create. (2) One of three decisions is taken and recorded: accept, accept with conditions, or reject. (3) Where conditional, the conditions are listed with owners and dates. (4) Where rejected, the reasons and what must be resolved are stated. (5) The decision is recorded and communicated, and accountability transfers on acceptance. • Proof it happened: the recorded handover decision with the conditions or rejection reasons, the owners and dates, and the confirmed point of accountability transfer. • Where it usually breaks: the project is accepted with conditions but the conditions are never tracked, so the gaps stay open and become delivery problems nobody owns. | • Require conditions of acceptance to be logged in a tracked register with owners and dates, and reviewed until closed. Untracked conditions are the standard way handover gaps become site problems. • Name the exact point at which delivery accountability transfers from the CTO to Projects, since ambiguity here causes disputes on every troubled project. • Limit conditional acceptance so that items which prevent safe or compliant work cannot be conditions, they must be closed first. • Require the decision to be recorded in writing with the reasons, not communicated verbally in a meeting. • State who may accept on the COO's behalf during absence, and within what limits.
274 | Projects | Appoint the Responsible Project Engineer and confirm execution accountability | Chief Operations Officer (COO) | Trigger: When the CTO submits a construction-ready package and commercial and financial gates are visible. Action: The Chief Operations Officer (COO) completes “Appoint the Responsible Project Engineer and confirm execution accountability” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. Control/Handoff: No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the CTO submits a construction-ready package and commercial and financial gates are visible. | The Chief Operations Officer (COO) completes “Appoint the Responsible Project Engineer and confirm execution accountability” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. | No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO names the person accountable for delivering the project and confirms what that person is answerable for. • Starts when: a project is accepted for execution. • How it runs: (1) the Project Engineer is selected against the project's complexity and the available capacity. (2) The appointment is made in writing with the accountability stated. (3) The authority limits applying to the role on this project are confirmed. (4) The appointee formally accepts, confirming they have reviewed the handover package. (5) The appointment is communicated internally and to the client where required. • Proof it happened: the written appointment with the accountability and authority limits stated and the appointee's formal acceptance recorded. • Where it usually breaks: the appointment is verbal and the person is already loaded with other projects, so accountability is nominal and attention is divided. | • Require the appointment in writing with formal acceptance by the appointee, since verbal appointment leaves accountability arguable when the project goes wrong. • Require the appointee's existing project load to be reviewed before appointment, and recorded. Nominal accountability on an overloaded engineer is the commonest cause of unmanaged projects. • Require acceptance to confirm that the handover package has been reviewed, so the engineer inherits known conditions knowingly. • State the project-specific authority limits in the appointment itself. • Name the deputy and the handover requirement for planned or unplanned absence.
275 | Projects | Approve the project readiness and mobilisation gate conditions | Chief Operations Officer (COO) | Trigger: When the CTO submits a construction-ready package and commercial and financial gates are visible. Action: The Chief Operations Officer (COO) completes “Approve the project readiness and mobilisation gate conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. Control/Handoff: No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the CTO submits a construction-ready package and commercial and financial gates are visible. | The Chief Operations Officer (COO) completes “Approve the project readiness and mobilisation gate conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. | No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO sets what must be in place before the site can start, and checks it before allowing mobilisation. • Starts when: a project is appointed and mobilisation is proposed. • How it runs: (1) the readiness conditions are defined: access, permits, approved drawings, safety plan, resources, subcontracts and utilities. (2) Readiness is verified against evidence, not assurance. (3) Conditions not met are assessed for whether they block start or can be worked around safely. (4) The mobilisation gate is approved, approved with conditions, or held. (5) The decision and any conditions are recorded with dates. • Proof it happened: the completed readiness gate record with the conditions verified against evidence and the approval, conditional approval or hold recorded. • Where it usually breaks: mobilisation is approved on the promise that permits and access will follow, and the site then stands idle with resources already committed and costing money. | • Prohibit mobilisation on the promise of access or permits. Standing time with resources already committed is the most expensive avoidable cost in project start-up. • Require readiness to be verified against documentary evidence rather than verbal assurance, item by item. • Separate the conditions that block start absolutely, such as access, permits and safety plan, from those that can be closed in parallel. • Require a hold decision to state what must change and who owns it, so the hold has an exit. • Record the gate decision with dates, since mobilisation timing is central to later delay claims.
276 | Projects | Approve execution governance, reporting cadence and project stage gates | Chief Operations Officer (COO) | Trigger: When the CTO submits a construction-ready package and commercial and financial gates are visible. Action: The Chief Operations Officer (COO) completes “Approve execution governance, reporting cadence and project stage gates” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. Control/Handoff: No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the CTO submits a construction-ready package and commercial and financial gates are visible. | The Chief Operations Officer (COO) completes “Approve execution governance, reporting cadence and project stage gates” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an accepted, conditional or rejected handover, assigned Project Engineer and approved readiness actions. | No execution ownership starts on verbal instruction; blocking gaps return to the responsible CXO and unresolved material readiness risk escalates to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO sets how the project will be governed: which meetings happen, what reporting is required, and the checkpoints work must pass through. • Starts when: a project is mobilising and its governance needs establishing. • How it runs: (1) the meeting structure is set with frequency, attendance and purpose. (2) The reporting requirements and formats are set with their deadlines. (3) Stage gates are defined with the criteria to pass each one. (4) Decision authority at each gate is confirmed. (5) The governance arrangement is issued to the project team and the client interface confirmed. • Proof it happened: the issued project governance plan with the meeting cadence, reporting requirements, stage gate criteria and decision authority. • Where it usually breaks: stage gates are defined without pass criteria, so the gate becomes a meeting that projects pass through regardless of readiness. | • Require each stage gate to carry written pass criteria and evidence requirements. A gate without criteria is a meeting, and projects pass through it regardless of readiness. • State who may approve passage through each gate, and whether conditional passage is permitted. • Scale the governance to project size, so small projects are not given the reporting load of large ones and consequently report nothing. • Fix the reporting formats and deadlines so periods and projects can be compared. • Confirm the client-facing meeting and reporting obligations from the contract, since these are mandatory rather than internal choices.
277 | Projects | Conduct the weekly project performance and exception review | Chief Operations Officer (COO) | Trigger: When the daily, weekly or monthly project-control cadence becomes due. Action: The Chief Operations Officer (COO) completes “Conduct the weekly project performance and exception review” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified portfolio dashboard, decision log, recovery action and named due date. Control/Handoff: The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the daily, weekly or monthly project-control cadence becomes due. | The Chief Operations Officer (COO) completes “Conduct the weekly project performance and exception review” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified portfolio dashboard, decision log, recovery action and named due date. | The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO runs a weekly meeting looking at how projects are performing and what has gone outside limits. • Starts when: the weekly review falls due. • How it runs: (1) project reports are received before the meeting in the required format. (2) Performance is reviewed against baseline and KPI thresholds. (3) Exceptions and threshold breaches are examined with their causes. (4) Decisions are taken on corrective action, resources and escalation, with owners and dates. (5) Actions are recorded and tracked to closure at subsequent reviews. • Proof it happened: the weekly review record with the performance reviewed, the exceptions examined, and the decisions with owners and dates tracked to closure. • Where it usually breaks: the meeting spends its time on reporting rather than deciding, so exceptions are described each week and never resolved. | • Require reports to be circulated and read before the meeting, and run the meeting on exceptions and decisions only. A meeting spent presenting status resolves nothing. • Require an action tracker with owner, date and status, carried forward until each item is closed. • Require repeat exceptions to be escalated automatically after a set number of weeks, since a recurring exception is a systemic problem, not a project one. • Fix the attendance so decisions can be taken in the meeting rather than deferred for absent parties. • Record decisions with their basis, so they are not reopened at the next review.
278 | Projects | Review daily critical delivery, safety, client and supply-chain exceptions | Chief Operations Officer (COO) | Trigger: When the daily, weekly or monthly project-control cadence becomes due. Action: The Chief Operations Officer (COO) completes “Review daily critical delivery, safety, client and supply-chain exceptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified portfolio dashboard, decision log, recovery action and named due date. Control/Handoff: The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the daily, weekly or monthly project-control cadence becomes due. | The Chief Operations Officer (COO) completes “Review daily critical delivery, safety, client and supply-chain exceptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified portfolio dashboard, decision log, recovery action and named due date. | The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO looks daily at the urgent things: safety events, delivery blockers, client issues and supply failures. • Starts when: daily site and project reports are received, or an urgent exception is raised. • How it runs: (1) daily reports and exception notifications are reviewed. (2) Critical items are identified: safety incidents, work stoppages, critical path blockers, client escalations, supply failures. (3) Items needing intervention today are separated from those for the weekly review. (4) Immediate decisions are taken and support directed to the site. (5) The intervention and its outcome are recorded and followed to closure. • Proof it happened: the daily exception review record with the critical items identified, the immediate decisions taken, and the outcomes followed to closure. • Where it usually breaks: everything is reported daily, so the genuinely critical items are lost in routine reporting and get the same attention as everything else. | • Define what qualifies as a daily exception in specific terms, so routine reporting does not bury the critical items. A daily report of everything is read as nothing. • Set immediate notification rules for safety incidents, work stoppages and client escalations, independent of the daily report cycle. • Require the daily review to end in either an action today or a transfer to the weekly review, with the choice recorded. • Name the contact route and the response time expected outside working hours. • Track daily interventions to closure, since urgent items resolved verbally are the easiest to lose.
279 | Projects | Review monthly forecast-at-completion, margin and cash inputs with Finance | Chief Operations Officer (COO) | Trigger: When the daily, weekly or monthly project-control cadence becomes due. Action: The Chief Operations Officer (COO) completes “Review monthly forecast-at-completion, margin and cash inputs with Finance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified portfolio dashboard, decision log, recovery action and named due date. Control/Handoff: The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the daily, weekly or monthly project-control cadence becomes due. | The Chief Operations Officer (COO) completes “Review monthly forecast-at-completion, margin and cash inputs with Finance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified portfolio dashboard, decision log, recovery action and named due date. | The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO and Finance look monthly at what each project is now expected to cost and earn by completion, and what that does to cash. • Starts when: the monthly financial review cycle falls due. • How it runs: (1) cost to date and committed cost are established with Finance. (2) The forecast cost at completion is reviewed against the baseline with the reasons for movement. (3) The margin position is reviewed, including risk and contingency remaining. (4) Cash inputs are reviewed: billing, certification, collection and payment obligations. (5) Actions are agreed on cost recovery, billing and cash, with owners and dates. • Proof it happened: the monthly forecast review record with cost to date, forecast at completion against baseline, the margin position, the cash actions and their owners. • Where it usually breaks: the forecast is updated for cost incurred but not for committed and known future cost, so the forecast improves on paper while the real position worsens. | • Require the forecast to include committed cost and known future exposure, not cost incurred alone. A forecast built on incurred cost only always looks better than the real position. • Require risk and contingency remaining to be reported against risk remaining, since contingency spent early on retained risk is the standard warning sign. • Require movement from the previous forecast to be explained item by item, not as a single revised figure. • Review billing, certification and collection alongside cost, since a profitable project can still fail on cash. • Fix responsibility for the forecast with the Project Engineer, with Finance verifying rather than producing it.
280 | Projects | Approve cross-project manpower, plant and equipment reallocation | Chief Operations Officer (COO) | Trigger: When the daily, weekly or monthly project-control cadence becomes due. Action: The Chief Operations Officer (COO) completes “Approve cross-project manpower, plant and equipment reallocation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified portfolio dashboard, decision log, recovery action and named due date. Control/Handoff: The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the daily, weekly or monthly project-control cadence becomes due. | The Chief Operations Officer (COO) completes “Approve cross-project manpower, plant and equipment reallocation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified portfolio dashboard, decision log, recovery action and named due date. | The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO decides when people, plant or equipment must be moved from one project to another. • Starts when: a project requires resources beyond its allocation, or resources are idle elsewhere. • How it runs: (1) the request is assessed against the portfolio priorities. (2) The effect on the project losing the resource is assessed, including programme and contractual exposure. (3) The reallocation decision is taken within authority, with the trade-off recorded. (4) Both project teams are informed with dates and duration. (5) Programme and cost effects on both projects are recorded and reflected in reporting. • Proof it happened: the reallocation decision record with the priority basis, the assessed effect on both projects, and the dates and durations communicated. • Where it usually breaks: resources are moved to fix the loudest problem without recording the effect on the project they left, which then reports a delay with no traceable cause. | • Require the programme and cost effect on the project losing the resource to be assessed and recorded before the move. Otherwise that project reports an untraceable delay and the decision is never held accountable. • Require a return date and duration, so a temporary reallocation does not become permanent by default. • Assess against the portfolio priority list rather than against urgency of request. • Require contractual exposure, such as delay damages, to be considered before moving resources off a project. • Record the decision so repeated reallocation from the same project is visible.
281 | Projects | Monitor portfolio procurement, authority, client and technical dependencies | Chief Operations Officer (COO) | Trigger: When the daily, weekly or monthly project-control cadence becomes due. Action: The Chief Operations Officer (COO) completes “Monitor portfolio procurement, authority, client and technical dependencies” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified portfolio dashboard, decision log, recovery action and named due date. Control/Handoff: The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When the daily, weekly or monthly project-control cadence becomes due. | The Chief Operations Officer (COO) completes “Monitor portfolio procurement, authority, client and technical dependencies” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified portfolio dashboard, decision log, recovery action and named due date. | The COO reviews only controlled evidence; department dependencies are assigned to their CXO and threshold breaches escalate to CEO. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO keeps watch on the outside things projects depend on: procurement, authority approvals, client actions and design. • Starts when: the monitoring cycle runs, or a dependency is reported at risk. • How it runs: (1) critical dependencies per project are identified with their required dates. (2) Status is tracked against those dates across the portfolio. (3) Dependencies at risk are identified early with their delivery consequence. (4) Escalation is made to the owning department or the client, with the consequence stated. (5) Mitigation or resequencing is directed where a dependency will not be met. • Proof it happened: the dependency tracker across the portfolio with required dates, status, at-risk items escalated, and the mitigation directed. • Where it usually breaks: dependencies are tracked only when a project raises them, so the ones nobody is chasing fail silently and surface as a stoppage. | • Require a standing dependency register per project with required-on-site or required-by dates, reviewed on cycle rather than only when a project raises an issue. Unchased dependencies fail silently. • Require escalation to state the delivery consequence and the date by which the dependency must be resolved. • Track client and consultant dependencies with the same discipline as internal ones, since these carry contractual notice implications. • Name the owner of each dependency, including where it sits outside Projects. • Require formal notice to the client where a client-owned dependency is at risk, since late notice loses entitlement.
282 | Projects | Approve material programme recovery plans and controlled rebaselines | Chief Operations Officer (COO) | Trigger: When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. Action: The Chief Operations Officer (COO) completes “Approve material programme recovery plans and controlled rebaselines” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved recovery, hold, restart, reallocation or escalation decision. Control/Handoff: The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. | The Chief Operations Officer (COO) completes “Approve material programme recovery plans and controlled rebaselines” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved recovery, hold, restart, reallocation or escalation decision. | The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: when a project is significantly behind, the COO approves the recovery plan or a formal reset of the programme. • Starts when: a project reports delay beyond the threshold, or a rebaseline is requested. • How it runs: (1) the delay is analysed for cause, extent and critical path effect. (2) The recovery plan is assessed: resources, sequence changes, acceleration and their cost. (3) The contractual position is checked with the entitlement and notice position confirmed. (4) Recovery is approved, or a controlled rebaseline is approved where recovery is not achievable. (5) The decision, the new baseline and the cost effect are recorded and reported. • Proof it happened: the approved recovery plan or rebaseline with the delay analysis, the cost effect, the contractual position and the recorded approval. • Where it usually breaks: the programme is rebaselined to hide the delay rather than recover it, so the original baseline is lost and the delay becomes unprovable in a claim. | • Require the original baseline to be retained and the rebaseline recorded as a new version with the reason. Overwriting the baseline destroys the delay evidence needed for entitlement. • Require the contractual notice and entitlement position to be confirmed before recovery is approved, since acceleration without entitlement is cost the company absorbs. • Require the recovery plan to be costed, with the source of funding stated: contingency, entitlement or margin. • Set the delay threshold that triggers a formal recovery plan, so recovery is not left to judgement. • Require post-implementation review of whether recovery actually delivered, since unmonitored recovery plans are usually optimistic.
283 | Projects | Decide major construction-sequence, temporary-work and site-strategy exceptions | Chief Operations Officer (COO) | Trigger: When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. Action: The Chief Operations Officer (COO) completes “Decide major construction-sequence, temporary-work and site-strategy exceptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved recovery, hold, restart, reallocation or escalation decision. Control/Handoff: The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. | The Chief Operations Officer (COO) completes “Decide major construction-sequence, temporary-work and site-strategy exceptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved recovery, hold, restart, reallocation or escalation decision. | The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO decides the significant construction sequence, temporary works and site strategy questions that a project cannot settle itself. • Starts when: a project raises a sequence, temporary works or site strategy issue beyond its authority. • How it runs: (1) the issue is defined with the options and their consequences. (2) Technical input is obtained from the CTO where design or temporary works safety is affected. (3) The safety, cost, programme and contractual implications of each option are assessed. (4) The decision is taken within authority, or escalated where beyond it. (5) The decision and its basis are recorded and issued to the site. • Proof it happened: the recorded decision with the options assessed, the technical input obtained, and the decision basis issued to the site. • Where it usually breaks: a sequence or temporary works decision is taken commercially without technical verification, and the structural or safety consequence appears later on site. | • Require technical verification by the CTO for any decision affecting structural behaviour, temporary works or construction loading. These decisions cannot be taken on cost and programme grounds alone. • Require options with consequences to be presented, rather than a single recommendation, so the decision is genuine. • Require the safety implication to be assessed explicitly, and prohibit approval where it is unresolved. • Record the decision basis and issue it to the site, since site teams implement what they understand rather than what was decided. • Check the contractual implication, since sequence changes often carry entitlement in both directions.
284 | Projects | Resolve cross-department conflicts affecting project delivery | Chief Operations Officer (COO) | Trigger: When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. Action: The Chief Operations Officer (COO) completes “Resolve cross-department conflicts affecting project delivery” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved recovery, hold, restart, reallocation or escalation decision. Control/Handoff: The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. | The Chief Operations Officer (COO) completes “Resolve cross-department conflicts affecting project delivery” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved recovery, hold, restart, reallocation or escalation decision. | The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: when other departments and the project team are stuck with each other, the COO settles it. • Starts when: a cross-department conflict is escalated and is affecting delivery. • How it runs: (1) the conflict is defined with each side's position and the delivery impact. (2) The relevant facts and the applicable policy or contract position are established. (3) The affected department heads are engaged and a resolution sought at that level. (4) Where unresolved, the COO decides within authority or escalates to the CEO. (5) The resolution is recorded with actions and communicated to both sides. • Proof it happened: the conflict resolution record with the positions, the delivery impact, the decision and the actions communicated. • Where it usually breaks: the conflict is resolved for the immediate case but the underlying process gap is never fixed, so the same conflict recurs on the next project. | • Require recurring conflicts to be logged and the underlying process gap fixed, not just the immediate case resolved. The same interface conflict recurring across projects is a process failure. • Require the delivery impact to be quantified, so resolution is prioritised on consequence rather than on volume of complaint. • Attempt resolution at department head level first, with a stated time limit before escalation. • Record the decision and communicate it to both sides in writing, since verbal resolutions are remembered differently. • Name the route to the CEO where the conflict is between departments the COO does not control.
285 | Projects | Approve suspension and controlled restart of affected project work | Chief Operations Officer (COO) | Trigger: When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. Action: The Chief Operations Officer (COO) completes “Approve suspension and controlled restart of affected project work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved recovery, hold, restart, reallocation or escalation decision. Control/Handoff: The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. | The Chief Operations Officer (COO) completes “Approve suspension and controlled restart of affected project work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved recovery, hold, restart, reallocation or escalation decision. | The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO decides when to stop work and when it is safe and sensible to start again. • Starts when: conditions arise requiring work to stop, such as safety risk, unresolved design, non-payment, authority action or force majeure. • How it runs: (1) the trigger is assessed for the risk of continuing. (2) The scope of suspension is defined: which activities, which areas, which resources. (3) Suspension is decided and issued, with the client notified where contractually required. (4) Resources, site security, preservation of work and cost exposure are managed during suspension. (5) Restart conditions are defined, verified and approved before work resumes. • Proof it happened: the suspension decision with its scope, the client notice where required, and the verified restart approval with conditions met. • Where it usually breaks: work restarts on verbal instruction once the immediate problem looks resolved, without verifying that the restart conditions were actually met. | • Require restart to be authorised in writing against verified conditions, and prohibit verbal restart. Restarting on the assumption that the problem is resolved is how the same stoppage recurs. • Require contractual notice to the client where the suspension carries entitlement or obligation, since late notice loses both. • Require the cost of suspension to be recorded from day one, including standing time, plant and preservation. • Define who may suspend work immediately on safety grounds without prior approval, since safety stoppages cannot wait for authority. • State the preservation and security requirements for suspended work, as deterioration during suspension becomes a quality dispute.
286 | Projects | Escalate project exceptions beyond delegated authority to the CEO | Chief Operations Officer (COO) | Trigger: When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. Action: The Chief Operations Officer (COO) completes “Escalate project exceptions beyond delegated authority to the CEO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved recovery, hold, restart, reallocation or escalation decision. Control/Handoff: The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a programme, resource, safety, client, cost or cross-department exception exceeds routine project authority. | The Chief Operations Officer (COO) completes “Escalate project exceptions beyond delegated authority to the CEO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved recovery, hold, restart, reallocation or escalation decision. | The affected work remains controlled; cost, scope, legal, safety and technical approvals follow the Delegation of Authority before implementation. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: when something is beyond what the COO may decide, it goes to the CEO with a recommendation. • Starts when: a project matter exceeds the COO's delegated authority or carries company-level consequence. • How it runs: (1) the matter is assessed against the authority limits. (2) The issue is prepared with the facts, the options, the consequences and a recommendation. (3) The urgency and the decision deadline are stated. (4) The matter is escalated to the CEO through the defined route. (5) The decision is recorded, implemented and communicated to the project. • Proof it happened: the escalation record with the options and recommendation, the stated deadline, the CEO decision and its implementation. • Where it usually breaks: escalation happens after the decision window has passed, so the CEO is asked to endorse something that has effectively already happened. | • Require escalation while a genuine decision remains available, with the decision deadline stated. Escalating after the window has closed makes the CEO a spectator and removes the control. • Require the escalation to carry options, consequences and a recommendation, not a description of the problem. • State the matters that must always be escalated regardless of value, such as client claims, safety incidents and contract terminations. • Define the route and response expectation for urgent escalations outside meeting cycles. • Record the decision and its basis, since escalated decisions are the ones most often revisited.
287 | Projects | Approve project testing, commissioning and completion readiness | Chief Operations Officer (COO) | Trigger: When a project reaches testing, practical completion, DLP or final-closeout stage. Action: The Chief Operations Officer (COO) completes “Approve project testing, commissioning and completion readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved readiness decision, handover record, DLP action, resource-release or improvement record. Control/Handoff: COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a project reaches testing, practical completion, DLP or final-closeout stage. | The Chief Operations Officer (COO) completes “Approve project testing, commissioning and completion readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved readiness decision, handover record, DLP action, resource-release or improvement record. | COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO checks that a project is genuinely ready to be tested, commissioned and completed before those activities start. • Starts when: a project reports readiness for testing and commissioning. • How it runs: (1) physical completion of the relevant systems and works is verified. (2) The testing and commissioning plan, procedures and resources are confirmed in place. (3) Prerequisites are verified: power, water, access, permits, specialist attendance and witnessing arrangements. (4) Outstanding work and defects are assessed for whether they prevent meaningful testing. (5) Approval to proceed is given, or held with the conditions stated. • Proof it happened: the testing readiness review with physical completion verified, prerequisites confirmed and the approval or hold recorded. • Where it usually breaks: commissioning starts on incomplete systems to hold a programme date, so tests fail, get repeated, and the record of what was actually proven becomes unreliable. | • Prohibit starting commissioning on incomplete systems to protect a programme date. Repeated failed tests cost more time than the delay avoided and leave an unreliable record of what was proven. • Require prerequisites to be verified item by item, including permanent power, water, access, permits and specialist attendance. • Require outstanding work to be listed and assessed for whether it invalidates the tests. • Confirm witnessing and certification arrangements with the client and authority before starting. • Record the readiness decision, since commissioning delay is a frequent source of dispute.
288 | Projects | Confirm practical completion and formal client handover readiness | Chief Operations Officer (COO) | Trigger: When a project reaches testing, practical completion, DLP or final-closeout stage. Action: The Chief Operations Officer (COO) completes “Confirm practical completion and formal client handover readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved readiness decision, handover record, DLP action, resource-release or improvement record. Control/Handoff: COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a project reaches testing, practical completion, DLP or final-closeout stage. | The Chief Operations Officer (COO) completes “Confirm practical completion and formal client handover readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved readiness decision, handover record, DLP action, resource-release or improvement record. | COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO confirms the project is genuinely complete enough to hand to the client. • Starts when: a project reports readiness for practical completion and handover. • How it runs: (1) completion is verified against the contract requirements for practical completion. (2) Testing, commissioning and statutory certification are confirmed complete. (3) The outstanding items list is reviewed and assessed against what the contract permits at completion. (4) The handover dossier is confirmed complete: as-builts, manuals, warranties, certificates and training. (5) Handover readiness is confirmed, or held with conditions, and the client process initiated. • Proof it happened: the completion readiness confirmation with the contract requirements verified, the certification confirmed, the outstanding list assessed and the dossier confirmed. • Where it usually breaks: handover is pushed through with the dossier incomplete, and the retention and final payment then sit unreleased for months over missing documents. | • Require the handover dossier to be complete before handover is confirmed, including as-builts, manuals, warranties, certificates and training records. Incomplete dossiers hold retention and final payment for months. • Verify completion against the contract definition of practical completion, not against site opinion. • Require statutory and authority certification to be complete and in the dossier, since occupation depends on it. • Assess the outstanding items list against what the contract permits at completion, rather than accepting any list. • Record the readiness confirmation, as the completion date drives damages, retention and defects liability.
289 | Projects | Govern DLP defect closure, retention and outstanding obligations | Chief Operations Officer (COO) | Trigger: When a project reaches testing, practical completion, DLP or final-closeout stage. Action: The Chief Operations Officer (COO) completes “Govern DLP defect closure, retention and outstanding obligations” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved readiness decision, handover record, DLP action, resource-release or improvement record. Control/Handoff: COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a project reaches testing, practical completion, DLP or final-closeout stage. | The Chief Operations Officer (COO) completes “Govern DLP defect closure, retention and outstanding obligations” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved readiness decision, handover record, DLP action, resource-release or improvement record. | COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: after handover, the COO makes sure defects get fixed, retention is recovered and remaining obligations are met. • Starts when: the defects liability period begins after handover. • How it runs: (1) reported defects are logged with their date, nature and responsibility. (2) Defects are assessed for whether they are the company's liability or a client or usage matter. (3) Rectification is assigned, resourced and tracked to closure with evidence. (4) Retention release milestones and the outstanding obligations are tracked. (5) Period completion is confirmed, retention recovered and the closeout recorded. • Proof it happened: the defects register with responsibility assessed and rectification evidenced, and the retention recovery and period completion recorded. • Where it usually breaks: defects are rectified but the evidence is never returned to the client, so retention stays held despite the work being done. | • Require rectification evidence to be submitted formally to the client and acknowledged, since retention is released against acknowledged closure, not against work done. • Require each defect to be assessed for liability, distinguishing company defects from client damage, misuse or maintenance failure. • Track retention release milestones as receivables with owners, since unclaimed retention is the commonest silent loss after handover. • Require subcontractor and supplier warranty obligations to be enforced rather than absorbed by the company. • Record recurring defect types and return them to the CTO and Estimating as lessons.
290 | Projects | Approve operational closeout and release of project resources | Chief Operations Officer (COO) | Trigger: When a project reaches testing, practical completion, DLP or final-closeout stage. Action: The Chief Operations Officer (COO) completes “Approve operational closeout and release of project resources” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved readiness decision, handover record, DLP action, resource-release or improvement record. Control/Handoff: COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a project reaches testing, practical completion, DLP or final-closeout stage. | The Chief Operations Officer (COO) completes “Approve operational closeout and release of project resources” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved readiness decision, handover record, DLP action, resource-release or improvement record. | COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO formally closes the project down and releases its people, plant and site facilities. • Starts when: the project reaches operational completion or the defects period ends. • How it runs: (1) outstanding operational obligations are confirmed closed. (2) Resources are released in a planned sequence to their next assignment. (3) Plant, equipment, materials and temporary facilities are recovered, reconciled and demobilised. (4) Project records are archived to the standard and the location recorded. (5) Closeout is confirmed with Finance for final cost and account closure. • Proof it happened: the closeout record with obligations confirmed closed, resources released, assets reconciled, records archived and the financial closure confirmed. • Where it usually breaks: plant, materials and temporary facilities are left on a closed site with nobody accountable, and the loss surfaces only at asset verification. | • Require a physical reconciliation and recovery of plant, equipment, surplus material and temporary facilities before closeout, with a named owner. Assets left on closed sites are a recurring and untraced loss. • Require resource release to be planned to next assignments, since unplanned release creates idle cost. • Require project records to be archived to a defined standard, with the archive location recorded and the archive tested. • Confirm financial closure with Finance, including final cost, accruals and account closure. • Prohibit closeout while operational obligations remain open, and list them as a check.
291 | Projects | Sponsor lessons learned, root-cause actions and operating-process improvements | Chief Operations Officer (COO) | Trigger: When a project reaches testing, practical completion, DLP or final-closeout stage. Action: The Chief Operations Officer (COO) completes “Sponsor lessons learned, root-cause actions and operating-process improvements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved readiness decision, handover record, DLP action, resource-release or improvement record. Control/Handoff: COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. Continuity/Escalation: A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. Timing: To be confirmed. | When a project reaches testing, practical completion, DLP or final-closeout stage. | The Chief Operations Officer (COO) completes “Sponsor lessons learned, root-cause actions and operating-process improvements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved readiness decision, handover record, DLP action, resource-release or improvement record. | COO verifies technical, quality, commercial, client and record closure with the relevant functional owners before changing project status. | A CEO-approved executive delegate may coordinate routine portfolio actions, but reserved approvals, material programme/cost/client/safety decisions and authority exceptions escalate to the CEO. | To be confirmed. | • In plain words: the COO makes sure the company actually learns from its projects and changes the way it works. • Starts when: a project completes, or a significant failure or success warrants review. • How it runs: (1) the project outcome is reviewed against baseline for cost, programme, quality and safety. (2) Root causes of significant variances are established rather than symptoms recorded. (3) Lessons are captured with the specific process change each implies. (4) Actions are assigned to the owning function, such as the CTO, Estimating or Procurement, with dates. (5) Implementation is tracked and the change is verified on subsequent projects. • Proof it happened: the lessons learned record with root causes, the assigned process change actions with owners and dates, and verification of implementation. • Where it usually breaks: lessons are documented and filed, and nothing in the process changes, so the same failure repeats on the next project with a fresh lessons document. | • Require every lesson to convert into a named change to a document, standard or checklist, with an owner and a date. A filed lessons register with no process change is why the same failures repeat. • Require root cause analysis rather than symptom recording, since symptoms produce reminders and causes produce fixes. • Assign actions to the owning function, such as the CTO, Estimating or Procurement, not to Projects by default. • Verify on later projects that the change took effect, and report the verification. • Trigger a review for significant failures immediately rather than waiting for project completion, when memory and evidence are still fresh.
292 | Projects | Accept project assignment and verify the COO handover record | Project Engineer (Lead) | Trigger: When the COO assigns the project after accepting the CTO-to-COO handover. Action: The Project Engineer (Lead) completes “Accept project assignment and verify the COO handover record” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a controlled project setup, confirmed scope, ownership matrix and live baseline registers. Control/Handoff: Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the COO assigns the project after accepting the CTO-to-COO handover. | The Project Engineer (Lead) completes “Accept project assignment and verify the COO handover record” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a controlled project setup, confirmed scope, ownership matrix and live baseline registers. | Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the Project Engineer formally takes the project on and checks what the COO has actually handed over. • Starts when: the appointment to the project is made. • How it runs: (1) the appointment and the accountability and authority stated in it are reviewed. (2) The handover record is checked, including the conditions of acceptance and open gaps. (3) The technical, commercial and programme position is understood before work starts. (4) Questions and missing items are raised with the COO and the CTO before acceptance. (5) Acceptance is confirmed in writing with the known conditions and gaps recorded as inherited. • Proof it happened: the written acceptance with the handover record checked, the inherited conditions and gaps listed, and the queries raised before acceptance. • Where it usually breaks: the engineer accepts the project without reading the estimate assumptions and exclusions, then manages against a budget without knowing what it was built on. | • Require the estimate assumptions, exclusions and qualifications to be read and acknowledged at acceptance. Managing a budget without knowing its basis is the most common cause of unexplained overrun. • Require acceptance in writing, listing the inherited conditions and open gaps, so what was inherited is distinguishable from what the project caused. • Give the engineer a stated period to raise queries before acceptance is binding. • Require a documented handover meeting with the CTO and Estimating rather than a file transfer. • Record the authority limits applying on this project in the acceptance itself.
293 | Projects | Validate contract scope, IFC package, BOQ, permits and approved assumptions | Project Engineer (Lead) | Trigger: When the COO assigns the project after accepting the CTO-to-COO handover. Action: The Project Engineer (Lead) completes “Validate contract scope, IFC package, BOQ, permits and approved assumptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a controlled project setup, confirmed scope, ownership matrix and live baseline registers. Control/Handoff: Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the COO assigns the project after accepting the CTO-to-COO handover. | The Project Engineer (Lead) completes “Validate contract scope, IFC package, BOQ, permits and approved assumptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a controlled project setup, confirmed scope, ownership matrix and live baseline registers. | Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer checks the contract scope, the drawings, the BOQ, the permits and the assumptions all agree with each other. • Starts when: the project is accepted and the documents require validation before execution planning. • How it runs: (1) the contract scope is compared against the IFC drawings and the BOQ. (2) Discrepancies between the three are identified and listed. (3) Permit and approval status is checked against what the work requires, with conditions extracted. (4) The approved assumptions are checked against site reality where verifiable. (5) Discrepancies are raised formally with the CTO, the client or the COO as appropriate, before work is planned around them. • Proof it happened: the validation record comparing contract, drawings and BOQ, with the discrepancies listed, the permit conditions extracted and the issues formally raised. • Where it usually breaks: a discrepancy between the BOQ and the drawings is noticed and resolved by building what the drawings show, and the quantity difference becomes an unclaimed cost. | • Require any discrepancy between contract, drawings and BOQ to be raised formally before work proceeds. Building to the drawings and absorbing the quantity difference is unclaimed cost that is never recovered. • Require permit and approval conditions to be extracted into a tracked list, since conditions rather than the permits themselves are what get breached. • Require verification of assumed site conditions early, since assumptions about ground, access and existing services drive cost. • Set a deadline for validation before mobilisation, so discrepancies are found before resources are committed. • Record the validation as the basis of the project scope understanding.
294 | Projects | Establish project codes, controlled files, registers and baseline references | Project Engineer (Lead) | Trigger: When the COO assigns the project after accepting the CTO-to-COO handover. Action: The Project Engineer (Lead) completes “Establish project codes, controlled files, registers and baseline references” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a controlled project setup, confirmed scope, ownership matrix and live baseline registers. Control/Handoff: Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the COO assigns the project after accepting the CTO-to-COO handover. | The Project Engineer (Lead) completes “Establish project codes, controlled files, registers and baseline references” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a controlled project setup, confirmed scope, ownership matrix and live baseline registers. | Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer sets up the project's filing, coding and registers so information can be found and controlled. • Starts when: the project is accepted and setup is required before execution. • How it runs: (1) project and cost codes are established consistently with Finance. (2) The controlled file structure is created with access and naming conventions. (3) The registers are opened: drawings, RFIs, submittals, instructions, variations, NCRs and correspondence. (4) The baseline references are recorded: contract, drawing revisions, BOQ, programme and budget. (5) The setup is communicated to the team and the control responsibility named. • Proof it happened: the project setup record with codes established, the controlled file structure, the opened registers and the recorded baseline references. • Where it usually breaks: registers are created but no single person owns keeping them current, so they are complete for a month and useless by the third. | • Name one person accountable for keeping each register current, with a review cycle. Registers without an owner are complete for a month and useless thereafter. • Establish cost codes with Finance at setup, since cost coded inconsistently cannot be analysed later. • Record the baseline references explicitly: contract version, drawing revisions, BOQ, programme and budget, as these are the comparison points for the whole project. • Set the file structure and naming convention from a standard template rather than per project. • Require registers to be held where the team and head office can both access them, not on a site machine.
295 | Projects | Prepare project organisation, RACI and communication matrix | Project Engineer (Lead) | Trigger: When the COO assigns the project after accepting the CTO-to-COO handover. Action: The Project Engineer (Lead) completes “Prepare project organisation, RACI and communication matrix” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a controlled project setup, confirmed scope, ownership matrix and live baseline registers. Control/Handoff: Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the COO assigns the project after accepting the CTO-to-COO handover. | The Project Engineer (Lead) completes “Prepare project organisation, RACI and communication matrix” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a controlled project setup, confirmed scope, ownership matrix and live baseline registers. | Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer sets out who does what on the project and how information flows. • Starts when: the project team is being formed at mobilisation. • How it runs: (1) the project organisation is defined with the roles required. (2) Responsibility is assigned per activity, distinguishing who does it, who approves it, who is consulted and who is informed. (3) Interfaces with other departments and with the client and consultants are defined. (4) The communication matrix states who communicates with whom, on what, and in what form. (5) The matrix is issued to the team, the client and the consultants as required. • Proof it happened: the issued project organisation, RACI and communication matrix with the interfaces and communication routes defined. • Where it usually breaks: several people communicate directly with the client on the same subject, so the client receives inconsistent positions and uses them against the company. | • Name single points of contact for client and consultant communication per subject, and require all others to route through them. Multiple voices to the client produce inconsistent positions that are later used against the company. • Require the RACI to name one approver per activity, since two approvers means neither is accountable. • Define the internal interfaces with Procurement, Finance, QHSE and the CTO explicitly. • State which communications must be in writing for contractual reasons, and which may be verbal. • Reissue the matrix when the team changes, since project teams change frequently.
296 | Projects | Open project risk, constraint, decision and assumption registers | Project Engineer (Lead) | Trigger: When the COO assigns the project after accepting the CTO-to-COO handover. Action: The Project Engineer (Lead) completes “Open project risk, constraint, decision and assumption registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a controlled project setup, confirmed scope, ownership matrix and live baseline registers. Control/Handoff: Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the COO assigns the project after accepting the CTO-to-COO handover. | The Project Engineer (Lead) completes “Open project risk, constraint, decision and assumption registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a controlled project setup, confirmed scope, ownership matrix and live baseline registers. | Missing IFC, contract, permit, BOQ, payment or access inputs are recorded and returned; execution does not proceed on an uncontrolled assumption. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer opens the registers that record risks, constraints, decisions and assumptions from the start. • Starts when: the project is set up and execution planning begins. • How it runs: (1) the risk register is opened with the inherited estimate risks carried in. (2) The constraint register records what limits the work: access, approvals, resources, dependencies. (3) The decision register records decisions taken, by whom and on what basis. (4) The assumption register records what is being assumed and what happens if it proves wrong. (5) Owners and review cycles are set for each register. • Proof it happened: the four opened registers with the inherited risks and assumptions carried in, owners named and review cycles set. • Where it usually breaks: the estimate risk register is not carried into the project, so the project starts with a blank risk register and rediscovers risks that were already priced. | • Require the estimate risk and assumption registers to be carried into the project registers at setup. Starting with a blank register discards the exposure that was already identified and priced. • Require a decision register recording who decided what, when and on what basis, since project decisions are the hardest thing to reconstruct later. • Set review cycles per register and require them to be reviewed in the weekly project meeting. • Require each risk to carry an owner, a mitigation and a trigger for escalation. • Require assumptions to state the consequence if they prove wrong, since that determines what to verify first.
297 | Projects | Prepare the project work breakdown structure and baseline programme | Project Engineer (Lead) | Trigger: When the project is accepted and mobilisation planning is authorised. Action: The Project Engineer (Lead) completes “Prepare the project work breakdown structure and baseline programme” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved baseline programme, mobilisation plan, resource plan and readiness schedule. Control/Handoff: Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the project is accepted and mobilisation planning is authorised. | The Project Engineer (Lead) completes “Prepare the project work breakdown structure and baseline programme” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved baseline programme, mobilisation plan, resource plan and readiness schedule. | Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer breaks the work into manageable parts and builds the programme that everything is measured against. • Starts when: the scope is validated and planning can begin. • How it runs: (1) the work breakdown structure is prepared, aligned to the BOQ and cost codes. (2) Activities, durations and logic are built with input from the site team and subcontractors. (3) Resources and productivity assumptions are attached to the activities. (4) The critical path and float are identified, and the programme is checked against contract milestones. (5) The baseline programme is approved, issued and locked as the comparison point. • Proof it happened: the approved baseline programme with the work breakdown structure aligned to the BOQ, the resourced activities and the identified critical path. • Where it usually breaks: the programme is built to fit the contract end date rather than from realistic durations, so it is unachievable from the day it is issued and stops being used. | • Require durations to be built from resources and productivity rather than reverse-engineered from the contract end date. A programme built backwards from the deadline is abandoned within weeks and then controls nothing. • Require the work breakdown structure to align with the BOQ and cost codes, so progress and cost can be compared. • Require site team and key subcontractor input into the logic, since a programme they did not build is a programme they do not follow. • Require the critical path and float to be identified and reported, not just the bar chart. • Lock the approved baseline and control later changes as recorded revisions.
298 | Projects | Prepare mobilisation, access, temporary-facility and site-logistics plans | Project Engineer (Lead) | Trigger: When the project is accepted and mobilisation planning is authorised. Action: The Project Engineer (Lead) completes “Prepare mobilisation, access, temporary-facility and site-logistics plans” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved baseline programme, mobilisation plan, resource plan and readiness schedule. Control/Handoff: Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the project is accepted and mobilisation planning is authorised. | The Project Engineer (Lead) completes “Prepare mobilisation, access, temporary-facility and site-logistics plans” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved baseline programme, mobilisation plan, resource plan and readiness schedule. | Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer plans how the site will be set up, accessed and organised. • Starts when: mobilisation is approved and site setup requires planning. • How it runs: (1) site access, entry points, roads and traffic routing are planned. (2) Temporary facilities are planned: offices, stores, welfare, power, water, drainage and communications. (3) Site logistics are planned: material laydown, storage, waste, vertical transport and crane positions. (4) The layout is checked against the construction sequence so facilities do not sit where permanent work must go. (5) The plans are approved, issued and set up, with statutory and client requirements met. • Proof it happened: the approved site logistics and temporary facilities layout checked against the construction sequence, with the statutory requirements met. • Where it usually breaks: temporary facilities are placed where permanent work is later required, so everything has to be moved mid-project at unbudgeted cost. | • Require the site layout to be checked against the full construction sequence before setup, including later phases. Relocating facilities mid-project is a predictable and avoidable cost. • Require statutory welfare, safety and environmental requirements to be included in the layout, not added afterwards. • Plan material laydown and storage against delivery volumes and the required-on-site schedule. • Coordinate access and traffic routing with the client and neighbours where the site is constrained or occupied. • Record the approved layout, since access and space disruption are frequent claim subjects.
299 | Projects | Prepare manpower, subcontractor, plant and equipment resource plans | Project Engineer (Lead) | Trigger: When the project is accepted and mobilisation planning is authorised. Action: The Project Engineer (Lead) completes “Prepare manpower, subcontractor, plant and equipment resource plans” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved baseline programme, mobilisation plan, resource plan and readiness schedule. Control/Handoff: Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the project is accepted and mobilisation planning is authorised. | The Project Engineer (Lead) completes “Prepare manpower, subcontractor, plant and equipment resource plans” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved baseline programme, mobilisation plan, resource plan and readiness schedule. | Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer plans what people, subcontractors and plant are needed, and when. • Starts when: the baseline programme is established and resources require planning. • How it runs: (1) manpower requirements are calculated from the programme by trade and period. (2) Subcontract packages are defined with their required start and duration. (3) Plant and equipment requirements are set with their on-site periods. (4) The resource plan is checked against actual availability and the portfolio allocation. (5) Shortfalls are identified and raised before they affect the programme. • Proof it happened: the resource plan by period covering manpower, subcontractors and plant, checked against availability with the shortfalls raised. • Where it usually breaks: the resource plan is built from the programme without checking whether those resources actually exist, so it is a requirement list rather than a plan. | • Require the resource plan to be reconciled against confirmed availability and the portfolio allocation, with shortfalls raised as risks. A resource requirement that is not confirmed available is not a plan. • Require the plan to be phased by period rather than stated as totals, since peak demand is what fails. • Identify the resources that require long notice, such as specialist trades and major plant, with their order dates. • Require subcontract package start dates to work back to award and mobilisation lead times. • Update the plan with each programme revision, since resource plans are usually left behind.
300 | Projects | Prepare procurement-package, long-lead and required-on-site schedules | Project Engineer (Lead) | Trigger: When the project is accepted and mobilisation planning is authorised. Action: The Project Engineer (Lead) completes “Prepare procurement-package, long-lead and required-on-site schedules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved baseline programme, mobilisation plan, resource plan and readiness schedule. Control/Handoff: Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the project is accepted and mobilisation planning is authorised. | The Project Engineer (Lead) completes “Prepare procurement-package, long-lead and required-on-site schedules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved baseline programme, mobilisation plan, resource plan and readiness schedule. | Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer works out what has to be bought, what takes a long time to arrive, and when each item is needed on site. • Starts when: the baseline programme is established and procurement requires scheduling. • How it runs: (1) procurement packages are defined from the scope and the BOQ. (2) The required-on-site date is set per package from the programme. (3) Lead times are established and worked back to the order and approval dates. (4) Long lead items are identified and flagged for immediate action. (5) The schedule is issued to Procurement and tracked as a project dependency. • Proof it happened: the procurement schedule with packages, required-on-site dates, lead times worked back to order dates, and the long lead items flagged. • Where it usually breaks: the required-on-site date is treated as the order date, so long lead items are ordered far too late and drive the programme. | • Require order dates to be calculated back from required-on-site dates using submittal, approval, manufacture and shipping lead times. Treating the need date as the order date is the standard cause of long lead delay. • Require long lead items to be identified in the first weeks and escalated if not ordered by their date. • Include submittal and approval time in the lead time, since technical approval regularly takes longer than manufacture. • Issue the schedule to Procurement formally and review it as a standing item. • Recalculate the schedule when the programme changes, since order dates move with it.
301 | Projects | Prepare method-statement, inspection, submittal and authority schedules | Project Engineer (Lead) | Trigger: When the project is accepted and mobilisation planning is authorised. Action: The Project Engineer (Lead) completes “Prepare method-statement, inspection, submittal and authority schedules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved baseline programme, mobilisation plan, resource plan and readiness schedule. Control/Handoff: Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the project is accepted and mobilisation planning is authorised. | The Project Engineer (Lead) completes “Prepare method-statement, inspection, submittal and authority schedules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved baseline programme, mobilisation plan, resource plan and readiness schedule. | Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer schedules the method statements, inspections, submittals and authority approvals the work needs. • Starts when: the programme is established and technical and approval activities require scheduling. • How it runs: (1) the required method statements are identified per activity with their approval dates. (2) The inspection and test plan is prepared with hold points and witnessing requirements. (3) Material and shop drawing submittals are scheduled back from their need dates. (4) Authority submissions and inspections are scheduled with their lead times. (5) The schedules are issued and tracked, with approvals treated as programme predecessors. • Proof it happened: the schedules for method statements, inspections, submittals and authority approvals, with dates worked back from need dates and tracked. • Where it usually breaks: approvals and submittals are not shown on the programme as activities, so work is planned to start on a date when nothing has been approved. | • Require submittals, approvals and inspections to appear on the programme as activities with durations. Work planned to start before its approvals exist is the commonest planning failure on site. • Require the inspection and test plan to define hold points where work may not proceed without inspection, with the witnessing party named. • Require method statements to be approved before the activity starts, and prohibit retrospective approval. • Schedule authority submissions with realistic authority response times rather than optimistic ones. • Track approval status weekly, since approvals are the quietest source of delay.
302 | Projects | Prepare rolling two-week and four-week lookahead plans and work-front releases | Project Engineer (Lead) | Trigger: When the project is accepted and mobilisation planning is authorised. Action: The Project Engineer (Lead) completes “Prepare rolling two-week and four-week lookahead plans and work-front releases” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved baseline programme, mobilisation plan, resource plan and readiness schedule. Control/Handoff: Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the project is accepted and mobilisation planning is authorised. | The Project Engineer (Lead) completes “Prepare rolling two-week and four-week lookahead plans and work-front releases” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved baseline programme, mobilisation plan, resource plan and readiness schedule. | Project Engineer coordinates QHSE, Technical, Procurement, Finance and site owners; blocking readiness gaps hold the affected start. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer plans the next two and four weeks in detail and releases work only when it can actually be done. • Starts when: the weekly planning cycle runs. • How it runs: (1) the activities due in the next two and four weeks are extracted from the programme. (2) Each activity is checked for readiness: drawings, materials, approvals, resources, access and preceding work. (3) Constraints are identified and assigned for removal before the activity is due. (4) Only ready activities are released as work fronts. (5) Plan reliability is measured against what was completed, and the causes of failure recorded. • Proof it happened: the two and four week lookahead plans with readiness checked per activity, the constraints assigned for removal, and the measured plan reliability. • Where it usually breaks: activities are released without a readiness check, so crews are sent to work fronts that are not ready and the time is lost regardless. | • Require a readiness check on every activity before release, covering drawings, materials, approvals, resources, access and preceding work. Releasing unready work fronts wastes crew time that cannot be recovered. • Measure plan reliability, such as the percentage of planned activities completed, and record the reasons for failure. Without this the same constraints recur every week. • Require constraints to be assigned to a named owner with a removal date ahead of the activity. • Use the four week view for constraint removal and the two week view for commitment. • Require subcontractor participation in the lookahead, since they control much of the readiness.
303 | Projects | Chair the daily site coordination and constraint-removal meeting | Project Engineer (Lead) | Trigger: When a workday, lookahead activity or controlled site instruction requires coordination. Action: The Project Engineer (Lead) completes “Chair the daily site coordination and constraint-removal meeting” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a released work front, current register, coordinated instruction and complete daily evidence. Control/Handoff: Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When a workday, lookahead activity or controlled site instruction requires coordination. | The Project Engineer (Lead) completes “Chair the daily site coordination and constraint-removal meeting” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a released work front, current register, coordinated instruction and complete daily evidence. | Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer runs the daily site meeting to remove whatever is blocking work. • Starts when: the daily coordination meeting falls due, normally at the start of the working day. • How it runs: (1) the previous day's planned versus actual output is reviewed briefly. (2) Today's work fronts, crews and equipment are confirmed. (3) Constraints and clashes are raised: access, materials, drawings, approvals, interfaces. (4) Actions are assigned to named people with a same-day or dated deadline. (5) Safety and quality points for the day are covered and the meeting record kept short and issued. • Proof it happened: the daily meeting record with the previous day's output, today's work fronts confirmed, the constraints raised and the actions assigned with owners. • Where it usually breaks: the meeting becomes a long status report, so it starts late, runs long, and the constraint removal actions are never assigned to anyone specific. | • Keep the meeting short and focused on constraint removal, with every action assigned to a named person and a deadline. A daily meeting that reports status delays the start of work and removes no constraints. • Fix the time, duration and attendance, including subcontractor supervision. • Require open actions from the previous day to be reviewed first, so nothing carries silently. • Cover safety and quality points for the day's specific activities rather than generally. • Keep a brief written record, since daily coordination records are valuable delay evidence.
304 | Projects | Release and coordinate civil and MEP work fronts | Project Engineer (Lead) | Trigger: When a workday, lookahead activity or controlled site instruction requires coordination. Action: The Project Engineer (Lead) completes “Release and coordinate civil and MEP work fronts” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a released work front, current register, coordinated instruction and complete daily evidence. Control/Handoff: Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When a workday, lookahead activity or controlled site instruction requires coordination. | The Project Engineer (Lead) completes “Release and coordinate civil and MEP work fronts” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a released work front, current register, coordinated instruction and complete daily evidence. | Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer releases the civil and MEP work fronts and keeps the two disciplines out of each other's way. • Starts when: work fronts are ready for release under the lookahead plan. • How it runs: (1) work front readiness is confirmed for both disciplines including preceding work. (2) The sequence between civil and MEP is confirmed, particularly embedded items, sleeves and penetrations. (3) The front is released to the responsible engineer or supervisor with the drawings and method confirmed. (4) Shared access, services and equipment are coordinated between disciplines. (5) Progress and interface issues are monitored and resolved as work proceeds. • Proof it happened: the work front release records with readiness and sequence confirmed for both disciplines and the interface coordination recorded. • Where it usually breaks: a civil element is closed before MEP sleeves and embedded items are installed, so it has to be broken out and reinstated at direct cost. | • Require MEP embedded items, sleeves and penetrations to be signed off as installed before any civil element is closed, as a hold point. Breaking out and reinstating completed work is pure avoidable loss. • Require the release record to name the drawings and revisions the front is released against. • Confirm preceding work completion and quality acceptance before release, not just physical availability. • Coordinate shared access, hoisting and services between disciplines in the release, since these clash predictably. • Require interface issues to be raised the same day, since they compound quickly.
305 | Projects | Coordinate subcontractors, logistics, plant and shared site access | Project Engineer (Lead) | Trigger: When a workday, lookahead activity or controlled site instruction requires coordination. Action: The Project Engineer (Lead) completes “Coordinate subcontractors, logistics, plant and shared site access” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a released work front, current register, coordinated instruction and complete daily evidence. Control/Handoff: Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When a workday, lookahead activity or controlled site instruction requires coordination. | The Project Engineer (Lead) completes “Coordinate subcontractors, logistics, plant and shared site access” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a released work front, current register, coordinated instruction and complete daily evidence. | Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer coordinates the subcontractors, deliveries, plant and shared access so they do not obstruct each other. • Starts when: multiple subcontractors, deliveries or plant movements require coordination. • How it runs: (1) subcontractor activities and locations are planned against each other by period. (2) Delivery slots, offloading and storage are scheduled to avoid congestion. (3) Shared plant, hoisting and access are allocated by time and location. (4) Conflicts are resolved by priority against the programme, not by who is loudest. (5) The coordination is recorded and communicated to all parties. • Proof it happened: the coordination record with subcontractor activities planned, delivery slots scheduled, shared resources allocated and the conflicts resolved by programme priority. • Where it usually breaks: shared access and hoisting are allocated informally on the day, so the critical activity waits while a non-critical one uses the equipment. | • Allocate shared access, hoisting and plant in advance by programme priority rather than on the day by request. Informal allocation gives the equipment to whoever asks first, not to the critical activity. • Require booked delivery slots with offloading and storage confirmed, since uncoordinated deliveries congest the site and cause standing time. • Record the coordination decisions and issue them, since subcontractor claims frequently rest on access disruption. • Require subcontractors to submit their short term plans so coordination is based on their intentions. • Name who resolves conflicts on site and within what limits.
306 | Projects | Maintain RFI, submittal, inspection, NCR and action registers | Project Engineer (Lead) | Trigger: When a workday, lookahead activity or controlled site instruction requires coordination. Action: The Project Engineer (Lead) completes “Maintain RFI, submittal, inspection, NCR and action registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a released work front, current register, coordinated instruction and complete daily evidence. Control/Handoff: Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When a workday, lookahead activity or controlled site instruction requires coordination. | The Project Engineer (Lead) completes “Maintain RFI, submittal, inspection, NCR and action registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a released work front, current register, coordinated instruction and complete daily evidence. | Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer keeps the project registers current so nothing raised gets lost. • Starts when: RFIs, submittals, inspections, non-conformances or actions are raised during execution. • How it runs: (1) each item is logged on the correct register when raised, with the date and the raiser. (2) The required response date and the owner are recorded. (3) Status is updated as items progress, with the response and its effect recorded. (4) Overdue items are reported and escalated on a fixed cycle. (5) Items are closed only against evidence, and the registers are reported in the weekly meeting. • Proof it happened: the current registers with items logged on being raised, response dates and owners recorded, overdue items escalated and closure evidenced. • Where it usually breaks: registers are updated in batches before meetings rather than as items arise, so overdue items are only noticed once they have already caused delay. | • Require items to be logged when raised rather than updated in batches before meetings. Batch updating means overdue items are discovered only after they have caused delay. • Require every item to carry a required response date, an owner and an escalation trigger when overdue. • Require closure against evidence, since items closed on assurance reopen later. • Report overdue RFIs, submittals and NCRs as a standing weekly item with their programme impact. • Keep the registers accessible to head office as well as site, so they survive site team changes.
307 | Projects | Control latest approved drawings and prevent superseded site use | Project Engineer (Lead) | Trigger: When a workday, lookahead activity or controlled site instruction requires coordination. Action: The Project Engineer (Lead) completes “Control latest approved drawings and prevent superseded site use” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a released work front, current register, coordinated instruction and complete daily evidence. Control/Handoff: Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When a workday, lookahead activity or controlled site instruction requires coordination. | The Project Engineer (Lead) completes “Control latest approved drawings and prevent superseded site use” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a released work front, current register, coordinated instruction and complete daily evidence. | Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer makes sure the site is building from the latest approved drawings and that old ones are removed. • Starts when: drawings are issued or revised for construction. • How it runs: (1) received drawings are registered with their revision and issue date. (2) The current revision is confirmed as approved for construction before issue to the site. (3) Drawings are issued to controlled distribution points with receipt recorded. (4) Superseded revisions are physically withdrawn or clearly marked, with withdrawal confirmed. (5) The revision status is checked before each activity starts, and the register is reconciled periodically. • Proof it happened: the drawing register showing current revisions issued with receipts and superseded revisions confirmed withdrawn. • Where it usually breaks: the new revision is issued but the old one is never physically withdrawn, so a crew builds from the drawing pinned up in their area. | • Require withdrawal of superseded drawings to be confirmed by the site as a completed step, not assumed on issue of the new revision. Work built from a superseded drawing is the most expensive documentation failure on site. • Require a revision check before each activity starts, recorded on the work release. • Control the number of distribution points, since uncontrolled copies cannot be withdrawn. • Reconcile the register against the physical drawings on site periodically. • Prohibit construction from unapproved or preliminary drawings, and name who may authorise an exception.
308 | Projects | Consolidate daily progress, manpower, material and equipment records | Project Engineer (Lead) | Trigger: When a workday, lookahead activity or controlled site instruction requires coordination. Action: The Project Engineer (Lead) completes “Consolidate daily progress, manpower, material and equipment records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a released work front, current register, coordinated instruction and complete daily evidence. Control/Handoff: Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When a workday, lookahead activity or controlled site instruction requires coordination. | The Project Engineer (Lead) completes “Consolidate daily progress, manpower, material and equipment records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a released work front, current register, coordinated instruction and complete daily evidence. | Only latest approved documents are used; unresolved site interface or missing information is logged and escalated before affected work proceeds. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer consolidates the daily records of progress, manpower, materials and equipment. • Starts when: the daily reporting cycle runs. • How it runs: (1) daily progress is collected by activity and location from the supervisors. (2) Manpower actually deployed is recorded by trade and location. (3) Material received and consumed is recorded. (4) Equipment deployed, working and idle is recorded with the reasons for idleness. (5) The consolidated record is checked for completeness, issued and filed as project evidence. • Proof it happened: the consolidated daily records covering progress, manpower, materials and equipment with idle time and its causes recorded. • Where it usually breaks: the daily record is filled in as a formality with round numbers, so it cannot support a delay or disruption claim when one is needed. | • Require daily records to be specific by activity and location, with actual manpower and idle time and causes recorded. Rounded formality records are worthless as delay and disruption evidence, which is their main value. • Require the record to note events affecting progress: weather, access denial, late information, client instructions. • Require supervisor sign-off on the source records, since consolidated records built from memory are unreliable. • Fix a daily deadline for submission, and treat missing records as a reportable failure. • Store records so they can be retrieved by date and location years later, as claims arise long afterwards.
309 | Projects | Submit verified procurement requisitions linked to IFC, BOQ and need dates | Project Engineer (Lead) | Trigger: When the programme creates a material, subcontract, billing or payment-support requirement. Action: The Project Engineer (Lead) completes “Submit verified procurement requisitions linked to IFC, BOQ and need dates” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified requisition, delivery/certification record, quantity review or finance handoff. Control/Handoff: Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the programme creates a material, subcontract, billing or payment-support requirement. | The Project Engineer (Lead) completes “Submit verified procurement requisitions linked to IFC, BOQ and need dates” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified requisition, delivery/certification record, quantity review or finance handoff. | Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer raises the purchase requests, checked against the drawings, the BOQ and the date the material is needed. • Starts when: material or subcontract requirements arise under the procurement schedule. • How it runs: (1) the requirement is verified against the IFC drawings and the BOQ quantity. (2) The specification and any approved submittal are confirmed. (3) The required-on-site date is stated with the lead time considered. (4) The requisition is checked against the budget and the remaining quantity. (5) The requisition is approved within authority and submitted to Procurement, then tracked. • Proof it happened: the approved requisition verified against drawings and BOQ, with the specification confirmed, the required date stated and the budget checked. • Where it usually breaks: requisitions are raised on estimated quantities without checking against the BOQ allowance, so the project over-orders and the surplus becomes waste and cost. | • Require each requisition to state the BOQ allowance, the quantity already ordered and the remaining balance. Ordering without this control is how projects quietly exceed their material budget. • Require verification against the current IFC drawing revision, so material is not ordered to a superseded design. • Require the approved submittal reference where the material requires technical approval. • State the required-on-site date rather than as soon as possible, since undated urgency is ignored. • Require approval within authority before submission to Procurement, and prohibit verbal ordering direct to suppliers.
310 | Projects | Coordinate procurement status, expediting and critical deliveries | Project Engineer (Lead) | Trigger: When the programme creates a material, subcontract, billing or payment-support requirement. Action: The Project Engineer (Lead) completes “Coordinate procurement status, expediting and critical deliveries” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified requisition, delivery/certification record, quantity review or finance handoff. Control/Handoff: Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the programme creates a material, subcontract, billing or payment-support requirement. | The Project Engineer (Lead) completes “Coordinate procurement status, expediting and critical deliveries” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified requisition, delivery/certification record, quantity review or finance handoff. | Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer chases procurement status and makes sure critical deliveries arrive when needed. • Starts when: requisitions are with Procurement and deliveries are pending against the programme. • How it runs: (1) status is tracked per package: enquiry, award, submittal, approval, manufacture, dispatch, delivery. (2) Items at risk against their required date are identified early. (3) Expediting is coordinated with Procurement, with the programme consequence stated. (4) Delivery dates are confirmed and site receipt arrangements prepared. (5) Items that will not meet their date are escalated with resequencing or mitigation proposed. • Proof it happened: the procurement status tracker per package with at-risk items identified, the expediting coordinated and the escalations with mitigation. • Where it usually breaks: status is tracked as ordered or not ordered, so a submittal stuck awaiting approval for weeks is invisible until the delivery date is missed. | • Track status through the full chain including submittal and approval stages, not order placed and delivered. Items stuck awaiting technical approval are invisible in a two-state tracker until the date is missed. • Require escalation to state the programme consequence and the date beyond which mitigation is impossible. • Require confirmed delivery dates from suppliers rather than assumed lead times. • Prepare site receipt, offloading and storage before delivery, since arrival without preparation causes damage and standing time. • Review procurement status as a standing weekly item with Procurement present.
311 | Projects | Certify site receipt, allocation and acceptance evidence for project materials | Project Engineer (Lead) | Trigger: When the programme creates a material, subcontract, billing or payment-support requirement. Action: The Project Engineer (Lead) completes “Certify site receipt, allocation and acceptance evidence for project materials” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified requisition, delivery/certification record, quantity review or finance handoff. Control/Handoff: Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the programme creates a material, subcontract, billing or payment-support requirement. | The Project Engineer (Lead) completes “Certify site receipt, allocation and acceptance evidence for project materials” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified requisition, delivery/certification record, quantity review or finance handoff. | Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer certifies that material actually arrived, was accepted and went where it should. • Starts when: project materials are delivered to site. • How it runs: (1) delivery is checked against the order for quantity, specification and condition. (2) Material is inspected against the approved submittal and any test certificate. (3) Acceptance, partial acceptance or rejection is recorded with the reasons. (4) Accepted material is recorded into store with its location and allocation. (5) The receipt evidence is certified and passed to Finance and Procurement for payment processing. • Proof it happened: the certified receipt records with the delivery checked against order and submittal, the acceptance decision recorded and the allocation logged. • Where it usually breaks: delivery notes are signed without checking quantity and specification, so a short or non-conforming delivery is paid for and discovered at installation. | • Prohibit signing delivery notes before checking quantity, specification and condition, and require any discrepancy to be noted on the note itself. A clean signature removes the ability to reject or claim later. • Require inspection against the approved submittal and test certificates for specified materials. • Require rejected material to be recorded, segregated and removed, with the supplier notified in writing. • Record the storage location and allocation, since unallocated material on a large site is effectively lost. • Name who may certify receipt for payment, and separate that person from the one placing the order where possible.
312 | Projects | Review Quantity Surveyor measurements, variations and billing support | Project Engineer (Lead) | Trigger: When the programme creates a material, subcontract, billing or payment-support requirement. Action: The Project Engineer (Lead) completes “Review Quantity Surveyor measurements, variations and billing support” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified requisition, delivery/certification record, quantity review or finance handoff. Control/Handoff: Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the programme creates a material, subcontract, billing or payment-support requirement. | The Project Engineer (Lead) completes “Review Quantity Surveyor measurements, variations and billing support” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified requisition, delivery/certification record, quantity review or finance handoff. | Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer reviews the surveyor's measurements, variations and billing support before they go out. • Starts when: the Quantity Surveyor submits measurements, variation valuations or billing support. • How it runs: (1) measured quantities are checked against the work actually completed and accepted. (2) Variation valuations are checked against the instruction, the scope and the records. (3) Supporting evidence is checked for completeness: records, drawings, approvals and instructions. (4) Discrepancies are resolved with the surveyor before submission. (5) The engineer confirms the technical accuracy and the submission proceeds. • Proof it happened: the review record with quantities verified against completed and accepted work, the variations checked against instructions, and the confirmation of technical accuracy. • Where it usually breaks: quantities are certified against work completed rather than work completed and quality accepted, so payment is claimed for work that is later rejected. | • Require measurement to be certified against work that is both complete and quality accepted, since certifying unaccepted work creates a claim that is later reversed. • Require variation valuations to reference the written instruction and prohibit valuing verbal instructions until confirmed. • Require supporting evidence to be attached at submission, since evidence assembled later is rarely accepted. • Separate the roles of measuring and technically certifying, so the same person does not do both. • Resolve discrepancies before submission, since a corrected claim damages credibility on all subsequent ones.
313 | Projects | Certify supplier and subcontractor operational evidence for payment processing | Project Engineer (Lead) | Trigger: When the programme creates a material, subcontract, billing or payment-support requirement. Action: The Project Engineer (Lead) completes “Certify supplier and subcontractor operational evidence for payment processing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified requisition, delivery/certification record, quantity review or finance handoff. Control/Handoff: Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the programme creates a material, subcontract, billing or payment-support requirement. | The Project Engineer (Lead) completes “Certify supplier and subcontractor operational evidence for payment processing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified requisition, delivery/certification record, quantity review or finance handoff. | Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer confirms that suppliers and subcontractors actually did the work before they get paid. • Starts when: supplier or subcontractor payment applications require operational certification. • How it runs: (1) the claimed work or delivery is verified against site records. (2) Quality acceptance and any required testing are confirmed. (3) Compliance obligations are checked: safety, documentation, insurance and statutory requirements. (4) Deductions are identified: defects, back charges, damage and unreturned items. (5) Certification is issued for the verified amount with the reasons for any reduction recorded. • Proof it happened: the certification record with the work verified against site records, the quality and compliance confirmed, and the deductions identified with reasons. • Where it usually breaks: certification is given on the subcontractor's own figures to keep them working, and the overpayment cannot be recovered once they leave the site. | • Require certification against site records rather than the applicant's figures, since overpayment to a subcontractor is rarely recovered once they demobilise. • Require quality acceptance and outstanding defects to be considered before certification, not after. • Require back charges, damage and unreturned items to be identified and deducted at certification. • Check compliance obligations, including safety documentation and insurance validity, as a condition of certification. • Record the reasons for any reduction in writing, since undocumented deductions become disputes.
314 | Projects | Coordinate project billing, collection and cash-priority actions with Finance | Project Engineer (Lead) | Trigger: When the programme creates a material, subcontract, billing or payment-support requirement. Action: The Project Engineer (Lead) completes “Coordinate project billing, collection and cash-priority actions with Finance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified requisition, delivery/certification record, quantity review or finance handoff. Control/Handoff: Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When the programme creates a material, subcontract, billing or payment-support requirement. | The Project Engineer (Lead) completes “Coordinate project billing, collection and cash-priority actions with Finance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified requisition, delivery/certification record, quantity review or finance handoff. | Every request links to IFC, BOQ, cost code, approval and need date; exceptions route to CPO, CFO, CTO or COO as applicable. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer works with Finance on getting the project billed and the money collected. • Starts when: the billing cycle falls due or collection issues arise. • How it runs: (1) the billing position is reviewed with Finance against the contract terms and milestones. (2) The evidence required for billing is confirmed complete before submission. (3) Submitted applications are tracked through certification to payment. (4) Delays and disputes in certification or payment are identified with their cause. (5) Actions are agreed on evidence, client engagement and cash priorities, with owners. • Proof it happened: the billing and collection review record with the position against contract terms, the evidence confirmed, and the actions agreed with owners. • Where it usually breaks: applications are submitted without the contractually required evidence, so certification is delayed and the delay is blamed on the client. | • Require the contractual evidence requirements to be checked as complete before every application, since incomplete applications are the most common self-inflicted cause of late payment. • Track applications through certification and payment, not just submission, with the delay cause recorded at each stage. • Require billing timing to follow the contract milestones and cut-off dates exactly, as late submission loses a full cycle. • Escalate certification disputes early with the contractual notice position confirmed. • Review the cash position with Finance rather than the billing position alone.
315 | Projects | Analyse weekly progress against baseline, productivity and critical path | Project Engineer (Lead) | Trigger: When progress review, client instruction, delay, RFI, variation or project risk requires action. Action: The Project Engineer (Lead) completes “Analyse weekly progress against baseline, productivity and critical path” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an updated programme, notice, change record, technical response, client action or recovery plan. Control/Handoff: The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When progress review, client instruction, delay, RFI, variation or project risk requires action. | The Project Engineer (Lead) completes “Analyse weekly progress against baseline, productivity and critical path” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an updated programme, notice, change record, technical response, client action or recovery plan. | The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer works out weekly how the project is actually performing against the plan. • Starts when: the weekly analysis cycle runs. • How it runs: (1) actual progress is measured against the baseline by activity. (2) Productivity achieved is compared against the planned rates by trade. (3) The critical path position is assessed with the current float. (4) The causes of variance are established rather than the variance simply reported. (5) The forecast completion position is updated and the areas needing intervention identified. • Proof it happened: the weekly analysis with progress against baseline, productivity against planned rates, the critical path position and the identified causes of variance. • Where it usually breaks: progress is measured as a percentage estimated by supervisors rather than from measured quantities, so the reported position is optimistic until it collapses near the end. | • Require progress to be measured from installed quantities against the BOQ rather than estimated percentages. Supervisor estimated percentages are optimistic and collapse in the final third of a project. • Require productivity to be compared against the rates the estimate and programme assumed, since this is the earliest reliable warning. • Require the critical path and float position to be reported, not overall percentage complete. • Require variance causes to be established, since a variance without a cause cannot be acted on. • Update the forecast completion date weekly, so the trend rather than the snapshot is visible.
316 | Projects | Prepare weekly project report, recovery plan and management exceptions | Project Engineer (Lead) | Trigger: When progress review, client instruction, delay, RFI, variation or project risk requires action. Action: The Project Engineer (Lead) completes “Prepare weekly project report, recovery plan and management exceptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an updated programme, notice, change record, technical response, client action or recovery plan. Control/Handoff: The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When progress review, client instruction, delay, RFI, variation or project risk requires action. | The Project Engineer (Lead) completes “Prepare weekly project report, recovery plan and management exceptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an updated programme, notice, change record, technical response, client action or recovery plan. | The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer writes the weekly report, sets out the recovery plan and flags what management must decide. • Starts when: the weekly reporting cycle falls due. • How it runs: (1) the report is prepared in the required format with progress, productivity, cost and safety. (2) Variances are reported with their causes and their consequences. (3) A recovery plan is proposed where behind, with resources, sequence changes and cost. (4) Exceptions requiring management decision or support are stated explicitly with a recommendation. (5) The report is submitted by the deadline and the actions tracked. • Proof it happened: the weekly report with the variances and causes, the recovery plan where behind, and the exceptions stated with recommendations. • Where it usually breaks: the report presents a recovery plan with no resources or cost attached, so it is accepted as a commitment and then does not happen. | • Require every recovery plan to state the resources, sequence changes and cost required, and who must approve them. A recovery plan with no resources attached is a statement of intent that never delivers. • Require exceptions to be stated with a recommendation and the decision needed, not as a description. • Fix the format and the deadline so the report is comparable across weeks and projects. • Require the previous week's actions to be reported to closure. • Require the report to be honest about trend, since a report that hides deterioration removes the chance to intervene.
317 | Projects | Maintain delay, disruption and extension-of-time evidence and notices | Project Engineer (Lead) | Trigger: When progress review, client instruction, delay, RFI, variation or project risk requires action. Action: The Project Engineer (Lead) completes “Maintain delay, disruption and extension-of-time evidence and notices” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an updated programme, notice, change record, technical response, client action or recovery plan. Control/Handoff: The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When progress review, client instruction, delay, RFI, variation or project risk requires action. | The Project Engineer (Lead) completes “Maintain delay, disruption and extension-of-time evidence and notices” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an updated programme, notice, change record, technical response, client action or recovery plan. | The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer keeps the evidence and issues the notices needed to protect the company's position on delay. • Starts when: an event occurs that delays or disrupts the work. • How it runs: (1) the event is recorded with its date, nature, cause and the work affected. (2) The contractual notice requirement is checked and the notice issued within the time limit. (3) Evidence is assembled contemporaneously: records, photographs, correspondence, programme impact. (4) The delay effect is analysed against the programme and the critical path. (5) The extension of time or disruption claim is prepared with the surveyor and submitted with the evidence. • Proof it happened: the delay event records with the notices issued within time, the contemporaneous evidence assembled and the programme impact analysis. • Where it usually breaks: the notice is issued late or not at all because the team is busy dealing with the event, and the entitlement is lost regardless of the merits. | • Require the contractual notice to be issued within its time limit as a mandatory step, independent of whether the claim is later pursued. Entitlement is lost on notice periods far more often than on merits. • Require evidence to be assembled contemporaneously, since evidence built later is weak and often rejected. • Require the programme impact to be demonstrated against the critical path, not asserted as days lost. • Maintain a notice register with the contractual time limits stated per notice type. • Name who is accountable for issuing notices when the project team is absorbed in managing the event.
318 | Projects | Control site instructions, variations and approved scope changes | Project Engineer (Lead) | Trigger: When progress review, client instruction, delay, RFI, variation or project risk requires action. Action: The Project Engineer (Lead) completes “Control site instructions, variations and approved scope changes” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an updated programme, notice, change record, technical response, client action or recovery plan. Control/Handoff: The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When progress review, client instruction, delay, RFI, variation or project risk requires action. | The Project Engineer (Lead) completes “Control site instructions, variations and approved scope changes” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an updated programme, notice, change record, technical response, client action or recovery plan. | The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer controls site instructions and makes sure scope changes are properly authorised before they are built. • Starts when: an instruction, change or additional work request is received. • How it runs: (1) the instruction is recorded with its source, date and content. (2) Whether it constitutes a change to scope, cost or programme is assessed. (3) Verbal instructions are confirmed in writing before implementation. (4) The cost and time effect is established with the surveyor and authorisation obtained before execution. (5) The variation is registered, implemented and tracked to valuation and payment. • Proof it happened: the instruction and variation register with written confirmation of verbal instructions, the cost and time effect established and the authorisation before execution. • Where it usually breaks: additional work is carried out on a verbal instruction to keep the client happy, and the company cannot prove entitlement to be paid for it. | • Prohibit executing additional work on a verbal instruction without written confirmation, and require confirmation to be sent within a stated period. Verbal instructions executed in good faith are the largest category of unpaid work. • Require the cost and time effect to be notified before execution where the contract requires it, since retrospective claims are weaker. • Require every instruction to be assessed for whether it is a change, since instructions dressed as clarifications carry cost. • Track variations through valuation, certification and payment, not just registration. • Name who may accept an instruction from the client, and prohibit acceptance by site staff outside that list.
319 | Projects | Maintain client and consultant communication and action tracker | Project Engineer (Lead) | Trigger: When progress review, client instruction, delay, RFI, variation or project risk requires action. Action: The Project Engineer (Lead) completes “Maintain client and consultant communication and action tracker” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an updated programme, notice, change record, technical response, client action or recovery plan. Control/Handoff: The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When progress review, client instruction, delay, RFI, variation or project risk requires action. | The Project Engineer (Lead) completes “Maintain client and consultant communication and action tracker” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an updated programme, notice, change record, technical response, client action or recovery plan. | The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer manages the correspondence with the client and consultants and tracks what each side owes the other. • Starts when: the project is running and client or consultant communication is required. • How it runs: (1) all formal communication is issued and received through the defined single points of contact. (2) Correspondence is registered with the date, subject and required response. (3) Actions arising for either party are tracked with owners and dates. (4) Outstanding client and consultant actions are reported and followed up formally where they affect progress. (5) The record is maintained as contractual evidence. • Proof it happened: the correspondence register and action tracker with the responses required, the actions owned by each party, and the formal follow-up on outstanding items. • Where it usually breaks: important matters are agreed in meetings and never confirmed in writing, so the position is disputed later with no record either way. | • Require anything agreed verbally or in a meeting to be confirmed in writing within a stated period. An unconfirmed agreement is worth nothing when the position is later disputed. • Track client and consultant actions with the same discipline as internal ones, since their delays carry entitlement. • Require formal follow-up where an outstanding client or consultant action is affecting progress, since informal chasing does not preserve entitlement. • Route formal communication through the named single points of contact. • Maintain the register as contractual evidence, retrievable by subject and date.
320 | Projects | Coordinate RFIs, technical clarifications and design changes with the CTO | Project Engineer (Lead) | Trigger: When progress review, client instruction, delay, RFI, variation or project risk requires action. Action: The Project Engineer (Lead) completes “Coordinate RFIs, technical clarifications and design changes with the CTO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an updated programme, notice, change record, technical response, client action or recovery plan. Control/Handoff: The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When progress review, client instruction, delay, RFI, variation or project risk requires action. | The Project Engineer (Lead) completes “Coordinate RFIs, technical clarifications and design changes with the CTO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an updated programme, notice, change record, technical response, client action or recovery plan. | The Project Engineer records time, cost and scope impact before commitment; material exceptions escalate to COO and the relevant CXO. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer routes technical questions and design changes to the CTO and gets them answered. • Starts when: a technical question, clarification need or design change arises on site. • How it runs: (1) the issue is defined clearly with the drawings, the site condition and the options. (2) An RFI is raised with the required response date driven by the programme. (3) The RFI is routed to the CTO or the consultant per the contract route. (4) The response is assessed for its effect on cost, programme, scope and other disciplines. (5) Where the response changes the design, a controlled drawing revision is required rather than working from the answer. • Proof it happened: the RFI register with the issues defined, the response dates driven by programme, the responses assessed for impact and the resulting drawing revisions. • Where it usually breaks: the site builds from the RFI answer and no revised drawing is ever issued, so the as-built condition exists only in a piece of correspondence. | • Require any RFI response that changes the design to be followed by a controlled drawing revision before or alongside construction. An answer in correspondence leaves the design record incomplete and the as-built unprovable. • Require the RFI to state the required response date derived from the programme, and escalate when overdue. • Require the response to be assessed for cost, programme and cross-discipline effect, since answers frequently carry both. • Route RFIs through the contractual route, since responses from the wrong party are not binding. • Report overdue RFIs weekly with their programme impact.
321 | Projects | Prepare and coordinate the testing and commissioning plan | Project Engineer (Lead) | Trigger: When construction reaches testing, snagging, completion, handover or DLP status. Action: The Project Engineer (Lead) completes “Prepare and coordinate the testing and commissioning plan” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. Control/Handoff: Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When construction reaches testing, snagging, completion, handover or DLP status. | The Project Engineer (Lead) completes “Prepare and coordinate the testing and commissioning plan” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. | Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer prepares and coordinates how the systems will be tested and commissioned. • Starts when: the project approaches the testing and commissioning stage. • How it runs: (1) the commissioning plan is prepared per system with the sequence and dependencies. (2) Procedures, test sheets and acceptance criteria are prepared and approved. (3) Prerequisites are scheduled: permanent power, water, access, specialist attendance and witnessing. (4) Resources and specialist vendors are mobilised against the plan. (5) Testing is executed with results recorded against the criteria and failures rectified and retested. • Proof it happened: the approved commissioning plan with procedures and acceptance criteria, the prerequisites scheduled and the test results recorded against criteria. • Where it usually breaks: commissioning is planned system by system without the dependencies between systems, so a system is tested before the one it depends on is available. | • Require the commissioning sequence to map dependencies between systems, since testing a system before its supporting systems are live produces invalid results and repeated work. • Require acceptance criteria to be approved before testing, and results to be recorded against those criteria rather than as pass or fail. • Schedule permanent power, water and access as prerequisites with dates, since these are the standard commissioning blockers. • Confirm specialist vendor attendance and witnessing arrangements in advance, including notice periods. • Require failures to be logged, rectified and retested with the retest recorded.
322 | Projects | Prepare snag and punch lists and drive closure by responsible owners | Project Engineer (Lead) | Trigger: When construction reaches testing, snagging, completion, handover or DLP status. Action: The Project Engineer (Lead) completes “Prepare snag and punch lists and drive closure by responsible owners” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. Control/Handoff: Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When construction reaches testing, snagging, completion, handover or DLP status. | The Project Engineer (Lead) completes “Prepare snag and punch lists and drive closure by responsible owners” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. | Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer builds the snag lists and drives them to closure with the people responsible. • Starts when: work areas reach substantial completion or inspections identify defects. • How it runs: (1) inspections are carried out by area and system against the specification. (2) Items are recorded with their location, description, responsible party and required completion date. (3) Items are assigned to the responsible subcontractor or trade with the closure date. (4) Progress is tracked and closure verified by re-inspection, not by report. (5) Closure evidence is retained and the list reported until cleared. • Proof it happened: the snag list by area with responsibility and dates assigned, closure verified by re-inspection and the closure evidence retained. • Where it usually breaks: items are marked closed on the subcontractor's word without re-inspection, and the client finds them still open at handover. | • Require closure to be verified by re-inspection and recorded, never on the responsible party's report. Items closed on assurance reappear on the client's list at handover and delay completion. • Require each item to carry a location, a responsible party and a required date, since unassigned lists do not close. • Carry out internal snagging before the client inspection, so the client list is short and credible. • Track closure rate and escalate subcontractors who do not close items before their demobilisation. • Retain closure evidence, including photographs, as handover and retention support.
323 | Projects | Coordinate authority, consultant and client final inspections | Project Engineer (Lead) | Trigger: When construction reaches testing, snagging, completion, handover or DLP status. Action: The Project Engineer (Lead) completes “Coordinate authority, consultant and client final inspections” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. Control/Handoff: Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When construction reaches testing, snagging, completion, handover or DLP status. | The Project Engineer (Lead) completes “Coordinate authority, consultant and client final inspections” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. | Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer arranges and manages the final inspections by the authorities, consultants and client. • Starts when: the work is complete and final inspections are required. • How it runs: (1) the required inspections are identified with their prerequisites and notice periods. (2) Readiness is verified before the inspection is requested, including documentation. (3) Inspections are requested formally with the required notice. (4) Inspections are attended, observations recorded and rectification assigned. (5) Rectification is completed, re-inspection obtained where needed and the certificates secured. • Proof it happened: the inspection records with readiness verified beforehand, the observations recorded and rectified, and the certificates obtained. • Where it usually breaks: an inspection is requested before the work and documents are actually ready, and the failed inspection puts the next available slot weeks away. | • Require internal verification of readiness, including documentation, before any authority or client inspection is requested. A failed inspection costs the next available slot, which can be weeks on authority inspections. • List the required inspections with their notice periods and prerequisites at project start, not at completion. • Require observations to be recorded and assigned with dates at the inspection itself. • Secure and file the certificates, since occupation, handover and payment depend on them. • Escalate where an inspection depends on client or consultant availability, since these delays are contractual.
324 | Projects | Compile as-built, O&M, warranty, quality and completion dossiers | Project Engineer (Lead) | Trigger: When construction reaches testing, snagging, completion, handover or DLP status. Action: The Project Engineer (Lead) completes “Compile as-built, O&M, warranty, quality and completion dossiers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. Control/Handoff: Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When construction reaches testing, snagging, completion, handover or DLP status. | The Project Engineer (Lead) completes “Compile as-built, O&M, warranty, quality and completion dossiers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. | Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer compiles the completion documents: as-builts, manuals, warranties and quality records. • Starts when: the project approaches completion and the dossier is required. • How it runs: (1) the dossier requirements are established from the contract with the required format. (2) As-built drawings are compiled from verified site records and the changes confirmed. (3) Operation and maintenance manuals, warranties and certificates are collected from suppliers and subcontractors. (4) Quality records, test results and inspection certificates are compiled. (5) The dossier is checked for completeness against the contract requirement and submitted. • Proof it happened: the completed dossier with as-builts from verified records, the collected manuals, warranties and certificates, and the completeness check against the contract. • Where it usually breaks: subcontractor warranties and manuals are collected at the end when the subcontractors have already left and stopped responding. | • Require supplier and subcontractor manuals, warranties and certificates to be a condition of their final payment, collected before demobilisation. Chasing documents from departed subcontractors is the main reason dossiers are late. • Require as-builts to be compiled from verified records progressively rather than reconstructed at the end. • Establish the dossier requirements and format from the contract at project start. • Check completeness against the contract requirement item by item before submission. • Retain a company copy of the dossier, since the only copy issued to the client is regularly needed later.
325 | Projects | Coordinate formal client handover, completion evidence and final billing inputs | Project Engineer (Lead) | Trigger: When construction reaches testing, snagging, completion, handover or DLP status. Action: The Project Engineer (Lead) completes “Coordinate formal client handover, completion evidence and final billing inputs” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. Control/Handoff: Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When construction reaches testing, snagging, completion, handover or DLP status. | The Project Engineer (Lead) completes “Coordinate formal client handover, completion evidence and final billing inputs” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. | Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: the engineer runs the formal handover to the client and supplies what Finance needs for final billing. • Starts when: completion readiness is confirmed and handover is arranged. • How it runs: (1) the handover is arranged with the client per the contract procedure. (2) Completion evidence is presented: certificates, dossier, test results and closed snag lists. (3) Outstanding items are agreed and recorded with dates and responsibility. (4) The completion certificate or acceptance is obtained, and the date recorded. (5) The final billing inputs are provided to Finance, including final quantities, variations and retention position. • Proof it happened: the handover record with the completion evidence presented, the outstanding items agreed, the completion certificate obtained and the final billing inputs issued. • Where it usually breaks: handover is treated as complete on a site walk with no signed acceptance, so the completion date, and with it the defects period and retention, remains arguable. | • Require a signed completion or acceptance document with a stated date. Without it the completion date is arguable, and the defects period, damages and retention all hang on that date. • Require outstanding items at handover to be agreed in writing with dates and responsibility, so they do not expand afterwards. • Require the final billing inputs to be issued to Finance within a set period, since final account delay is where recovery is lost. • Present the completion evidence formally rather than relying on a site walk. • Record the retention position and release milestones at handover, while attention is still on the project.
326 | Projects | Track DLP defects and coordinate final project closeout | Project Engineer (Lead) | Trigger: When construction reaches testing, snagging, completion, handover or DLP status. Action: The Project Engineer (Lead) completes “Track DLP defects and coordinate final project closeout” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. Control/Handoff: Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. Continuity/Escalation: A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. Timing: To be confirmed. | When construction reaches testing, snagging, completion, handover or DLP status. | The Project Engineer (Lead) completes “Track DLP defects and coordinate final project closeout” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved test evidence, closed snags, as-builts, O&M records, handover evidence or DLP closure. | Failed tests, missing records, open critical snags or authority comments keep the affected gate on hold and escalate to COO/CTO/QHSE. | A formally appointed competent Project Engineer may provide operational backup; accountability remains with the named Responsible Project Engineer and material exceptions escalate to the COO. | To be confirmed. | • In plain words: after handover the engineer handles reported defects and finishes closing the project out. • Starts when: the defects liability period begins. • How it runs: (1) reported defects are logged with the date, description and reporting source. (2) Each is assessed for liability, distinguishing company defects from client damage or misuse. (3) Rectification is assigned, executed and evidenced, with subcontractor warranties enforced. (4) Closure evidence is submitted to the client and acknowledgement obtained. (5) At period end, completion is confirmed, retention release is pursued and the project records are archived. • Proof it happened: the defects register with liability assessed and rectification evidenced, the client acknowledgement obtained, and the retention release and archiving recorded. • Where it usually breaks: the site team has moved on and nobody owns the defects period, so defects sit unattended and the retention is written off by default. | • Name an accountable owner for the defects period after the site team demobilises, with a response time for reported defects. Unowned defect periods are how retention is lost by default. • Require liability assessment per defect, distinguishing company defects from client damage, misuse or maintenance failure. • Enforce subcontractor and supplier warranty obligations rather than absorbing the rectification cost. • Require closure evidence to be submitted and acknowledged, since retention releases against acknowledgement. • Archive the project records to the standard at closeout, with the location recorded and retrievable.
327 | Projects | Verify civil site access, survey benchmarks and existing conditions | Site Civil Engineer | Trigger: When a civil work front is scheduled for mobilisation or release. Action: The Site Civil Engineer completes “Verify civil site access, survey benchmarks and existing conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified civil readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When a civil work front is scheduled for mobilisation or release. | The Site Civil Engineer completes “Verify civil site access, survey benchmarks and existing conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified civil readiness record, controlled input set and closed or assigned pre-start actions. | Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: before any civil work starts, the site engineer goes out and checks that the site is really as the drawings show. Access, survey markers, ground conditions and anything already standing there. • Starts when: the work front is handed over to the engineer, or before a new area is opened up. • How it runs: (1) confirm physical access for men, plant and material deliveries. (2) Check the survey benchmarks and coordinates against the drawing datum. (3) Walk the area and record existing conditions, obstructions, services and levels. (4) Photograph everything before anyone disturbs it. (5) Report differences between the drawings and the ground before work begins. • Proof it happened: a signed site verification record, survey check notes, existing condition photographs and a list of differences raised. • Where it usually breaks: work starts on the assumption the drawings are right, and a level or boundary error is found only after concrete is poured. | • Make the benchmark check mandatory and independent. State that levels are verified against the project datum before any setting out, because every dimension afterwards depends on it. • Require dated existing condition photographs before disturbance. Without them the company cannot defend itself against damage claims from neighbours or the client. • List what counts as a blocking condition: no access, no confirmed datum, live services in the work area, or unresolved boundary dispute. Work does not start on any of these. • Name who receives a reported difference and the answer time, so the engineer is not left holding an unanswered problem while the programme runs. • Add a service scanning or trial pit step where records show buried services, because striking a live service is the highest consequence civil site risk.
328 | Projects | Review civil IFC drawings, specifications, BOQ scope and latest revisions | Site Civil Engineer | Trigger: When a civil work front is scheduled for mobilisation or release. Action: The Site Civil Engineer completes “Review civil IFC drawings, specifications, BOQ scope and latest revisions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified civil readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When a civil work front is scheduled for mobilisation or release. | The Site Civil Engineer completes “Review civil IFC drawings, specifications, BOQ scope and latest revisions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified civil readiness record, controlled input set and closed or assigned pre-start actions. | Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer reads the drawings, specification and BOQ for the work in hand, and confirms he is holding the latest issued revision. • Starts when: a work package is about to start, or a new drawing revision arrives. • How it runs: (1) check the drawing register and confirm the revision in hand is the current one. (2) Read the specification clauses that apply to the activity. (3) Compare the BOQ scope against what the drawings show. (4) List anything missing, contradictory or not buildable. (5) Withdraw superseded prints from the site office and the work front. • Proof it happened: a marked up drawing review record, a revision check against the register and a list of queries raised. • Where it usually breaks: a superseded print stays pinned up at the work front and the crew builds from it. | • Make removal of superseded prints a physical, recorded step. Set who collects them from the work front and who confirms it, because an old print at the work face is the commonest cause of rework. • Require a revision check on the morning of any pour or covering activity, not just at package start. • State that specification requirements govern where the drawing is silent, and that the engineer must read both rather than working from drawings alone. • Route every contradiction into the RFI process rather than allowing an on the spot engineering decision. • Add a controlled distribution list per work front so it is always known who holds which revision.
329 | Projects | Assess civil work-front constructability, interfaces and temporary-work needs | Site Civil Engineer | Trigger: When a civil work front is scheduled for mobilisation or release. Action: The Site Civil Engineer completes “Assess civil work-front constructability, interfaces and temporary-work needs” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified civil readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When a civil work front is scheduled for mobilisation or release. | The Site Civil Engineer completes “Assess civil work-front constructability, interfaces and temporary-work needs” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified civil readiness record, controlled input set and closed or assigned pre-start actions. | Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer works out whether the design can actually be built in that location with the space, access and sequence available, and what temporary works are needed to do it. • Starts when: a work package is being planned, or the sequence in an area needs deciding. • How it runs: (1) study the area for working space, crane and plant reach and material movement. (2) Identify what other trades need in the same space and when. (3) Decide the build sequence that avoids trapping work. (4) Identify temporary works needed: shoring, propping, access, dewatering, edge protection. (5) Raise the temporary works requirement to be designed and approved before it is needed. • Proof it happened: a constructability review note, an agreed sequence, an interface list and a temporary works requirement raised. • Where it usually breaks: temporary works are recognised only when the activity is due to start, so the crew improvises. | • Treat temporary works as designed items with a lead time. State that shoring, propping and deep excavation support require a design and an approval before use, never a site decision. • Require the temporary works requirement to be raised a stated number of days ahead, so design and material are available before the activity. • Include a load check on any existing structure used to support temporary works, since this is a frequent cause of collapse. • Make the interface list an output of this step and hand it to the MEP engineer, so openings and embeds are captured before elements are closed. • Add a removal and de propping condition, because early removal of props is as dangerous as installing them wrongly.
330 | Projects | Confirm civil permits, approved method statements and pre-start conditions | Site Civil Engineer | Trigger: When a civil work front is scheduled for mobilisation or release. Action: The Site Civil Engineer completes “Confirm civil permits, approved method statements and pre-start conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified civil readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When a civil work front is scheduled for mobilisation or release. | The Site Civil Engineer completes “Confirm civil permits, approved method statements and pre-start conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified civil readiness record, controlled input set and closed or assigned pre-start actions. | Site Civil Engineer checks survey, drawings, permits, method and interfaces; unsafe or incomplete conditions are returned to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: before work starts, the engineer confirms the permits are in place, the method statement is approved, and every pre start condition has actually been met. • Starts when: an activity is due to start, and again after any stoppage. • How it runs: (1) list the permits the activity needs: excavation, hot work, lifting, confined space, road closure. (2) Confirm the method statement and risk assessment are approved, not just submitted. (3) Check the pre start conditions: inspection released, previous activity signed off, safety measures in place. (4) Brief the crew on the approved method. (5) Only then release the work front. • Proof it happened: valid permits, approved method statement, a completed pre start checklist and a signed crew briefing record. • Where it usually breaks: the method statement is still under review and work proceeds on the assumption that approval will follow. | • State plainly that submitted is not approved. Work does not start on a pending method statement or permit, whatever the programme pressure, and name who may stop it. • Make the pre start checklist a single sheet with signature, so there is one place to check rather than several registers. • Require the crew briefing to be recorded with names, because an approved method that the crew has not been briefed on protects nobody. • Set permit validity and renewal rules, since expired permits on continuing activities are a common audit finding. • Add a restart check after any stoppage of more than a stated period, because conditions and crews change during a break.
331 | Projects | Prepare daily civil work plans, crew allocations and resource requirements | Site Civil Engineer | Trigger: When an approved civil activity enters the daily or lookahead plan. Action: The Site Civil Engineer completes “Prepare daily civil work plans, crew allocations and resource requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a civil work plan, engineering record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil activity enters the daily or lookahead plan. | The Site Civil Engineer completes “Prepare daily civil work plans, crew allocations and resource requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a civil work plan, engineering record, resource request and coordinated interface decision. | Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer plans each day. What will be built, by which crew, with what material and plant, and how much is expected to be done. • Starts when: daily, before the shift, and whenever the plan changes during the day. • How it runs: (1) take the target from the weekly programme. (2) Set the day's activities and target quantities per work front. (3) Allocate crews, plant and tools to each front. (4) Confirm the material and access needed is actually available. (5) Brief supervisors and record what was planned against what was achieved. • Proof it happened: a daily work plan, crew allocation record and a planned against achieved comparison. • Where it usually breaks: the plan is issued without checking material and access, so crews reach the front and stand idle. | • Require a material and access confirmation before the plan is issued. A plan that sends crews to a front with no material is the main source of lost site hours. • Make the planned against achieved comparison a daily habit, not weekly. Daily variance is the earliest reliable warning of a slipping programme. • Set a rule for reallocating idle crews within the shift, so lost time is reduced rather than only reported. • Include target quantities per crew, since a plan with activities but no quantities cannot measure productivity. • Feed persistent constraints into the weekly look ahead, so the same blockage is not rediscovered every morning.
332 | Projects | Control setting-out, grids, levels, coordinates and survey records | Site Civil Engineer | Trigger: When an approved civil activity enters the daily or lookahead plan. Action: The Site Civil Engineer completes “Control setting-out, grids, levels, coordinates and survey records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a civil work plan, engineering record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil activity enters the daily or lookahead plan. | The Site Civil Engineer completes “Control setting-out, grids, levels, coordinates and survey records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a civil work plan, engineering record, resource request and coordinated interface decision. | Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer controls the setting out. The grid lines, levels and coordinates that everything else is built from, and keeps the survey records. • Starts when: before any element is set out, and at every stage where position or level must be confirmed. • How it runs: (1) set out from the verified project grid and datum, never from previously built work alone. (2) Mark grids, offsets and levels and protect the reference points. (3) Check the setting out independently before work proceeds. (4) Record the setting out with coordinates and levels. (5) Re check position and level at each stage: base, mid height and final. • Proof it happened: setting out records with coordinates and levels, independent check signatures and protected reference point records. • Where it usually breaks: setting out is taken from an element already built slightly out of position, and the error is carried through the structure. | • Require independent checking of setting out by a second competent person before work proceeds. Self checked setting out is the root of most positional errors. • State that setting out is always taken from the project grid and datum, not from adjacent built work, so errors do not accumulate. • Make reference point protection an instructed responsibility with a named owner, because destroyed benchmarks stop work and cost survey re establishment. • Set mandatory stage checks: after base, at mid height and before completion, so position errors are caught while they are still correctable. • Keep survey records in one controlled file, since they are the primary evidence in any dimensional dispute.
333 | Projects | Prepare civil method-statement, risk-assessment and ITP technical inputs | Site Civil Engineer | Trigger: When an approved civil activity enters the daily or lookahead plan. Action: The Site Civil Engineer completes “Prepare civil method-statement, risk-assessment and ITP technical inputs” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a civil work plan, engineering record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil activity enters the daily or lookahead plan. | The Site Civil Engineer completes “Prepare civil method-statement, risk-assessment and ITP technical inputs” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a civil work plan, engineering record, resource request and coordinated interface decision. | Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer provides the technical content for the method statement, the risk assessment and the inspection and test plan for civil activities. • Starts when: a method statement or ITP is being prepared or revised for a civil activity. • How it runs: (1) describe the actual construction method, sequence and equipment. (2) Identify the technical hazards: excavation stability, formwork loading, lifting, concrete pours. (3) Set the inspection and test points, hold points and acceptance criteria from the specification. (4) Pass the input to QHSE and the Project Engineer for compilation and submission. (5) Update it when the method changes on site. • Proof it happened: technical inputs recorded in the issued method statement, risk assessment and approved ITP. • Where it usually breaks: the method statement describes an ideal method that differs from what site actually does, so it stops being a real control. | • Require the method statement to describe the method actually intended, and to be revised when site practice changes. A document that does not match reality is a liability in an incident investigation. • Make hold points explicit in the ITP with the acceptance criteria and the witness required, because vague hold points get passed by default. • Name the specification clause behind each acceptance criterion, so inspection is not argued on opinion. • Include the temporary works and lifting content in the technical input rather than leaving it to safety alone. • Set who may authorise a deviation from an approved method, and require it in writing before the deviation is worked.
334 | Projects | Raise civil material, plant, tool and specialist-subcontract requirements | Site Civil Engineer | Trigger: When an approved civil activity enters the daily or lookahead plan. Action: The Site Civil Engineer completes “Raise civil material, plant, tool and specialist-subcontract requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a civil work plan, engineering record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil activity enters the daily or lookahead plan. | The Site Civil Engineer completes “Raise civil material, plant, tool and specialist-subcontract requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a civil work plan, engineering record, resource request and coordinated interface decision. | Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer raises what is needed to build the work. Material, plant, tools and any specialist subcontract, early enough to arrive on time. • Starts when: the look ahead programme shows an activity approaching, or a shortage is identified. • How it runs: (1) work out quantities from the drawings and the planned sequence. (2) Check what is already on site or ordered. (3) Raise the requisition with specification, quantity and required on site date. (4) Include the approval and lead time in the required date. (5) Follow up and report a risk to the programme if delivery slips. • Proof it happened: requisitions with required dates, a material status record and escalations raised on delays. • Where it usually breaks: the requisition is raised for when the material is needed rather than allowing for approval and lead time, so it always arrives late. | • Require the required on site date to be calculated backwards from the activity, including submittal approval and procurement lead time. Requisitioning on need date is why site is permanently waiting. • Set a minimum notice period per material category, and publish it so nobody claims not to have known. • Make the engineer check existing stock before requisitioning, since duplicate ordering is common where several fronts run together. • State that no material is requisitioned against an unapproved submittal without flagging the approval risk. • Add a weekly material status review with a shortage list, so delivery risk reaches the Project Engineer while it is still recoverable.
335 | Projects | Coordinate civil subcontractor activities and technical deliverables | Site Civil Engineer | Trigger: When an approved civil activity enters the daily or lookahead plan. Action: The Site Civil Engineer completes “Coordinate civil subcontractor activities and technical deliverables” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a civil work plan, engineering record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil activity enters the daily or lookahead plan. | The Site Civil Engineer completes “Coordinate civil subcontractor activities and technical deliverables” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a civil work plan, engineering record, resource request and coordinated interface decision. | Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer coordinates the civil subcontractors on site. What they do, when, in what sequence, and whether their technical submissions are in order. • Starts when: a subcontractor is mobilising or working on a civil front. • How it runs: (1) confirm the subcontractor's scope boundary and technical deliverables. (2) Agree the sequence and access with the main works and other trades. (3) Check their submittals, method statements and personnel competence. (4) Monitor their work against specification and quantity. (5) Record their progress, delays and non compliances. • Proof it happened: subcontractor coordination records, technical deliverable status, inspection records and progress logs. • Where it usually breaks: the subcontractor is instructed verbally on scope changes, and the additional work is disputed at payment. | • Require all scope instructions to subcontractors in writing through a named route. Verbal instruction is the standard cause of subcontractor claims. • State that the engineer does not agree rates or commercial terms, and route any commercial matter to the Quantity Surveyor. • Make the technical deliverable status visible per subcontractor, since missing submittals surface as inspection failures later. • Require competence and permit checks before their crew is allowed to a work front. • Keep a dated record of subcontractor delays and interferences, because it is the evidence for both back charges and defence.
336 | Projects | Coordinate civil openings, sleeves, embeds and MEP interfaces | Site Civil Engineer | Trigger: When an approved civil activity enters the daily or lookahead plan. Action: The Site Civil Engineer completes “Coordinate civil openings, sleeves, embeds and MEP interfaces” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a civil work plan, engineering record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil activity enters the daily or lookahead plan. | The Site Civil Engineer completes “Coordinate civil openings, sleeves, embeds and MEP interfaces” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a civil work plan, engineering record, resource request and coordinated interface decision. | Requests reference IFC and programme; technical ambiguity goes to CTO and resource or delivery conflicts go to the Project Engineer. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer makes sure every opening, sleeve and embedded item the services need is in place before the civil element is closed. • Starts when: any element that will contain services is being prepared, and before any pour or closing activity. • How it runs: (1) take the sleeve and opening requirements from the coordinated drawings. (2) Mark them physically on the formwork or blockwork. (3) Have the MEP engineer verify position, size and level before closing. (4) Obtain the joint sign off. (5) Record any missed item and process a corrective approval rather than cutting silently. • Proof it happened: a marked sleeve and opening drawing, a joint civil and MEP pre closing sign off and records of any approved corrections. • Where it usually breaks: an item is missed, and someone cuts a structural element afterwards without engineering approval. | • Make the joint civil and MEP sign off a hard hold point before any pour or closing. This single control removes most of the cutting and chasing that follows. • State that no cutting of a structural element is permitted without written structural approval, whatever the size, and name who approves. • Require the sleeve and embed schedule to be checked against the latest drawing revision on the day, since coordinated routes change. • Log every missed item and its cause, because the pattern shows whether the failure is coordination or supervision. • Include firestopping and sealing responsibility at the boundary, so it is not left unowned between the two trades.
337 | Projects | Supervise earthworks, excavation, backfilling and substructure execution | Site Civil Engineer | Trigger: When an approved civil work front, method and inspection plan are released. Action: The Site Civil Engineer completes “Supervise earthworks, excavation, backfilling and substructure execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: executed civil work meeting drawing, sequence, tolerance and protection requirements. Control/Handoff: Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil work front, method and inspection plan are released. | The Site Civil Engineer completes “Supervise earthworks, excavation, backfilling and substructure execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | executed civil work meeting drawing, sequence, tolerance and protection requirements. | Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises the ground works. Excavation, backfilling and everything below ground level, so it is safe, to level and properly compacted. • Starts when: excavation or substructure work is released to start. • How it runs: (1) confirm permits, service clearance and excavation support are in place. (2) Control excavation to line, level and safe slope or support. (3) Have the founding level inspected and tested before anything is built on it. (4) Control backfill material, layer thickness and compaction with testing. (5) Record levels, test results and any ground condition differing from expectation. • Proof it happened: excavation and founding level inspection records, compaction test results, level records and a report on any unforeseen ground condition. • Where it usually breaks: backfill is placed in thick layers without compaction testing, and settlement appears after the surfaces above are finished. | • Set backfill layer thickness and compaction testing frequency in the SOP with the acceptance value, since settlement after finishes is expensive and highly visible. • Make the founding level inspection a hold point with the geotechnical or consultant witness named. Building on an unapproved founding level is unrecoverable. • Require excavation support or battering per the approved temporary works, with a daily inspection of the excavation before entry. • State the immediate action if ground conditions differ from the report: stop, record, notify, and obtain engineering direction before proceeding. • Include groundwater and dewatering control, because uncontrolled water is the most common cause of excavation collapse.
338 | Projects | Supervise formwork, reinforcement and concrete execution | Site Civil Engineer | Trigger: When an approved civil work front, method and inspection plan are released. Action: The Site Civil Engineer completes “Supervise formwork, reinforcement and concrete execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: executed civil work meeting drawing, sequence, tolerance and protection requirements. Control/Handoff: Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil work front, method and inspection plan are released. | The Site Civil Engineer completes “Supervise formwork, reinforcement and concrete execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | executed civil work meeting drawing, sequence, tolerance and protection requirements. | Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises formwork, reinforcement and concrete. The core structural work where mistakes cannot be undone once the concrete sets. • Starts when: a structural element is being prepared for pour. • How it runs: (1) check the formwork for line, level, dimension, tightness and propping against the temporary works design. (2) Check the reinforcement for size, spacing, laps, cover and cleanliness against the drawing and BBS. (3) Obtain the pre pour inspection release and hold the record. (4) Control the pour: concrete grade, slump, testing, placing, compaction and construction joints. (5) Control curing, formwork stripping time and protection. • Proof it happened: pre pour inspection releases, concrete delivery tickets, cube test records, pour records and stripping and curing records. • Where it usually breaks: concrete is placed before the pre pour inspection is signed, and any reinforcement error is permanently buried. | • Make the pre pour inspection an absolute hold point. No concrete without the signed release, and name who may authorise a pour so it cannot be self released. • Set concrete acceptance controls in the SOP: grade check on the ticket, slump testing frequency, cube sampling rate and the maximum time from batching to placing. • State minimum stripping and propping removal times, and require engineering approval for any early stripping. • Require cover checks with spacer type and spacing stated, because insufficient cover is the leading cause of long term concrete deterioration. • Include a curing requirement per element and climate, since poor curing weakens concrete invisibly and is rarely recorded.
339 | Projects | Supervise masonry, plaster, waterproofing and roofing execution | Site Civil Engineer | Trigger: When an approved civil work front, method and inspection plan are released. Action: The Site Civil Engineer completes “Supervise masonry, plaster, waterproofing and roofing execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: executed civil work meeting drawing, sequence, tolerance and protection requirements. Control/Handoff: Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil work front, method and inspection plan are released. | The Site Civil Engineer completes “Supervise masonry, plaster, waterproofing and roofing execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | executed civil work meeting drawing, sequence, tolerance and protection requirements. | Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises masonry, plaster, waterproofing and roofing. The work that keeps the building weathertight and looking right. • Starts when: these activities are released on a work front. • How it runs: (1) confirm the substrate is prepared, clean and to level before starting. (2) Control materials, mix and workmanship against the specification. (3) Control waterproofing preparation, application, laps, terminations and protection. (4) Test the waterproofing before it is covered. (5) Inspect and record each stage before the next covers it. • Proof it happened: substrate approval, material approvals, waterproofing test records such as flood tests, and stage inspection records. • Where it usually breaks: waterproofing is covered before the flood test, and the leak is found after the finishes are complete. | • Make the waterproofing test a mandatory hold point before covering, with the test duration and acceptance criteria stated. Leaks found after finishes are among the most expensive site failures. • Require substrate acceptance before application, because most waterproofing failures are substrate failures. • Set the termination and upstand details as inspected items, since failures concentrate at edges, drains and penetrations rather than in open areas. • Include protection of completed waterproofing and the sequence for placing screed above it. • Add curing and moisture requirements before plaster and finishes, so cracking is prevented rather than repaired.
340 | Projects | Supervise architectural finishes and external civil works | Site Civil Engineer | Trigger: When an approved civil work front, method and inspection plan are released. Action: The Site Civil Engineer completes “Supervise architectural finishes and external civil works” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: executed civil work meeting drawing, sequence, tolerance and protection requirements. Control/Handoff: Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil work front, method and inspection plan are released. | The Site Civil Engineer completes “Supervise architectural finishes and external civil works” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | executed civil work meeting drawing, sequence, tolerance and protection requirements. | Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises the finishes and the external works. The visible parts the client will judge, and the surrounding hard and soft landscaping. • Starts when: finishes or external work are released on a front. • How it runs: (1) confirm the approved samples, mock ups and setting out patterns. (2) Check the substrate and preceding services are complete and inspected. (3) Control workmanship: alignment, joints, levels, falls and tolerances. (4) Control protection of completed finishes from following trades. (5) Inspect and record against the approved sample and tolerance. • Proof it happened: approved sample references, mock up approvals, stage inspection records and protection records. • Where it usually breaks: finishes are started before services in the wall or floor are complete, and finished work is broken open again. | • Require a services complete and inspected confirmation before finishes start in any area. Breaking finished work for missed services is pure waste and highly visible. • Make the approved sample the reference for acceptance, held physically on site, so acceptance is not argued from memory. • Set out falls and drainage in wet areas as an inspected item before tiling, because remedying falls afterwards means full removal. • Include a protection requirement with a named owner per area, since damage by following trades is the biggest source of snags. • Add tolerance values from the specification into the inspection sheet, so acceptance is measurable rather than a matter of opinion.
341 | Projects | Control civil dimensions, tolerances, productivity and approved sequence | Site Civil Engineer | Trigger: When an approved civil work front, method and inspection plan are released. Action: The Site Civil Engineer completes “Control civil dimensions, tolerances, productivity and approved sequence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: executed civil work meeting drawing, sequence, tolerance and protection requirements. Control/Handoff: Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil work front, method and inspection plan are released. | The Site Civil Engineer completes “Control civil dimensions, tolerances, productivity and approved sequence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | executed civil work meeting drawing, sequence, tolerance and protection requirements. | Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer keeps the work within the allowed dimensions and tolerances, in the approved sequence, and at the productivity the programme assumes. • Starts when: continuously, during execution on every front. • How it runs: (1) check dimensions and tolerances against the drawing and specification at each stage. (2) Confirm work follows the approved sequence rather than the convenient one. (3) Measure crew output against the planned productivity. (4) Identify and remove the causes of low output. (5) Report deviations in dimension, sequence or productivity with the corrective action. • Proof it happened: dimensional check records, sequence compliance notes, productivity records and corrective actions. • Where it usually breaks: out of sequence work is allowed to keep crews busy, and it traps other trades or forces rework later. | • State that out of sequence work needs the Project Engineer's approval, because working out of sequence to keep crews busy usually costs more than the idle time saved. • Set tolerance values per element in the SOP and put them on the inspection sheet, so acceptance is a measurement rather than a judgement. • Require productivity to be recorded per crew per activity, since without it there is no basis for future estimating or for resource claims. • Make repeated low output an escalation with a stated cause code, so the pattern can be acted on rather than absorbed. • Add a cumulative dimensional check at floor level, because small tolerances that pass individually can add up to a failure across a building.
342 | Projects | Protect completed civil work and control temporary conditions | Site Civil Engineer | Trigger: When an approved civil work front, method and inspection plan are released. Action: The Site Civil Engineer completes “Protect completed civil work and control temporary conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: executed civil work meeting drawing, sequence, tolerance and protection requirements. Control/Handoff: Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved civil work front, method and inspection plan are released. | The Site Civil Engineer completes “Protect completed civil work and control temporary conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | executed civil work meeting drawing, sequence, tolerance and protection requirements. | Site Civil Engineer controls supervisors and subcontractors; deviations, unsafe conditions and unapproved changes stop and escalate. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer protects work that is already finished and controls temporary conditions on site, so completed work is not damaged before handover. • Starts when: an element or area is completed, and while temporary conditions exist on site. • How it runs: (1) identify completed work at risk of damage. (2) Apply the specified protection and mark the area. (3) Control temporary conditions: water, drainage, lighting, access, loading and storage. (4) Restrict access and loading on completed areas. (5) Inspect protection regularly and record damage with the responsible party. • Proof it happened: protection installation records, area access controls, inspection rounds and damage reports naming the responsible party. • Where it usually breaks: protection is removed early for convenience, and the damage is discovered at snagging with nobody accountable. | • Require damage to be recorded with the responsible party at the time it is found, since back charging is impossible once the trade has left the area. • Name who may remove protection and under what condition, because early removal for convenience is the usual cause of damage. • Set loading limits on completed slabs and areas, particularly for material storage, since overloading young structure is a real structural risk. • Include temporary water and drainage control in the SOP, because uncontrolled water damages finished work faster than any other cause. • Add protection cost to the activity rather than treating it as overhead, so it is planned rather than skipped.
343 | Projects | Verify civil materials against approved submittals and storage requirements | Site Civil Engineer | Trigger: When civil material arrives or work reaches inspection, concealment or resource-control point. Action: The Site Civil Engineer completes “Verify civil materials against approved submittals and storage requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. Control/Handoff: No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When civil material arrives or work reaches inspection, concealment or resource-control point. | The Site Civil Engineer completes “Verify civil materials against approved submittals and storage requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. | No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer checks that the material arriving is exactly what was approved, and that it is stored on site the way it should be. • Starts when: material is delivered, and while it is stored on site. • How it runs: (1) compare the delivered material against the approved submittal: make, grade, size, batch and certificate. (2) Inspect for damage, age and shelf life. (3) Reject and segregate anything not compliant. (4) Confirm storage: off ground, covered, ventilated, protected from weather and separated by grade. (5) Record acceptance, rejection and storage condition. • Proof it happened: material inspection records, mill and test certificates, rejection records and storage inspection notes. • Where it usually breaks: material is accepted on the delivery note alone, and a substitution or a wrong grade is found only when the work is inspected. | • Require acceptance against the approved submittal, not the delivery note or the purchase order. This is the point where substitutions are caught or missed. • Make certificate collection at delivery mandatory, since chasing mill and batch certificates later is a standard closeout delay. • Set physical segregation and marking for rejected material, because unmarked rejected material gets used. • Include shelf life and storage rules for cement, admixtures, adhesives and sealants, where age directly affects performance. • Name who may accept a minor deviation and require it in writing, so a site convenience does not become an unrecorded specification change.
344 | Projects | Perform civil pre-inspection and raise work-inspection requests | Site Civil Engineer | Trigger: When civil material arrives or work reaches inspection, concealment or resource-control point. Action: The Site Civil Engineer completes “Perform civil pre-inspection and raise work-inspection requests” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. Control/Handoff: No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When civil material arrives or work reaches inspection, concealment or resource-control point. | The Site Civil Engineer completes “Perform civil pre-inspection and raise work-inspection requests” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. | No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer checks his own work first, fixes anything obvious, and only then formally calls the consultant or client for inspection. • Starts when: an activity is complete and ready for inspection. • How it runs: (1) inspect the work against the drawing, specification and ITP. (2) Correct minor items before calling anyone. (3) Confirm the preceding inspections and material approvals are in place. (4) Raise the inspection request with the correct notice, location and reference. (5) Attend the inspection, record the result and close any comments. • Proof it happened: internal pre inspection checklists, raised inspection requests, inspection results and comment closure records. • Where it usually breaks: inspection is called without a pre check, it fails on obvious items, and the relationship and the programme both suffer. | • Make the internal pre inspection a required step with a completed checklist attached to the request. Failed inspections on obvious items damage credibility and cost days. • Set the notice period for inspection requests and require the exact location reference, since vague requests get rejected or attended at the wrong place. • Track inspection first time pass rate per activity and per crew, because it is the clearest measure of supervision quality. • Require that all preceding inspections and material approvals are closed before a request is raised. • Set a closure route for inspection comments with a re inspection record, so comments are not left open at handover.
345 | Projects | Inspect civil work before concealment, covering or subsequent trade release | Site Civil Engineer | Trigger: When civil material arrives or work reaches inspection, concealment or resource-control point. Action: The Site Civil Engineer completes “Inspect civil work before concealment, covering or subsequent trade release” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. Control/Handoff: No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When civil material arrives or work reaches inspection, concealment or resource-control point. | The Site Civil Engineer completes “Inspect civil work before concealment, covering or subsequent trade release” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. | No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer inspects work before it disappears. Anything about to be covered, concealed or built over must be checked while it can still be seen. • Starts when: before any covering, concealing, pouring or release to the next trade. • How it runs: (1) identify what is about to be concealed: reinforcement, services, waterproofing, embedded items. (2) Inspect against the drawing and specification. (3) Take dated photographs with location reference. (4) Obtain the sign off from all parties who need to verify. (5) Only then release the covering activity. • Proof it happened: pre concealment inspection records, dated location referenced photographs and multi party sign off. • Where it usually breaks: covering proceeds without the record, and later verification means opening up finished work. | • List the concealment hold points explicitly in the SOP, since these are the inspections that cannot be repeated at any price. • Make dated, location referenced photography mandatory, and set where the photographs are stored. Photographs with no location are worthless as evidence. • Name every party whose sign off is needed before covering, so nobody discovers afterwards that their verification was missed. • State that covering without a release is a reportable non conformance, not a scheduling matter. • Add a rule that opening up for verification is at the cost of the party that covered without release, which changes behaviour quickly.
346 | Projects | Raise civil RFIs for missing, conflicting or impractical information | Site Civil Engineer | Trigger: When civil material arrives or work reaches inspection, concealment or resource-control point. Action: The Site Civil Engineer completes “Raise civil RFIs for missing, conflicting or impractical information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. Control/Handoff: No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When civil material arrives or work reaches inspection, concealment or resource-control point. | The Site Civil Engineer completes “Raise civil RFIs for missing, conflicting or impractical information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. | No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: when the information is missing, contradictory or cannot be built, the engineer asks the question formally instead of guessing. • Starts when: a gap, conflict or impractical detail is found in the design information. • How it runs: (1) confirm the issue is real by checking the latest revision and specification. (2) Write the query with the location, the drawing reference and the problem. (3) Propose a solution where possible, to speed the answer. (4) State the date the answer is needed and the programme impact. (5) Log it, follow it up and distribute the answer to everyone affected. • Proof it happened: a query register with dates, the query itself, the received answer and the distribution record. • Where it usually breaks: the site solves the problem itself to save time, and the built work no longer matches the design or the contract. | • State clearly that the site does not resolve design gaps by itself. An unrecorded site solution transfers design liability to the company with no record of why. • Require the query to state the required answer date and the programme impact, since queries with no consequence stated are answered last. • Track ageing of open queries and escalate on a set threshold, because unanswered information is a legitimate delay event only if it is on record. • Require the answer to be distributed to every affected trade, not just filed, since undistributed answers cause the same clash twice. • Add a rule that any answer changing the design must be followed by a drawing revision, so the record stays correct.
347 | Projects | Record civil defects, NCRs, rework and corrective-action closure | Site Civil Engineer | Trigger: When civil material arrives or work reaches inspection, concealment or resource-control point. Action: The Site Civil Engineer completes “Record civil defects, NCRs, rework and corrective-action closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. Control/Handoff: No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When civil material arrives or work reaches inspection, concealment or resource-control point. | The Site Civil Engineer completes “Record civil defects, NCRs, rework and corrective-action closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. | No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: when work is wrong, the engineer records it properly, gets it put right, and confirms the cause has been dealt with rather than just the symptom. • Starts when: a defect or non compliance is found by anyone. • How it runs: (1) record the defect with location, description, photograph and the requirement breached. (2) Decide the disposition: repair, replace, or accept as is with approval. (3) Identify the cause and the responsible party. (4) Execute and inspect the correction. (5) Close it with evidence and act on the cause where it repeats. • Proof it happened: a defect and NCR register, dispositions with approvals, rework records and closure evidence with photographs. • Where it usually breaks: the defect is repaired quietly with no record, so the same failure repeats and there is no basis for back charging. | • Require the record even when the fix is immediate. Unrecorded rework means no cause analysis, no back charge and the same defect appearing again next month. • State that accept as is requires the designer's written approval, since it is a design acceptance and not a site decision. • Make cause identification and responsible party mandatory fields, otherwise every defect ends up owned by nobody. • Set a repeat defect threshold that triggers a method or training review rather than another repair. • Require closure evidence with photographs, because a register entry marked closed with no evidence fails audit.
348 | Projects | Verify daily civil material consumption, wastage and balance at site | Site Civil Engineer | Trigger: When civil material arrives or work reaches inspection, concealment or resource-control point. Action: The Site Civil Engineer completes “Verify daily civil material consumption, wastage and balance at site” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. Control/Handoff: No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When civil material arrives or work reaches inspection, concealment or resource-control point. | The Site Civil Engineer completes “Verify daily civil material consumption, wastage and balance at site” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved material evidence, WIR, RFI, NCR closure or reconciled consumption record. | No work is concealed without required inspection; rejected material and nonconforming work are identified, quarantined or corrected before release. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer checks each day how much material was actually used against how much should have been used, and where the balance is. • Starts when: daily, and at material reconciliation points. • How it runs: (1) record issued quantities per work front. (2) Calculate the theoretical requirement from the completed work. (3) Compare the two and calculate wastage. (4) Verify the physical balance remaining on site. (5) Investigate and report any variance beyond the allowed wastage. • Proof it happened: daily consumption records, theoretical against actual comparison, wastage calculation and a physical balance record. • Where it usually breaks: consumption is recorded but never compared with the theoretical figure, so losses go unnoticed for months. | • Make the theoretical against actual comparison the required output, not just consumption recording. Recording issues without comparison detects nothing. • Set allowed wastage percentages per material in the SOP, so a variance can be judged rather than debated. • Require a physical stock check at a stated frequency, including a joint check with stores, since paper balances drift from reality. • Set an investigation threshold and a reporting route for unexplained loss, because material loss without an owner is normalised quickly. • Include high value and controlled items on a separate tighter reconciliation, since they carry most of the value at risk.
349 | Projects | Record daily civil progress, quantities, photographs and constraints | Site Civil Engineer | Trigger: When the daily reporting, measurement, snag or civil-closeout milestone becomes due. Action: The Site Civil Engineer completes “Record daily civil progress, quantities, photographs and constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified civil quantities, progress evidence, red-lines, inspection status and completion handover. Control/Handoff: Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, snag or civil-closeout milestone becomes due. | The Site Civil Engineer completes “Record daily civil progress, quantities, photographs and constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified civil quantities, progress evidence, red-lines, inspection status and completion handover. | Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer writes down each day what was built, how much, what it looked like, and what stopped the work. • Starts when: daily, at the end of every shift. • How it runs: (1) record activities and quantities completed per location. (2) Record manpower, plant and material used. (3) Take dated progress photographs. (4) Record constraints, delays, instructions and events with times. (5) Submit the report the same day and keep the record. • Proof it happened: signed daily progress reports, quantity records, dated photographs and a constraint and event log. • Where it usually breaks: the report records only quantities, not the delays and events, so the company has no evidence when a claim is made months later. | • Require delays, disruptions, instructions and visits to be recorded with times, not just quantities. This log is the single most valuable evidence in any delay claim, and it can only be written on the day. • Set same day submission with a named recipient, because reports written days later have little evidential weight. • Standardise photograph naming with date and location, since an unlabelled photograph library cannot be used as evidence. • Include actual manpower and plant against planned, so productivity and standing time are both provable. • State that the daily report is a contemporaneous record and must not be edited later, only supplemented with a dated addendum.
350 | Projects | Verify civil measurements and completed quantities with the Quantity Surveyor | Site Civil Engineer | Trigger: When the daily reporting, measurement, snag or civil-closeout milestone becomes due. Action: The Site Civil Engineer completes “Verify civil measurements and completed quantities with the Quantity Surveyor” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified civil quantities, progress evidence, red-lines, inspection status and completion handover. Control/Handoff: Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, snag or civil-closeout milestone becomes due. | The Site Civil Engineer completes “Verify civil measurements and completed quantities with the Quantity Surveyor” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified civil quantities, progress evidence, red-lines, inspection status and completion handover. | Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer and the quantity surveyor go over the completed quantities together, so what gets measured and billed matches what was actually built. • Starts when: at the measurement cycle, or when an activity or section is complete. • How it runs: (1) measure the completed work jointly on site against the drawings. (2) Agree the basis of measurement and the deductions. (3) Separate approved variation work from base scope. (4) Sign the joint measurement record. (5) Hand it to the Quantity Surveyor for billing and keep a copy. • Proof it happened: signed joint measurement records, agreed quantity sheets and variation quantities recorded separately. • Where it usually breaks: the engineer's figures and the surveyor's figures differ, the difference is discovered at billing, and payment is delayed. | • Require joint measurement signed by both engineer and surveyor, since separately produced quantities always differ and get argued at billing. • State the measurement basis in the SOP, whether net or gross and how openings are deducted, because most disputes are about method rather than dimensions. • Keep variation quantities separate from base scope from the start, otherwise the variation entitlement is lost in the total. • Set the measurement cycle to the billing cycle, so measurement is not compressed into the last days before submission. • Require any measurement not yet agreed to be flagged rather than averaged, so unresolved items stay visible.
351 | Projects | Maintain civil red-lines and verified as-built information | Site Civil Engineer | Trigger: When the daily reporting, measurement, snag or civil-closeout milestone becomes due. Action: The Site Civil Engineer completes “Maintain civil red-lines and verified as-built information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified civil quantities, progress evidence, red-lines, inspection status and completion handover. Control/Handoff: Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, snag or civil-closeout milestone becomes due. | The Site Civil Engineer completes “Maintain civil red-lines and verified as-built information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified civil quantities, progress evidence, red-lines, inspection status and completion handover. | Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer marks up on drawings what was actually built where it differs from the design, and keeps that record verified and up to date. • Starts when: continuously as work is built, and at each area completion. • How it runs: (1) mark every deviation from the drawing on the record set as it happens. (2) Include actual dimensions, levels and routes. (3) Verify the mark up against the physical work rather than assuming. (4) Have it checked and signed by the engineer. (5) Hand it to drafting for the as built drawings. • Proof it happened: signed red line mark ups with dates, verified dimensions and a handover record to drafting. • Where it usually breaks: red lines are done from memory at the end of the job, so the as built drawings do not reflect the building. | • Require red lines to be updated as work proceeds, with a monthly completeness check. Red lines produced from memory at the end are the reason as builts are unreliable. • Set who signs the red line as verified, since unverified mark ups passed to drafting simply move the error into a formal document. • State that concealed work must be red lined before covering, because it cannot be verified afterwards. • Require actual dimensions and levels rather than notes such as as per site, which carry no information. • Make an up to date red line set a condition of the monthly progress certification, which is the only reliable way to keep it current.
352 | Projects | Coordinate civil snag identification and closure | Site Civil Engineer | Trigger: When the daily reporting, measurement, snag or civil-closeout milestone becomes due. Action: The Site Civil Engineer completes “Coordinate civil snag identification and closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified civil quantities, progress evidence, red-lines, inspection status and completion handover. Control/Handoff: Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, snag or civil-closeout milestone becomes due. | The Site Civil Engineer completes “Coordinate civil snag identification and closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified civil quantities, progress evidence, red-lines, inspection status and completion handover. | Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer finds the small outstanding defects in his area, lists them, gets them fixed and confirms they are properly closed. • Starts when: an area approaches completion, and during client or consultant walkthroughs. • How it runs: (1) walk the area and list every snag with location and description. (2) Assign each snag to a responsible trade with a target date. (3) Have the work done and inspect it. (4) Photograph the closure and obtain acceptance. (5) Report the open and closed status until the list is clear. • Proof it happened: a snag list with locations, assignments and dates, closure photographs and accepted closure records. • Where it usually breaks: snags are marked closed without inspection, and the client finds them again at final inspection. | • Require inspected and photographed closure for every snag, since a list closed on a verbal assurance always reopens at final inspection. • Run an internal snagging round before inviting the client, because a long client generated list creates a perception problem that lasts to handover. • Assign each snag to a trade with a target date and hold an ageing view, so old snags are not buried in a long list. • Set a rule for snags caused by damage rather than workmanship, so responsibility and cost are correctly allocated. • Require the protection of closed areas after snag clearance, otherwise the same snags are recreated by following trades.
353 | Projects | Support civil authority, consultant and client inspections | Site Civil Engineer | Trigger: When the daily reporting, measurement, snag or civil-closeout milestone becomes due. Action: The Site Civil Engineer completes “Support civil authority, consultant and client inspections” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified civil quantities, progress evidence, red-lines, inspection status and completion handover. Control/Handoff: Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, snag or civil-closeout milestone becomes due. | The Site Civil Engineer completes “Support civil authority, consultant and client inspections” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified civil quantities, progress evidence, red-lines, inspection status and completion handover. | Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer prepares for and attends inspections by the authority, the consultant and the client, so they go well and any comments are dealt with. • Starts when: an inspection is scheduled or requested. • How it runs: (1) confirm what the inspection covers and what evidence is needed. (2) Pre inspect the work and prepare the documents, approvals and test results. (3) Confirm access, safety and site readiness. (4) Attend, record the comments and confirm understanding of each one. (5) Close every comment with evidence and confirm acceptance in writing. • Proof it happened: inspection notices, prepared evidence packs, recorded comments and closure records with written acceptance. • Where it usually breaks: comments are noted verbally, understood differently by each side, and reappear at the next inspection. | • Require comments to be written and read back at the inspection, so both sides record the same thing. Verbally noted comments reappear as failures later. • Prepare the evidence pack before the inspection: approvals, test results, material certificates. Most inspection failures are documentary rather than physical. • Set a closure route with written acceptance per comment, since an inspection is not closed until the comment is accepted. • Include a site readiness and safety check before the visit, because a stopped inspection wastes an approval slot that may take weeks to get back. • Record authority conditions separately and track them to occupancy, as these directly block handover.
354 | Projects | Handover the civil completion and closeout evidence package | Site Civil Engineer | Trigger: When the daily reporting, measurement, snag or civil-closeout milestone becomes due. Action: The Site Civil Engineer completes “Handover the civil completion and closeout evidence package” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified civil quantities, progress evidence, red-lines, inspection status and completion handover. Control/Handoff: Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. Continuity/Escalation: A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, snag or civil-closeout milestone becomes due. | The Site Civil Engineer completes “Handover the civil completion and closeout evidence package” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified civil quantities, progress evidence, red-lines, inspection status and completion handover. | Site Civil Engineer reconciles evidence with the Project Engineer, QS and QHSE; unresolved completion issues remain assigned with dates. | A competent civil engineer may provide documented backup; unresolved IFC, quality, quantity, temporary-work or safety risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: at the end, the engineer hands over the whole civil evidence package. Drawings, tests, approvals, certificates and closed snags, in one complete set. • Starts when: civil work is complete and handover is approaching. • How it runs: (1) list what the contract requires in the handover package. (2) Collect as builts, test results, material certificates, inspection records and approvals. (3) Confirm all snags and non conformances are closed. (4) Check the package against the required list, item by item. (5) Hand it over formally with a signed receipt and archive a copy. • Proof it happened: a completed handover index, the compiled document set, a snag and NCR closure statement and a signed handover receipt. • Where it usually breaks: documents are collected only at handover, missing items cannot be recreated, and retention is held for paperwork rather than for work. | • Build the handover index at project start and populate it as work proceeds. Assembling it at the end is why closeout drags for months and retention stays unpaid. • Make missing documents a tracked item with an owner and a date, since a package is only as complete as its weakest section. • Require confirmation that all NCRs and snags are closed as part of the handover statement, not as a separate exercise. • Take a signed receipt for the handover, and archive a complete copy, because handing over the only copy is a permanent loss. • Add a lessons learned note per project on what could not be produced at closeout, so the same gaps are prevented next time.
355 | Projects | Review MEP IFC drawings, specifications, BOQ scope and latest revisions | Site MEP Engineer | Trigger: When an MEP work front is scheduled for mobilisation or release. Action: The Site MEP Engineer completes “Review MEP IFC drawings, specifications, BOQ scope and latest revisions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an MEP work front is scheduled for mobilisation or release. | The Site MEP Engineer completes “Review MEP IFC drawings, specifications, BOQ scope and latest revisions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. | Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the MEP site engineer reads the services drawings, specification and BOQ for his area and confirms he is working from the current revision. • Starts when: an MEP package is about to start, or a new revision is issued. • How it runs: (1) check the drawing register and confirm the revision in hand is current. (2) Read the specification for the systems involved. (3) Compare the BOQ scope with what the drawings show. (4) List missing, conflicting or unbuildable information. (5) Withdraw superseded prints from the site office and the work front. • Proof it happened: a drawing review record, revision check against the register and a list of queries raised. • Where it usually breaks: installation follows an old coordinated route, and clashes appear once another trade installs to the current one. | • Require a revision check before starting any installation run, since MEP routes change more often than any other discipline's drawings. • Make removal of superseded prints from the work front a recorded step with a named owner. • State that the coordinated services drawing governs the route, not the single discipline drawing, and say what to do when they disagree. • Route every conflict into an RFI rather than allowing a site route decision, because unrecorded rerouting breaks the as built and the maintenance access. • Keep a per work front distribution record, so it is known who holds which revision.
356 | Projects | Survey existing utilities, services, connection points and site constraints | Site MEP Engineer | Trigger: When an MEP work front is scheduled for mobilisation or release. Action: The Site MEP Engineer completes “Survey existing utilities, services, connection points and site constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an MEP work front is scheduled for mobilisation or release. | The Site MEP Engineer completes “Survey existing utilities, services, connection points and site constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. | Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer surveys the services already there. Where the utilities run, where the connection points are, and what on site limits the installation. • Starts when: before services installation begins, and before any connection or tie in work. • How it runs: (1) obtain the utility records and locate the existing services physically. (2) Confirm the connection point positions, sizes, levels and capacities. (3) Record site constraints: headroom, access, existing structures. (4) Compare against the design assumptions. (5) Report differences before installation starts. • Proof it happened: a utility survey record, confirmed connection point details, constraint photographs and a report on the differences found. • Where it usually breaks: a connection point is assumed from the drawing, and the actual invert level or capacity makes the design unworkable. | • Require physical verification of every connection point: position, size, level and capacity, in writing from the utility where possible. Drainage inverts and incoming pressure change the whole distribution design. • Include a service detection or trial pit step before any excavation near recorded services, since strikes here are the highest consequence site event. • Record the difference between design assumption and site reality formally, because it is often a legitimate variation. • Confirm utility application and approval lead times at this point, as connections are a classic late programme failure. • Add headroom and access constraints to the coordination input, so routes are not designed into spaces that cannot be reached.
357 | Projects | Coordinate MEP zones, plant spaces, builders work and access requirements | Site MEP Engineer | Trigger: When an MEP work front is scheduled for mobilisation or release. Action: The Site MEP Engineer completes “Coordinate MEP zones, plant spaces, builders work and access requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an MEP work front is scheduled for mobilisation or release. | The Site MEP Engineer completes “Coordinate MEP zones, plant spaces, builders work and access requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. | Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer coordinates the space. Which services go where, what the plant rooms need, what holes the builder must leave, and how it will all be reached later. • Starts when: before installation in a zone, and whenever a route or plant layout changes. • How it runs: (1) check the coordinated route against the actual site conditions and levels. (2) Confirm the plant space is adequate for installation, operation, access and removal. (3) List the builders work required: openings, sleeves, plinths, supports. (4) Agree the installation sequence between the services trades. (5) Confirm maintenance access and valve or panel reachability. • Proof it happened: coordinated route confirmation, a builders work list issued to civil, an agreed installation sequence and access confirmation. • Where it usually breaks: the trade that installs first takes the best space, and later trades cannot install to the coordinated route. | • Set the installation sequence in congested zones as a controlled decision, because whoever installs first takes the space and everyone after it pays for the rework. • Require the builders work list to be issued before the civil element is built, and to be checked back against what was left. • Make maintenance access a checked item: can the valve be reached, the filter changed, the panel opened, the equipment removed. This is the defect operations lives with for decades. • Require confirmation of plinth, support and hanger requirements before the slab is finished. • State that a route change on site needs coordination approval, since one trade's local reroute becomes another's clash.
358 | Projects | Confirm MEP permits, approved methods and authority pre-start conditions | Site MEP Engineer | Trigger: When an MEP work front is scheduled for mobilisation or release. Action: The Site MEP Engineer completes “Confirm MEP permits, approved methods and authority pre-start conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. Control/Handoff: Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an MEP work front is scheduled for mobilisation or release. | The Site MEP Engineer completes “Confirm MEP permits, approved methods and authority pre-start conditions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified MEP readiness record, controlled input set and closed or assigned pre-start actions. | Site MEP Engineer checks utilities, drawings, approvals, permits and builders-work interfaces; incomplete conditions are held and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: before MEP work starts, the engineer confirms the permits, the approved method and every authority pre start condition are actually in place. • Starts when: an MEP activity is due to start, and again after any stoppage. • How it runs: (1) list the permits needed: hot work, electrical isolation, confined space, lifting, working at height. (2) Confirm the method statement and risk assessment are approved. (3) Check the authority pre start conditions for the systems involved. (4) Brief the crew on the approved method. (5) Release the work front only when all are in place. • Proof it happened: valid permits, approved method statements, an authority condition checklist and a signed crew briefing. • Where it usually breaks: work starts on a submitted but unapproved method statement, and any incident then has no defensible control behind it. | • State that submitted is not approved, and name who may stop work started without approval. • Treat electrical isolation and lock off as a separate controlled permit with a named authorising person, because this is where lives are lost. • Require a hot work permit with fire watch and post work monitoring, since fire risk continues after the work stops. • Set permit validity and renewal rules for continuing activities. • List the authority pre start conditions per system, so a fire or utility condition is not discovered at inspection stage.
359 | Projects | Prepare daily MEP work plans, crew allocations and resource requirements | Site MEP Engineer | Trigger: When an approved MEP activity enters the daily or lookahead plan. Action: The Site MEP Engineer completes “Prepare daily MEP work plans, crew allocations and resource requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an MEP work plan, technical-readiness record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP activity enters the daily or lookahead plan. | The Site MEP Engineer completes “Prepare daily MEP work plans, crew allocations and resource requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an MEP work plan, technical-readiness record, resource request and coordinated interface decision. | Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer plans each MEP day. What gets installed, by which crew, with what material, and how much is expected. • Starts when: daily, before the shift, and whenever the plan changes. • How it runs: (1) take the target from the weekly programme. (2) Set activities and target quantities per zone. (3) Allocate crews, tools and lifting equipment. (4) Confirm the material, shop drawing approval and access needed are all available. (5) Brief supervisors and record planned against achieved. • Proof it happened: daily MEP work plans, crew allocation records and planned against achieved comparison. • Where it usually breaks: crews are sent to a zone where the ceiling is not ready or the material has not been approved, and the day is lost. | • Require confirmation of material availability, submittal approval and zone readiness before the plan is issued, since MEP crews are the most frequently idled by unready fronts. • Include access equipment in the daily allocation, because scaffold and platform shortage is a common hidden constraint in services work. • Compare planned against achieved daily with a cause code for the loss, so the same constraint is not repeated. • Set a reallocation rule within the shift for crews blocked in one zone. • Feed recurring constraints into the look ahead so they are cleared before the crew arrives, not after.
360 | Projects | Confirm MEP shop drawings, material submittals and technical approvals are ready | Site MEP Engineer | Trigger: When an approved MEP activity enters the daily or lookahead plan. Action: The Site MEP Engineer completes “Confirm MEP shop drawings, material submittals and technical approvals are ready” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an MEP work plan, technical-readiness record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP activity enters the daily or lookahead plan. | The Site MEP Engineer completes “Confirm MEP shop drawings, material submittals and technical approvals are ready” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an MEP work plan, technical-readiness record, resource request and coordinated interface decision. | Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer confirms the shop drawings, material submittals and technical approvals for his area are actually approved before installation starts. • Starts when: before a package or a zone is released for installation. • How it runs: (1) list the shop drawings and submittals needed for the activity. (2) Check each one's approval status and any conditions attached. (3) Confirm the material ordered matches the approved submittal. (4) Confirm the installation drawing in use reflects the approval comments. (5) Block release where an approval is missing and escalate. • Proof it happened: an approval status register, approved shop drawings and submittals in use, and escalations for missing approvals. • Where it usually breaks: installation starts on an approved as noted submittal without incorporating the notes, and the whole run has to be modified. | • Require the approval conditions on any approved as noted submittal to be incorporated and confirmed before installation. Ignoring the notes is a common and expensive failure. • Keep one visible approval status register per zone, so release does not depend on someone remembering. • State that no installation is released against a pending approval, and set the escalation route when the programme conflicts with it. • Require a check that delivered material matches the approved submittal, not the purchase order. • Add a re check when a submittal is revised, since a superseded approval in use is as bad as none.
361 | Projects | Raise MEP material, equipment, tool and specialist-subcontract requirements | Site MEP Engineer | Trigger: When an approved MEP activity enters the daily or lookahead plan. Action: The Site MEP Engineer completes “Raise MEP material, equipment, tool and specialist-subcontract requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an MEP work plan, technical-readiness record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP activity enters the daily or lookahead plan. | The Site MEP Engineer completes “Raise MEP material, equipment, tool and specialist-subcontract requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an MEP work plan, technical-readiness record, resource request and coordinated interface decision. | Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer raises what MEP work needs. Material, equipment, tools and specialist subcontracts, in time for the approvals and the delivery. • Starts when: the look ahead shows an activity approaching, or a shortage is identified. • How it runs: (1) take off quantities from the coordinated drawings. (2) Check existing site stock and outstanding orders. (3) Raise the requisition with technical specification, quantity and required date. (4) Include submittal approval and equipment lead time in the required date. (5) Track and escalate delivery risk. • Proof it happened: requisitions with technical specifications and required dates, a material status record and escalations on delays. • Where it usually breaks: long lead equipment such as chillers, switchgear and pumps is requisitioned on need date, and the programme is missed by months. | • Maintain a long lead equipment list with order by dates, and review it weekly. Late ordering of major plant is the standard reason MEP misses handover. • Require the required date to be calculated backwards including submittal approval, manufacture and shipping. • Ensure requisitions state performance duty and technical specification, not just an equipment name, so procurement cannot substitute on price alone. • Include tools, testing instruments and calibration status in the requirement, since uncalibrated instruments invalidate test records. • Set a shortage escalation route to the Project Engineer with programme impact attached.
362 | Projects | Coordinate MEP specialist subcontractors and vendor technical deliverables | Site MEP Engineer | Trigger: When an approved MEP activity enters the daily or lookahead plan. Action: The Site MEP Engineer completes “Coordinate MEP specialist subcontractors and vendor technical deliverables” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an MEP work plan, technical-readiness record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP activity enters the daily or lookahead plan. | The Site MEP Engineer completes “Coordinate MEP specialist subcontractors and vendor technical deliverables” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an MEP work plan, technical-readiness record, resource request and coordinated interface decision. | Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer coordinates the specialist subcontractors and vendors. Lifts, fire systems, generators, BMS, and whatever technical documents they owe. • Starts when: a specialist is appointed, mobilising or due to deliver a technical document. • How it runs: (1) confirm the scope boundary and the interface with the main MEP works. (2) Obtain their shop drawings, submittals, method statements and test plans. (3) Agree their site sequence, access and prerequisites. (4) Supervise their work against specification. (5) Track their commissioning, training and documentation obligations. • Proof it happened: scope boundary records, technical deliverable status, coordination minutes and their inspection and commissioning records. • Where it usually breaks: their prerequisites such as power, cooling or a clean space are not ready when they mobilise, and their standing time is charged to the project. | • Require a prerequisite checklist to be confirmed before any specialist mobilises. Standing time and remobilisation charges from specialists are avoidable and often substantial. • Make training and documentation a condition of their final payment, since specialists demobilise before handover otherwise. • State the interface boundary in writing, particularly for power supply, containment and final connection, because these are the classic gaps. • Route all commercial and scope change matters to the Quantity Surveyor rather than the site engineer. • Track their spare parts, warranty and consumable obligations, which are usually forgotten until operations needs them.
363 | Projects | Coordinate MEP routes, ceilings, openings, sleeves and interdisciplinary interfaces | Site MEP Engineer | Trigger: When an approved MEP activity enters the daily or lookahead plan. Action: The Site MEP Engineer completes “Coordinate MEP routes, ceilings, openings, sleeves and interdisciplinary interfaces” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an MEP work plan, technical-readiness record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP activity enters the daily or lookahead plan. | The Site MEP Engineer completes “Coordinate MEP routes, ceilings, openings, sleeves and interdisciplinary interfaces” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an MEP work plan, technical-readiness record, resource request and coordinated interface decision. | Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer keeps all the services fitting together. Routes, ceiling space, openings, sleeves and the points where trades meet. • Starts when: before installation in an area, and continuously while several trades work together. • How it runs: (1) confirm route levels and elevations in the ceiling or shaft against the coordinated drawing. (2) Confirm openings and sleeves are in place and correctly positioned. (3) Confirm the ceiling void has room for insulation, hangers, access and the ceiling itself. (4) Resolve clashes through coordination rather than local rerouting. (5) Record any agreed change and pass it to drafting. • Proof it happened: route confirmation records, sleeve and opening verification, clash resolution records and change notes to drafting. • Where it usually breaks: services are installed at their drawn level with no allowance for insulation, hangers and the ceiling, and the ceiling cannot then be closed. | • Require the installed level check to include insulation thickness, hanger depth, gradient and ceiling zone. Services that fit on paper but not with insulation are a repeated cause of ceiling void rework. • State that clashes are resolved through coordination with a recorded change, never by local rerouting. • Give drainage and gravity systems route priority in the SOP, since they cannot be rerouted around obstructions. • Require verification of sleeves and openings before the trade installs, so mistakes are found before cutting is needed. • Pass every agreed route change to drafting the same week, otherwise the as built diverges permanently.
364 | Projects | Prepare MEP inspection, testing, commissioning and authority schedules | Site MEP Engineer | Trigger: When an approved MEP activity enters the daily or lookahead plan. Action: The Site MEP Engineer completes “Prepare MEP inspection, testing, commissioning and authority schedules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an MEP work plan, technical-readiness record, resource request and coordinated interface decision. Control/Handoff: Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP activity enters the daily or lookahead plan. | The Site MEP Engineer completes “Prepare MEP inspection, testing, commissioning and authority schedules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an MEP work plan, technical-readiness record, resource request and coordinated interface decision. | Requests reference IFC, submittal and programme; technical ambiguity goes to CTO and resource conflicts go to the Project Engineer. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer plans out the testing, commissioning and authority inspections early, so they are not squeezed into the last weeks. • Starts when: at the start of the installation phase, and updated as work progresses. • How it runs: (1) list every test, commissioning activity and authority inspection required per system. (2) Set the prerequisites for each: completion, power, water, cleaning, approvals. (3) Place them in the programme with realistic durations and dependencies. (4) Identify who witnesses each one and what notice they need. (5) Track prerequisite readiness against the schedule. • Proof it happened: a testing and commissioning schedule, a prerequisite matrix, witness requirements and a readiness tracker. • Where it usually breaks: commissioning is planned as one late block, prerequisites such as permanent power are not ready, and handover slips. | • Require the prerequisite matrix per test, especially permanent power, water and clean conditions. Commissioning failures are almost always prerequisite failures, not technical ones. • Programme commissioning as a phased activity per system and zone, not as a single block at the end. • Identify the permanent power date as a tracked milestone, because it gates most commissioning and is usually outside the project's control. • State witness and notice requirements per test, including authority and client witnesses. • Include integrated and cause and effect testing as separate scheduled activities, since these need all systems complete at once.
365 | Projects | Supervise HVAC installation, equipment, ductwork and piping execution | Site MEP Engineer | Trigger: When an approved MEP work front, method and inspection plan are released. Action: The Site MEP Engineer completes “Supervise HVAC installation, equipment, ductwork and piping execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: installed MEP work meeting approved routing, access, sequence, performance and protection requirements. Control/Handoff: Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP work front, method and inspection plan are released. | The Site MEP Engineer completes “Supervise HVAC installation, equipment, ductwork and piping execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | installed MEP work meeting approved routing, access, sequence, performance and protection requirements. | Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises the HVAC installation. Equipment, ductwork and piping installed correctly, supported properly and sealed as specified. • Starts when: HVAC installation is released in a zone. • How it runs: (1) confirm the material, route and level against the approved drawing. (2) Control installation: joints, supports, spacing, gradients, expansion and access. (3) Control insulation, vapour barrier and finishing. (4) Witness pressure and duct leakage testing before concealment. (5) Inspect and record each stage before it is covered. • Proof it happened: installation inspection records, support and spacing checks, pressure and leakage test records and insulation inspections. • Where it usually breaks: ductwork or pipework is insulated and the ceiling closed before pressure or leakage testing, so a leak means opening finished work. | • Make pressure and leakage testing a hold point before insulation and concealment. Testing after covering is the most expensive avoidable sequence error in HVAC. • Set support type and spacing per size and service in the SOP, since inadequate support causes sagging, joint failure and noise. • Require condensate drain routes with falls and traps to be checked, as condensate is the commonest source of water damage in fit out. • Include vapour barrier continuity in insulation inspection, because breaks cause condensation and hidden corrosion. • Require access provision at every valve, damper, filter and coil to be verified against the ceiling layout.
366 | Projects | Supervise plumbing, drainage, water and pump-system execution | Site MEP Engineer | Trigger: When an approved MEP work front, method and inspection plan are released. Action: The Site MEP Engineer completes “Supervise plumbing, drainage, water and pump-system execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: installed MEP work meeting approved routing, access, sequence, performance and protection requirements. Control/Handoff: Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP work front, method and inspection plan are released. | The Site MEP Engineer completes “Supervise plumbing, drainage, water and pump-system execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | installed MEP work meeting approved routing, access, sequence, performance and protection requirements. | Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises plumbing and drainage. Water supply, waste, drainage and pumps installed to the right falls, tested and clean. • Starts when: plumbing or drainage installation is released in a zone. • How it runs: (1) confirm material, route, invert levels and gradients against the drawing. (2) Control jointing, supports, fixing and thermal movement. (3) Confirm drainage falls, cleanouts and venting. (4) Witness pressure testing on supply and gravity or ball testing on drainage before concealment. (5) Control flushing, disinfection and pump installation and alignment. • Proof it happened: level and gradient records, pressure and drainage test records, flushing and disinfection certificates and pump installation records. • Where it usually breaks: drainage gradient is lost by one or two millimetres over a long run, and the blockage problem is permanent. | • Require invert level and gradient recording along drainage runs, not just at the ends. A lost fall in a concealed run is a permanent operational defect. • Make pressure and drainage testing a hold point before concealment, with the test duration and acceptance stated. • Require flushing and disinfection certificates with water sampling before handover, since this is both a health matter and a common closeout gap. • Include cleanout and rodding access positions as verified items against the finished layout. • Set pump alignment, base fixing and vibration isolation as inspected items, because misalignment destroys pumps early.
367 | Projects | Supervise electrical power, lighting, containment and earthing execution | Site MEP Engineer | Trigger: When an approved MEP work front, method and inspection plan are released. Action: The Site MEP Engineer completes “Supervise electrical power, lighting, containment and earthing execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: installed MEP work meeting approved routing, access, sequence, performance and protection requirements. Control/Handoff: Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP work front, method and inspection plan are released. | The Site MEP Engineer completes “Supervise electrical power, lighting, containment and earthing execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | installed MEP work meeting approved routing, access, sequence, performance and protection requirements. | Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises the electrical installation. Power, lighting, containment and earthing installed safely and to the drawings. • Starts when: electrical installation is released in a zone. • How it runs: (1) confirm cable type, size, route and containment against the approved drawing. (2) Control containment installation, support, segregation and fill. (3) Control cable pulling, bending radius, termination and glanding. (4) Control the earthing and bonding installation and its connections. (5) Test insulation, continuity and earthing before energisation and record the results. • Proof it happened: installation inspection records, cable schedules, termination records and insulation, continuity and earth test results. • Where it usually breaks: circuits are energised for temporary use before the earthing and testing are complete, which is a direct danger to life. | • Make energisation a controlled hold point requiring completed earthing, insulation and continuity testing, witnessed and authorised by a named person. This is a life safety control, not a documentation step. • Prohibit temporary energisation of permanent systems without a separate written authorisation and isolation control. • Set segregation rules between power, data and fire cabling in containment, since mixed containment causes interference and code failures. • Require cable bending radius and pulling tension limits to be observed, because damage during pulling is invisible and fails later. • Require earthing continuity records at every connection point, as earthing defects are the hardest to trace after completion.
368 | Projects | Supervise ELV, fire-alarm and life-safety system execution within scope | Site MEP Engineer | Trigger: When an approved MEP work front, method and inspection plan are released. Action: The Site MEP Engineer completes “Supervise ELV, fire-alarm and life-safety system execution within scope” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: installed MEP work meeting approved routing, access, sequence, performance and protection requirements. Control/Handoff: Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP work front, method and inspection plan are released. | The Site MEP Engineer completes “Supervise ELV, fire-alarm and life-safety system execution within scope” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | installed MEP work meeting approved routing, access, sequence, performance and protection requirements. | Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises the low voltage and life safety systems in his scope. Fire alarm, detection, data and security, installed to the design. • Starts when: ELV or life safety installation is released in a zone. • How it runs: (1) confirm device positions and cable types against the approved drawing and the specialist's shop drawings. (2) Control containment, segregation and cable handling. (3) Control device installation, labelling and addressing. (4) Confirm the cause and effect requirements with the specialist before programming. (5) Witness pre tests and record results. • Proof it happened: device position records, cable test results, addressing schedules and pre test records. • Where it usually breaks: detector and device positions are adjusted on site for ceiling layout without checking coverage rules, and the system fails authority inspection. | • Require any device relocation to be checked against coverage and spacing rules and approved, since authority inspection failures here delay occupancy directly. • Require a written and approved cause and effect schedule before programming, otherwise fire system behaviour is invented during commissioning. • Set cable segregation and fire rated cable requirements explicitly, because substitution here is a code violation, not a preference. • Require device labelling and addressing to match the schedule and the panel, as mismatches make the system unmaintainable. • Coordinate with the authority inspection schedule early, since life safety approval commonly gates handover.
369 | Projects | Supervise MEP equipment installation, alignment and service connections | Site MEP Engineer | Trigger: When an approved MEP work front, method and inspection plan are released. Action: The Site MEP Engineer completes “Supervise MEP equipment installation, alignment and service connections” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: installed MEP work meeting approved routing, access, sequence, performance and protection requirements. Control/Handoff: Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP work front, method and inspection plan are released. | The Site MEP Engineer completes “Supervise MEP equipment installation, alignment and service connections” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | installed MEP work meeting approved routing, access, sequence, performance and protection requirements. | Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer supervises the installation of major equipment. Getting it in place, aligned correctly and connected to its services. • Starts when: equipment is delivered and its installation area is ready. • How it runs: (1) confirm the base, plinth, fixing and vibration isolation are per approval. (2) Confirm the rigging and lifting plan and the access route. (3) Position the equipment and check level, alignment and clearances. (4) Connect services: power, control, water, drainage, ducting, with flexible connections where required. (5) Record installation against the manufacturer's requirements and protect it until commissioning. • Proof it happened: plinth and fixing approvals, a lifting plan, alignment and level records, service connection records and manufacturer sign off where required. • Where it usually breaks: the equipment is installed correctly but with no clearance for filter change or coil removal, and it becomes an operations problem for its whole life. | • Require the manufacturer's clearance requirements to be verified before positioning, for both maintenance and removal. Access lost here is lost for the life of the building. • Require an approved lifting and rigging plan for major plant, since these lifts carry both damage and injury risk. • Make vibration isolation and flexible connection installation an inspected item, because rigid connections transmit noise and destroy equipment. • Require manufacturer supervision or sign off where the warranty depends on it, and confirm that condition before installation. • Set protection requirements after installation, since major plant is often damaged or contaminated between installation and commissioning.
370 | Projects | Control MEP builders work, firestopping, access and approved installation sequence | Site MEP Engineer | Trigger: When an approved MEP work front, method and inspection plan are released. Action: The Site MEP Engineer completes “Control MEP builders work, firestopping, access and approved installation sequence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: installed MEP work meeting approved routing, access, sequence, performance and protection requirements. Control/Handoff: Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When an approved MEP work front, method and inspection plan are released. | The Site MEP Engineer completes “Control MEP builders work, firestopping, access and approved installation sequence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | installed MEP work meeting approved routing, access, sequence, performance and protection requirements. | Site MEP Engineer controls supervisors and specialists; unsafe, unapproved or conflicting installation is stopped and escalated. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer controls the builders work, the firestopping, the access provisions and the order in which services are installed. • Starts when: during installation, and before any penetration is sealed or closed. • How it runs: (1) confirm openings and penetrations match the approved builders work. (2) Confirm the approved installation sequence is being followed between trades. (3) Install firestopping to the approved system and rating for each penetration. (4) Confirm access panels and hatches are provided where equipment needs them. (5) Inspect and photograph firestopping before it is concealed. • Proof it happened: builders work verification, sequence compliance records, firestopping inspection records with photographs and an access panel schedule. • Where it usually breaks: firestopping is done with whatever is available rather than the approved system, so the fire rating is void and nobody can tell by looking. | • Require firestopping to the approved system with the product and rating recorded and photographed per penetration. An unapproved seal looks identical and voids the fire rating. • Make firestopping photography with location reference mandatory before concealment, since it cannot be verified afterwards without opening up. • Require an access panel schedule cross checked against every item needing maintenance access before ceilings are closed. • State that new penetrations in rated or structural elements need written approval, whatever the size. • Assign firestopping responsibility explicitly at trade boundaries, because it is the most commonly unowned activity on site.
371 | Projects | Verify MEP materials and equipment against approved submittals and storage rules | Site MEP Engineer | Trigger: When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. Action: The Site MEP Engineer completes “Verify MEP materials and equipment against approved submittals and storage rules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. Control/Handoff: Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. | The Site MEP Engineer completes “Verify MEP materials and equipment against approved submittals and storage rules” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. | Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer checks that MEP material and equipment arriving is what was approved, and that it is stored so it does not get damaged. • Starts when: material or equipment is delivered, and while it is stored. • How it runs: (1) compare the delivery against the approved submittal: make, model, rating, capacity and certificate. (2) Inspect for transport damage, completeness and accessories. (3) Reject and segregate non compliant material. (4) Confirm storage: indoors, covered, dry, sealed ends, protected from dust and rotated where required. (5) Record acceptance, rejection and storage condition. • Proof it happened: material inspection records against submittals, test and compliance certificates, rejection records and storage inspections. • Where it usually breaks: equipment is accepted without checking accessories and loose items, and the missing parts are discovered at commissioning. | • Require an accessories and loose item check against the packing list at delivery, since missing parts found at commissioning cause the worst timed delays. • Require acceptance against the approved submittal rather than the delivery note or purchase order, as this is where substitution is caught. • Set storage rules for sensitive items: sealed duct and pipe ends, dry storage for panels and motors, dust protection and rotation of stored plant. • Collect equipment certificates and test reports at delivery, because chasing them at closeout is a standard delay. • Name who may accept a deviation and require it in writing, so no substitution enters the works unrecorded.
372 | Projects | Perform MEP pre-inspection and raise work-inspection requests | Site MEP Engineer | Trigger: When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. Action: The Site MEP Engineer completes “Perform MEP pre-inspection and raise work-inspection requests” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. Control/Handoff: Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. | The Site MEP Engineer completes “Perform MEP pre-inspection and raise work-inspection requests” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. | Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer checks his own MEP work first, corrects the obvious items, then formally calls for inspection. • Starts when: an MEP activity is complete and ready for inspection. • How it runs: (1) inspect against the drawing, specification and ITP. (2) Fix minor items before calling anyone. (3) Confirm preceding inspections, tests and material approvals are in place. (4) Raise the inspection request with correct notice, location and system reference. (5) Attend, record the result and close comments with evidence. • Proof it happened: internal pre inspection checklists, raised inspection requests, results and comment closure records. • Where it usually breaks: inspection is called before the pre test results are available, and it is rejected on documents rather than on the work. | • Require pre test results and material approvals to be attached to the inspection request, since MEP inspections fail on documents more often than on installation. • Make the internal pre inspection checklist a required attachment, not an informal walk. • Track first time pass rate per system and per crew, as it is the clearest indicator of supervision quality. • Set the notice period and require the exact system and location reference on the request. • Set a comment closure route with a re inspection record, so nothing is left open at handover.
373 | Projects | Witness pressure, leakage, insulation, continuity and functional pre-tests | Site MEP Engineer | Trigger: When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. Action: The Site MEP Engineer completes “Witness pressure, leakage, insulation, continuity and functional pre-tests” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. Control/Handoff: Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. | The Site MEP Engineer completes “Witness pressure, leakage, insulation, continuity and functional pre-tests” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. | Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer witnesses the early tests. Pressure, leakage, insulation and continuity checks done before anything is closed up. • Starts when: an installed section is ready for testing, and before concealment. • How it runs: (1) confirm the section is complete, isolated and safe to test. (2) Confirm the instruments are calibrated and in date. (3) Apply the test to the specified value and duration. (4) Record the result, the instrument used and the witness. (5) Repair, retest and record where the test fails. • Proof it happened: test records with values, durations, instrument identity and calibration reference, witness signature and retest records. • Where it usually breaks: tests are recorded as passed without stated values, durations or calibrated instruments, so the record proves nothing. | • Require the test value, duration, instrument identity and calibration reference on every test record. A pass with no data is not evidence. • Make instrument calibration validity a pre test check, because results from an uncalibrated instrument are void and may need full retesting. • Require retest after any repair, and keep both the failed and passed records rather than replacing them. • State that testing is a hold point before concealment or insulation for every relevant system. • Set who may witness each test type, and require the witness to sign at the time rather than afterwards.
374 | Projects | Raise MEP RFIs for missing, conflicting or impractical information | Site MEP Engineer | Trigger: When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. Action: The Site MEP Engineer completes “Raise MEP RFIs for missing, conflicting or impractical information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. Control/Handoff: Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. | The Site MEP Engineer completes “Raise MEP RFIs for missing, conflicting or impractical information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. | Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: when MEP information is missing, contradictory or unbuildable, the engineer raises it formally rather than solving it on site. • Starts when: a gap, clash or impractical detail is found in the services information. • How it runs: (1) confirm the issue against the latest revision and the coordinated drawing. (2) Write the query with location, drawing reference and the problem. (3) Propose a solution where possible. (4) State the answer date needed and the programme impact. (5) Log, follow up and distribute the answer to all affected trades. • Proof it happened: a query register with dates, the query, the answer received and the distribution record. • Where it usually breaks: site reroutes services to get past a clash without recording it, and the as built and the maintenance access are both wrong. | • State plainly that site does not resolve services clashes by rerouting without a recorded change. Unrecorded rerouting is the main reason as builts cannot be trusted. • Require the answer date and programme impact on every query, because queries without a stated consequence are answered last. • Track ageing of open queries with an escalation threshold, so information delay is on record as a delay event. • Require answers to be distributed to every affected trade, not just filed. • Require a coordinated drawing revision after any answer that changes a route, so the record stays usable.
375 | Projects | Record MEP defects, NCRs, rework and corrective-action closure | Site MEP Engineer | Trigger: When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. Action: The Site MEP Engineer completes “Record MEP defects, NCRs, rework and corrective-action closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. Control/Handoff: Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. | The Site MEP Engineer completes “Record MEP defects, NCRs, rework and corrective-action closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. | Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: when MEP work is wrong, the engineer records it, gets it corrected, and confirms the cause has been addressed. • Starts when: a defect or non compliance is identified by anyone. • How it runs: (1) record the defect with location, system, description, photograph and the requirement breached. (2) Decide the disposition: repair, replace, or accept as is with approval. (3) Identify the cause and the responsible party. (4) Execute, inspect and retest the correction. (5) Close with evidence and act on repeated causes. • Proof it happened: an NCR and defect register, dispositions with approvals, rework and retest records and closure evidence. • Where it usually breaks: the repair is done but the system is not retested, so the defect is closed on paper and remains real. | • Require a retest after any corrective work on a tested system, since a repair without retest leaves the defect unproven either way. • Require the record even where the correction is immediate, so cause analysis and back charging remain possible. • State that accept as is needs the designer's written approval, as it is a design acceptance. • Make cause and responsible party mandatory fields, otherwise defects end up owned by nobody. • Set a repeat defect threshold that triggers a method or competence review rather than another repair.
376 | Projects | Verify daily MEP material use, equipment protection and site allocation | Site MEP Engineer | Trigger: When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. Action: The Site MEP Engineer completes “Verify daily MEP material use, equipment protection and site allocation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. Control/Handoff: Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When MEP material arrives or work reaches inspection, testing, concealment or resource-control point. | The Site MEP Engineer completes “Verify daily MEP material use, equipment protection and site allocation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved equipment/material evidence, WIR, test result, RFI, NCR closure or allocation record. | Unapproved material, failed test and inaccessible/nonconforming work are held, recorded and corrected before release. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer checks each day what MEP material was used, that equipment on site is protected, and that material is where it is supposed to be. • Starts when: daily, and at reconciliation points. • How it runs: (1) record material issued per zone and system. (2) Compare against the theoretical requirement for the work done. (3) Verify the physical balance and the condition of stored equipment. (4) Confirm high value items are secured and accounted for. (5) Report variance and loss. • Proof it happened: consumption records, theoretical against actual comparison, equipment protection checks and a high value item register. • Where it usually breaks: high value items such as cable, copper, valves and fittings are not tracked closely, and losses are only found at reconciliation. | • Put high value items such as cable, copper, brass and control devices on a tighter controlled register with issue against signature, since these carry the highest theft and loss risk on site. • Require theoretical against actual comparison rather than consumption recording alone. • Set allowed wastage per material type, including cable offcut allowance, so variance can be judged. • Include a stored equipment condition check, because damage during storage is common and is disputed later with vendors. • Set an investigation threshold and reporting route for unexplained loss.
377 | Projects | Record daily MEP progress, quantities, photographs and constraints | Site MEP Engineer | Trigger: When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. Action: The Site MEP Engineer completes “Record daily MEP progress, quantities, photographs and constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. Control/Handoff: Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. | The Site MEP Engineer completes “Record daily MEP progress, quantities, photographs and constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. | Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer records daily what MEP work was installed, how much, with photographs, and what held the work up. • Starts when: daily, at the end of every shift. • How it runs: (1) record installed quantities per system and zone. (2) Record manpower, plant and material used. (3) Take dated progress photographs, particularly of work about to be concealed. (4) Record constraints, delays, instructions and events with times. (5) Submit the same day and retain the record. • Proof it happened: signed daily reports, installed quantity records, dated photographs and a constraint and event log. • Where it usually breaks: waiting time caused by another trade's incomplete work is not recorded, so the disruption cannot be proven or recovered. | • Require waiting time and the trade or cause responsible to be recorded with times. MEP is the trade most disrupted by others, and this log is the only evidence of it. • Require photographs of work about to be concealed, with location naming, since these become the only record of what is inside the ceiling or wall. • Set same day submission with a named recipient. • Record actual against planned manpower, so both productivity and standing time are provable. • State that the daily report is a contemporaneous record and is not edited later, only supplemented with a dated addendum.
378 | Projects | Verify MEP measurements and completed quantities with the Quantity Surveyor | Site MEP Engineer | Trigger: When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. Action: The Site MEP Engineer completes “Verify MEP measurements and completed quantities with the Quantity Surveyor” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. Control/Handoff: Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. | The Site MEP Engineer completes “Verify MEP measurements and completed quantities with the Quantity Surveyor” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. | Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer and the quantity surveyor agree the MEP quantities installed, so billing matches what is actually in the building. • Starts when: at the measurement cycle, or on completion of a system or zone. • How it runs: (1) measure installed quantities jointly against the drawings. (2) Agree the measurement basis and what is included in the rate. (3) Keep variation work separate from base scope. (4) Sign the joint measurement record. (5) Hand it to the Quantity Surveyor for billing and retain a copy. • Proof it happened: signed joint measurement records, agreed quantity sheets and separately recorded variation quantities. • Where it usually breaks: concealed installed quantities are claimed without a verified record, and the client rejects them at valuation. | • Require concealed work quantities to be recorded and jointly verified before concealment, since after closing there is no way to substantiate them at valuation. • Require joint measurement signed by engineer and surveyor, because separately produced quantities always diverge. • State the measurement basis, particularly what fittings, supports and accessories are deemed included in the rate. This is the most argued point in MEP measurement. • Keep variation quantities separate from base scope from the start. • Align the measurement cycle with the billing cycle so measurement is not rushed at submission.
379 | Projects | Coordinate integrated MEP testing and commissioning activities | Site MEP Engineer | Trigger: When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. Action: The Site MEP Engineer completes “Coordinate integrated MEP testing and commissioning activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. Control/Handoff: Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. | The Site MEP Engineer completes “Coordinate integrated MEP testing and commissioning activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. | Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer coordinates the testing and commissioning of the systems together, so they work as a whole rather than only individually. • Starts when: individual systems are complete and pre tested, and integrated operation can be demonstrated. • How it runs: (1) confirm every prerequisite: permanent power, water, cleaning, controls, individual test completion. (2) Sequence commissioning by system and dependency. (3) Run balancing, functional testing and integrated cause and effect testing. (4) Record results against design values, item by item. (5) Close deficiencies, retest and obtain witnessed acceptance. • Proof it happened: commissioning records with measured against design values, balancing reports, cause and effect test records and witnessed acceptance. • Where it usually breaks: commissioning sheets are signed without comparing measured values against design, so the systems are accepted without evidence they perform. | • Require every commissioning record to show the measured value against the design value item by item. A signed sheet with no comparison proves nothing and hides underperformance. • Require integrated cause and effect testing as a separate witnessed activity, because systems that pass individually still fail together. • Confirm the permanent power and water prerequisites in writing before commissioning is scheduled. • Require balancing results per terminal, since headline plant performance hides local failures. • Set a deficiency and retest route so items are closed with evidence rather than carried into handover.
380 | Projects | Maintain MEP red-lines and verified as-built information | Site MEP Engineer | Trigger: When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. Action: The Site MEP Engineer completes “Maintain MEP red-lines and verified as-built information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. Control/Handoff: Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. | The Site MEP Engineer completes “Maintain MEP red-lines and verified as-built information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. | Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer marks up where the services were actually installed when it differs from the drawings, and keeps that record verified. • Starts when: continuously during installation, and before any concealment. • How it runs: (1) mark route, level and device position changes on the record set as they happen. (2) Record actual dimensions, levels and equipment locations. (3) Mark concealed items before covering, since they cannot be verified later. (4) Verify against the physical installation and sign. (5) Hand to drafting for the as built drawings. • Proof it happened: signed and dated red line mark ups, verified concealed item records and a handover record to drafting. • Where it usually breaks: concealed services are not red lined before covering, so nobody can locate them when maintenance or alteration is needed. | • Make red lining of concealed services a hold point before covering. Once closed, buried route information is lost permanently and future works will damage the services. • Require actual measured dimensions from fixed reference points, not descriptive notes, so items can be located again. • Require a monthly completeness check of the red line set as a condition of progress certification. • Name who signs the mark up as verified, since unverified mark ups just move the error into a formal drawing. • Include valve, damper and isolation point locations, as these are what operations needs first in an emergency.
381 | Projects | Coordinate MEP snag identification and closure | Site MEP Engineer | Trigger: When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. Action: The Site MEP Engineer completes “Coordinate MEP snag identification and closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. Control/Handoff: Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. | The Site MEP Engineer completes “Coordinate MEP snag identification and closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. | Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer identifies and clears the small outstanding MEP items so the systems are complete and acceptable. • Starts when: systems approach completion, and at client or consultant walkthroughs. • How it runs: (1) walk the systems and list snags with location and system reference. (2) Assign each to a trade or specialist with a target date. (3) Complete and inspect the work, retesting where it affects performance. (4) Photograph the closure and obtain acceptance. (5) Report open and closed status until clear. • Proof it happened: a snag list with system references, assignments and dates, retest records where applicable and accepted closure records. • Where it usually breaks: a snag that affects system performance is closed without retesting, and the problem is only found by operations after handover. | • Require a retest where a snag affects performance, flow, pressure or protection, rather than a visual closure. Performance snags closed visually reappear as operational failures. • Run an internal snagging round before inviting the client, because a long client generated list damages confidence right at handover. • Track specialist subcontractor snags separately with contractual leverage attached, since specialists demobilise early. • Hold an ageing view so old snags do not disappear into a long list. • Require protection and access restoration after snag clearance, including replacement of ceiling tiles and access panels.
382 | Projects | Compile MEP O&M, warranty, test and handover evidence | Site MEP Engineer | Trigger: When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. Action: The Site MEP Engineer completes “Compile MEP O&M, warranty, test and handover evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. Control/Handoff: Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. Continuity/Escalation: A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. Timing: To be confirmed. | When the daily reporting, measurement, testing, snag or MEP-closeout milestone becomes due. | The Site MEP Engineer completes “Compile MEP O&M, warranty, test and handover evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified MEP quantities, progress evidence, test status, red-lines, O&M data and completion handover. | Site MEP Engineer reconciles evidence with Project Engineer, QS, QHSE and CTO; unresolved issues remain assigned with dates. | A competent MEP engineer may provide documented backup; unresolved technical, testing, authority, life-safety or interface risk escalates to the Project Engineer, CTO or QHSE as applicable. | To be confirmed. | • In plain words: the engineer compiles the MEP handover pack. Operating manuals, warranties, test results, as builts and training records, in one complete set. • Starts when: systems are completed and commissioned, and handover approaches. • How it runs: (1) list what the contract requires: O&M manuals, warranties, test and commissioning records, as builts, spares, training. (2) Collect from vendors and specialists as their work completes, not at the end. (3) Confirm warranty start dates and conditions. (4) Deliver the operator training and record attendance. (5) Hand over formally with a signed index and archive a copy. • Proof it happened: a completed handover index, O&M manuals, warranty certificates with dates, commissioning records, as builts, spares receipts and signed training records. • Where it usually breaks: manuals and warranties are chased after the vendors have demobilised, and retention is held for missing documents rather than for missing work. | • Make vendor documentation, spares and training a condition of their final payment, and collect it as each vendor completes. Chasing demobilised vendors is why MEP closeout runs for months. • Record the warranty start date and conditions per item, because warranties that start at delivery rather than handover quietly expire during the defect period. • Build the handover index at project start and populate it progressively rather than assembling it at the end. • Require spares and special tools to be delivered, counted and receipted, since these are routinely never supplied. • Require recorded operator training with attendance and content, as untrained operators damage new plant within the warranty period.
383 | Projects | Receive the approved daily civil work plan and latest drawings | Civil Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The Civil Supervisor completes “Receive the approved daily civil work plan and latest drawings” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The Civil Supervisor completes “Receive the approved daily civil work plan and latest drawings” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: at the start of the shift the civil supervisor collects the day's work plan and the current drawings, so the crews are built off the same instruction the engineer issued. • Starts when: the shift begins, or the plan changes during the day because of access, weather or a material shortage. • How it runs: (1) the supervisor takes the plan from the site engineer. (2) He checks he holds the current drawing revision for each activity in it. (3) He reads it against what the crews physically finished yesterday. (4) He raises anything unworkable before crews are deployed rather than after. (5) He confirms he has understood the plan for the shift. • Proof it happened: the received daily plan, the drawing revision list held at the work front, and the supervisor's acknowledgement. • Where it usually breaks: the supervisor works from memory or from a marked up print from last week, and a crew builds to a superseded revision. | • State in the SOP that the supervisor must physically hold the drawing, not have seen it. Working from memory is the root cause of most rework at this level. • Require a revision check against the controlled register at the start of every shift, and require superseded prints at the work front to be removed. • Give the supervisor an explicit duty to reject an unworkable plan before deployment, with the reason recorded. That protects him and gives the engineer real information. • Set the handover point between shifts, including what the outgoing supervisor must pass on about incomplete work. • Keep the plan format short enough to be usable on site. A plan the supervisor cannot carry will not be followed.
384 | Projects | Check civil work-front access, benchmarks and pre-start readiness | Civil Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The Civil Supervisor completes “Check civil work-front access, benchmarks and pre-start readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The Civil Supervisor completes “Check civil work-front access, benchmarks and pre-start readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: before crews move in, the supervisor walks the work front and checks it is actually ready: it can be reached safely, the reference marks are there, and nothing is in the way. • Starts when: a new work front opens, or before restarting a front that was left standing. • How it runs: (1) he walks the area physically. (2) He checks safe access, edge protection, lighting and housekeeping. (3) He confirms the benchmarks and reference lines the crew will work from are present and undamaged. (4) He checks the preceding activity is complete and released. (5) He confirms readiness to the engineer or reports what is blocking it. • Proof it happened: the work front readiness check, the access confirmation and the recorded blockers. • Where it usually breaks: crews are sent to a front that was ready last week, and stand waiting while the obstruction is cleared. | • Make the walk mandatory and physical in the SOP. A readiness check done from the office is the standard cause of standing time. • List the minimum checks: safe access, fall protection, lighting, preceding activity released, references present, area clear of stored material. • Require the blocker to be reported before deployment, with the crew held rather than sent. Standing time at the front costs more than a delayed start. • State who may declare a front ready and who may release the preceding activity, so readiness is not self declared by the crew that wants to start. • Add a rule that damaged or missing benchmarks are reported to the engineer and never re established by the crew.
385 | Projects | Allocate civil crews and chargehands to approved work fronts | Civil Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The Civil Supervisor completes “Allocate civil crews and chargehands to approved work fronts” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The Civil Supervisor completes “Allocate civil crews and chargehands to approved work fronts” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor decides which crew and chargehand goes to which work front, and how many people each front needs. • Starts when: the daily plan is confirmed, or resources have to be moved during the shift. • How it runs: (1) he matches the trade and skill needed to the crews available. (2) He allocates each crew to an approved and ready front. (3) He names the chargehand accountable for each front. (4) He briefs each chargehand on the target and the sequence. (5) He records the deployment for the day. • Proof it happened: the daily deployment record showing crew, chargehand, front and headcount. • Where it usually breaks: crews get spread thinly across too many fronts, so nothing is finished and every front looks half done. | • Put a rule in the SOP that a crew is only deployed to an approved and ready front. That closes the loop with the readiness check. • Require a named chargehand per front. Accountability without a name attached is where work quietly goes unsupervised. • Discourage opening more fronts than the crew count supports, and say who authorises opening an additional front. • Require the deployment record to be kept, since it is the only evidence of how labour was actually used when productivity is questioned later. • Define how skill certification is checked for restricted work, so an uncertified worker is not deployed to it.
386 | Projects | Check civil materials, tools, scaffolds, plant and access arrangements | Civil Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The Civil Supervisor completes “Check civil materials, tools, scaffolds, plant and access arrangements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The Civil Supervisor completes “Check civil materials, tools, scaffolds, plant and access arrangements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor checks the crews have what they need before they start: materials, tools, scaffold, plant and a safe way to reach the work. • Starts when: before deployment, and whenever a shortage appears during the shift. • How it runs: (1) he checks material at the front against the day's activity. (2) He checks tools and plant are present and serviceable. (3) He confirms scaffold and access equipment are inspected and tagged. (4) He raises shortages to the engineer or storekeeper immediately. (5) He confirms the front is equipped or holds the activity. • Proof it happened: the pre start resource check, the shortage notes and the scaffold or access tags. • Where it usually breaks: the shortage is spotted after the crew is already at the front, so the whole gang waits. | • Require the resource check before deployment, not at the front. Finding the gap early is the entire value of the item. • State that untagged or expired scaffold and access equipment may not be used, and that the supervisor may not authorise its use under time pressure. • Require unserviceable tools and plant to be removed from the front, not left in service, and set who is told. • Give a shortage escalation route with a response time, so the supervisor is not left chasing material informally. • Add a check on quantities against the day's target, so material is not brought in a volume that guarantees wastage or theft.
387 | Projects | Deliver the civil method and safety briefing with the engineer and QHSE team | Civil Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The Civil Supervisor completes “Deliver the civil method and safety briefing with the engineer and QHSE team” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The Civil Supervisor completes “Deliver the civil method and safety briefing with the engineer and QHSE team” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: before work starts, the supervisor talks the crew through how the job will be done and the specific dangers involved, together with the engineer and safety team. • Starts when: at the start of an activity, on a change of method, after an incident, or when new workers join the crew. • How it runs: (1) he goes through the method and sequence in the language the crew understands. (2) The QHSE representative covers the hazards and controls. (3) The permit conditions are stated where a permit applies. (4) Workers confirm understanding and are given the chance to raise concerns. (5) Attendance is recorded by name. • Proof it happened: the signed briefing record with names, the method referred to, and the permit reference. • Where it usually breaks: the sheet is signed at the end of the shift for a briefing nobody actually received. | • State in the SOP that the briefing happens before work starts and that signatures are taken at the briefing. A sheet signed retrospectively is a false record and should be treated as a discipline matter. • Require the briefing to be delivered in a language the crew genuinely understands, and name who translates where needed. • Require a new briefing whenever the method, sequence or crew composition changes, not just at first start. • Include the worker's right to stop or question the task, said in plain words, since that is what makes the briefing a control rather than a formality. • Keep the record traceable to the activity and the front, so it can be produced during an investigation.
388 | Projects | Supervise civil setting-out, earthworks and substructure activities | Civil Supervisor | Trigger: When the approved civil crew begins the assigned activity. Action: The Civil Supervisor completes “Supervise civil setting-out, earthworks and substructure activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled civil execution completed to the daily target and ready for checking. Control/Handoff: The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved civil crew begins the assigned activity. | The Civil Supervisor completes “Supervise civil setting-out, earthworks and substructure activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled civil execution completed to the daily target and ready for checking. | The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the ground works: setting out from the marks, excavation, filling and the parts of the structure below ground level. • Starts when: the front is released, the excavation permit is in place and setting out has been checked. • How it runs: (1) he confirms the setting out against the engineer's checked marks. (2) He supervises excavation to the required line and level, with support and dewatering as required. (3) He controls fill placement and compaction in layers. (4) He calls the engineer for inspection at the required points. (5) He does not proceed past a hold point without release. • Proof it happened: the level records, compaction test results, inspection releases and the daily record. • Where it usually breaks: excavation continues past the design depth or without support, which is both a safety and a stability problem. | • Write the excavation safety rules in plain terms: support or battering, exclusion zones, spoil placement distance, and no entry to an unsupported deep excavation. This is the highest fatality risk activity in civil work. • Require services clearance and permit before breaking ground, with a check against the marked services drawing. • Set the hold points clearly: formation level, compaction results, and any work below the design depth. Say that over excavation is reported and never simply refilled. • Require layer by layer compaction with test frequency stated, since compaction failure is invisible once the slab is above it. • Add a rule that the supervisor stops work on any unexpected ground condition or buried obstruction and calls the engineer.
389 | Projects | Supervise formwork, reinforcement and concrete activities | Civil Supervisor | Trigger: When the approved civil crew begins the assigned activity. Action: The Civil Supervisor completes “Supervise formwork, reinforcement and concrete activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled civil execution completed to the daily target and ready for checking. Control/Handoff: The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved civil crew begins the assigned activity. | The Civil Supervisor completes “Supervise formwork, reinforcement and concrete activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled civil execution completed to the daily target and ready for checking. | The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the concrete work: putting up the shuttering, fixing the steel, and pouring and curing the concrete. • Starts when: the reinforcement and formwork are ready and the pre pour inspection is due. • How it runs: (1) he checks formwork line, level, tightness and support. (2) He checks the reinforcement matches the drawing for size, spacing, laps and cover. (3) He arranges the pre pour inspection and does not pour without the release. (4) He supervises placing, compaction and finishing. (5) He controls curing and formwork removal timing. • Proof it happened: the pre pour release, pour record, cube sample references and the curing record. • Where it usually breaks: the pour goes ahead on a verbal go ahead while the release is still pending, and the covered work can never be checked again. | • Make it absolute in the SOP that concrete is not placed without the signed pre pour release, and that no verbal release is valid. This is the single most important rule in the civil SOP. • Require cover spacers and a cover check as a named step, because insufficient cover is the main long term durability failure. • Set minimum curing periods and formwork striking times by element type, and require them to be recorded, not judged. • Require the supervisor to stop the pour and call the engineer on any formwork movement, blockage or delivery interruption, and to record the interruption. • State who takes cube samples and how they are identified back to the pour, since unidentified samples cannot be used as evidence.
390 | Projects | Supervise masonry, plaster, waterproofing and roofing activities | Civil Supervisor | Trigger: When the approved civil crew begins the assigned activity. Action: The Civil Supervisor completes “Supervise masonry, plaster, waterproofing and roofing activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled civil execution completed to the daily target and ready for checking. Control/Handoff: The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved civil crew begins the assigned activity. | The Civil Supervisor completes “Supervise masonry, plaster, waterproofing and roofing activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled civil execution completed to the daily target and ready for checking. | The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs blockwork, plastering, waterproofing and roofing: the works that enclose the building and keep water out. • Starts when: the structure is released for these activities and the materials are approved and on site. • How it runs: (1) he sets out walls and openings from the approved drawing. (2) He supervises blockwork for line, plumb, tying and lintels. (3) He controls plaster mix, thickness and curing. (4) He supervises waterproofing surface preparation, application and laps, and arranges the water test. (5) He supervises roofing layers, falls and terminations. • Proof it happened: the inspection records, the waterproofing water test result, and the material approvals. • Where it usually breaks: waterproofing is covered before the water test, and the leak only appears after finishes are installed. | • State the hold point in plain words: nothing covers waterproofing until the water test has passed and been signed. Say the test duration explicitly. • Require openings to be set out from the current drawing and checked before blockwork proceeds, since cutting openings later damages the wall and the programme. • Require substrate preparation to be inspected before any waterproofing or plaster is applied, because adhesion failure comes from preparation, not from the product. • Require falls to be checked with levels on roofs and wet areas rather than by eye, and record the readings. • Add protection rules for completed waterproofing, and require damage from following trades to be reported rather than patched quietly.
391 | Projects | Supervise finishing and external-works activities | Civil Supervisor | Trigger: When the approved civil crew begins the assigned activity. Action: The Civil Supervisor completes “Supervise finishing and external-works activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled civil execution completed to the daily target and ready for checking. Control/Handoff: The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved civil crew begins the assigned activity. | The Civil Supervisor completes “Supervise finishing and external-works activities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled civil execution completed to the daily target and ready for checking. | The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the finishing work inside the building and the works outside it: tiling, painting, doors, paving, kerbs and landscaping. • Starts when: the area is released for finishes, or external works are released after backfilling and services. • How it runs: (1) he confirms the area is clean, dry and ready to receive finishes. (2) He confirms the approved material and colour for each location. (3) He sets out tiling, paving and joints from the approved layout. (4) He supervises workmanship, levels, joints and edges. (5) He arranges protection of completed finishes. • Proof it happened: the finishes inspection records, the approved material references and the protection record. • Where it usually breaks: finishes are installed in an area still being used by other trades, and the same work is paid for twice. | • Require a written area release before finishes start, confirming preceding trades are complete. Finishes started early is the most common source of double cost. • Require the approved material and code to be confirmed per location, because a finish installed to the wrong specification is usually replaced in full. • Require setting out of tile and paving joints to be checked before laying, since joint alignment cannot be corrected afterwards. • Make protection of completed work a named step with a responsible party, and require damage to be reported and charged to the trade that caused it. • Add a snag walk before handover to the engineer, so obvious defects are corrected before formal inspection.
392 | Projects | Control temporary works, protection and civil work sequence | Civil Supervisor | Trigger: When the approved civil crew begins the assigned activity. Action: The Civil Supervisor completes “Control temporary works, protection and civil work sequence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled civil execution completed to the daily target and ready for checking. Control/Handoff: The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved civil crew begins the assigned activity. | The Civil Supervisor completes “Control temporary works, protection and civil work sequence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled civil execution completed to the daily target and ready for checking. | The Civil Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor keeps control of the temporary items that hold the work up while it is being built, such as props and shoring, and keeps the trades working in the right order. • Starts when: temporary works are erected, loading changes, or the sequence has to be altered. • How it runs: (1) he checks temporary works are erected to the approved design. (2) He confirms props and shoring are not removed before the permitted time. (3) He controls loading on newly built elements. (4) He keeps the trade sequence as planned and raises clashes to the engineer. (5) He protects completed work from following activities. • Proof it happened: the temporary works inspection records, the propping removal approvals and the sequence notes. • Where it usually breaks: props are removed early to free up access, which is a collapse risk and never recorded. | • State plainly that no prop, shoring or support is removed without written engineering approval, whatever access pressure exists. This is a life safety rule, not an administrative one. • Require temporary works to be erected to an approved design and inspected before loading, with the inspector named. • Set loading limits on new slabs, including material stacking, and say who authorises an exception. • Require sequence changes to be approved rather than absorbed by the supervisor, because an altered sequence often removes a required inspection. • Add a protection responsibility so completed work damaged by following trades is recorded and attributed.
393 | Projects | Monitor civil crew productivity against the daily target | Civil Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The Civil Supervisor completes “Monitor civil crew productivity against the daily target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The Civil Supervisor completes “Monitor civil crew productivity against the daily target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor watches how much the crews are actually producing against what the day's target said, and acts during the shift rather than reporting the shortfall afterwards. • Starts when: during the shift, at set checkpoints. • How it runs: (1) he takes the target for each front from the plan. (2) He checks progress at intervals during the shift. (3) He finds the cause where output is behind, whether access, material, method or manpower. (4) He redeploys or escalates within the shift. (5) He records the actual output and the reason for any gap. • Proof it happened: the daily productivity record showing target, actual and cause. • Where it usually breaks: the shortfall is only reported at the end of the day, when nothing can be done about it. | • Set mid shift checkpoints in the SOP rather than end of shift reporting only. A gap found at noon can still be recovered. • Require the cause to be recorded alongside the number, because output figures without causes give management nothing to act on. • Give the supervisor a stated authority to redeploy within his own crews, and a threshold above which he must escalate. • Define the unit of measurement for each activity so productivity is comparable between fronts and days. • Require repeated shortfalls on the same cause to be raised formally, since that is a planning or supply problem rather than a crew problem.
394 | Projects | Check civil dimensions, levels, workmanship and tolerances | Civil Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The Civil Supervisor completes “Check civil dimensions, levels, workmanship and tolerances” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The Civil Supervisor completes “Check civil dimensions, levels, workmanship and tolerances” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor checks the work as it is being built against the drawing: the dimensions, the levels and the standard of finish. • Starts when: continuously during the activity, and before calling the engineer to inspect. • How it runs: (1) he checks dimensions and levels against the current drawing. (2) He checks workmanship against the agreed standard or benchmark sample. (3) He checks tolerances at the points that matter. (4) He corrects deviations while the work is still open. (5) He only calls the engineer once he believes the work will pass. • Proof it happened: the supervisor's check records, the corrections made and the inspection request. • Where it usually breaks: the supervisor relies on the engineer to find the errors, so inspections fail repeatedly and time is lost each round. | • State in the SOP that the supervisor's check is a separate control from the engineer's inspection, not a duplicate of it. If he only requests inspection, the first line of quality control does not exist. • Require a benchmark sample or mock up for repetitive finishes, so the standard is a physical reference rather than an opinion. • Give the tolerances in the SOP, by element, in figures. A tolerance nobody can quote is not enforced. • Require deviations found to be recorded even when corrected immediately, because the pattern shows where the real problem is. • Add a rule that repeated inspection failures on the same activity trigger a retraining or method review.
395 | Projects | Control civil material use, wastage and work-front stock | Civil Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The Civil Supervisor completes “Control civil material use, wastage and work-front stock” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The Civil Supervisor completes “Control civil material use, wastage and work-front stock” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor controls how much material the crews take and waste, and how much is stacked at the work front. • Starts when: material is issued to the front, and throughout the activity. • How it runs: (1) he requests only the quantity the day's work needs. (2) He checks material is stacked and protected correctly. (3) He watches cutting and mixing to limit waste. (4) He returns surplus to store rather than leaving it out. (5) He records consumption and any abnormal wastage. • Proof it happened: the material request and issue records, the return notes and the wastage record. • Where it usually breaks: a week of material is dumped at the front, then damaged, buried or taken, and the loss never appears anywhere. | • Tie the material request to the day's target in the SOP. Bulk delivery to the work front is the main source of unexplained material loss. • Require surplus to be returned to store with a return note, because material left at the front is treated as consumed and disappears from control. • Require abnormal wastage to be reported with the cause, and set a threshold above which the engineer investigates. • Add stacking and protection rules for the materials that are commonly damaged on site, such as blocks, cement, tiles and reinforcement. • State that consumption records are compared against installed quantities, since that comparison is the only real check on wastage.
396 | Projects | Correct minor civil defects before engineer inspection | Civil Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The Civil Supervisor completes “Correct minor civil defects before engineer inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The Civil Supervisor completes “Correct minor civil defects before engineer inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor gets the small defects fixed before the engineer comes to inspect, so inspections are not wasted on things the crew could have corrected. • Starts when: an activity is nearing completion, or the supervisor's own check finds defects. • How it runs: (1) he walks the work and lists the defects. (2) He decides which are within his crews' ability to correct. (3) He gets them corrected before requesting inspection. (4) He refers anything involving design, structure or specification to the engineer instead of correcting it. (5) He records what was corrected. • Proof it happened: the defect list, the correction record and the inspection request. • Where it usually breaks: a defect that needed an engineering decision is quietly patched, so a real problem is hidden under a cosmetic repair. | • Draw the line clearly in the SOP: which defects the supervisor may correct, and which must be referred. Cosmetic correction of a structural or specification defect is concealment and must be named as such. • Require correction before inspection request, so engineer time is not spent on avoidable defects. • Require the defect and the correction to be recorded, since repeated defects point to a method, material or skill problem. • Say that no repair method outside the approved specification may be used, however minor it appears. • Add a rule that a defect involving a covered element is reported immediately, because time closes the window for proper repair.
397 | Projects | Record civil delays, shortages, rework and access constraints | Civil Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The Civil Supervisor completes “Record civil delays, shortages, rework and access constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The Civil Supervisor completes “Record civil delays, shortages, rework and access constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor writes down what held the work up during the shift: waiting for access, missing material, rework and anything else that stopped the crews. • Starts when: any delay, shortage or rework occurs during the shift. • How it runs: (1) he records what happened, at what time, and for how long. (2) He records how many workers and which plant were affected. (3) He records the cause and who raised it. (4) He passes the record to the engineer the same day. (5) He follows up whether it was resolved. • Proof it happened: the daily delay and constraint record with times, resources and causes. • Where it usually breaks: the delay is mentioned verbally and never written, so months later there is no evidence it happened. | • Require time, duration and affected resources in figures, not descriptions. Waiting time recorded without numbers is worthless in a claim. • Require same day submission to the engineer, since the record loses its value as contemporaneous evidence once it is written from memory. • Give a short standard cause list so records are comparable across supervisors and can be totalled. • State that recording a delay is not blame, otherwise supervisors under pressure stop recording, which is exactly when it matters most. • Require rework to be recorded with its cause, because rework hidden inside normal progress makes quality problems invisible.
398 | Projects | Record civil attendance, overtime and crew deployment | Civil Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The Civil Supervisor completes “Record civil attendance, overtime and crew deployment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The Civil Supervisor completes “Record civil attendance, overtime and crew deployment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor records who turned up, who worked extra hours, and where each person was deployed during the shift. • Starts when: at the start of the shift and at any change in deployment. • How it runs: (1) he takes attendance by name against the crew list. (2) He records absences. (3) He records the front each worker was deployed to. (4) He records overtime with the reason and the authorisation. (5) He submits the record to the engineer and to people administration. • Proof it happened: the signed attendance and deployment record with the overtime authorisation. • Where it usually breaks: attendance is recorded in bulk by crew, so nobody can prove who was where when a payroll or accident question arises. | • Require attendance by name and by work front, not by crew total. Without it there is no evidence of who was present at an incident location. • Require overtime to be authorised before it is worked, and name who may authorise it. Retrospective approval is where overtime cost control fails. • Set the submission deadline, since late attendance records cause payroll errors that damage trust with the workforce. • Add a check that the deployment record matches the productivity record, so labour hours can be tied to output. • State how a worker who leaves site during the shift is recorded, because this is the common gap in headcount evidence.
399 | Projects | Report civil completed quantities and daily work status | Civil Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The Civil Supervisor completes “Report civil completed quantities and daily work status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The Civil Supervisor completes “Report civil completed quantities and daily work status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: at the end of the shift the supervisor reports what was actually completed and how much, so the engineer can measure progress. • Starts when: at shift end, and at any interim reporting point. • How it runs: (1) he measures or counts what was physically completed per front. (2) He states what is part complete and how far. (3) He states what did not start and why. (4) He submits the status to the engineer. (5) He carries incomplete items into the next shift's plan. • Proof it happened: the daily work status report with quantities per front. • Where it usually breaks: the supervisor reports a percentage feeling rather than a measured quantity, and progress reporting drifts away from reality. | • Require quantities, not percentages, in the SOP. A supervisor estimating a percentage is where optimistic progress reporting starts. • Define what counts as complete for each activity, so completion is not claimed on work still needing finishing. • Require part complete work to be reported with the remaining quantity, which is what the next day's plan needs. • Add a periodic cross check between the supervisor's reported quantities and the surveyor's measurement, and require differences to be explained. • Set the reporting deadline so the engineer can build the next day's plan the same evening.
400 | Projects | Escalate civil resource, drawing and work-front requirements | Civil Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The Civil Supervisor completes “Escalate civil resource, drawing and work-front requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The Civil Supervisor completes “Escalate civil resource, drawing and work-front requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: when the supervisor cannot solve something at his level, such as needing more people, a clearer drawing or a released work front, he raises it up. • Starts when: a requirement or blocker is beyond the supervisor's authority or capacity to resolve. • How it runs: (1) he defines what is needed, in what quantity, and by when. (2) He states the impact if it is not provided. (3) He raises it to the site engineer. (4) He follows up rather than assuming it was handled. (5) He records the request and the outcome. • Proof it happened: the escalation record with the requirement, the impact and the response. • Where it usually breaks: the request is made verbally in passing, forgotten, and the same shortage repeats for weeks. | • Require escalations in writing with a quantity and a required by date. A request without those two things cannot be actioned or tracked. • Set a response time expectation, so the supervisor knows when to escalate further rather than waiting indefinitely. • Require the impact to be stated, because a request without consequence gets deprioritised against everything else. • Keep a running open items list at the work front so repeated requests are visible rather than reset daily. • Name who the supervisor goes to if the engineer does not respond, and make that route legitimate rather than a breach of protocol.
401 | Projects | Handover completed civil work for engineer and QHSE inspection | Civil Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The Civil Supervisor completes “Handover completed civil work for engineer and QHSE inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The Civil Supervisor completes “Handover completed civil work for engineer and QHSE inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: when work is finished the supervisor hands it over for the engineer and safety team to inspect, rather than declaring it complete himself. • Starts when: an activity is complete and has passed the supervisor's own check. • How it runs: (1) he confirms his own check is complete and defects are corrected. (2) He requests inspection giving the location and the activity. (3) He makes the area accessible and provides the crew to assist. (4) He receives the result and gets any rejected items corrected. (5) He requests re inspection where required. • Proof it happened: the inspection request, the inspection result and the re inspection record. • Where it usually breaks: work is treated as accepted because nobody objected, and the next activity covers it without a release. | • State in the SOP that acceptance is a signed release, not the absence of comment. Silence being read as approval is how unapproved work gets covered. • Require the inspection request to name the location and activity precisely, so the record can be traced back to the physical work. • Set an inspection response time, otherwise the supervisor is blamed for a delay that belongs to the inspecting party. • Require rejected items to be corrected and re inspected, with the rejection kept on record rather than replaced by the pass. • List the activities where the following work may not begin without a release, and make that list visible at the work front.
402 | Projects | Secure, clean and protect the civil work front at shift end | Civil Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The Civil Supervisor completes “Secure, clean and protect the civil work front at shift end” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The Civil Supervisor completes “Secure, clean and protect the civil work front at shift end” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent civil supervisor may cover routine supervision; engineering decisions remain with the Site Civil Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: at the end of the shift the supervisor makes sure the work front is left safe, clean and protected until the crews return. • Starts when: at the end of every shift, and before any planned stoppage such as a holiday or shutdown. • How it runs: (1) he stops work and clears the crews safely. (2) He makes sure materials, tools and plant are secured or returned. (3) He checks openings, edges, excavations and live services are protected and barricaded. (4) He confirms completed work is protected from weather and damage. (5) He confirms the front is secured and reports anything unresolved. • Proof it happened: the shift end securing check and the handover note to the next shift or to security. • Where it usually breaks: the crew leaves in a rush, an unprotected opening or excavation is left, and someone is injured after hours. | • List the shift end checks in the SOP as a short physical checklist: openings covered, excavations barricaded, edges protected, energised equipment isolated, plant secured. • Require the check before the crew leaves, not after, and name who performs it when the supervisor is absent. • Add extended requirements before weekends, holidays and shutdowns, since incidents in unattended periods are the worst outcome of this item. • Require a written handover of anything left incomplete or temporarily supported, so the next shift does not inherit a hidden risk. • Include weather protection for completed work, because unprotected finishes and fresh concrete are routinely lost overnight.
403 | Projects | Receive the approved daily MEP work plan and latest drawings | MEP Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The MEP Supervisor completes “Receive the approved daily MEP work plan and latest drawings” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The MEP Supervisor completes “Receive the approved daily MEP work plan and latest drawings” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: at the start of the shift the MEP supervisor collects the day's services work plan and the current drawings, so the crews install from the same instruction the engineer issued. • Starts when: the shift begins, or the plan changes because of access, permits or material. • How it runs: (1) he takes the plan from the site MEP engineer. (2) He checks he holds the current revision for each service and area. (3) He reads it against what was actually installed yesterday. (4) He raises anything unworkable before crews are deployed. (5) He confirms he has understood the plan for the shift. • Proof it happened: the received daily plan, the drawing revision list at the work front and the acknowledgement. • Where it usually breaks: services are installed from an old revision, and the clash only appears when the next trade arrives. | • Require the supervisor to hold the current revision physically for each service, since MEP drawings revise more often than any other discipline. • Require a revision check against the controlled register every shift, and removal of superseded prints from the work front. • State that installation follows the coordinated drawing, not the single service drawing, because installing from a single discipline drawing is the main cause of services clashes. • Give the supervisor a duty to reject an unworkable plan before deployment, with the reason recorded. • Set the shift handover content, including part installed runs and open testing.
404 | Projects | Check MEP work-front access, permits and pre-start readiness | MEP Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The MEP Supervisor completes “Check MEP work-front access, permits and pre-start readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The MEP Supervisor completes “Check MEP work-front access, permits and pre-start readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: before crews move in, the supervisor checks the area can be worked safely, the permits are in place, and the preceding trade has finished. • Starts when: a new work front opens, or before restarting a front that was left standing. • How it runs: (1) he walks the area physically. (2) He checks access, working at height provision, lighting and housekeeping. (3) He confirms the required permits are issued and their conditions are in place. (4) He confirms the preceding civil or fit out activity is complete and released. (5) He confirms readiness or reports the blocker. • Proof it happened: the readiness check, the permit references and the recorded blockers. • Where it usually breaks: crews arrive to find the permit not issued or the ceiling void not released, and the shift is lost. | • Make the permit check explicit and name every permit type used: hot work, working at height, confined space, electrical isolation, energisation. • Require the permit conditions to be physically verified, not just the permit number recorded, since the conditions are the actual control. • Require the preceding trade release to be written, because MEP crews are routinely sent into areas that are not handed over. • Require the crew to be held rather than deployed to an unready front, and set who authorises the hold. • Add an access equipment check, since most MEP work is at height and unsuitable access is the standard workaround.
405 | Projects | Allocate MEP crews and chargehands to approved work fronts | MEP Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The MEP Supervisor completes “Allocate MEP crews and chargehands to approved work fronts” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The MEP Supervisor completes “Allocate MEP crews and chargehands to approved work fronts” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor decides which crew and chargehand works on which service in which area, and how many people each front needs. • Starts when: the daily plan is confirmed, or resources have to be moved during the shift. • How it runs: (1) he matches the trade and certification needed to the crews available. (2) He allocates each crew to an approved and ready front. (3) He names the chargehand accountable for each front. (4) He briefs each chargehand on the target and the sequence with other services. (5) He records the deployment. • Proof it happened: the daily deployment record showing crew, trade, chargehand, area and headcount. • Where it usually breaks: two services are sent into the same congested void at the same time, and both install in each other's way. | • Require the installation sequence between services to be respected in deployment, since the order of installation in a ceiling void decides whether it fits at all. • Require certification checks for restricted trades such as electrical, welding and refrigerant handling, before deployment rather than after. • Require a named chargehand per front and per service, so accountability does not blur where trades overlap. • Require the deployment record, since it is the only evidence of labour use when productivity or claims are examined. • Set who resolves a conflict when two services need the same access at the same time.
406 | Projects | Check MEP materials, tools, access equipment and testing instruments | MEP Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The MEP Supervisor completes “Check MEP materials, tools, access equipment and testing instruments” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The MEP Supervisor completes “Check MEP materials, tools, access equipment and testing instruments” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor checks the crews have the material, tools, access equipment and test instruments they need before starting. • Starts when: before deployment, and whenever a shortage appears during the shift. • How it runs: (1) he checks material at the front against the day's activity, including supports and fixings. (2) He checks tools and access equipment are present, serviceable and tagged. (3) He checks test instruments are present and within calibration. (4) He raises shortages immediately. (5) He confirms the front is equipped or holds the activity. • Proof it happened: the pre start resource check, the calibration records and the shortage notes. • Where it usually breaks: supports and fixings are forgotten, so pipe and duct is laid loose and has to be revisited. | • Include supports, hangers, fixings and sleeves in the material check by name. These are the items routinely missed, and the rework is significant. • Require calibration validity to be checked before use, and state that results from an uncalibrated instrument are void. • Require untagged or expired access equipment to be refused, with no supervisor discretion under time pressure. • Give a shortage escalation route with a response time, and require the same shortage repeating to be raised formally. • Add a check that materials delivered match the approved submittal, since substituted fittings are commonly discovered only at testing.
407 | Projects | Deliver the MEP method and safety briefing with the engineer and QHSE team | MEP Supervisor | Trigger: When the engineer releases the daily work plan and work-front target. Action: The MEP Supervisor completes “Deliver the MEP method and safety briefing with the engineer and QHSE team” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a ready work front, allocated crew, verified resources and completed briefing. Control/Handoff: The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the engineer releases the daily work plan and work-front target. | The MEP Supervisor completes “Deliver the MEP method and safety briefing with the engineer and QHSE team” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a ready work front, allocated crew, verified resources and completed briefing. | The supervisor does not release work without current drawings, access, method and safety controls; blockers return to the engineer. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: before work starts, the supervisor talks the crew through the installation method and the specific dangers, with the engineer and safety team present. • Starts when: at the start of an activity, on a change of method, after an incident, or when new workers join. • How it runs: (1) he goes through the method and sequence in the language the crew understands. (2) The QHSE representative covers the hazards and controls. (3) Permit conditions and isolation arrangements are stated. (4) Workers confirm understanding and may raise concerns. (5) Attendance is recorded by name. • Proof it happened: the signed briefing record with names, the method reference and the permit reference. • Where it usually breaks: electrical isolation is assumed rather than confirmed in the briefing, and someone works on a live circuit. | • Require the isolation and lock out arrangement to be stated in the briefing by circuit or system, not in general terms. Assumed isolation is the fatal error in this trade. • State that signatures are taken at the briefing, before work. A sheet signed later is a false record. • Require re briefing on any change of method, sequence, crew or permit condition. • Require delivery in a language the crew understands, and name who translates. • Include the worker's right to stop the task in plain words, especially for live working, height and confined space.
408 | Projects | Supervise HVAC ductwork, piping and equipment installation | MEP Supervisor | Trigger: When the approved MEP crew begins the assigned activity. Action: The MEP Supervisor completes “Supervise HVAC ductwork, piping and equipment installation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled MEP execution completed to the daily target and ready for checking. Control/Handoff: The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved MEP crew begins the assigned activity. | The MEP Supervisor completes “Supervise HVAC ductwork, piping and equipment installation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled MEP execution completed to the daily target and ready for checking. | The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the installation of air conditioning ductwork, pipework and equipment. • Starts when: the area is released, the coordinated drawing is issued and the material is approved and on site. • How it runs: (1) he sets out routes and levels from the coordinated drawing. (2) He supervises support spacing, alignment and joint sealing on ductwork. (3) He supervises pipe joints, slopes, expansion provision and insulation readiness. (4) He supervises equipment setting, levelling, isolation and vibration provision. (5) He arranges inspection at the required points. • Proof it happened: the installation inspection records, the support and alignment checks and the equipment setting record. • Where it usually breaks: supports are spaced too widely to save fittings, and ducts and pipes sag once loaded or insulated. | • Give support spacing and fixing types in figures in the SOP, by size and service. Support spacing decided on site is the commonest quiet defect in MEP work. • Require duct joint sealing to be inspected before concealment, because leakage cannot be corrected once the ceiling closes. • Require access provision to be checked at every valve, damper and filter position while the run is still open. • Require equipment to be set with its access and removal route confirmed, since equipment installed without a removal route is a lifetime maintenance problem. • State that no route deviation from the coordinated drawing is made without the engineer's approval and a marked up record.
409 | Projects | Supervise plumbing, drainage and water-system installation | MEP Supervisor | Trigger: When the approved MEP crew begins the assigned activity. Action: The MEP Supervisor completes “Supervise plumbing, drainage and water-system installation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled MEP execution completed to the daily target and ready for checking. Control/Handoff: The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved MEP crew begins the assigned activity. | The MEP Supervisor completes “Supervise plumbing, drainage and water-system installation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled MEP execution completed to the daily target and ready for checking. | The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the installation of water supply, drainage and sanitary systems. • Starts when: the area is released and the approved pipe and fitting materials are on site. • How it runs: (1) he sets out pipe routes, invert levels and fixture positions from the drawing. (2) He supervises jointing to the approved method for each material. (3) He checks drainage falls with levels rather than by eye. (4) He arranges pressure and flow tests before concealment. (5) He arranges inspection and records the results. • Proof it happened: the pressure test records, the level readings on drainage and the inspection releases. • Where it usually breaks: a drainage line is laid flat or against the fall, and it only shows when the system is in use. | • Make falls a measured and recorded item in the SOP, with readings taken by instrument. A drainage line judged by eye is the classic failure of this trade. • State the hold point plainly: no concealment before the pressure test has passed and been signed. Include the test pressure and duration. • Require fixture positions to be confirmed against the architectural setting out before pipework is fixed, since a shifted fixture means breaking finished work. • Require the correct jointing method per pipe material and require crews to be certified where the method demands it. • Require isolation valve positions to be checked as installed against the plan, because they decide the size of any future shutdown.
410 | Projects | Supervise electrical containment, cabling, power and lighting installation | MEP Supervisor | Trigger: When the approved MEP crew begins the assigned activity. Action: The MEP Supervisor completes “Supervise electrical containment, cabling, power and lighting installation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled MEP execution completed to the daily target and ready for checking. Control/Handoff: The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved MEP crew begins the assigned activity. | The MEP Supervisor completes “Supervise electrical containment, cabling, power and lighting installation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled MEP execution completed to the daily target and ready for checking. | The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the installation of electrical containment, cabling, power outlets and lighting. • Starts when: the area is released, the coordinated drawing is issued and cable and containment material is approved. • How it runs: (1) he sets out containment routes and outlet positions from the drawing. (2) He supervises containment support, bonding and separation from other services. (3) He supervises cable pulling within bending radius and fill limits. (4) He supervises terminations, gland fitting and labelling. (5) He arranges testing before energisation and never energises without release. • Proof it happened: the installation records, the cable schedules, the test results and the energisation release. • Where it usually breaks: cables are pulled beyond their bending radius or into overfilled containment, damaging insulation invisibly. | • Give bending radius and containment fill limits in the SOP in figures, and require the check during pulling rather than after. Insulation damaged during pulling fails months later. • State absolutely that no circuit is energised without completed and witnessed testing and a signed release. Name who may authorise energisation. • Require separation distances from other services, especially data and water, since interference and water ingress problems are designed out at installation only. • Require circuit labelling at both ends as the cable is installed, because retrospective identification is slow and unreliable. • Require containment bonding continuity to be checked as a named step, not assumed from the fixings.
411 | Projects | Supervise ELV, fire-alarm and specialist-system installation within scope | MEP Supervisor | Trigger: When the approved MEP crew begins the assigned activity. Action: The MEP Supervisor completes “Supervise ELV, fire-alarm and specialist-system installation within scope” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled MEP execution completed to the daily target and ready for checking. Control/Handoff: The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved MEP crew begins the assigned activity. | The MEP Supervisor completes “Supervise ELV, fire-alarm and specialist-system installation within scope” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled MEP execution completed to the daily target and ready for checking. | The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the installation of low voltage and specialist systems within his scope, such as fire alarm, data and security cabling and devices. • Starts when: the area is released and the specialist system drawings and device schedules are issued. • How it runs: (1) he sets out device positions from the drawing and the device schedule. (2) He supervises cable installation with segregation from power cabling. (3) He supervises device mounting heights and orientation. (4) He coordinates with the specialist vendor where the vendor terminates or programmes. (5) He arranges continuity and loop testing and records results. • Proof it happened: the device installation records, the cable test results and the vendor interface records. • Where it usually breaks: the split between contractor work and vendor work is unclear, so cabling is done twice or not at all. | • Require a written scope split with the specialist vendor before installation, stating who supplies, installs, terminates, programmes and tests each part. This is the biggest source of dispute in ELV work. • Require segregation from power cabling to be checked physically, since induced interference on data and fire loops is not correctable later. • Require device mounting heights to be confirmed against the approved drawing and the applicable code, because device height is a compliance item on fire and accessibility. • Require devices to be protected and left unenergised until commissioning, since damage during fit out is common and hard to attribute. • Require the as installed device address list to be recorded during installation, not reconstructed at commissioning.
412 | Projects | Supervise MEP testing, final connections and service integration | MEP Supervisor | Trigger: When the approved MEP crew begins the assigned activity. Action: The MEP Supervisor completes “Supervise MEP testing, final connections and service integration” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled MEP execution completed to the daily target and ready for checking. Control/Handoff: The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the approved MEP crew begins the assigned activity. | The MEP Supervisor completes “Supervise MEP testing, final connections and service integration” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled MEP execution completed to the daily target and ready for checking. | The MEP Supervisor applies the engineer instruction and approved method; deviation, damage or unsafe condition stops and escalates. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor runs the testing of installed services, the final connections, and the point where separate systems are joined together and made to work as one. • Starts when: installation is complete and the systems are ready for testing and connection. • How it runs: (1) he confirms installation is complete and inspected before any test starts. (2) He arranges the test with the engineer and the instruments required. (3) He supervises the test and records the readings as measured. (4) He supervises final connections under the required permit and isolation. (5) He supports integration testing between systems and records the outcome. • Proof it happened: the signed test records with readings, the connection permits and the integration test results. • Where it usually breaks: a test is recorded as passed without readings, so nobody can tell whether it was performed at all. | • Require measured readings on every test record, with the instrument and its calibration reference. A pass with no reading is not evidence and should be rejected by the SOP. • Require the test to be witnessed and state who may witness each type, including where the consultant or authority must attend. • Require final connections to be made under permit and isolation, with the isolation verified at the point of work. • Require failed tests to be recorded and retained alongside the pass, since the failure history is what shows whether the installation is sound. • Require integration testing to be scheduled as its own activity, because systems that individually pass frequently fail when connected.
413 | Projects | Monitor MEP crew productivity against the daily target | MEP Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The MEP Supervisor completes “Monitor MEP crew productivity against the daily target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The MEP Supervisor completes “Monitor MEP crew productivity against the daily target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor watches how much the crews are actually installing against the day's target, and acts during the shift rather than reporting the gap afterwards. • Starts when: during the shift, at set checkpoints. • How it runs: (1) he takes the target for each front from the plan. (2) He checks installed quantities at intervals. (3) He identifies the cause where output is behind, whether access, material, coordination or manpower. (4) He redeploys or escalates within the shift. (5) He records the actual output and the reason for the gap. • Proof it happened: the daily productivity record showing target, actual and cause. • Where it usually breaks: lost time is caused by waiting for another trade's clearance, and that cause never gets recorded against the right party. | • Set mid shift checkpoints rather than end of shift reporting only, so a gap can still be recovered the same day. • Require the cause to be recorded and require coordination waiting time to be attributed to the trade or party responsible. In MEP this is the largest hidden loss. • Define the measurement unit per activity, such as metres of containment or number of devices, so output is comparable. • Give the supervisor a stated redeployment authority and an escalation threshold. • Require repeated shortfalls on the same cause to be escalated as a planning issue rather than treated as crew performance.
414 | Projects | Check MEP installation workmanship, levels, supports and access | MEP Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The MEP Supervisor completes “Check MEP installation workmanship, levels, supports and access” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The MEP Supervisor completes “Check MEP installation workmanship, levels, supports and access” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor checks the installed work against the drawing and the standard: is it straight, properly supported, correctly positioned and reachable for maintenance. • Starts when: continuously during installation, and before calling the engineer to inspect. • How it runs: (1) he checks routes, levels and positions against the coordinated drawing. (2) He checks support type and spacing. (3) He checks access provision at valves, dampers, filters and boards. (4) He corrects deviations while the work is still open. (5) He only requests inspection once he believes it will pass. • Proof it happened: the supervisor's check records, the corrections and the inspection request. • Where it usually breaks: maintenance access is only considered after the ceiling is closed, and the panel or valve becomes unreachable. | • Make maintenance access a named check while the void is still open. Access checked after closing is worth nothing, and this is the defect operations complains about most. • State that the supervisor's check is a separate control from the engineer's inspection, not a request for one. • Give the tolerances and support requirements in figures so the check is objective. • Require deviations to be recorded even where corrected immediately, since the pattern identifies the real cause. • Require repeated inspection failures on the same activity to trigger a method or training review.
415 | Projects | Control MEP material use, wastage and work-front stock | MEP Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The MEP Supervisor completes “Control MEP material use, wastage and work-front stock” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The MEP Supervisor completes “Control MEP material use, wastage and work-front stock” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor controls how much material the crews take and waste, and what is left stacked in the work area. • Starts when: material is issued to the front, and throughout the activity. • How it runs: (1) he requests only what the day's work needs. (2) He checks material is stored and protected, especially cable, fittings and insulation. (3) He watches cutting and offcut use to limit waste. (4) He returns surplus to store with a return note. (5) He records consumption and abnormal wastage. • Proof it happened: the material request and issue records, the return notes and the wastage record. • Where it usually breaks: cable and copper are the highest value items on site and go missing when left at open work fronts. | • Set tighter control on high value items in the SOP by name: cable, copper pipe, valves, fittings and equipment. Treat these differently from general material. • Tie issue quantity to the day's target and require surplus to be returned rather than left at the front. • Require drum and reel records so cable consumption can be reconciled against installed lengths, since this is the only real check on cable loss. • Require abnormal wastage to be reported with the cause and set the threshold that triggers investigation. • Add protection rules for items that are easily damaged in storage, such as insulation, sensors and light fittings.
416 | Projects | Correct minor MEP defects before engineer inspection | MEP Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The MEP Supervisor completes “Correct minor MEP defects before engineer inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The MEP Supervisor completes “Correct minor MEP defects before engineer inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor gets small installation defects fixed before the engineer inspects, so inspections are not wasted. • Starts when: an activity is nearing completion, or the supervisor's own check finds defects. • How it runs: (1) he walks the work and lists the defects. (2) He decides which are within his crews' scope to correct. (3) He gets them corrected before requesting inspection. (4) He refers anything involving design, specification or an approved submittal to the engineer. (5) He records what was corrected. • Proof it happened: the defect list, the correction record and the inspection request. • Where it usually breaks: an undersized or substituted item is made to fit rather than reported, and the system underperforms permanently. | • Draw the line in the SOP: adjusting supports or alignment is correction, making a wrong size or unapproved item fit is concealment. Name it as a reportable matter. • Require correction before inspection request so engineer time is spent on real verification. • Require any material substitution found on site to be stopped and referred, since substitution changes system performance. • Require the defect and its correction to be recorded, because repeat defects point to method, material or skill. • State that no repair outside the approved method may be used, including improvised supports and fixings.
417 | Projects | Record MEP delays, shortages, rework and access constraints | MEP Supervisor | Trigger: When work is underway or reaches the supervisor self-check point. Action: The MEP Supervisor completes “Record MEP delays, shortages, rework and access constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a verified productivity, quality, material-use and constraint record. Control/Handoff: The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When work is underway or reaches the supervisor self-check point. | The MEP Supervisor completes “Record MEP delays, shortages, rework and access constraints” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a verified productivity, quality, material-use and constraint record. | The supervisor corrects minor issues within authority and escalates repeated defects, shortages, delays or unsafe conditions. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor writes down what held the work up: waiting for access, missing material, another trade in the way, and rework. • Starts when: any delay, shortage or rework occurs during the shift. • How it runs: (1) he records what happened, at what time and for how long. (2) He records how many workers were affected. (3) He records the cause and the party responsible. (4) He passes the record to the engineer the same day. (5) He follows up on resolution. • Proof it happened: the daily delay and constraint record with times, resources, causes and parties. • Where it usually breaks: waiting on another trade is treated as normal site life and never recorded, so the cost sits with the wrong party. | • Require the responsible party to be named on coordination delays. Without attribution the MEP crews absorb costs caused by others. • Require time, duration and affected headcount in figures, since descriptive records carry no weight in a claim. • Require same day submission so the record remains contemporaneous evidence. • Give a short standard cause list so records can be totalled across supervisors and periods. • Require rework to be recorded with its cause, so quality problems do not hide inside normal progress.
418 | Projects | Record MEP attendance, overtime and crew deployment | MEP Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The MEP Supervisor completes “Record MEP attendance, overtime and crew deployment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The MEP Supervisor completes “Record MEP attendance, overtime and crew deployment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: the supervisor records who turned up, who worked extra hours, and where each person was deployed. • Starts when: at the start of the shift and at any change of deployment. • How it runs: (1) he takes attendance by name against the crew list. (2) He records absences. (3) He records the area and service each worker was deployed to. (4) He records overtime with the reason and authorisation. (5) He submits the record to the engineer and people administration. • Proof it happened: the signed attendance and deployment record with the overtime authorisation. • Where it usually breaks: certified trades are recorded generically, so there is no evidence a certified electrician did the work that required one. | • Require the trade and certification to be recorded against restricted work, so it can be proven that certified personnel performed it. • Require attendance by name and by area rather than by crew total, since incident investigation needs to know who was where. • Require overtime authorisation before the hours are worked, and name who may authorise. • Set the submission deadline to protect payroll accuracy and workforce trust. • Require the deployment record to reconcile with the productivity record so hours tie to installed output.
419 | Projects | Report MEP completed quantities and daily work status | MEP Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The MEP Supervisor completes “Report MEP completed quantities and daily work status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The MEP Supervisor completes “Report MEP completed quantities and daily work status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: at the end of the shift the supervisor reports what was actually installed and how much, so the engineer can measure progress. • Starts when: at shift end and at any interim reporting point. • How it runs: (1) he measures or counts the installed quantity per area and service. (2) He states what is part complete and how far. (3) He states what did not start and why. (4) He submits the status to the engineer. (5) He carries incomplete items into the next shift plan. • Proof it happened: the daily work status report with installed quantities per service and area. • Where it usually breaks: installed is reported as complete when testing is still outstanding, so progress looks better than it is. | • Define complete in the SOP as installed, inspected and tested where testing applies. Reporting installation as completion is the standard overstatement in MEP progress. • Require quantities rather than percentages, measured against the same unit used in the plan. • Require part complete runs to be reported with the remaining quantity, which the next plan needs. • Add a periodic cross check with the surveyor's measurement and require differences to be explained. • Set the reporting deadline so the next day's plan can be built the same evening.
420 | Projects | Escalate MEP resource, drawing and work-front requirements | MEP Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The MEP Supervisor completes “Escalate MEP resource, drawing and work-front requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The MEP Supervisor completes “Escalate MEP resource, drawing and work-front requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: when the supervisor cannot solve something at his level, such as needing more crews, a coordinated drawing or a released area, he raises it up. • Starts when: a requirement or blocker is beyond his authority or capacity to resolve. • How it runs: (1) he defines what is needed, in what quantity, and by when. (2) He states the impact if it is not provided. (3) He raises it to the site MEP engineer. (4) He follows up rather than assuming it was handled. (5) He records the request and outcome. • Proof it happened: the escalation record with the requirement, the impact and the response. • Where it usually breaks: a drawing coordination problem is reported verbally, installation continues in the meantime, and the clash is built in. | • State that installation stops in the affected area when a coordination conflict is raised, rather than continuing while the answer is awaited. Continuing is what turns a query into rework. • Require escalations in writing with quantity and required by date, and set a response time expectation. • Require the impact to be stated, since requests without consequences get deprioritised. • Keep a visible open items list at the work front so repeated requests are not reset daily. • Name the route if the engineer does not respond, and make using it legitimate.
421 | Projects | Handover completed MEP work for engineer and QHSE inspection | MEP Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The MEP Supervisor completes “Handover completed MEP work for engineer and QHSE inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The MEP Supervisor completes “Handover completed MEP work for engineer and QHSE inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: when installation is finished the supervisor hands it over for the engineer and safety team to inspect, rather than declaring it complete himself. • Starts when: an activity is complete and has passed the supervisor's own check. • How it runs: (1) he confirms his own check is done and defects corrected. (2) He requests inspection giving the area, service and drawing reference. (3) He keeps the work accessible and provides crew to assist. (4) He receives the result and corrects rejected items. (5) He requests re inspection where required. • Proof it happened: the inspection request, the inspection result and the re inspection record. • Where it usually breaks: the ceiling is closed before the release is signed, and opening it up again is charged to the wrong party. | • State plainly that no concealment happens before the signed release, and name concealment as a controlled step with its own permission. This single rule prevents most MEP rework cost. • State that acceptance is a signed release, never the absence of comment. • Require the inspection request to name the area, service and drawing revision so the record ties to the physical work. • Set an inspection response time, otherwise concealment delay is blamed on the supervisor. • Require rejections to be retained on record alongside the eventual pass.
422 | Projects | Secure, clean and protect the MEP work front at shift end | MEP Supervisor | Trigger: When the shift, task or inspection point is completed. Action: The MEP Supervisor completes “Secure, clean and protect the MEP work front at shift end” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The MEP Supervisor completes “Secure, clean and protect the MEP work front at shift end” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A nominated competent MEP supervisor may cover routine supervision; engineering decisions remain with the Site MEP Engineer and unsafe or nonconforming work is stopped. | To be confirmed. | • In plain words: at the end of the shift the supervisor leaves the work area safe, clean and protected, with nothing left live or hanging unsupported. • Starts when: at the end of every shift and before any planned stoppage. • How it runs: (1) he stops work and clears the crews safely. (2) He confirms temporary supplies and part installed circuits are isolated and labelled. (3) He confirms open pipe ends and duct openings are capped. (4) He confirms part installed runs are properly supported and not left hanging. (5) He secures material, tools and instruments and reports anything unresolved. • Proof it happened: the shift end securing check and the handover note to the next shift or security. • Where it usually breaks: an unlabelled temporary circuit is left live overnight, or open pipe ends let debris into the system. | • Make isolation and labelling of temporary supplies a named shift end step. An unlabelled live temporary circuit is the most dangerous thing left on an MEP front. • Require open pipe and duct ends to be capped, because debris entering the system is not recoverable and shows up at commissioning. • Require part installed runs to be properly supported before the crew leaves, not tied off temporarily. • Add extended checks before weekends, holidays and shutdowns, and require a written handover of anything temporarily supported or energised. • Require high value items and test instruments to be removed from the front and secured.
423 | Projects | Receive the supervisor daily target, drawing and approved work method | Foreman | Trigger: When the supervisor issues the approved daily target. Action: The Foreman completes “Receive the supervisor daily target, drawing and approved work method” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a briefed crew, ready work front and recorded pre-start constraint status. Control/Handoff: The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the supervisor issues the approved daily target. | The Foreman completes “Receive the supervisor daily target, drawing and approved work method” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a briefed crew, ready work front and recorded pre-start constraint status. | The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman takes the day's target from the supervisor, along with the drawing and the agreed way of doing the job, so his crews work to the same instruction. • Starts when: at the start of the shift, or when the target changes during the day. • How it runs: (1) he receives the target quantity and location from the supervisor. (2) He takes the drawing for that work and checks it is the current revision. (3) He goes through the approved method for the activity. (4) He asks about anything he does not understand before crews start. (5) He confirms he has taken the target on. • Proof it happened: the daily target record, the drawing held at the front, and the foreman's acknowledgement. • Where it usually breaks: the target is passed verbally with no drawing, so the crew builds by habit rather than to the drawing. | • Require the target to be given in a quantity and a location, not as an instruction to carry on. A target nobody can measure cannot be reported against. • Require the foreman to physically hold the drawing for the day's work, and to check the revision. • Give the foreman a stated right to ask for clarification before starting, so questions are raised at the front rather than absorbed. • Define what the foreman does when the target is not achievable with the crews he has, so the constraint reaches the supervisor before the day is lost. • Keep the instruction format simple enough to be used on site, since a form the foreman cannot carry will not be used.
424 | Projects | Conduct the crew toolbox and work-method briefing | Foreman | Trigger: When the supervisor issues the approved daily target. Action: The Foreman completes “Conduct the crew toolbox and work-method briefing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a briefed crew, ready work front and recorded pre-start constraint status. Control/Handoff: The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the supervisor issues the approved daily target. | The Foreman completes “Conduct the crew toolbox and work-method briefing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a briefed crew, ready work front and recorded pre-start constraint status. | The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: before the crew starts, the foreman gathers them and talks through what the job is, how it is to be done and what could hurt them. • Starts when: at the start of the shift, at the start of a new activity, after an incident, or when a new worker joins. • How it runs: (1) he explains the task and the method in the language the crew understands. (2) He explains the hazards and the controls, including PPE. (3) He states the permit conditions where a permit applies. (4) He asks the crew to confirm understanding and to raise concerns. (5) He records attendance by name. • Proof it happened: the signed toolbox briefing record with names and the topic covered. • Where it usually breaks: the briefing becomes a signature exercise, the same topic every day, and the crew stops listening. | • Require the briefing to be specific to the day's task and hazards. A generic daily talk is the reason crews stop paying attention to briefings entirely. • Require signatures at the briefing, before work starts. A sheet signed later is a false record and should be treated as such. • Require delivery in the language the crew actually understands, and name who translates where needed. • Include the worker's right to stop or question a task, in plain words, since that is what turns the briefing into a control. • Require a fresh briefing on any change of method, sequence or crew composition.
425 | Projects | Confirm work-front access, tools, materials and PPE readiness | Foreman | Trigger: When the supervisor issues the approved daily target. Action: The Foreman completes “Confirm work-front access, tools, materials and PPE readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a briefed crew, ready work front and recorded pre-start constraint status. Control/Handoff: The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the supervisor issues the approved daily target. | The Foreman completes “Confirm work-front access, tools, materials and PPE readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a briefed crew, ready work front and recorded pre-start constraint status. | The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman checks the crew can actually start: they can reach the work safely, and they have the tools, material and protective equipment they need. • Starts when: before the crew is deployed, and when a shortage appears during the shift. • How it runs: (1) he checks safe access to the work position. (2) He checks tools and access equipment are present, serviceable and tagged. (3) He checks the material at the front against the day's target. (4) He checks every worker has the right PPE and it is in usable condition. (5) He confirms readiness or holds the crew and reports the gap. • Proof it happened: the pre start readiness check, the shortage notes and the access equipment tags. • Where it usually breaks: the crew starts with worn or missing PPE because holding the work feels like losing time. | • State that work does not start with missing or unserviceable PPE, and that the foreman has no discretion to allow it under time pressure. This needs to be written, because the pressure is real. • Require untagged or expired access equipment to be refused, and name who arranges the replacement. • Require the material check against the day's target, so a shortage is found before the crew is standing at the front. • Give a shortage escalation route with a response time, and require repeated shortages to be raised formally. • Require damaged PPE to be exchanged rather than repaired, and say where the stock is held on site.
426 | Projects | Identify missing information, hazards and constraints before starting | Foreman | Trigger: When the supervisor issues the approved daily target. Action: The Foreman completes “Identify missing information, hazards and constraints before starting” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a briefed crew, ready work front and recorded pre-start constraint status. Control/Handoff: The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the supervisor issues the approved daily target. | The Foreman completes “Identify missing information, hazards and constraints before starting” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a briefed crew, ready work front and recorded pre-start constraint status. | The Foreman verifies instruction, resources and PPE; unclear, unsafe or unavailable conditions are escalated before starting. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: before starting, the foreman looks for what is missing or dangerous: unclear information, a hazard nobody has controlled, or something in the way. • Starts when: before the activity starts, and whenever conditions change. • How it runs: (1) he checks the drawing and instruction for anything unclear or contradictory. (2) He looks over the work area for hazards, including work above and around. (3) He identifies constraints such as other trades, access or services. (4) He raises what he finds to the supervisor before starting. (5) He holds the activity where the risk is not controlled. • Proof it happened: the recorded queries, hazards and constraints, and the supervisor's response. • Where it usually breaks: the foreman starts anyway and works around the problem, so the risk stays and the query never reaches anyone. | • Give the foreman explicit authority to hold work where a hazard is not controlled, and state that he will not be penalised for using it. Without that written line, the authority does not exist in practice. • Require missing or contradictory information to be raised rather than resolved by site judgement, since site resolution silently changes the design. • Require simultaneous work above and below to be identified, because dropped object incidents come from exactly this gap. • Set a response time on queries so the foreman is not left holding an idle crew with no answer. • Require repeat queries on the same drawing to be escalated, since that points to a drawing problem rather than a site problem.
427 | Projects | Organise chargehands and crews by location and task | Foreman | Trigger: When the crew is released to execute the approved task. Action: The Foreman completes “Organise chargehands and crews by location and task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: organised and sequenced work with protected interfaces, controlled materials and safe access. Control/Handoff: The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the crew is released to execute the approved task. | The Foreman completes “Organise chargehands and crews by location and task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | organised and sequenced work with protected interfaces, controlled materials and safe access. | The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman decides which chargehand and which workers go where, and how many people each task needs. • Starts when: the target is received, or when work has to be reorganised during the shift. • How it runs: (1) he splits the day's target into tasks by location. (2) He matches the skill needed to the workers available. (3) He assigns each task to a named chargehand. (4) He tells each chargehand the target, the method and the sequence. (5) He records the deployment. • Proof it happened: the deployment record showing task, location, chargehand and headcount. • Where it usually breaks: workers are spread across too many tasks, so nothing finishes and the day shows movement but no completion. | • Require every task to have a named chargehand. Work without a name attached is where supervision quietly disappears. • Require skill and certification to be matched to the task before deployment, particularly for restricted work. • Discourage opening more tasks than the crew can complete, and state who authorises an additional task front. • Require the deployment record to be kept, since it is the only evidence of how labour was used when output is questioned. • State how a worker moved between tasks mid shift is recorded, because that is the usual gap in labour evidence.
428 | Projects | Sequence daily work to protect preceding and following trades | Foreman | Trigger: When the crew is released to execute the approved task. Action: The Foreman completes “Sequence daily work to protect preceding and following trades” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: organised and sequenced work with protected interfaces, controlled materials and safe access. Control/Handoff: The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the crew is released to execute the approved task. | The Foreman completes “Sequence daily work to protect preceding and following trades” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | organised and sequenced work with protected interfaces, controlled materials and safe access. | The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman keeps the day's work in the right order so his crew does not damage what came before or block what comes next. • Starts when: at planning the day's tasks, and whenever another trade appears in the same area. • How it runs: (1) he checks what the preceding trade has completed and released. (2) He plans his own tasks so completed work is not walked over or damaged. (3) He checks what the following trade needs from him and in what order. (4) He raises a sequence clash to the supervisor rather than pushing through. (5) He keeps to the agreed sequence. • Proof it happened: the daily task sequence, the recorded clashes and the supervisor's decisions. • Where it usually breaks: the crew works in the order that suits it, and the following trade has to undo part of it. | • Require the sequence to be taken from the plan rather than chosen at the front, and require clashes to be raised rather than resolved by whoever is stronger on the day. • Require confirmation that the preceding activity is released before starting on top of it. • State that damage to another trade's completed work is recorded and attributed, since without attribution nobody changes behaviour. • Require the foreman to know what the following trade needs from him, which is the only way sequence errors get caught early. • Add a rule that a sequence change is approved, because an altered sequence often skips a required inspection.
429 | Projects | Control use of tools, access equipment and work-front materials | Foreman | Trigger: When the crew is released to execute the approved task. Action: The Foreman completes “Control use of tools, access equipment and work-front materials” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: organised and sequenced work with protected interfaces, controlled materials and safe access. Control/Handoff: The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the crew is released to execute the approved task. | The Foreman completes “Control use of tools, access equipment and work-front materials” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | organised and sequenced work with protected interfaces, controlled materials and safe access. | The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman controls the tools, ladders and platforms, and the material stacked at the work front, so they are used properly and not lost or damaged. • Starts when: tools and material are issued to the front, and throughout the shift. • How it runs: (1) he checks tools issued against the tool record. (2) He confirms access equipment is inspected and used as intended. (3) He checks material at the front is stacked and protected. (4) He stops misuse or improvised use of equipment. (5) He accounts for tools and equipment at the end of the shift. • Proof it happened: the tool issue and return record, the access equipment tags and the shift end account. • Where it usually breaks: access equipment is used in ways it was never meant for because the right equipment is not at the front. | • State that improvised access is prohibited and name the common improvisations seen on site, since a general rule does not stop them. • Require tools to be issued and returned against a record, so losses are visible and attributable rather than absorbed. • Require unserviceable tools to be removed from the front rather than left in circulation, and name who they go to. • Require material stacking and protection rules for the items commonly damaged, and state where surplus goes. • Add a shift end account of tools and equipment, since this is the point at which losses can still be traced.
430 | Projects | Coordinate trade interfaces and avoid damage to completed work | Foreman | Trigger: When the crew is released to execute the approved task. Action: The Foreman completes “Coordinate trade interfaces and avoid damage to completed work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: organised and sequenced work with protected interfaces, controlled materials and safe access. Control/Handoff: The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the crew is released to execute the approved task. | The Foreman completes “Coordinate trade interfaces and avoid damage to completed work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | organised and sequenced work with protected interfaces, controlled materials and safe access. | The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman deals with the points where his crew meets other trades, and keeps them from damaging work that is already finished. • Starts when: another trade is working in or next to the same area, or the crew is working near completed work. • How it runs: (1) he identifies the completed work at risk in his area. (2) He agrees access and working arrangements with the other trade's foreman. (3) He arranges protection over finished surfaces and installed services. (4) He raises unresolved interface problems to the supervisor. (5) He reports damage rather than covering it. • Proof it happened: the interface agreements, the protection arrangements and the recorded damage reports. • Where it usually breaks: damage is discovered later with nobody willing to own it, and the company absorbs the repair. | • Require damage to be reported immediately with the location and cause. Damage found later with no owner is always paid for by the company, and this rule is the only defence. • Require protection to be in place before work starts near completed finishes or installed services, and name who provides it. • Require interface arrangements between trades to be agreed at foreman level and confirmed to the supervisor, so they are not personal deals. • Set who decides when two trades cannot both work in the same space safely. • State that concealing damage is a discipline matter, in plain words.
431 | Projects | Maintain housekeeping and safe access during execution | Foreman | Trigger: When the crew is released to execute the approved task. Action: The Foreman completes “Maintain housekeeping and safe access during execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: organised and sequenced work with protected interfaces, controlled materials and safe access. Control/Handoff: The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the crew is released to execute the approved task. | The Foreman completes “Maintain housekeeping and safe access during execution” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | organised and sequenced work with protected interfaces, controlled materials and safe access. | The Foreman controls only the approved task; trade conflict, damage or method deviation is reported to the supervisor. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman keeps the work area tidy and the routes clear while the work is going on, not only at the end of the shift. • Starts when: throughout the shift, and whenever the area becomes obstructed. • How it runs: (1) he keeps access routes and escape routes clear. (2) He arranges regular waste and offcut removal during the shift. (3) He keeps material stacked clear of edges, openings and routes. (4) He keeps cables, hoses and leads managed off walking routes. (5) He confirms the area is clear at shift end. • Proof it happened: the housekeeping checks and the recorded corrections. • Where it usually breaks: housekeeping is left to the end of the shift, and the trip and fall hazards exist all day. | • Require housekeeping during the shift, not only at the end. Most slip, trip and fall incidents happen in the middle of the day, which is exactly what end of shift cleaning does not address. • Require escape and access routes to be kept clear as a named check, since these are the routes needed in an emergency. • Require trailing cables, leads and hoses to be managed off routes, as this is the most common site trip hazard. • Set who provides waste removal and at what frequency, because crews cannot maintain housekeeping without a disposal route. • State the material stacking distance from edges and openings in figures.
432 | Projects | Monitor crew output against the approved daily target | Foreman | Trigger: When work is in progress or ready for internal checking. Action: The Foreman completes “Monitor crew output against the approved daily target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a productivity, quality, wastage, delay and corrective-action record. Control/Handoff: Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When work is in progress or ready for internal checking. | The Foreman completes “Monitor crew output against the approved daily target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a productivity, quality, wastage, delay and corrective-action record. | Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman keeps an eye on how much his crew is actually producing against the target, and acts during the shift rather than explaining it afterwards. • Starts when: during the shift, at set checkpoints. • How it runs: (1) he knows the target quantity for each task. (2) He checks actual output at intervals during the shift. (3) He finds the cause where output is behind. (4) He reorganises within his crew or reports the constraint. (5) He records actual output and the reason for any gap. • Proof it happened: the crew output record showing target, actual and cause. • Where it usually breaks: the gap is only known at shift end, when nothing can be recovered. | • Set a mid shift check in the SOP, since a gap found at midday can still be recovered and one found at six cannot. • Require the cause with the number, because output figures without causes give the supervisor nothing to act on. • Define the measurement unit per activity so output is comparable between days and crews. • Give the foreman a stated authority to reorganise within his own crew, and a threshold above which he must report. • Require the same cause repeating to be escalated, since that is a planning or supply failure rather than a crew failure.
433 | Projects | Check work against drawing, dimensions and workmanship standard | Foreman | Trigger: When work is in progress or ready for internal checking. Action: The Foreman completes “Check work against drawing, dimensions and workmanship standard” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a productivity, quality, wastage, delay and corrective-action record. Control/Handoff: Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When work is in progress or ready for internal checking. | The Foreman completes “Check work against drawing, dimensions and workmanship standard” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a productivity, quality, wastage, delay and corrective-action record. | Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman checks the work as it goes up: the sizes, the positions and whether the standard of finish is acceptable. • Starts when: continuously during the work, and before presenting it to the supervisor. • How it runs: (1) he checks dimensions and positions against the drawing. (2) He compares the workmanship against the approved sample or benchmark. (3) He checks the details that are hard to correct later. (4) He gets deviations corrected while the work is still open. (5) He records his checks. • Proof it happened: the foreman's check records and the corrections made. • Where it usually breaks: the crew relies on the supervisor and engineer to find the errors, so the same mistake is repeated across a whole area. | • State that the foreman's check is a real control in its own right, not a step before someone else checks. If it is treated as optional, errors repeat across an entire area before anyone catches them. • Require a physical benchmark or approved sample for repetitive work, so the standard is a reference rather than an opinion. • Give the tolerances that matter in figures, since a tolerance nobody can quote is not applied. • Require correction while the work is still open and accessible, and require anything that cannot be corrected to be reported. • Require checks to be recorded so patterns of error can be traced to method or training.
434 | Projects | Correct minor defects and prevent repeated rework | Foreman | Trigger: When work is in progress or ready for internal checking. Action: The Foreman completes “Correct minor defects and prevent repeated rework” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a productivity, quality, wastage, delay and corrective-action record. Control/Handoff: Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When work is in progress or ready for internal checking. | The Foreman completes “Correct minor defects and prevent repeated rework” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a productivity, quality, wastage, delay and corrective-action record. | Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman gets small faults fixed straight away and works out why they keep happening, so the same rework does not repeat. • Starts when: a defect is found during work or at the foreman's check. • How it runs: (1) he identifies the defect and its cause. (2) He gets it corrected where it is within the crew's scope. (3) He refers anything involving design, structure or specification to the supervisor. (4) He briefs the crew on avoiding the repeat. (5) He records the defect and the correction. • Proof it happened: the defect and correction record and the crew briefing note. • Where it usually breaks: defects are fixed one by one without ever asking why, so the crew keeps producing them. | • Require the cause to be identified, not just the defect corrected. Correcting without diagnosing is why the same rework appears for weeks. • Draw the line between what the crew may correct and what must be referred, and name cosmetic covering of a real defect as a reportable matter. • Require the crew to be briefed after a repeated defect, since retraining at the front is the cheapest correction available. • Require rework to be recorded rather than absorbed into normal progress, otherwise the cost is invisible. • State that no repair method outside the approved specification may be used, however small the defect.
435 | Projects | Record idle time, shortages, delays and productivity loss | Foreman | Trigger: When work is in progress or ready for internal checking. Action: The Foreman completes “Record idle time, shortages, delays and productivity loss” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a productivity, quality, wastage, delay and corrective-action record. Control/Handoff: Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When work is in progress or ready for internal checking. | The Foreman completes “Record idle time, shortages, delays and productivity loss” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a productivity, quality, wastage, delay and corrective-action record. | Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman writes down time his crew lost and why: waiting for access, no material, waiting on another trade, or redoing work. • Starts when: any idle time, shortage, delay or rework occurs. • How it runs: (1) he records what happened, at what time and for how long. (2) He records how many workers were idle. (3) He records the cause and who was informed. (4) He gives the record to the supervisor the same day. (5) He follows up whether it was resolved. • Proof it happened: the daily idle time and delay record with times, headcount and causes. • Where it usually breaks: idle time is treated as part of site life and never recorded, so the same loss repeats every week with no evidence. | • Require times and idle headcount in figures. Waiting time without numbers cannot be costed and carries no weight in a claim. • Require same day submission, since a record written from memory later is no longer contemporaneous evidence. • Give a short standard cause list so records can be added up across foremen and weeks. • State clearly that recording idle time is not an admission of poor performance, otherwise foremen under pressure stop recording exactly when it matters. • Require rework to be recorded with its cause alongside idle time, so both losses are visible.
436 | Projects | Control material wastage and protect issued materials | Foreman | Trigger: When work is in progress or ready for internal checking. Action: The Foreman completes “Control material wastage and protect issued materials” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a productivity, quality, wastage, delay and corrective-action record. Control/Handoff: Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When work is in progress or ready for internal checking. | The Foreman completes “Control material wastage and protect issued materials” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a productivity, quality, wastage, delay and corrective-action record. | Minor defects are corrected before supervisor inspection; repeated rework, low output or shortage is escalated. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman controls how much material his crew uses and wastes, and looks after what has been issued to the front. • Starts when: material is issued to the front, and throughout the work. • How it runs: (1) he takes only what the day's target needs. (2) He checks material is stacked and protected. (3) He watches cutting and mixing to reduce waste. (4) He returns surplus to store with a return note. (5) He records consumption and any abnormal wastage. • Proof it happened: the material request and issue records, the return notes and the wastage record. • Where it usually breaks: surplus is left at the front, becomes damaged or disappears, and the loss shows up nowhere. | • Tie the material request to the day's target, since bulk material at the front is the main cause of unexplained loss. • Require surplus to be returned with a return note, because material left at the front is counted as consumed and vanishes from control. • Require high value items to be handled separately and returned to secure storage at shift end. • Require abnormal wastage to be reported with the cause, and set the threshold that triggers investigation. • Require consumption to be compared against installed quantity, since that comparison is the only genuine wastage check.
437 | Projects | Report attendance, completed quantities and remaining work | Foreman | Trigger: When the task or shift reaches reporting and handover cutoff. Action: The Foreman completes “Report attendance, completed quantities and remaining work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported attendance, completed quantity, next-shift need and secured work-front status. Control/Handoff: Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the task or shift reaches reporting and handover cutoff. | The Foreman completes “Report attendance, completed quantities and remaining work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported attendance, completed quantity, next-shift need and secured work-front status. | Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: at the end of the shift the foreman reports who worked, what was finished, how much, and what is still left. • Starts when: at shift end, and at any interim reporting point. • How it runs: (1) he confirms attendance by name against the deployment record. (2) He measures or counts what was completed per task. (3) He states what is part complete and how much remains. (4) He submits the report to the supervisor. (5) He carries the remaining work into the next shift. • Proof it happened: the daily report with attendance, completed quantities and remaining work. • Where it usually breaks: the foreman reports a feeling about progress rather than a measured quantity, and reporting drifts from reality. | • Require quantities rather than percentages. A foreman estimating a percentage is where optimistic progress reporting begins. • Define what counts as complete for each activity, so completion is not claimed on work still needing finishing. • Require the remaining quantity to be stated, because that is what the next shift plan needs. • Require attendance by name to be reconciled with the deployment record, so hours tie to output. • Set the reporting deadline so the supervisor can build the next day's plan the same evening.
438 | Projects | Request next-shift materials, tools and access requirements | Foreman | Trigger: When the task or shift reaches reporting and handover cutoff. Action: The Foreman completes “Request next-shift materials, tools and access requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported attendance, completed quantity, next-shift need and secured work-front status. Control/Handoff: Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the task or shift reaches reporting and handover cutoff. | The Foreman completes “Request next-shift materials, tools and access requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported attendance, completed quantity, next-shift need and secured work-front status. | Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: the foreman says now what his crew will need tomorrow: material, tools and a work area they can get into. • Starts when: at the end of the shift, or as soon as a forward requirement is known. • How it runs: (1) he works out what the next shift's target needs. (2) He lists material, tools and access equipment with quantities. (3) He states the work fronts that must be released or cleared. (4) He submits the request to the supervisor before leaving. (5) He confirms at the start of the next shift whether it arrived. • Proof it happened: the next shift requirement request and the confirmation of what was provided. • Where it usually breaks: the request is made on the morning it is needed, which is too late for the store or the supplier to act. | • Require the request to be submitted at the end of the previous shift, with a quantity and a required by time. Same morning requests cannot be met and guarantee standing time. • Require access and work front release needs to be included, not just material, because access is the more common blocker. • Set the store's response commitment so the foreman knows what to expect and when to escalate. • Require unmet requests to be carried forward visibly rather than reset each day. • Require long lead or special items to be flagged separately, since these cannot be met on a daily cycle.
439 | Projects | Present completed work to the supervisor for inspection | Foreman | Trigger: When the task or shift reaches reporting and handover cutoff. Action: The Foreman completes “Present completed work to the supervisor for inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported attendance, completed quantity, next-shift need and secured work-front status. Control/Handoff: Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the task or shift reaches reporting and handover cutoff. | The Foreman completes “Present completed work to the supervisor for inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported attendance, completed quantity, next-shift need and secured work-front status. | Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: when the work is finished the foreman shows it to the supervisor for checking rather than deciding himself that it is acceptable. • Starts when: a task is complete and has passed the foreman's own check. • How it runs: (1) he confirms his own check is done and defects are corrected. (2) He presents the work with the location and the task named. (3) He keeps the work accessible and provides a worker to assist. (4) He receives the result and gets rejected items corrected. (5) He presents it again where required. • Proof it happened: the presentation record, the supervisor's result and the re presentation record. • Where it usually breaks: the crew moves on and the next activity covers the work before anyone checked it. | • State that the crew does not move on and nothing covers the work until it has been checked and accepted. This is the rule that keeps unchecked work out of the building. • Require the presentation to name the location and task so the record ties to physical work. • Set a check response time, otherwise the delay is blamed on the foreman. • Require rejected items to be corrected and re presented, and keep the rejection on record alongside the eventual acceptance. • List the activities where following work may not start without acceptance, and keep that list at the front.
440 | Projects | Secure the area and hand over end-of-shift status | Foreman | Trigger: When the task or shift reaches reporting and handover cutoff. Action: The Foreman completes “Secure the area and hand over end-of-shift status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported attendance, completed quantity, next-shift need and secured work-front status. Control/Handoff: Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. Continuity/Escalation: A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. Timing: To be confirmed. | When the task or shift reaches reporting and handover cutoff. | The Foreman completes “Secure the area and hand over end-of-shift status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported attendance, completed quantity, next-shift need and secured work-front status. | Foreman submits records to the supervisor and does not claim unverified quantities or completed inspection status. | A nominated competent Foreman may cover the work front; changes to drawing, method, sequence or resource commitment require supervisor approval. | To be confirmed. | • In plain words: at the end of the shift the foreman leaves the area safe and tells the next shift or the supervisor where things stand. • Starts when: at the end of every shift and before any planned stoppage. • How it runs: (1) he stops the crew and clears them safely. (2) He confirms openings, edges and excavations are protected. (3) He confirms tools, equipment and material are secured or returned. (4) He confirms completed work is protected. (5) He hands over the status, including anything left incomplete or temporarily supported. • Proof it happened: the shift end securing check and the written handover of status. • Where it usually breaks: the handover is verbal, so the next shift does not know what is half finished or temporarily supported. | • Require the handover in writing for anything incomplete or temporarily supported. A verbal handover is how the next shift inherits a hidden risk. • List the shift end safety checks as a short physical checklist: openings covered, edges protected, excavations barricaded, equipment isolated and secured. • Require the check before the crew leaves, and name who does it when the foreman is absent. • Add extended requirements before weekends, holidays and shutdowns, since unattended period incidents are the worst outcome here. • Require weather protection of completed work, because unprotected finishes are routinely lost overnight.
441 | Projects | Receive the foreman work instruction and target | Chargehand | Trigger: When the Foreman assigns a crew task and target. Action: The Chargehand completes “Receive the foreman work instruction and target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: workers allocated, briefed and equipped for the approved task. Control/Handoff: The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the Foreman assigns a crew task and target. | The Chargehand completes “Receive the foreman work instruction and target” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | workers allocated, briefed and equipped for the approved task. | The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand takes the instruction and the target from the foreman, so the small group he leads knows exactly what it has to finish today. • Starts when: at the start of the shift, or when the instruction changes during the day. • How it runs: (1) he receives the task, location and target quantity from the foreman. (2) He goes through the method and the standard expected. (3) He confirms how many workers he has for it. (4) He asks about anything unclear before starting. (5) He confirms he has taken the task on. • Proof it happened: the task instruction record and the chargehand's acknowledgement. • Where it usually breaks: the instruction is a general one to carry on, so the group works without a finish point and nobody can say whether the day succeeded. | • Require the instruction to carry a quantity and a location. Carry on with yesterday's work is not a target and cannot be reported against. • Require the standard expected to be stated with the task, since the chargehand is the person who decides what good enough looks like at the face. • Give the chargehand a clear right to ask before starting, because at this level questions are usually suppressed. • Require the chargehand to say if the task cannot be done with the workers he has, and make that acceptable to report. • Keep the instruction verbal but recorded by the foreman, so it stays practical at this level while remaining traceable.
442 | Projects | Allocate individual tasks to assigned workers | Chargehand | Trigger: When the Foreman assigns a crew task and target. Action: The Chargehand completes “Allocate individual tasks to assigned workers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: workers allocated, briefed and equipped for the approved task. Control/Handoff: The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the Foreman assigns a crew task and target. | The Chargehand completes “Allocate individual tasks to assigned workers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | workers allocated, briefed and equipped for the approved task. | The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand gives each worker in his group their specific job for the shift. • Starts when: the task is received, or work has to be reshuffled during the shift. • How it runs: (1) he splits the task into individual jobs. (2) He matches the job to each worker's skill and experience. (3) He tells each worker what to do, where, and to what standard. (4) He keeps the less experienced workers alongside experienced ones. (5) He adjusts allocation as the work progresses. • Proof it happened: the worker allocation for the shift, recorded with the crew output. • Where it usually breaks: an inexperienced worker is given work beyond his skill and left alone, and the work has to be redone. | • Require skill to be matched to the task, and require new or inexperienced workers to be paired with an experienced one. This is the cheapest quality control available on site. • State that restricted work is only allocated to certified workers, with no exception for workload pressure. • Require the standard to be stated with the allocation, not assumed from experience. • Require the chargehand to check in on inexperienced workers during the shift rather than at the end. • State how allocation changes during the shift are recorded, since this is where labour evidence usually breaks down.
443 | Projects | Demonstrate the required work method and quality standard | Chargehand | Trigger: When the Foreman assigns a crew task and target. Action: The Chargehand completes “Demonstrate the required work method and quality standard” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: workers allocated, briefed and equipped for the approved task. Control/Handoff: The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the Foreman assigns a crew task and target. | The Chargehand completes “Demonstrate the required work method and quality standard” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | workers allocated, briefed and equipped for the approved task. | The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand shows the workers how the job is to be done and what an acceptable result looks like, rather than only describing it. • Starts when: at the start of a new activity, when a new worker joins, or when the quality is not being met. • How it runs: (1) he performs or demonstrates the method himself. (2) He points out the parts that are easy to get wrong. (3) He shows the approved sample or a completed acceptable piece. (4) He watches the worker do it once and corrects immediately. (5) He confirms the worker can produce the standard before leaving him to it. • Proof it happened: the demonstration record within the crew briefing and the approved sample kept at the front. • Where it usually breaks: the method is described in words only, so each worker interprets it differently and the finish varies across the area. | • Require a physical demonstration rather than a verbal instruction for any repetitive or finishing activity. Described methods produce inconsistent work across an area. • Require an approved sample or first accepted piece to be kept at the work front as the reference, since a sample in the office controls nothing. • Require the chargehand to watch the first attempt and correct it immediately, because the first hour sets the standard for the whole area. • Require a fresh demonstration when the quality drops or a new worker joins, not only at the start. • Name who approves the sample, so the standard is not set at chargehand level alone.
444 | Projects | Confirm workers have correct tools, materials and PPE | Chargehand | Trigger: When the Foreman assigns a crew task and target. Action: The Chargehand completes “Confirm workers have correct tools, materials and PPE” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: workers allocated, briefed and equipped for the approved task. Control/Handoff: The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the Foreman assigns a crew task and target. | The Chargehand completes “Confirm workers have correct tools, materials and PPE” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | workers allocated, briefed and equipped for the approved task. | The Chargehand confirms understanding and readiness; unclear or unsafe instructions return to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand checks each of his workers actually has the right tools, the material and the protective equipment before they start. • Starts when: before the group starts, and when something runs out or breaks during the shift. • How it runs: (1) he checks each worker's tools are present and serviceable. (2) He checks the material at the face is the approved one and enough for the task. (3) He checks each worker's PPE is complete and usable. (4) He replaces or reports what is missing before work starts. (5) He stops any worker without the required protection. • Proof it happened: the pre start check within the crew record and the shortage or replacement notes. • Where it usually breaks: a worker starts with damaged PPE or the wrong tool because stopping feels like making trouble. | • State that a worker without complete and usable PPE does not start, and that the chargehand is required to stop him. Put it in writing, because at this level the social pressure runs the other way. • Require damaged PPE to be exchanged, not repaired, and say where the stock sits on site. • Require the material at the face to be checked as the approved one, since wrong material used at the face is discovered only at inspection. • Require improvised tools to be refused and name the common improvisations. • Give a fast replacement route, because a slow one guarantees the rule is broken.
445 | Projects | Supervise worker sequence and task coordination | Chargehand | Trigger: When workers begin the authorised task. Action: The Chargehand completes “Supervise worker sequence and task coordination” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: coordinated crew execution, stable material supply and controlled interfaces. Control/Handoff: The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When workers begin the authorised task. | The Chargehand completes “Supervise worker sequence and task coordination” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | coordinated crew execution, stable material supply and controlled interfaces. | The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand keeps his workers working in the right order so they do not get in each other's way or undo each other's work. • Starts when: throughout the shift as the work progresses. • How it runs: (1) he sets the order in which the parts of the task are done. (2) He keeps workers spaced so they can work safely. (3) He makes sure one worker's activity does not damage another's finished part. (4) He adjusts the order when conditions change. (5) He raises anything he cannot resolve to the foreman. • Proof it happened: the task sequence followed and the recorded issues raised. • Where it usually breaks: everyone starts at the convenient point instead of the correct one, and part of the work has to be redone. | • Require the sequence within the task to be set by the chargehand at the start rather than left to each worker, since this is the main source of small scale rework. • Require safe working distance between workers, especially where tools, heat or cutting are involved. • Require the chargehand to raise a sequence problem he cannot resolve rather than working around it. • State that completed parts of the task are protected from the workers still finishing. • Add a rule that a sequence change affecting other trades goes to the foreman, not agreed at the face.
446 | Projects | Monitor attendance, tool use and work-front discipline | Chargehand | Trigger: When workers begin the authorised task. Action: The Chargehand completes “Monitor attendance, tool use and work-front discipline” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: coordinated crew execution, stable material supply and controlled interfaces. Control/Handoff: The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When workers begin the authorised task. | The Chargehand completes “Monitor attendance, tool use and work-front discipline” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | coordinated crew execution, stable material supply and controlled interfaces. | The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand keeps track of who is present, that tools are being used properly, and that behaviour at the work face is acceptable. • Starts when: at the start of the shift and continuously through it. • How it runs: (1) he confirms who is present against his group list. (2) He reports absences to the foreman. (3) He watches tool use and stops misuse. (4) He addresses unsafe behaviour, horseplay or unauthorised absence from the face. (5) He reports repeated issues to the foreman. • Proof it happened: the attendance record for the group and the recorded discipline reports. • Where it usually breaks: a worker leaves the face unnoticed for long periods, and nobody can account for where he was if something happens. | • Require a headcount at the face at set points in the shift, not only at the gate. In an emergency, gate attendance does not tell anyone where people are. • Require unaccounted absence from the face to be reported to the foreman the same shift. • Set out what the chargehand handles himself and what he must escalate on behaviour, so discipline does not depend on personality. • Require tool misuse to be stopped and reported, since misuse damages both the tool and the worker. • State that raising a discipline issue is a duty, not an act of hostility, and that the foreman handles the consequence.
447 | Projects | Maintain continuous supply of approved materials to the crew | Chargehand | Trigger: When workers begin the authorised task. Action: The Chargehand completes “Maintain continuous supply of approved materials to the crew” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: coordinated crew execution, stable material supply and controlled interfaces. Control/Handoff: The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When workers begin the authorised task. | The Chargehand completes “Maintain continuous supply of approved materials to the crew” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | coordinated crew execution, stable material supply and controlled interfaces. | The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand makes sure the material keeps arriving at the face so the group is never standing waiting for it. • Starts when: continuously through the shift as material is consumed. • How it runs: (1) he tracks how fast material is being used against what is at the face. (2) He requests the next quantity before the current stock runs out. (3) He confirms the material arriving is the approved one. (4) He keeps it stacked so it is usable and not damaged. (5) He reports a shortage to the foreman immediately. • Proof it happened: the material request records and the recorded shortages. • Where it usually breaks: the request is made when the material runs out, so the group is idle for as long as the delivery takes. | • Require the next request to be raised while stock is still running, with a stated trigger level. Requesting on empty guarantees idle time. • Require the arriving material to be confirmed as the approved item, since substituted material entering at the face is rarely caught later. • Require shortages to be reported immediately to the foreman with the affected headcount. • Keep quantities at the face limited to what the shift needs, so supply continuity does not become stockpiling. • Set the store or supply response time so the trigger level can be set sensibly.
448 | Projects | Coordinate minor interfaces with adjacent crews | Chargehand | Trigger: When workers begin the authorised task. Action: The Chargehand completes “Coordinate minor interfaces with adjacent crews” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: coordinated crew execution, stable material supply and controlled interfaces. Control/Handoff: The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When workers begin the authorised task. | The Chargehand completes “Coordinate minor interfaces with adjacent crews” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | coordinated crew execution, stable material supply and controlled interfaces. | The Chargehand prevents unauthorised task changes and escalates constraint or interface conflict to the Foreman. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: where the chargehand's group meets a neighbouring crew, he sorts out the small practical issues between them. • Starts when: another crew is working in or next to the same space. • How it runs: (1) he identifies where the two crews overlap. (2) He agrees access, timing and space with the other chargehand. (3) He keeps his group from damaging the neighbouring crew's work. (4) He raises anything that cannot be agreed to the foreman. (5) He reports damage rather than leaving it. • Proof it happened: the recorded interface arrangements and the damage reports. • Where it usually breaks: an informal deal is struck at the face that cuts across the planned sequence, and the consequence appears later. | • Draw the line in the SOP between what the chargehand may agree at the face and what must go to the foreman. Informal deals that change the sequence are the risk here. • Require damage to a neighbouring crew's work to be reported immediately with the location and cause. • Require protection where the group works next to completed work, and name who provides it. • State that access disputes go to the foremen rather than being settled by whoever is more forceful. • Require any arrangement made at the face to be reported to the foreman the same shift.
449 | Projects | Check workmanship during execution and correct minor defects | Chargehand | Trigger: When work is underway or a hazard/quality concern is observed. Action: The Chargehand completes “Check workmanship during execution and correct minor defects” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: corrected minor work, protected assets and a safe, orderly work front. Control/Handoff: Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When work is underway or a hazard/quality concern is observed. | The Chargehand completes “Check workmanship during execution and correct minor defects” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | corrected minor work, protected assets and a safe, orderly work front. | Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand watches the quality while the work is happening and corrects small faults on the spot. • Starts when: continuously during execution. • How it runs: (1) he checks the work against the sample or standard as it progresses. (2) He checks the measurements that matter at the face. (3) He corrects small faults immediately with the worker who made them. (4) He tells the foreman about anything he cannot correct. (5) He records what was corrected with the crew output. • Proof it happened: the in progress check notes and the corrections recorded. • Where it usually breaks: faults are left for the final inspection, by which time a whole area is affected and the correction is expensive. | • State that the chargehand corrects at the point of work, with the worker present. Correction hours later, without the worker, teaches nobody and repeats the fault. • Require the sample or standard to be physically available at the face for comparison. • Draw the line between what the chargehand corrects and what he must report, and name covering up a real defect as a reportable matter. • Require repeated faults to be reported so retraining or a method change can be arranged. • Require corrections to be recorded even when immediate, since the pattern is what identifies the real cause.
450 | Projects | Stop unsafe or unauthorised work and notify the foreman | Chargehand | Trigger: When work is underway or a hazard/quality concern is observed. Action: The Chargehand completes “Stop unsafe or unauthorised work and notify the foreman” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: corrected minor work, protected assets and a safe, orderly work front. Control/Handoff: Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When work is underway or a hazard/quality concern is observed. | The Chargehand completes “Stop unsafe or unauthorised work and notify the foreman” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | corrected minor work, protected assets and a safe, orderly work front. | Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: if something being done is unsafe or was never authorised, the chargehand stops it and tells the foreman. • Starts when: an unsafe act or condition appears, or work is being done without authorisation. • How it runs: (1) he stops the activity immediately. (2) He removes workers from the danger. (3) He makes the area safe as far as he can. (4) He notifies the foreman without delay. (5) He does not allow restart until the foreman or supervisor releases it. • Proof it happened: the stop work record with the reason, the notification and the restart approval. • Where it usually breaks: the chargehand hesitates to stop work because he is afraid of the reaction, and the exposure continues. | • Write the stop work authority in plain words and state that the chargehand will be supported for using it, even if the stop turns out to be unnecessary. Without that written backing the authority is not real. • Require the stop to be recorded with the reason, so the pattern of unsafe conditions becomes visible to management. • State that restart requires a release from the foreman or supervisor, never a decision at the face. • Require unauthorised work to be stopped as well as unsafe work, since work with no authorisation has no controls behind it. • Name what counts as an immediate stop condition, so the judgement is not left entirely to the individual.
451 | Projects | Protect completed work, materials and company tools | Chargehand | Trigger: When work is underway or a hazard/quality concern is observed. Action: The Chargehand completes “Protect completed work, materials and company tools” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: corrected minor work, protected assets and a safe, orderly work front. Control/Handoff: Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When work is underway or a hazard/quality concern is observed. | The Chargehand completes “Protect completed work, materials and company tools” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | corrected minor work, protected assets and a safe, orderly work front. | Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand looks after finished work, the material at the face and the company's tools so they are not damaged or lost. • Starts when: throughout the shift and particularly at the end of it. • How it runs: (1) he arranges protection over completed work in his area. (2) He keeps material stacked, covered and clear of traffic. (3) He accounts for tools issued to his group. (4) He returns tools and surplus material at shift end. (5) He reports loss or damage rather than absorbing it. • Proof it happened: the tool issue and return record, the protection arrangements and the loss or damage reports. • Where it usually breaks: tools go missing gradually with nobody accountable, and losses are only found at a stocktake months later. | • Require tools to be issued to a named chargehand and accounted for at shift end. Tools issued to a crew in general are tools nobody is responsible for. • Require loss or damage to be reported the same shift, and state that reporting is expected rather than penalised, otherwise it is hidden. • Require protection of completed work as a named duty with the material provided for it. • Require high value items to be returned to secure storage rather than left at the face overnight. • Set a periodic tool reconciliation so losses surface within weeks rather than at a yearly count.
452 | Projects | Maintain work-front housekeeping and safe access | Chargehand | Trigger: When work is underway or a hazard/quality concern is observed. Action: The Chargehand completes “Maintain work-front housekeeping and safe access” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: corrected minor work, protected assets and a safe, orderly work front. Control/Handoff: Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When work is underway or a hazard/quality concern is observed. | The Chargehand completes “Maintain work-front housekeeping and safe access” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | corrected minor work, protected assets and a safe, orderly work front. | Unsafe work is stopped immediately; significant defect, hazard or damage is reported and preserved for investigation. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand keeps the immediate work area tidy and the way in and out clear while the work is going on. • Starts when: continuously through the shift. • How it runs: (1) he keeps the route to the work face clear. (2) He has waste and offcuts cleared as they are produced. (3) He keeps material off walkways and away from openings. (4) He keeps leads and hoses managed off the walking route. (5) He confirms the face is clear before the group leaves. • Proof it happened: the housekeeping checks recorded with the crew record. • Where it usually breaks: waste accumulates around the face all day and the group works in its own obstruction. | • Require clearing as work proceeds rather than at shift end. A face cleared only at the end is obstructed for the whole shift, which is when incidents happen. • Require access and escape routes to be kept clear as a named check. • Require leads, hoses and cables to be managed off walking routes, the commonest site trip hazard. • Name who provides waste removal and how often, since crews cannot clear without somewhere to put it. • State the stacking distance from openings and edges in figures.
453 | Projects | Record crew output and completed task quantities | Chargehand | Trigger: When the shift, task or material issue is completed. Action: The Chargehand completes “Record crew output and completed task quantities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: crew output, exception, material return and completion status reported to the Foreman. Control/Handoff: Only observed quantities and conditions are reported; discrepancy is checked before record closure. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the shift, task or material issue is completed. | The Chargehand completes “Record crew output and completed task quantities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | crew output, exception, material return and completion status reported to the Foreman. | Only observed quantities and conditions are reported; discrepancy is checked before record closure. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand records what his group actually finished during the shift, counted rather than estimated. • Starts when: during and at the end of the shift. • How it runs: (1) he counts or measures what was completed. (2) He notes what is part finished and how much is left. (3) He notes which worker completed which part where it matters. (4) He gives the output to the foreman. (5) He keeps the count consistent with the unit used in the target. • Proof it happened: the crew output record with quantities per task. • Where it usually breaks: output is reported as a rough impression, so the foreman's report to the supervisor is built on guesswork. | • Require a counted or measured quantity in the same unit as the target. An impression at this level becomes a false progress figure three levels up. • Define what counts as complete for the common tasks, so completion is not claimed on unfinished work. • Require part finished work to be reported with the remaining quantity. • Keep the recording method simple enough to be done at the face, because a complex form will be filled in from memory. • Require the output record to be handed over the same shift, not the next morning.
454 | Projects | Report shortages, hazards, delays and missing information | Chargehand | Trigger: When the shift, task or material issue is completed. Action: The Chargehand completes “Report shortages, hazards, delays and missing information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: crew output, exception, material return and completion status reported to the Foreman. Control/Handoff: Only observed quantities and conditions are reported; discrepancy is checked before record closure. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the shift, task or material issue is completed. | The Chargehand completes “Report shortages, hazards, delays and missing information” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | crew output, exception, material return and completion status reported to the Foreman. | Only observed quantities and conditions are reported; discrepancy is checked before record closure. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand tells the foreman about anything blocking his group: no material, a hazard, a delay or missing information. • Starts when: as soon as the problem appears. • How it runs: (1) he identifies what is missing or wrong. (2) He states what is needed and by when. (3) He states how many workers are affected. (4) He reports it to the foreman immediately rather than at shift end. (5) He follows up whether it was resolved. • Proof it happened: the reported shortage, hazard and delay records with times and affected headcount. • Where it usually breaks: the problem is reported at shift end, so the whole day is lost before anyone could have acted. | • Require immediate reporting rather than shift end reporting. A shortage reported at six o'clock has already cost the full day. • Require the affected headcount and time to be stated, since that is what turns a complaint into a costed constraint. • State that hazards are reported directly and immediately, without waiting for a convenient moment. • Require missing information to be reported rather than resolved at the face, because face level resolution changes the work silently. • Require the foreman to close the loop back to the chargehand, otherwise reporting stops.
455 | Projects | Return unused material and tools to controlled storage | Chargehand | Trigger: When the shift, task or material issue is completed. Action: The Chargehand completes “Return unused material and tools to controlled storage” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: crew output, exception, material return and completion status reported to the Foreman. Control/Handoff: Only observed quantities and conditions are reported; discrepancy is checked before record closure. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the shift, task or material issue is completed. | The Chargehand completes “Return unused material and tools to controlled storage” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | crew output, exception, material return and completion status reported to the Foreman. | Only observed quantities and conditions are reported; discrepancy is checked before record closure. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: at the end of the shift the chargehand takes the unused material and the tools back to proper storage instead of leaving them at the face. • Starts when: at the end of the shift, or when an activity finishes. • How it runs: (1) he collects unused material at the face. (2) He returns it to the store with a return note. (3) He collects the tools issued to his group. (4) He returns them and accounts for any missing or damaged item. (5) He reports losses and damage. • Proof it happened: the material return notes and the tool return record. • Where it usually breaks: material and tools are left at the face because returning them takes time, and both disappear. | • Make the return a required end of shift step with a return note, since material left at the face is treated as consumed and is never recovered. • Require tools to be accounted for by the named chargehand at shift end, with missing items reported the same day. • Keep the store open at shift end or provide a secure interim point, because a closed store guarantees the rule is broken. • Require damaged items to be returned and reported rather than discarded at the face. • Require returns to be recorded against the original issue, so consumption figures stay meaningful.
456 | Projects | Confirm completed work and shift status to the foreman | Chargehand | Trigger: When the shift, task or material issue is completed. Action: The Chargehand completes “Confirm completed work and shift status to the foreman” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: crew output, exception, material return and completion status reported to the Foreman. Control/Handoff: Only observed quantities and conditions are reported; discrepancy is checked before record closure. Continuity/Escalation: A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. Timing: To be confirmed. | When the shift, task or material issue is completed. | The Chargehand completes “Confirm completed work and shift status to the foreman” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | crew output, exception, material return and completion status reported to the Foreman. | Only observed quantities and conditions are reported; discrepancy is checked before record closure. | A nominated competent Chargehand may cover crew coordination; technical, quality, safety and resource exceptions escalate to the Foreman or Supervisor. | To be confirmed. | • In plain words: the chargehand tells the foreman what is finished, what is not, and anything he needs to know before the shift ends. • Starts when: at the end of every shift. • How it runs: (1) he confirms the completed quantities. (2) He states what is part complete and what remains. (3) He states anything left temporarily supported, open or unsafe. (4) He states what the group will need next shift. (5) He confirms the face is left clean, safe and secured. • Proof it happened: the shift end confirmation to the foreman with quantities and outstanding items. • Where it usually breaks: the confirmation is a passing word at the gate, and the detail the next shift needs is lost. | • Require the shift end confirmation to be given face to face and recorded by the foreman, not called out while leaving. This is the point where next shift problems are created. • Require anything left temporarily supported, open or energised to be stated explicitly, since this is the hidden risk handed to the next shift. • Require the next shift requirement to be included, so the request reaches the store in time. • Require confirmation that the face is left clean, safe and secured, with the checks named. • Set what happens when the chargehand leaves before the foreman is available, so the handover is never simply skipped.
457 | Projects | Attend the toolbox briefing and confirm the assigned skilled task | Skilled Labour | Trigger: When a skilled worker receives the approved task. Action: The Skilled Labour completes “Attend the toolbox briefing and confirm the assigned skilled task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed task understanding, safe tools/materials and readiness to execute. Control/Handoff: The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When a skilled worker receives the approved task. | The Skilled Labour completes “Attend the toolbox briefing and confirm the assigned skilled task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed task understanding, safe tools/materials and readiness to execute. | The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: the tradesman attends the briefing at the start of the shift and confirms he has understood the task he has been given, where it is and how it is to be done. • Starts when: the shift begins, or he is moved to a different task or a different area during the shift. • How it runs: (1) he attends the briefing on time. (2) He listens to the task, the location, the method and the safety points. (3) He confirms he has understood, and asks if anything is unclear. (4) He signs the briefing record. (5) He goes to the correct work front and begins only that task. • Proof it happened: his signature on the toolbox briefing record for that shift. • Where it usually breaks: he signs without understanding, because asking a question in front of the group feels like admitting he does not know his trade. | • State in the SOP that the briefing is given in a language the worker actually understands, and that a translator is arranged where it is not. A signature on a briefing he could not follow is worthless. • Require the chargehand to ask the worker to repeat the task back rather than asking whether he understood. Everyone answers yes to that question. • Say plainly that questions are expected and that no worker is penalised for asking. Without that line, workers stay silent and guess. • Add the rule for mid shift reassignment. A worker moved to new work gets a new briefing, because the risks in the new area are different. • Require the briefing record to name the task and location, not just the date. A generic record cannot show what any individual was briefed to do.
458 | Projects | Inspect tools, equipment, materials and work-front condition | Skilled Labour | Trigger: When a skilled worker receives the approved task. Action: The Skilled Labour completes “Inspect tools, equipment, materials and work-front condition” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed task understanding, safe tools/materials and readiness to execute. Control/Handoff: The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When a skilled worker receives the approved task. | The Skilled Labour completes “Inspect tools, equipment, materials and work-front condition” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed task understanding, safe tools/materials and readiness to execute. | The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: before starting, the tradesman checks his tools, his equipment, the materials he has been given and the condition of the work front. • Starts when: at the start of the shift, and again whenever he starts at a new work front. • How it runs: (1) he checks tools and power leads for damage. (2) He checks equipment guards and safety devices are in place. (3) He checks the material issued is the right type and is not damaged. (4) He checks the work front is safe, clean and ready. (5) He reports anything wrong to the chargehand before starting. • Proof it happened: the tool and equipment check record, and the reported items in the chargehand's log. • Where it usually breaks: he finds a damaged tool, cannot get a replacement quickly, and uses it anyway to avoid losing time. | • Give the worker explicit authority to refuse a damaged tool and require the SOP to name who provides the replacement and how fast. Authority without a replacement route just makes him use the damaged tool. • Require damaged tools to be physically removed and tagged, not put back in the box. A damaged tool left in circulation reaches the next man. • Include a short list of what makes a tool unfit, so the judgement does not rest on the individual's opinion. • State that guards and safety devices are never removed to make work faster, and that a tool arriving without its guard is reported rather than used. • Require material to be checked for type and grade, not just damage. Using the wrong grade of the right looking material is the more expensive error.
459 | Projects | Verify the latest work instruction, dimensions and quality expectation | Skilled Labour | Trigger: When a skilled worker receives the approved task. Action: The Skilled Labour completes “Verify the latest work instruction, dimensions and quality expectation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed task understanding, safe tools/materials and readiness to execute. Control/Handoff: The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When a skilled worker receives the approved task. | The Skilled Labour completes “Verify the latest work instruction, dimensions and quality expectation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed task understanding, safe tools/materials and readiness to execute. | The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: the tradesman confirms he is working to the current instruction, and that he knows the dimensions and the standard of finish expected. • Starts when: before starting any element, and again whenever the chargehand notifies a change. • How it runs: (1) he checks the instruction or sketch he has is the current one. (2) He confirms the key dimensions and levels. (3) He confirms the finish and tolerance expected. (4) He raises anything he cannot read or that contradicts what he sees. (5) He works to that instruction only. • Proof it happened: his acknowledgement of the current instruction, and his marked up copy at the work front. • Where it usually breaks: he works from the sketch in his pocket from last week, and nobody told him the detail changed. | • Require the chargehand to physically collect and destroy the old sketch when a detail changes. A superseded sketch in a pocket is the single commonest cause of trade rework. • State that the worker never works from memory of a dimension. It must be in front of him, in writing, at the work face. • Define the finish standard in a way a tradesman can check himself, with a sample panel or a measurable tolerance rather than words like neat or good. • Add the rule that a contradiction between the instruction and site conditions stops work and is reported. Deciding it himself is what turns one error into a hundred repeated units. • Require an acknowledgement step for changes, so the record shows which workers were told and when.
460 | Projects | Report any unsafe, missing or conflicting requirement before work | Skilled Labour | Trigger: When a skilled worker receives the approved task. Action: The Skilled Labour completes “Report any unsafe, missing or conflicting requirement before work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed task understanding, safe tools/materials and readiness to execute. Control/Handoff: The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When a skilled worker receives the approved task. | The Skilled Labour completes “Report any unsafe, missing or conflicting requirement before work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed task understanding, safe tools/materials and readiness to execute. | The worker does not proceed on unclear drawing, unsafe access or unsuitable material and reports immediately. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: if something is unsafe, missing or does not make sense, the tradesman says so before he starts rather than working around it. • Starts when: the moment he identifies the problem, at any point in the shift. • How it runs: (1) he stops or does not start that activity. (2) He tells the chargehand directly. (3) He explains what is unsafe, missing or contradictory. (4) He waits for the instruction or the correction. (5) He resumes only when it is resolved. • Proof it happened: the report entered in the chargehand's log, and the closure of the issue. • Where it usually breaks: he reports it once, nothing happens, and he stops reporting from then on. | • Require every report to be answered, even if the answer is that work continues. An unanswered report teaches the whole crew that reporting is pointless, and that is how a site goes quiet. • Write the right to refuse unsafe work in plain language in the SOP, with the line that the worker is supported for using it. Without that line it exists only on paper. • Give a second route when the chargehand does not act, naming who else the worker may go to. One blocked route must not end the matter. • Say explicitly that reports are never treated as complaints or as slowing the job, and name the consequence for any supervisor who treats them that way. • Require the chargehand to log the report as received, so the record does not depend on whether it was later found to be valid.
461 | Projects | Execute the assigned skilled trade work to approved drawings and method | Skilled Labour | Trigger: When the skilled task is released by the Chargehand or Foreman. Action: The Skilled Labour completes “Execute the assigned skilled trade work to approved drawings and method” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: completed trade work meeting the approved method, dimensions and productivity expectation. Control/Handoff: The worker follows the assigned scope only and seeks instruction before changing method, material or location. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task is released by the Chargehand or Foreman. | The Skilled Labour completes “Execute the assigned skilled trade work to approved drawings and method” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | completed trade work meeting the approved method, dimensions and productivity expectation. | The worker follows the assigned scope only and seeks instruction before changing method, material or location. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: the tradesman does his trade work exactly as the approved drawing and method say, and not the way he prefers to do it. • Starts when: the work front is released and the materials and instruction are in place. • How it runs: (1) he sets out from the marked reference points. (2) He follows the approved method and sequence. (3) He uses the specified material and fixing. (4) He keeps to the dimensions and tolerances given. (5) He stops and asks if he cannot achieve the drawing on site. • Proof it happened: the completed work, the quantity recorded, and the inspection or check record. • Where it usually breaks: he substitutes a fixing or a method that he considers just as good, and nobody realises until the inspection. | • State plainly that no substitution of material, fixing or method is made at worker level for any reason, and name who may approve one. Just as good decided at the work face is not an approval. • Require the worker to stop and report when the drawing cannot be built as shown, rather than adapting it. Site adaptation without a record is how as built and design diverge. • Define the sequence where sequence matters, since doing correct steps in the wrong order can still fail the inspection. • Add a first off check for repetitive work, where the first unit is checked before the rest are built. It is the difference between correcting one unit and correcting a floor. • Require the worker to work only within his trade and certification, with a clear rule on tasks he must not touch.
462 | Projects | Maintain required dimensions, levels, tolerances and finish | Skilled Labour | Trigger: When the skilled task is released by the Chargehand or Foreman. Action: The Skilled Labour completes “Maintain required dimensions, levels, tolerances and finish” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: completed trade work meeting the approved method, dimensions and productivity expectation. Control/Handoff: The worker follows the assigned scope only and seeks instruction before changing method, material or location. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task is released by the Chargehand or Foreman. | The Skilled Labour completes “Maintain required dimensions, levels, tolerances and finish” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | completed trade work meeting the approved method, dimensions and productivity expectation. | The worker follows the assigned scope only and seeks instruction before changing method, material or location. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: he keeps the work within the dimensions, levels, tolerances and finish quality that were specified. • Starts when: continuously while the work is being carried out. • How it runs: (1) he checks against the reference marks as he goes. (2) He measures rather than judges by eye. (3) He checks level and alignment at intervals rather than at the end. (4) He corrects small deviations immediately. (5) He reports anything he cannot bring back within tolerance. • Proof it happened: his own check measurements and the inspection record for the element. • Where it usually breaks: the drift accumulates unnoticed over a long run, and by the time it is measured the whole run is out. | • Require checks at set intervals through the work rather than only at completion, since deviation found at the end can rarely be corrected without demolition. • State the tolerance in figures in the SOP and make sure the worker has the means to measure it. A tolerance he cannot measure is not a control. • Require the reference marks to be protected and re checked, because working from a disturbed mark reproduces the error perfectly. • Add the rule that out of tolerance work is reported rather than adjusted with packing or filler, which hides the error rather than fixing it. • Name who verifies tolerance independently at completion, so acceptance does not rest solely on the man who did the work.
463 | Projects | Use materials, tools and equipment only for the authorised task | Skilled Labour | Trigger: When the skilled task is released by the Chargehand or Foreman. Action: The Skilled Labour completes “Use materials, tools and equipment only for the authorised task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: completed trade work meeting the approved method, dimensions and productivity expectation. Control/Handoff: The worker follows the assigned scope only and seeks instruction before changing method, material or location. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task is released by the Chargehand or Foreman. | The Skilled Labour completes “Use materials, tools and equipment only for the authorised task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | completed trade work meeting the approved method, dimensions and productivity expectation. | The worker follows the assigned scope only and seeks instruction before changing method, material or location. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: tools, equipment and materials are used only for the job they were issued for, and not borrowed for something else. • Starts when: from the moment items are issued to him until they are returned. • How it runs: (1) he uses each item only for its intended purpose. (2) He uses only the material issued for that task. (3) He does not lend issued items on without telling the chargehand. (4) He does not improvise a tool from something else. (5) He returns what he does not use. • Proof it happened: the issue and return record, and the material consumption record for the task. • Where it usually breaks: material issued for one area gets consumed in another, and both areas then show a shortage nobody can explain. | • Require material issued for a specific area to be recorded against that area, and any transfer to be reported. Without this, consumption records cannot be reconciled to anything. • Ban improvised tools explicitly, with examples. Improvised tools cause a large share of hand injuries and this is where they are invented. • Require certified equipment to be used only by certified operators, and say that lending it on is a reportable act. • Define the return route for unused material, since material left at the work front is what becomes site waste and unexplained loss. • Add the rule that specialist tools are signed for individually, so accountability is not shared across a crew.
464 | Projects | Coordinate the assigned work with adjacent trades through the chargehand | Skilled Labour | Trigger: When the skilled task is released by the Chargehand or Foreman. Action: The Skilled Labour completes “Coordinate the assigned work with adjacent trades through the chargehand” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: completed trade work meeting the approved method, dimensions and productivity expectation. Control/Handoff: The worker follows the assigned scope only and seeks instruction before changing method, material or location. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task is released by the Chargehand or Foreman. | The Skilled Labour completes “Coordinate the assigned work with adjacent trades through the chargehand” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | completed trade work meeting the approved method, dimensions and productivity expectation. | The worker follows the assigned scope only and seeks instruction before changing method, material or location. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: where his work meets another trade, he goes through the chargehand rather than making a private arrangement with the other crew. • Starts when: he reaches a point where another trade's work affects his, or his affects theirs. • How it runs: (1) he identifies the clash or the dependency. (2) He reports it to the chargehand instead of negotiating directly. (3) He waits for the sequence to be agreed. (4) He works to the agreed sequence. (5) He reports if the other trade does not follow it. • Proof it happened: the coordination entry in the chargehand's log and the agreed sequence. • Where it usually breaks: two tradesmen sort it out between themselves, and the arrangement is never recorded, so nobody can tell later who agreed what. | • State that trade to trade arrangements are not made privately, and explain why in one line. Private deals are invisible to planning and cannot be enforced when they fail. • Require the agreed sequence to be recorded and communicated to both crews, so it survives a change of shift. • Give the escalation route when the other trade ignores the agreed sequence, with a time limit rather than leaving it to persistence. • Add the rule that no worker cuts, moves or removes another trade's installed work, whatever the obstruction. That single rule prevents most inter trade damage. • Require repeated clashes in the same location to be escalated as a design or coordination issue rather than resolved again each shift.
465 | Projects | Self-check completed skilled work and correct minor defects | Skilled Labour | Trigger: When work is being performed or reaches self-check. Action: The Skilled Labour completes “Self-check completed skilled work and correct minor defects” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: self-checked work, safe housekeeping and protected assets. Control/Handoff: Defect, hazard, damage or missing information is reported; unsafe work stops without waiting for routine reporting. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When work is being performed or reaches self-check. | The Skilled Labour completes “Self-check completed skilled work and correct minor defects” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | self-checked work, safe housekeeping and protected assets. | Defect, hazard, damage or missing information is reported; unsafe work stops without waiting for routine reporting. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: before calling the work finished, he checks his own work and puts right the small things himself. • Starts when: an element or a section is complete, before the chargehand or the engineer is called. • How it runs: (1) he checks the work against the instruction and the dimensions. (2) He looks for the defects common to his trade. (3) He corrects what he can correct. (4) He reports anything he cannot correct himself. (5) He then offers the work for check. • Proof it happened: the self check record and the reduced defect count at the formal inspection. • Where it usually breaks: he skips the self check because he assumes the inspection will catch anything wrong, which turns his defects into someone else's list. | • Give the worker a short trade specific check list of the five or six things that usually go wrong in his trade. A general instruction to check produces no consistent check at all. • Require the self check before the work is offered for inspection, and say that work offered without it is returned. Otherwise the self check is dropped whenever the programme tightens. • Draw a clear line between minor defects he may correct and defects he must report, since correcting the wrong thing can hide a structural or safety issue. • Require repeat defects to be tracked by trade rather than by individual, so the response is training rather than blame. • State that a defect he caused and corrected is still recorded, because hidden corrections remove any chance of finding the cause.
466 | Projects | Maintain PPE, safe access and work-front housekeeping | Skilled Labour | Trigger: When work is being performed or reaches self-check. Action: The Skilled Labour completes “Maintain PPE, safe access and work-front housekeeping” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: self-checked work, safe housekeeping and protected assets. Control/Handoff: Defect, hazard, damage or missing information is reported; unsafe work stops without waiting for routine reporting. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When work is being performed or reaches self-check. | The Skilled Labour completes “Maintain PPE, safe access and work-front housekeeping” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | self-checked work, safe housekeeping and protected assets. | Defect, hazard, damage or missing information is reported; unsafe work stops without waiting for routine reporting. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: he keeps his PPE in usable condition, keeps his access safe, and keeps his own work area tidy as he works. • Starts when: continuously through the shift. • How it runs: (1) he checks and wears the PPE required for his task. (2) He reports damaged or worn out PPE for replacement. (3) He keeps the access route to his work front clear. (4) He clears offcuts and packaging as he goes. (5) He does not leave trailing leads, open holes or loose material behind him. • Proof it happened: the housekeeping and PPE observation records for the area. • Where it usually breaks: housekeeping is left to the end of the shift, so the work front stays hazardous for the whole shift. | • Require housekeeping through the shift and not only at the end, and say so with a specific instruction such as clearing at each break. End of shift only cleaning leaves the hazard in place for eight hours. • Make PPE replacement immediate and free at the point of need. Any friction here converts directly into workers using worn out protection. • Name the task specific PPE for each trade rather than a general list, because the general list gets ignored where it clearly does not apply. • Include the rule that trailing leads, open penetrations and unsecured material are attended to at once, since these are the injuries that happen to other trades. • Add the duty to report a hazard he cannot fix himself, so the hazard is transferred rather than abandoned.
467 | Projects | Protect completed work, issued materials and company assets | Skilled Labour | Trigger: When work is being performed or reaches self-check. Action: The Skilled Labour completes “Protect completed work, issued materials and company assets” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: self-checked work, safe housekeeping and protected assets. Control/Handoff: Defect, hazard, damage or missing information is reported; unsafe work stops without waiting for routine reporting. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When work is being performed or reaches self-check. | The Skilled Labour completes “Protect completed work, issued materials and company assets” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | self-checked work, safe housekeeping and protected assets. | Defect, hazard, damage or missing information is reported; unsafe work stops without waiting for routine reporting. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: he protects finished work, the material issued to him and company equipment from damage and loss. • Starts when: as soon as work is completed or material is issued to him. • How it runs: (1) he applies the protection specified for the finished work. (2) He stores unused material properly rather than leaving it exposed. (3) He secures tools and equipment at breaks and at the end of the shift. (4) He reports damage he finds, including damage he did not cause. (5) He does not remove protection applied by others. • Proof it happened: the protection in place, the tool return record, and reported damage entries. • Where it usually breaks: another trade removes his protection to get access and does not put it back, and it is nobody's job to notice. | • Put a rule in the SOP that protection removed by another trade must be reinstated by that trade before they leave, and require the worker to report it when it is not. Otherwise unprotected finished work is discovered only when it is already damaged. • Require damage to be reported even where the worker did not cause it, and say clearly that reporting found damage carries no blame. Fear of blame is why damage is reported late or not at all. • Specify how each type of finish is protected and for how long, since improvised protection often damages the finish itself. • Add secure storage and end of shift arrangements for tools and small plant, which is where most loss occurs. • Require damage reports to record the location and the probable time, because a report without those cannot be attributed to anyone.
468 | Projects | Report completed quantity, defect, delay or material shortage | Skilled Labour | Trigger: When the skilled task or shift is completed. Action: The Skilled Labour completes “Report completed quantity, defect, delay or material shortage” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported output, clean work front and returned tools/materials. Control/Handoff: The Chargehand verifies handover; unresolved defects or shortages remain open and assigned. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task or shift is completed. | The Skilled Labour completes “Report completed quantity, defect, delay or material shortage” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported output, clean work front and returned tools/materials. | The Chargehand verifies handover; unresolved defects or shortages remain open and assigned. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: at the end of the shift he says how much he actually completed, and reports any defect, delay or shortage of material. • Starts when: at the end of the shift, and immediately for anything that stops the work. • How it runs: (1) he reports the quantity he actually completed. (2) He reports any defect he found or caused. (3) He reports delays and how long he was waiting. (4) He reports material shortages and what he still needs. (5) The chargehand records it and passes it up. • Proof it happened: the shift completion record and the entries in the chargehand's log. • Where it usually breaks: he rounds his output up to look productive, which quietly corrupts the progress figures the whole project relies on. | • Require output to be counted in real units, such as square metres or numbers fixed, rather than in percentages. A percentage from a worker is an opinion, and opinions do not add up across a site. • State that reporting a shortfall carries no penalty where the reason is recorded, otherwise the numbers get inflated by default and everything built on them is wrong. • Require waiting time to be reported with the cause and the duration, since this is the only record that later supports a delay claim. • Ask for the material still needed rather than only what has run out, which turns the report into something procurement can act on. • Set a same shift rule for reporting defects, because a defect reported after the work is covered costs many times more to put right.
469 | Projects | Clean and hand over the completed skilled work front | Skilled Labour | Trigger: When the skilled task or shift is completed. Action: The Skilled Labour completes “Clean and hand over the completed skilled work front” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported output, clean work front and returned tools/materials. Control/Handoff: The Chargehand verifies handover; unresolved defects or shortages remain open and assigned. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task or shift is completed. | The Skilled Labour completes “Clean and hand over the completed skilled work front” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported output, clean work front and returned tools/materials. | The Chargehand verifies handover; unresolved defects or shortages remain open and assigned. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: when his part is finished, he cleans the area and hands it over so the next trade can start without argument. • Starts when: his scope at that work front is complete. • How it runs: (1) he completes the remaining items on his scope. (2) He removes his waste, offcuts and surplus material. (3) He confirms the finished work is protected. (4) He tells the chargehand the front is ready to hand over. (5) The handover is recorded with the condition noted. • Proof it happened: the recorded handover of the work front and its noted condition. • Where it usually breaks: the front is left with waste and unfinished corners, and the next trade starts anyway, so the condition at handover is never established. | • Require the condition at handover to be recorded, ideally with photographs, before the next trade starts. Once they begin, nobody can prove who caused what. • State that the front is not handed over with outstanding items unless they are listed and accepted, since silent outstanding items become the next trade's obstruction. • Include waste removal as a condition of handover rather than as a separate housekeeping task, because otherwise it is nobody's job. • Require protection to be confirmed in place at handover, and say who is responsible for it after that point. • Add a route for the receiving trade to reject a front, with the reason recorded, so quality of handover is visible rather than absorbed.
470 | Projects | Return tools and unused material through the approved route | Skilled Labour | Trigger: When the skilled task or shift is completed. Action: The Skilled Labour completes “Return tools and unused material through the approved route” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: reported output, clean work front and returned tools/materials. Control/Handoff: The Chargehand verifies handover; unresolved defects or shortages remain open and assigned. Continuity/Escalation: Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. Timing: To be confirmed. | When the skilled task or shift is completed. | The Skilled Labour completes “Return tools and unused material through the approved route” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | reported output, clean work front and returned tools/materials. | The Chargehand verifies handover; unresolved defects or shortages remain open and assigned. | Another competent and authorised trade worker may provide task backup; no worker substitutes without the required trade competence and site authorisation. | To be confirmed. | • In plain words: at the end of the job he returns the tools and any unused material through the proper route rather than leaving them lying about. • Starts when: at the end of the shift or at the end of the task. • How it runs: (1) he collects the tools issued to him. (2) He checks them for damage and reports any. (3) He returns them to the store and gets the return recorded. (4) He returns unused material to the store rather than leaving or dumping it. (5) He reports anything missing straight away. • Proof it happened: the signed tool return record and the material return note. • Where it usually breaks: unused material never goes back, so it is written off as consumed and the real consumption rate is never known. | • Make returning unused material a mandatory recorded step, not a courtesy. Material never returned is booked as consumed, which corrupts every future estimate built on those rates. • Require the return to be signed by the store, so the worker is discharged of the tools and the record has two parties. • Include a damage on return check, since damage found later cannot be attributed to anyone. • Set a clear rule for reporting missing items immediately, with the line that immediate honest reporting is treated differently from a later discovery. • Name the route for material that cannot be returned to store, such as opened or part used items, so it is disposed of properly rather than left on site.
471 | Projects | Attend the toolbox briefing and receive the assigned support task | Unskilled Labour | Trigger: When the general worker receives a support task. Action: The Unskilled Labour completes “Attend the toolbox briefing and receive the assigned support task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed instruction, PPE, safe route and basic-tool readiness. Control/Handoff: The worker performs only the assigned support activity and reports unclear or unsafe conditions. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the general worker receives a support task. | The Unskilled Labour completes “Attend the toolbox briefing and receive the assigned support task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed instruction, PPE, safe route and basic-tool readiness. | The worker performs only the assigned support activity and reports unclear or unsafe conditions. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: the helper attends the briefing and is told what support task he is doing, where, and who he is working for that shift. • Starts when: the shift begins, or he is moved to a different crew or area. • How it runs: (1) he attends the briefing on time. (2) He is told his task, his location and which crew he supports. (3) He is told the safety points that apply to him. (4) He confirms he has understood and signs. (5) He reports to the crew he has been assigned to. • Proof it happened: his signature on the briefing record, and the crew allocation for the shift. • Where it usually breaks: he is moved between crews during the day and ends up working for whoever calls him, so nobody is actually accountable for him. | • Require the SOP to name one person accountable for each helper for the whole shift, and to record any reassignment. A helper shared informally between crews has no supervisor, and that is exactly who gets hurt. • Insist the briefing is given in a language he understands, with a translator where needed. This is the group most often briefed in a language they do not follow. • Require confirmation by repeating the task back, not by asking whether he understood. • State that a helper moved to a new area receives a new briefing, because the hazards there are different and he has no trade knowledge to fall back on. • Add the rule that he is given only tasks he has been briefed and trained for, however busy the crew is.
472 | Projects | Check PPE, access route and basic tools before starting | Unskilled Labour | Trigger: When the general worker receives a support task. Action: The Unskilled Labour completes “Check PPE, access route and basic tools before starting” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed instruction, PPE, safe route and basic-tool readiness. Control/Handoff: The worker performs only the assigned support activity and reports unclear or unsafe conditions. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the general worker receives a support task. | The Unskilled Labour completes “Check PPE, access route and basic tools before starting” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed instruction, PPE, safe route and basic-tool readiness. | The worker performs only the assigned support activity and reports unclear or unsafe conditions. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: before he starts he checks his PPE, checks the route he will be walking and carrying along, and checks the basic tools he has been given. • Starts when: at the start of the shift, and again after any change of area. • How it runs: (1) he checks he has the PPE required for the area. (2) He checks the access and carrying route is clear and safe. (3) He checks basic tools such as barrows and shovels for damage. (4) He reports anything missing or damaged to the chargehand. (5) He starts only once these are in order. • Proof it happened: the PPE and access check record for the crew, and reported items in the log. • Where it usually breaks: the carrying route is blocked or uneven, he works around it all day, and the trip hazard stays there for everyone else. | • Require the carrying route to be checked as a route, end to end, and not just the work area. Manual handling injuries happen along the route, not at the destination. • Make PPE replacement immediate and free, because a helper is the least likely person to push for it and the most likely to work without it. • Require a blocked or damaged route to be reported and fixed rather than worked around, since working around it hides the hazard from everyone who follows. • Include lighting in the check for internal, basement and early morning areas, where poor light is a common unreported cause of falls. • Add the rule that he does not start without the PPE required, and place the duty to stop him on the chargehand rather than on him alone.
473 | Projects | Report unsafe conditions or unclear instructions | Unskilled Labour | Trigger: When the general worker receives a support task. Action: The Unskilled Labour completes “Report unsafe conditions or unclear instructions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: confirmed instruction, PPE, safe route and basic-tool readiness. Control/Handoff: The worker performs only the assigned support activity and reports unclear or unsafe conditions. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the general worker receives a support task. | The Unskilled Labour completes “Report unsafe conditions or unclear instructions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | confirmed instruction, PPE, safe route and basic-tool readiness. | The worker performs only the assigned support activity and reports unclear or unsafe conditions. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: if something looks unsafe or he does not understand what he has been asked to do, he says so before doing it. • Starts when: the moment he notices the hazard or the unclear instruction. • How it runs: (1) he stops or does not start. (2) He tells the chargehand what the problem is. (3) He waits for a clear instruction or a correction. (4) He starts once it is clear and safe. (5) He reports again if the same problem comes back. • Proof it happened: the report logged by the chargehand and its closure. • Where it usually breaks: he does not report, because at his level asking a question feels like refusing work. | • Write in the SOP that a helper is never disciplined for asking or for stopping unsafe work, and say it in plain words. Without that line this group simply does not report. • Give a second route when the chargehand does not act, and make sure it does not require going through the person he is reporting. • Require the chargehand to respond to every report, since one ignored report is enough to stop a helper reporting anything for the rest of the job. • Allow reports to be made verbally and require the chargehand to write them down, because a written form is a barrier for workers who cannot read or write easily. • Add the rule that unclear instructions are clarified rather than guessed, which is where most helper related damage originates.
474 | Projects | Move, stage and prepare materials safely for the work crew | Unskilled Labour | Trigger: When the work crew requires authorised material or physical support. Action: The Unskilled Labour completes “Move, stage and prepare materials safely for the work crew” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safely staged material, prepared access/protection and completed support task. Control/Handoff: The Chargehand controls location and method; unsafe manual handling or unauthorised work is stopped. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the work crew requires authorised material or physical support. | The Unskilled Labour completes “Move, stage and prepare materials safely for the work crew” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safely staged material, prepared access/protection and completed support task. | The Chargehand controls location and method; unsafe manual handling or unauthorised work is stopped. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he moves materials to where they are needed, stacks them properly and prepares them so the trade crew can work without stopping. • Starts when: the crew needs material at a work front, or a delivery needs distributing. • How it runs: (1) he is told what material goes where and how much. (2) He checks the route and uses the right handling aid or barrow. (3) He moves the material without exceeding safe manual handling limits. (4) He stacks it stably, clear of access routes and away from edges. (5) He tells the chargehand once it is staged. • Proof it happened: the material staged at the work front and the movement recorded in the shift log. • Where it usually breaks: material is stacked wherever there is space, which blocks access, overloads a slab or gets it damaged before use. | • Require staging locations to be designated rather than chosen on the spot, and to consider slab loading limits. Material stacked on a young or unpropped slab is a genuine structural risk. • State maximum manual lifting weights in figures and name the handling aid to be used above them, since a general instruction to lift safely changes nothing. • Ban stacking within a set distance of open edges, openings and access routes, with the distance given as a number. • Require heights and stacking method to be specified for materials that are unstable when stacked, such as blocks, pipe and board. • Add the rule that material is not staged where it must be moved again, because double handling is the largest hidden waste in this role.
475 | Projects | Support skilled trades in the authorised activity | Unskilled Labour | Trigger: When the work crew requires authorised material or physical support. Action: The Unskilled Labour completes “Support skilled trades in the authorised activity” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safely staged material, prepared access/protection and completed support task. Control/Handoff: The Chargehand controls location and method; unsafe manual handling or unauthorised work is stopped. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the work crew requires authorised material or physical support. | The Unskilled Labour completes “Support skilled trades in the authorised activity” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safely staged material, prepared access/protection and completed support task. | The Chargehand controls location and method; unsafe manual handling or unauthorised work is stopped. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he assists the trade crew with the task he has been authorised for, and does not take on trade work himself. • Starts when: the trade crew requires support during the authorised activity. • How it runs: (1) he is told exactly what support is needed. (2) He works under the direction of the chargehand or the tradesman. (3) He stays within the support tasks he is trained for. (4) He refuses tasks that need a trade skill or a certificate. (5) He reports when he is asked to do something outside his scope. • Proof it happened: the crew allocation and the completed activity record for the shift. • Where it usually breaks: he is asked to do trade work when the crew is short handed, and does it, because refusing is difficult at his level. | • List in the SOP exactly what a helper may not do, naming the tasks, and place the responsibility for the breach on the supervisor who asked rather than on the helper who complied. That is the only way this rule holds under programme pressure. • State that no helper operates powered equipment, hot works or lifting equipment without training and authorisation, whatever the shortage of hands. • Require any task expansion to be trained and recorded before it happens, not afterwards. • Make clear who directs him at any moment, since taking instructions from several people is how a helper ends up in an unbriefed activity. • Add the rule that a helper is never left to complete a trade activity alone when the tradesman is called away.
476 | Projects | Assist with protection, barricading and access preparation | Unskilled Labour | Trigger: When the work crew requires authorised material or physical support. Action: The Unskilled Labour completes “Assist with protection, barricading and access preparation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safely staged material, prepared access/protection and completed support task. Control/Handoff: The Chargehand controls location and method; unsafe manual handling or unauthorised work is stopped. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the work crew requires authorised material or physical support. | The Unskilled Labour completes “Assist with protection, barricading and access preparation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safely staged material, prepared access/protection and completed support task. | The Chargehand controls location and method; unsafe manual handling or unauthorised work is stopped. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he helps put up barricades, signs and protection, and helps prepare safe access before work starts. • Starts when: a work front needs to be barricaded, signed or protected, or access needs preparing. • How it runs: (1) he is told what needs barricading or protecting and to what standard. (2) He installs the barricade or protection as instructed. (3) He fixes signage where it can actually be seen. (4) He checks it is stable and complete. (5) He reports damaged or missing barricades he finds elsewhere. • Proof it happened: the barricading and protection in place, recorded in the safety walk records. • Where it usually breaks: barricades are moved for access and never put back, and the open edge or hole stays exposed for days. | • Make reinstatement of a removed barricade a named step with a named responsible person, and require a check at the end of every shift. Removed and not reinstated is the single commonest fall hazard on a live site. • State the standard for hole covers, including fixing down and marking, because a loose unmarked cover is more dangerous than an open hole. • Require any barricade he cannot install properly to be reported rather than improvised, since a weak barricade gives false confidence. • Give him the duty to report damaged barricades anywhere on site, not just in his own area, and treat that as expected rather than as interference. • Require signage to be in the languages used on site and in pictogram form, or it will not be read by the people most at risk.
477 | Projects | Maintain housekeeping, waste segregation and clear access routes | Unskilled Labour | Trigger: When work or housekeeping is in progress. Action: The Unskilled Labour completes “Maintain housekeeping, waste segregation and clear access routes” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: clear access, segregated waste, protected property and compliant work-front condition. Control/Handoff: Hazards, damage or spill are reported immediately and the affected area is controlled. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When work or housekeeping is in progress. | The Unskilled Labour completes “Maintain housekeeping, waste segregation and clear access routes” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | clear access, segregated waste, protected property and compliant work-front condition. | Hazards, damage or spill are reported immediately and the affected area is controlled. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he keeps the area clean, keeps waste in the right bins and keeps access routes clear through the shift. • Starts when: continuously through the shift, with a clear up at the end. • How it runs: (1) he removes waste and offcuts as they accumulate. (2) He puts waste into the correct segregated bin. (3) He keeps walkways, stairs and exits clear. (4) He reports overflowing bins or blocked routes. (5) He does a final clear at the end of the shift. • Proof it happened: the housekeeping records and waste segregation records for the area. • Where it usually breaks: waste is piled at a convenient spot instead of a bin, which blocks a route and eventually becomes a fire risk. | • Require housekeeping through the shift rather than only at the end, with a specific trigger such as clearing at each break. An end of shift only rule leaves hazards in place all day. • Name the bin types and where they are, since segregation fails because the correct bin is too far away, not because the rule is unknown. • Give the escalation route for full bins with a response time, because a full bin turns immediately into a pile on the floor. • Make emergency routes and stairs a separate stated rule with zero tolerance, as these are the routes that must work on the worst day. • Require flammable waste to be removed the same day and kept away from hot works, which is the origin of most site fires.
478 | Projects | Use manual-handling methods and basic tools safely | Unskilled Labour | Trigger: When work or housekeeping is in progress. Action: The Unskilled Labour completes “Use manual-handling methods and basic tools safely” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: clear access, segregated waste, protected property and compliant work-front condition. Control/Handoff: Hazards, damage or spill are reported immediately and the affected area is controlled. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When work or housekeeping is in progress. | The Unskilled Labour completes “Use manual-handling methods and basic tools safely” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | clear access, segregated waste, protected property and compliant work-front condition. | Hazards, damage or spill are reported immediately and the affected area is controlled. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he lifts and carries the safe way, and uses basic tools the way he was shown. • Starts when: whenever he lifts, carries or uses a basic tool. • How it runs: (1) he assesses the load before lifting it. (2) He asks for help or a handling aid where it is too heavy or awkward. (3) He uses the correct lifting technique. (4) He uses basic tools only as shown and only for their purpose. (5) He stops and reports if he cannot do it safely. • Proof it happened: his training or induction record, and observation records from safety walks. • Where it usually breaks: he lifts alone because asking for help would slow the crew down, and the injury shows up later as a back problem nobody links to the day it happened. | • Put a stated weight limit in the SOP above which two people or an aid are mandatory, and make it the chargehand's duty to enforce it. Judgement alone always loses to programme pressure. • Provide the handling aids named in the procedure. A rule requiring an aid that is not available on site simply gets ignored. • Require refresher demonstration rather than a signed sheet, since manual handling training that is only read has almost no effect. • Ban improvised tools explicitly, with examples, because improvisation is common in this role and causes a large share of hand injuries. • Add a rule for awkward rather than heavy loads, such as long pipe, board and glass, where the shape rather than the weight causes the injury.
479 | Projects | Protect materials, completed work and company property | Unskilled Labour | Trigger: When work or housekeeping is in progress. Action: The Unskilled Labour completes “Protect materials, completed work and company property” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: clear access, segregated waste, protected property and compliant work-front condition. Control/Handoff: Hazards, damage or spill are reported immediately and the affected area is controlled. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When work or housekeeping is in progress. | The Unskilled Labour completes “Protect materials, completed work and company property” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | clear access, segregated waste, protected property and compliant work-front condition. | Hazards, damage or spill are reported immediately and the affected area is controlled. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he looks after materials, finished work and company property rather than treating them as somebody else's concern. • Starts when: continuously, while handling material or working near completed work. • How it runs: (1) he handles material so it is not damaged in transit. (2) He avoids walking on or resting loads on finished work. (3) He keeps protection in place and does not remove it for convenience. (4) He secures material against weather and theft where instructed. (5) He reports damage he sees, including damage he did not cause. • Proof it happened: the condition of materials and finished work, and reported damage entries. • Where it usually breaks: material is dragged or dropped during handling, and the damage is only discovered when the trade comes to install it. | • State how material is handled rather than only that it must be protected, naming what must not be dragged, dropped or stacked directly on the ground. • Ban walking on or loading finished floors and waterproofing, and require the protected route to be marked physically. Told not to walk there is not a control. • Require damage to be reported without blame where the report is immediate, because the alternative is damage discovered at installation with no explanation. • Include weather protection with a specific trigger, since material left out for one rainy night is a routine and avoidable loss. • Add the rule that protection is never removed for access without permission and reinstatement.
480 | Projects | Report damage, shortage, hazard or delay to the chargehand | Unskilled Labour | Trigger: When the support task or shift is completed. Action: The Unskilled Labour completes “Report damage, shortage, hazard or delay to the chargehand” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: cleaned area, returned tools and reported completion/exception status. Control/Handoff: The Chargehand checks the area before release; unresolved waste, damage or hazard remains open. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the support task or shift is completed. | The Unskilled Labour completes “Report damage, shortage, hazard or delay to the chargehand” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | cleaned area, returned tools and reported completion/exception status. | The Chargehand checks the area before release; unresolved waste, damage or hazard remains open. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: if something is damaged, short, hazardous or holding up the work, he tells the chargehand rather than waiting for someone to notice. • Starts when: as soon as he becomes aware of it. • How it runs: (1) he stops if the situation is unsafe. (2) He tells the chargehand what he has seen. (3) He says where it is and when he noticed it. (4) The chargehand records it and acts or escalates. (5) He confirms once it has been dealt with. • Proof it happened: the entry in the chargehand's log and the closure of the item. • Where it usually breaks: he assumes someone else has already reported it, so an obvious hazard goes unreported for days. | • State that a hazard is reported even if he assumes it is already known, since assuming it is reported is the commonest reason obvious hazards stay open. • Allow verbal reporting with the chargehand writing it down, because a written form excludes exactly the people who see the most hazards. • Require the report to be acknowledged, since acknowledgement is what keeps the reporting habit alive in this group. • Set a same shift rule for material shortages, so procurement and the crew learn about them before the following morning is lost. • Add the rule that reporting damage he caused himself is treated as expected behaviour, with the response focused on the cause rather than on punishment.
481 | Projects | Clear debris and clean the assigned work area | Unskilled Labour | Trigger: When the support task or shift is completed. Action: The Unskilled Labour completes “Clear debris and clean the assigned work area” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: cleaned area, returned tools and reported completion/exception status. Control/Handoff: The Chargehand checks the area before release; unresolved waste, damage or hazard remains open. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the support task or shift is completed. | The Unskilled Labour completes “Clear debris and clean the assigned work area” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | cleaned area, returned tools and reported completion/exception status. | The Chargehand checks the area before release; unresolved waste, damage or hazard remains open. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: he clears the debris out of the area he has been given and leaves it clean. • Starts when: during the shift as debris builds up, and at the end of the shift. • How it runs: (1) he collects debris from the area. (2) He separates it into the correct waste streams. (3) He moves it to the designated waste point using the right route and equipment. (4) He checks the area is clear including behind and under materials. (5) He reports if the waste point is full or the area cannot be cleared. • Proof it happened: the cleared area and the waste removal records. • Where it usually breaks: debris is swept into a corner or a void rather than removed, which hides it until it becomes a fire load or blocks a service route. | • State explicitly that debris is removed from site rather than moved out of sight, and name voids, risers, ceiling spaces and shafts as places where it must never be left. Debris in a riser is a fire path. • Require a check behind and under stacked material, since that is where debris accumulates unseen for months. • Name the disposal route and the responsible person for each waste type, including hazardous waste, which needs a separate handling rule. • Give a response time for full or unavailable waste points, because the alternative is always a pile on the floor. • Require debris to be cleared before an area is handed over, so the receiving trade does not inherit someone else's waste.
482 | Projects | Return tools and hand over shift completion status | Unskilled Labour | Trigger: When the support task or shift is completed. Action: The Unskilled Labour completes “Return tools and hand over shift completion status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: cleaned area, returned tools and reported completion/exception status. Control/Handoff: The Chargehand checks the area before release; unresolved waste, damage or hazard remains open. Continuity/Escalation: Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. Timing: To be confirmed. | When the support task or shift is completed. | The Unskilled Labour completes “Return tools and hand over shift completion status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | cleaned area, returned tools and reported completion/exception status. | The Chargehand checks the area before release; unresolved waste, damage or hazard remains open. | Another inducted worker may provide backup for the same authorised support task; hazardous or skilled work is not performed without competence and instruction. | To be confirmed. | • In plain words: at the end of the shift he returns the tools he was given and reports what he finished and what is outstanding. • Starts when: at the end of the shift or when he is released from the task. • How it runs: (1) he collects the tools issued to him. (2) He checks them and reports any damage. (3) He returns them to the store or the crew store and has the return recorded. (4) He reports what he completed and what is still outstanding. (5) He reports anything unsafe he is leaving behind. • Proof it happened: the tool return record and the shift completion entry in the chargehand's log. • Where it usually breaks: tools are left at the work front for the next day and then walk, so losses are discovered weeks later with no accountability. | • Require tools to be physically returned and the return recorded, rather than left at the work front. Left out overnight is how most small tool loss occurs, and it is discovered too late to attribute. • Include a handover of anything left unsafe or incomplete, such as an open hole or a removed barricade, since a helper leaving at shift end may be the only person who knows. • Ask for outstanding work as well as completed work, which is what makes the next shift's briefing accurate. • Require the store or the chargehand to sign the return, so the worker is discharged and the record has two parties. • Add the rule that immediate reporting of a lost tool is treated differently from a later discovery, which is what makes honest reporting worthwhile.
483 | Projects | Complete the vehicle pre-use safety and condition inspection | Driver | Trigger: When an authorised transport request is received. Action: The Driver completes “Complete the vehicle pre-use safety and condition inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a roadworthy vehicle, verified driver documents and controlled trip/load instruction. Control/Handoff: No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When an authorised transport request is received. | The Driver completes “Complete the vehicle pre-use safety and condition inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a roadworthy vehicle, verified driver documents and controlled trip/load instruction. | No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: before the driver takes the vehicle out he walks around it and checks it is fit to be driven. • Starts when: at the start of every shift, and again after any change of vehicle. • How it runs: (1) he checks tyres, lights, brakes, mirrors, wipers and horn. (2) He checks fluid levels and looks underneath for leaks. (3) He checks the first aid kit, extinguisher and warning triangle are present. (4) He records the result on the pre use check sheet. (5) He reports any defect and does not take the vehicle out if it is unsafe. • Proof it happened: the signed daily pre use inspection sheet and any defect report raised from it. • Where it usually breaks: the sheet gets filled in for the whole week on Monday, so the check exists on paper and not in reality. | • Require the check to be recorded at the actual time of the check, with a rule that a sheet completed in advance is treated as a false record. Pre filled sheets are the standard failure in this control. • List the defects that stop the vehicle from moving at all, so the driver is not left deciding what counts as unsafe under pressure to get going. • Name who provides a replacement vehicle and how quickly, because without that the driver takes the defective vehicle out anyway. • Require defects to be closed and the closure recorded, otherwise the same defect gets reported daily and eventually stops being reported. • Add a periodic verification where a supervisor spot checks a vehicle against that day's sheet, which is the only thing that keeps the check honest.
484 | Projects | Verify licence, registration, insurance and vehicle documents | Driver | Trigger: When an authorised transport request is received. Action: The Driver completes “Verify licence, registration, insurance and vehicle documents” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a roadworthy vehicle, verified driver documents and controlled trip/load instruction. Control/Handoff: No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When an authorised transport request is received. | The Driver completes “Verify licence, registration, insurance and vehicle documents” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a roadworthy vehicle, verified driver documents and controlled trip/load instruction. | No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he confirms his licence and the vehicle's registration, insurance and permits are valid and actually in the vehicle. • Starts when: at the start of the shift, and whenever a document is close to expiry. • How it runs: (1) he checks his own licence is valid for that class of vehicle. (2) He checks registration and insurance are current and present. (3) He checks any site or route permit needed. (4) He reports anything expired or missing before driving. (5) He does not drive without valid documents. • Proof it happened: the document validity register and the copies held in the vehicle. • Where it usually breaks: an expiry is noticed on the day it expires, so either the vehicle stops or it runs uninsured. | • Put expiry tracking with advance alerts on the fleet administrator rather than on the driver, and set the alert well ahead. An expiry found on the day forces a choice between stopping work and driving uninsured. • State plainly that driving with an expired licence, registration or insurance is never permitted, whatever the delivery urgency, and name who may stand the vehicle down. • Require licence class to be matched to the vehicle actually assigned, since drivers get moved between vehicle types informally. • Include driver medical and any route or hazardous goods permits in the same register, as these are the ones normally forgotten. • Require original or certified copies in the vehicle as the local authority demands, because a photograph on a phone is refused at many checkpoints.
485 | Projects | Confirm the authorised trip request, route, load and timing | Driver | Trigger: When an authorised transport request is received. Action: The Driver completes “Confirm the authorised trip request, route, load and timing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a roadworthy vehicle, verified driver documents and controlled trip/load instruction. Control/Handoff: No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When an authorised transport request is received. | The Driver completes “Confirm the authorised trip request, route, load and timing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a roadworthy vehicle, verified driver documents and controlled trip/load instruction. | No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he confirms the trip is authorised, and that he knows the route, the load and the timing before he sets off. • Starts when: a trip request is issued to him. • How it runs: (1) he receives the authorised trip request. (2) He confirms the pickup and delivery points and the timing. (3) He confirms what he is carrying and its weight. (4) He confirms the route and any access restriction. (5) He starts only against an authorised request. • Proof it happened: the authorised trip request and the trip log entry. • Where it usually breaks: someone senior asks him verbally to make an extra trip, and the vehicle disappears for two hours with no record of where it went. | • State that no trip is made without an authorised request, and name who may authorise. Verbal requests from senior staff are how vehicle use becomes untraceable. • Provide a fast route for genuine urgent trips, recorded and confirmed afterwards, so the rule is not simply bypassed when it matters. • Require the load weight to be confirmed against the vehicle rating before departure, as overload is decided at this step and not at the weighbridge. • Require access restrictions such as gate hours, permits and height limits to be checked when the trip is planned, since discovering them on arrival wastes the whole trip. • Add a rule for combining trips, so consolidation is an authorised decision rather than the driver's own arrangement.
486 | Projects | Check load security, capacity and required delivery documents | Driver | Trigger: When an authorised transport request is received. Action: The Driver completes “Check load security, capacity and required delivery documents” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a roadworthy vehicle, verified driver documents and controlled trip/load instruction. Control/Handoff: No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When an authorised transport request is received. | The Driver completes “Check load security, capacity and required delivery documents” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a roadworthy vehicle, verified driver documents and controlled trip/load instruction. | No trip begins with expired documents, unsafe condition, overload or missing authorisation; the Driver escalates to the Project Engineer. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he checks the load is secure, within the vehicle's capacity, and that he has the paperwork that goes with it. • Starts when: after loading, before the vehicle moves. • How it runs: (1) he checks the load is within the rated capacity. (2) He checks it is distributed and secured with the right straps or bindings. (3) He checks nothing overhangs unsafely or projects without marking. (4) He checks the delivery note, gate pass or material transfer documents. (5) He does not move until the load is secure and documented. • Proof it happened: the load security check record and the signed delivery documents. • Where it usually breaks: he is not the one who loaded it, so he accepts the loading crew's word that it is secure and within capacity. | • Make the driver the final authority on whether his load is secure, with the right to refuse to move, and require the loader to be recorded. Responsibility for a load nobody signed for always ends up nowhere. • Provide the correct securing equipment in the vehicle as standard, since improvised securing with rope or offcuts is what causes load loss. • State the marking requirement for projecting and overhanging loads in figures rather than by judgement. • Require paperwork to be checked before departure, because a delivery arriving without documents is usually refused and returns as a wasted trip. • Add a rule for loads that shift in transit, requiring a re check after the first part of the journey on rough or long routes.
487 | Projects | Collect and transport authorised materials, staff or equipment | Driver | Trigger: When the approved vehicle, route, load and timing are confirmed. Action: The Driver completes “Collect and transport authorised materials, staff or equipment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe transport and completed collection/delivery according to instruction. Control/Handoff: The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When the approved vehicle, route, load and timing are confirmed. | The Driver completes “Collect and transport authorised materials, staff or equipment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe transport and completed collection/delivery according to instruction. | The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he collects and transports the authorised materials, people or equipment, and only those. • Starts when: the authorised trip begins. • How it runs: (1) he collects only what is on the authorised request. (2) He checks quantity and condition at collection. (3) He carries people only in vehicles authorised to carry them. (4) He delivers to the stated point and nowhere else. (5) He reports any difference between what was requested and what was collected. • Proof it happened: the trip record, the delivery note and the receipt at the delivery point. • Where it usually breaks: an extra item gets added at the collection point without authorisation, and the paperwork no longer matches the load. | • Require any addition or deduction at the collection point to be authorised and recorded before departure, since a load that does not match its paperwork cannot be reconciled and invites both loss and dispute. • State clearly which vehicles may carry personnel and ban passengers in load areas without exception, as this is the most common serious transport risk on a construction operation. • Require a condition check at collection, so damage in transit can be separated from damage that arrived with the goods. • Require a deviation from the stated destination to be authorised, not decided en route. • Add the rule that partial collections are recorded as such, so the store does not close a request that was never fully met.
488 | Projects | Follow approved route, speed, rest and site-access controls | Driver | Trigger: When the approved vehicle, route, load and timing are confirmed. Action: The Driver completes “Follow approved route, speed, rest and site-access controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe transport and completed collection/delivery according to instruction. Control/Handoff: The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When the approved vehicle, route, load and timing are confirmed. | The Driver completes “Follow approved route, speed, rest and site-access controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe transport and completed collection/delivery according to instruction. | The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he sticks to the approved route and speed, takes his rest breaks, and follows the site access rules. • Starts when: from departure until the trip is complete. • How it runs: (1) he follows the approved route. (2) He keeps within the legal and site speed limits. (3) He takes rest breaks at the required intervals. (4) He follows site access, induction and escort rules at each site. (5) He reports any forced deviation from the route. • Proof it happened: the trip log, tracking data where fitted, and site gate records. • Where it usually breaks: a tight delivery window is met by skipping the rest break, and fatigue risk is created by the schedule rather than by the driver. | • Set maximum driving hours and mandatory rest intervals in figures, and require the scheduler to plan trips inside them. Fatigue is created by the schedule, so the control belongs with whoever plans it. • State that a delivery window is never a reason to skip a rest break or exceed a limit, and place the consequence on the person who set the window. • Require route deviations to be reported at the time rather than explained afterwards, since a diverted vehicle is untraceable in an emergency. • Set site speed limits separately from road limits and require them explicitly, because site speed is where pedestrian incidents occur. • Add mandatory site induction and escort requirements per site, so the driver knows which rules apply where before he arrives at the gate.
489 | Projects | Protect transported goods and prevent unauthorised passengers or loads | Driver | Trigger: When the approved vehicle, route, load and timing are confirmed. Action: The Driver completes “Protect transported goods and prevent unauthorised passengers or loads” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe transport and completed collection/delivery according to instruction. Control/Handoff: The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When the approved vehicle, route, load and timing are confirmed. | The Driver completes “Protect transported goods and prevent unauthorised passengers or loads” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe transport and completed collection/delivery according to instruction. | The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he keeps the goods he is carrying safe, and does not pick up unauthorised passengers or extra loads. • Starts when: from loading until the delivery is signed for. • How it runs: (1) he keeps the load covered and protected as required. (2) He does not leave the vehicle unattended and unsecured with goods on board. (3) He refuses unauthorised passengers. (4) He refuses any load not on the authorised request. (5) He reports any pressure to carry unauthorised items or people. • Proof it happened: the delivered condition of goods, the trip record and any exception report. • Where it usually breaks: a colleague asks for a lift or asks him to drop something off, and refusing feels unreasonable, so the vehicle carries unrecorded people and goods. | • Write the ban on unauthorised passengers and loads plainly, with the line that the driver is supported for refusing. Without that, social pressure decides the outcome every time. • Make it clear that the driver is not held responsible for goods he was pressured into carrying, provided he reports it, since that is what makes reporting possible at all. • State the protection requirement for weather sensitive and high value goods, and provide the covers rather than assuming improvisation. • Require the vehicle to be secured whenever the driver leaves it with goods on board, including short stops, which is when most in transit loss happens. • Add a rule for personal use of company vehicles, since that ambiguity is where most misuse begins.
490 | Projects | Coordinate loading, unloading and delivery access safely | Driver | Trigger: When the approved vehicle, route, load and timing are confirmed. Action: The Driver completes “Coordinate loading, unloading and delivery access safely” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe transport and completed collection/delivery according to instruction. Control/Handoff: The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When the approved vehicle, route, load and timing are confirmed. | The Driver completes “Coordinate loading, unloading and delivery access safely” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe transport and completed collection/delivery according to instruction. | The Driver follows traffic, load and access controls; unauthorised passenger, route or load changes are prohibited. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he makes sure loading, unloading and getting into the delivery point happen safely, with the right people helping. • Starts when: on arrival at the loading or delivery point. • How it runs: (1) he positions the vehicle safely with the handbrake and wheels secured. (2) He confirms who is directing the loading or unloading. (3) He stays clear of the load path and out of the swing zone. (4) He uses a banksman where reversing or space is restricted. (5) He stops the operation if it becomes unsafe. • Proof it happened: the delivery record and any incident or near miss reports from the operation. • Where it usually breaks: reversing in a congested yard with no banksman, which is the classic way a pedestrian gets struck. | • Make a banksman mandatory for reversing in congested or pedestrian areas, and name who provides one. Reversing without a banksman is the most frequent cause of vehicle pedestrian incidents on site. • Require the vehicle to be immobilised before loading or unloading begins, with a stated method, since vehicle movement during unloading is a routine cause of serious injury. • State that the driver stays out of the load path and the crane swing zone, and give him authority to stop the operation. • Require the delivery point to confirm readiness before the vehicle is despatched, which prevents vehicles queueing in live traffic. • Add lighting and visibility requirements for night deliveries, when most yard incidents occur.
491 | Projects | Obtain delivery, transfer or passenger-completion evidence | Driver | Trigger: When a trip, delivery or refuelling event occurs. Action: The Driver completes “Obtain delivery, transfer or passenger-completion evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: delivery evidence and complete trip, fuel, mileage and exception records. Control/Handoff: Records reconcile to authorised trips; unusual fuel, mileage, loss or delay is reported for review. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When a trip, delivery or refuelling event occurs. | The Driver completes “Obtain delivery, transfer or passenger-completion evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | delivery evidence and complete trip, fuel, mileage and exception records. | Records reconcile to authorised trips; unusual fuel, mileage, loss or delay is reported for review. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he gets signed proof that the delivery, transfer or passenger trip was actually completed. • Starts when: on completion of the delivery or the trip. • How it runs: (1) he presents the delivery or transfer document at the receiving point. (2) He gets it signed by the person receiving. (3) He records the received quantity and any shortage or damage noted. (4) He keeps the signed copy. (5) He submits it with the shift records. • Proof it happened: the signed delivery note, transfer note or trip completion record. • Where it usually breaks: nobody is available to sign, so the delivery is left and the company has no proof it was ever received. | • Set the rule for what happens when there is nobody to sign, requiring authorisation before goods are left plus photographic evidence. An unsigned delivery is an undeliverable claim later. • Require the receiver's name to be legible alongside the signature, since an illegible signature identifies nobody. • Require any shortage or damage to be noted on the document at the point of receipt, because a note added later has no standing. • Set a same day submission rule for signed documents, as delays here hold up supplier payment and stock reconciliation. • Allow photographic proof of delivery as a supporting record, which resolves most disputes at almost no cost.
492 | Projects | Maintain trip, fuel, mileage, toll and vehicle-use records | Driver | Trigger: When a trip, delivery or refuelling event occurs. Action: The Driver completes “Maintain trip, fuel, mileage, toll and vehicle-use records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: delivery evidence and complete trip, fuel, mileage and exception records. Control/Handoff: Records reconcile to authorised trips; unusual fuel, mileage, loss or delay is reported for review. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When a trip, delivery or refuelling event occurs. | The Driver completes “Maintain trip, fuel, mileage, toll and vehicle-use records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | delivery evidence and complete trip, fuel, mileage and exception records. | Records reconcile to authorised trips; unusual fuel, mileage, loss or delay is reported for review. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: he keeps the records for each trip, including fuel, mileage, tolls and how the vehicle was used. • Starts when: continuously during the shift, completed at the end. • How it runs: (1) he records start and end mileage for each trip. (2) He records fuel taken with the receipt attached. (3) He records tolls, parking and other trip costs. (4) He records waiting and idle time. (5) He submits the log with the receipts at the end of the shift. • Proof it happened: the completed trip log with attached fuel and toll receipts. • Where it usually breaks: mileage is written from memory at the end of the week, so fuel consumption cannot be checked against distance and fuel loss is invisible. | • Require mileage to be recorded at the time of each trip and reconciled against fuel monthly. Fuel theft and misuse are only ever detectable through consumption against distance, so the record has to be contemporaneous. • Require receipts for all fuel and expenses, and state what happens when one is missing, rather than leaving it to habit. • Include waiting and idle time with the reason, because that is the data that shows whether the fleet is too small or simply badly scheduled. • Set a threshold for consumption variance that triggers an investigation, so the record is actually used rather than merely filed. • Require the log to be checked and signed by a supervisor, since an unchecked log is not a control.
493 | Projects | Report delay, traffic, route or delivery exception promptly | Driver | Trigger: When a trip, delivery or refuelling event occurs. Action: The Driver completes “Report delay, traffic, route or delivery exception promptly” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: delivery evidence and complete trip, fuel, mileage and exception records. Control/Handoff: Records reconcile to authorised trips; unusual fuel, mileage, loss or delay is reported for review. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When a trip, delivery or refuelling event occurs. | The Driver completes “Report delay, traffic, route or delivery exception promptly” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | delivery evidence and complete trip, fuel, mileage and exception records. | Records reconcile to authorised trips; unusual fuel, mileage, loss or delay is reported for review. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: if he is delayed, blocked or cannot complete the delivery, he tells the office at the time and not afterwards. • Starts when: the moment the delay or the exception occurs. • How it runs: (1) he identifies the delay or the problem. (2) He informs the transport coordinator immediately. (3) He states the cause and the expected effect on timing. (4) He follows the instruction he is given. (5) He records the exception in the trip log. • Proof it happened: the exception entry in the trip log and the communication record. • Where it usually breaks: he only reports on return, by which time the receiving site has already lost a crew waiting for material. | • Require immediate notification with a stated time limit rather than reporting on return. The value of this report is entirely in letting the receiving site redeploy its crew. • Name who the driver calls and give an alternative when that person is unavailable, since one unanswered call otherwise ends the attempt. • Require the receiving site to be informed as well as the transport coordinator, or the information stops at the office. • Require the cause to be recorded in categories, so recurring route or supplier problems become visible instead of being treated as one off. • Provide a means of communication and cover its cost, because a rule that depends on the driver's personal phone credit will fail.
494 | Projects | Report accident, breakdown, damage or vehicle defect immediately | Driver | Trigger: When a breakdown, accident, delay, defect or shift close occurs. Action: The Driver completes “Report accident, breakdown, damage or vehicle defect immediately” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: secured vehicle, notified incident, authorised recovery/maintenance and closed shift record. Control/Handoff: Accident and unsafe defect are reported immediately; the vehicle remains out of use until authorised release. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When a breakdown, accident, delay, defect or shift close occurs. | The Driver completes “Report accident, breakdown, damage or vehicle defect immediately” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | secured vehicle, notified incident, authorised recovery/maintenance and closed shift record. | Accident and unsafe defect are reported immediately; the vehicle remains out of use until authorised release. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: any accident, breakdown, damage or fault is reported straight away, not at the end of the day. • Starts when: at the moment of the accident, breakdown or discovery of damage. • How it runs: (1) he makes the scene safe and attends to any injury first. (2) He reports immediately to the transport coordinator and, where required, to the authorities. (3) He does not move the vehicle where an accident report requires it to stay. (4) He records the details, the location and photographs. (5) He submits the incident report and cooperates with the investigation. • Proof it happened: the incident report, the police or insurer notification and the photographs. • Where it usually breaks: minor damage goes unreported and accumulates, so nobody can attribute it and the insurance position is weakened. | • Set a strict immediate reporting rule for any accident regardless of severity, and explain that late notification can void insurance cover. This is the single most expensive consequence in the whole transport process. • Give the driver a short scene action list covering injuries, scene safety, whether to move the vehicle, and who to call, since nobody thinks clearly at that moment. • Treat honest immediate reporting of minor damage differently from concealment, otherwise minor damage is never reported and the fleet degrades invisibly. • Require photographs and third party details at the scene, because these cannot be recovered afterwards. • Name who notifies the insurer and within what period, so that duty does not sit with the driver by default.
495 | Projects | Coordinate authorised recovery, maintenance and replacement transport | Driver | Trigger: When a breakdown, accident, delay, defect or shift close occurs. Action: The Driver completes “Coordinate authorised recovery, maintenance and replacement transport” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: secured vehicle, notified incident, authorised recovery/maintenance and closed shift record. Control/Handoff: Accident and unsafe defect are reported immediately; the vehicle remains out of use until authorised release. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When a breakdown, accident, delay, defect or shift close occurs. | The Driver completes “Coordinate authorised recovery, maintenance and replacement transport” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | secured vehicle, notified incident, authorised recovery/maintenance and closed shift record. | Accident and unsafe defect are reported immediately; the vehicle remains out of use until authorised release. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: when a vehicle is off the road he arranges the approved recovery or repair and gets replacement transport organised. • Starts when: a breakdown, accident or defect takes the vehicle out of service. • How it runs: (1) he reports the vehicle as out of service. (2) He arranges recovery through the approved provider only. (3) He arranges the repair through the approved workshop. (4) He arranges replacement transport for the affected trips. (5) He records the downtime, the cost and the return to service. • Proof it happened: the recovery and repair records, and the replacement transport arrangement. • Where it usually breaks: a roadside repair is arranged locally to save time, and the vehicle returns with unapproved parts and no repair record. | • Require recovery and repair through approved providers only, and name the approval route for a genuine roadside emergency. Unapproved repairs leave no record and often void warranty. • State a value threshold above which repair requires authorisation before the work starts, since retrospective approval leaves the company with no choice. • Require replacement transport to be arranged for affected trips, and name who decides priority when there are more trips than vehicles. • Require downtime and cost to be recorded per vehicle, because replacement decisions cannot be made without a repair history. • Add a return to service check confirming the defect is actually cleared, rather than assuming a returned vehicle is a repaired vehicle.
496 | Projects | Secure the vehicle and submit end-of-shift records and keys | Driver | Trigger: When a breakdown, accident, delay, defect or shift close occurs. Action: The Driver completes “Secure the vehicle and submit end-of-shift records and keys” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: secured vehicle, notified incident, authorised recovery/maintenance and closed shift record. Control/Handoff: Accident and unsafe defect are reported immediately; the vehicle remains out of use until authorised release. Continuity/Escalation: Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. Timing: To be confirmed. | When a breakdown, accident, delay, defect or shift close occurs. | The Driver completes “Secure the vehicle and submit end-of-shift records and keys” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | secured vehicle, notified incident, authorised recovery/maintenance and closed shift record. | Accident and unsafe defect are reported immediately; the vehicle remains out of use until authorised release. | Only a licensed and authorised Driver may provide backup; accident, unsafe vehicle, expired document or material transport delay escalates immediately to the Project Engineer. | To be confirmed. | • In plain words: at the end of the shift he parks and secures the vehicle, hands in the keys and submits his records. • Starts when: at the end of the shift. • How it runs: (1) he parks in the designated area. (2) He checks the vehicle over and notes any new defect. (3) He removes valuables, secures the vehicle and locks it. (4) He hands the keys to the authorised holder. (5) He submits the trip log, receipts and delivery documents. • Proof it happened: the key handover record and the submitted shift records. • Where it usually breaks: keys are kept overnight for an early start, so the vehicle is used out of hours with nothing recorded. | • Require keys to be handed back to a named holder rather than retained overnight, and name the authorisation route for a genuine early start. Retained keys are how out of hours use becomes untraceable. • Require an end of shift condition note as well as a pre use check, since that pairing is the only way damage can be placed within a shift. • Require records to be submitted the same shift, because a log completed from memory days later cannot be reconciled to anything. • Designate the parking area and state the security requirements, including whether the vehicle may be taken home. • Add a weekly reconciliation of key returns against vehicles on site, which surfaces informal use quickly.
497 | Projects | Complete plant and equipment pre-start inspection | Plant & Equipment Operator | Trigger: When an authorised equipment task is scheduled. Action: The Plant & Equipment Operator completes “Complete plant and equipment pre-start inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified operator, certified equipment and completed pre-start record. Control/Handoff: Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When an authorised equipment task is scheduled. | The Plant & Equipment Operator completes “Complete plant and equipment pre-start inspection” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified operator, certified equipment and completed pre-start record. | Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: before starting the machine the operator inspects it and confirms it is fit to work. • Starts when: at the start of every shift, and after any change of machine. • How it runs: (1) he walks around the machine and checks for damage and leaks. (2) He checks fluid levels, tyres or tracks and attachments. (3) He tests brakes, steering, alarms and lights. (4) He records the result on the pre start check sheet. (5) He reports defects and does not start work if the machine is unsafe. • Proof it happened: the signed pre start inspection sheet and any defect report raised. • Where it usually breaks: the check is signed without being done, because the machine worked yesterday and is needed now. | • Require the check to be recorded at the time it is done and treat a pre filled sheet as a false record. Plant pre start checks are among the most routinely falsified records on any site. • List the defects that stop the machine from operating at all, so the operator is not deciding what unsafe means while the crew waits. • Name who authorises a machine to be taken out of service and who arranges the replacement, otherwise the defective machine keeps working. • Require defect closure to be recorded, since the same repeated defect eventually stops being reported. • Add supervisor spot checks against that day's sheet, which is the only thing that keeps the check real.
498 | Projects | Verify operator competency, certification and equipment documents | Plant & Equipment Operator | Trigger: When an authorised equipment task is scheduled. Action: The Plant & Equipment Operator completes “Verify operator competency, certification and equipment documents” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified operator, certified equipment and completed pre-start record. Control/Handoff: Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When an authorised equipment task is scheduled. | The Plant & Equipment Operator completes “Verify operator competency, certification and equipment documents” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified operator, certified equipment and completed pre-start record. | Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: the operator's certificate is valid for that machine, and the machine's own certificates are current. • Starts when: before he operates a machine, and whenever a certificate nears expiry. • How it runs: (1) he confirms his certification covers that specific type of machine. (2) He confirms the third party inspection certificate for the machine is valid. (3) He confirms attachment and lifting gear certificates where applicable. (4) He reports anything expired before operating. (5) He does not operate uncertified plant. • Proof it happened: the operator certification register and the valid machine inspection certificates. • Where it usually breaks: an operator certified for one machine type is put on a similar looking machine, which is not certification at all. | • State that certification is machine type specific and that similar is not equivalent. Putting a certified operator on the wrong machine type is a common and serious substitution. • Put expiry tracking with advance alerts on the plant administrator rather than the operator, covering both operator and machine certificates. • State that uncertified plant does not operate whatever the programme pressure, and name who may stand a machine down. • Include lifting gear, slings and attachments in the register, since these expire independently of the machine and are the ones usually missed. • Require certificates to be available on site rather than in head office, because an inspector at the gate will not wait.
499 | Projects | Confirm authorised activity, location, lift or operating plan | Plant & Equipment Operator | Trigger: When an authorised equipment task is scheduled. Action: The Plant & Equipment Operator completes “Confirm authorised activity, location, lift or operating plan” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified operator, certified equipment and completed pre-start record. Control/Handoff: Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When an authorised equipment task is scheduled. | The Plant & Equipment Operator completes “Confirm authorised activity, location, lift or operating plan” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified operator, certified equipment and completed pre-start record. | Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he confirms what he is doing, where, and against which approved lift or operating plan before he starts. • Starts when: at the start of the activity, and again when the task or location changes. • How it runs: (1) he receives the authorised task and location. (2) He reviews the lift plan or the operating method that applies. (3) He confirms ground conditions and overhead clearances. (4) He confirms the banksman and the exclusion zone arrangement. (5) He starts only once these are confirmed. • Proof it happened: the authorised task record and the signed lift or operating plan. • Where it usually breaks: the machine is moved to a new location without a fresh check, and the ground or the overhead clearance there is completely different. | • Require a fresh location check at every setup rather than once per shift, covering ground bearing, edges, excavations, buried services and overhead lines. Plant overturns and contacts are location specific. • State when a written lift plan is mandatory, with a clear threshold, rather than leaving it to judgement. • Require ground conditions to be confirmed by the engineer for heavy plant and outrigger loads, since the operator cannot assess bearing capacity. • Require overhead line clearances in figures with the required exclusion distance, as this is the standard fatal risk with mobile plant. • Add the rule that a change of task means a new authorisation, so machines are not redirected verbally.
500 | Projects | Check guards, alarms, attachments, fuel and safety devices | Plant & Equipment Operator | Trigger: When an authorised equipment task is scheduled. Action: The Plant & Equipment Operator completes “Check guards, alarms, attachments, fuel and safety devices” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified operator, certified equipment and completed pre-start record. Control/Handoff: Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When an authorised equipment task is scheduled. | The Plant & Equipment Operator completes “Check guards, alarms, attachments, fuel and safety devices” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified operator, certified equipment and completed pre-start record. | Plant is not operated with expired certification, failed safety device, unsuitable attachment or unclear operating plan. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he checks the guards, alarms, attachments, fuel and safety devices are all present and working. • Starts when: at pre start, and again after any attachment change. • How it runs: (1) he checks guards are fitted and secure. (2) He tests reversing alarms, beacons and horns. (3) He checks the attachment is correctly fitted, pinned and secured. (4) He checks fuel and fluid levels for the shift. (5) He reports and does not operate with a defeated safety device. • Proof it happened: the pre start record and the attachment fitting check. • Where it usually breaks: an alarm that annoys people is disconnected, and nobody records that it was ever working. | • State that defeating or disconnecting any safety device is a serious breach, name who could authorise a temporary measure, and require it to be recorded. Disconnected alarms are common and are usually done for convenience. • Require attachment changes to be checked and recorded by a competent person, since incorrectly pinned attachments detach and kill. • Require alarms and beacons to be function tested rather than visually checked, because a fitted alarm is not a working alarm. • Include quick hitch checks explicitly for excavators, a well known and frequently fatal failure point. • Add the rule that fuel is checked for the planned duration, since running out mid lift or mid excavation creates its own hazard.
501 | Projects | Operate plant only within rated capacity and authorised task | Plant & Equipment Operator | Trigger: When the equipment and work zone are formally released. Action: The Plant & Equipment Operator completes “Operate plant only within rated capacity and authorised task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe plant output within approved capacity, method and exclusion-zone controls. Control/Handoff: Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When the equipment and work zone are formally released. | The Plant & Equipment Operator completes “Operate plant only within rated capacity and authorised task” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe plant output within approved capacity, method and exclusion-zone controls. | Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he works the machine only within its rated capacity and only on the task he was authorised for. • Starts when: from the start of operation until the machine is shut down. • How it runs: (1) he confirms the rated capacity for the configuration and radius he is working at. (2) He keeps loads within that rating. (3) He uses the machine only for the authorised task. (4) He refuses instructions to exceed the rating. (5) He reports any pressure to work outside the rating or the task. • Proof it happened: the operating record and the load chart used for the configuration. • Where it usually breaks: capacity is judged by feel rather than read off the load chart at the actual radius, which is where crane and excavator overturns come from. | • Require the load chart to be read at the actual radius and configuration rather than assumed, and require it to be physically available in the cab. Capacity judged by feel is the direct cause of most overturns. • Give the operator absolute authority to refuse an overload, with the line that he is supported for refusing, and place the breach on whoever instructed it. • State the machine specific prohibitions plainly, such as lifting personnel in a bucket or using an excavator as a crane without the right rating and gear. • Require load weights to be provided to the operator rather than estimated by him, since he has no way to know them. • Add the rule that a task change requires reauthorisation, because plant is routinely borrowed for unauthorised tasks.
502 | Projects | Maintain the exclusion zone, banksman communication and safe movement | Plant & Equipment Operator | Trigger: When the equipment and work zone are formally released. Action: The Plant & Equipment Operator completes “Maintain the exclusion zone, banksman communication and safe movement” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe plant output within approved capacity, method and exclusion-zone controls. Control/Handoff: Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When the equipment and work zone are formally released. | The Plant & Equipment Operator completes “Maintain the exclusion zone, banksman communication and safe movement” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe plant output within approved capacity, method and exclusion-zone controls. | Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he keeps people out of the machine's working area, stays in contact with the banksman and moves the machine safely. • Starts when: continuously while the machine is operating or moving. • How it runs: (1) he confirms the exclusion zone is set up and respected. (2) He agrees signals with the banksman before starting. (3) He stops the moment he loses sight or contact with the banksman. (4) He does not move or slew if anyone is inside the zone. (5) He reports repeated incursions into the zone. • Proof it happened: the exclusion zone arrangement and the banksman allocation, plus near miss records. • Where it usually breaks: people walk through the zone routinely, the operator gets used to it, and eventually he slews with someone behind him. | • Require the machine to stop on any incursion into the exclusion zone, and require repeated incursions to be escalated rather than tolerated. Habituation is what turns a near miss into a fatality here. • Name who provides and dedicates the banksman, and state that he has no other duties while the machine is working. A part time banksman is not a banksman. • Require signals to be agreed before the operation and require the machine to stop on lost contact, with no assumption permitted. • Require zones to be physically barricaded rather than marked verbally, since a spoken zone does not exist to anyone who was not there. • Add specific rules for working near live traffic, pedestrian routes and other machines, which is where incursions come from.
503 | Projects | Follow approved lifting, excavation or equipment operating method | Plant & Equipment Operator | Trigger: When the equipment and work zone are formally released. Action: The Plant & Equipment Operator completes “Follow approved lifting, excavation or equipment operating method” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe plant output within approved capacity, method and exclusion-zone controls. Control/Handoff: Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When the equipment and work zone are formally released. | The Plant & Equipment Operator completes “Follow approved lifting, excavation or equipment operating method” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe plant output within approved capacity, method and exclusion-zone controls. | Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he follows the approved method for the lift, the excavation or the operation rather than his own preferred way. • Starts when: the activity begins under an approved method or lift plan. • How it runs: (1) he works to the approved lift plan or excavation method. (2) He follows the stated sequence and limits, such as depth, slope and reach. (3) He keeps within the stated support and battering requirements. (4) He stops and reports where the method cannot be followed. (5) He resumes only on a revised approved method. • Proof it happened: the signed method statement or lift plan and the operating record against it. • Where it usually breaks: the method is changed on the spot to save time, and the change is never assessed by anyone competent. | • State that no on the spot change to an approved lift or excavation method is permitted, and name who may revise it. This is the point at which excavation collapses and lift failures are actually caused. • Require excavation depth, slope and support limits to be stated in figures and displayed, not left in a document in the office. • Require a stop and report when the ground or the conditions differ from the assumption, since the operator often sees the change first. • Require the revised method to be briefed before work resumes rather than issued afterwards. • Add the rule that no person enters an unsupported excavation, which is the failure that kills most often in this activity.
504 | Projects | Prevent damage to utilities, structures, materials and completed work | Plant & Equipment Operator | Trigger: When the equipment and work zone are formally released. Action: The Plant & Equipment Operator completes “Prevent damage to utilities, structures, materials and completed work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: safe plant output within approved capacity, method and exclusion-zone controls. Control/Handoff: Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When the equipment and work zone are formally released. | The Plant & Equipment Operator completes “Prevent damage to utilities, structures, materials and completed work” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | safe plant output within approved capacity, method and exclusion-zone controls. | Banksman and QHSE controls apply; unauthorised overload, route or task change is prohibited. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he avoids damaging buried services, structures, stored material and work that is already finished. • Starts when: continuously while operating, especially when excavating or slewing. • How it runs: (1) he confirms buried services have been located and marked before excavating. (2) He hand digs or uses safe methods near marked services. (3) He keeps clear of structures, edges and completed work when slewing or tracking. (4) He stops immediately on contact or suspected contact. (5) He reports any damage at once. • Proof it happened: the service clearance permit, the marked drawings and any damage reports. • Where it usually breaks: the machine excavates in an area where the service search was never actually confirmed, which is how live cables and mains get struck. | • Require a written service clearance permit before any ground breaking, and state that verbal clearance is not accepted. Striking a live service is the highest consequence risk in this whole role. • Require hand digging within a stated distance of any marked service, given as a figure rather than as caution. • Require an immediate stop and evacuation procedure for a suspected strike, including gas and electricity, since the first minute decides the outcome. • Require damage to structures and completed work to be reported at once, because concealed impact damage is far more expensive than the repair. • Add clearance rules for slewing and tracking near scaffolds, edges and finished work, which is where the routine damage occurs.
505 | Projects | Record operating hours, output, idle time, fuel and utilisation | Plant & Equipment Operator | Trigger: When equipment is operating or a performance concern appears. Action: The Plant & Equipment Operator completes “Record operating hours, output, idle time, fuel and utilisation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: utilisation record, monitored condition and reported safety/productivity exception. Control/Handoff: The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When equipment is operating or a performance concern appears. | The Plant & Equipment Operator completes “Record operating hours, output, idle time, fuel and utilisation” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | utilisation record, monitored condition and reported safety/productivity exception. | The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he records how long the machine ran, what it produced, how long it stood idle and how much fuel it used. • Starts when: continuously during the shift, submitted at the end. • How it runs: (1) he records the hour meter reading at start and end. (2) He records the output achieved, such as loads moved or lifts completed. (3) He records idle and standing time with the reason. (4) He records fuel taken. (5) He submits the utilisation record at the end of the shift. • Proof it happened: the plant utilisation record with hour meter readings and fuel entries. • Where it usually breaks: idle time is not recorded, so a machine standing half the shift looks fully utilised and the fleet keeps growing. | • Require idle and standing time with the reason, because this is the only data that shows whether the fleet is too large or simply poorly deployed. Without it, hire decisions are guesswork. • Require hour meter readings rather than estimated hours, and reconcile fuel to hours periodically to detect loss. • Require output in real units so productivity per machine hour can be compared against the estimate. • Set a utilisation threshold that triggers a release or redeployment review, so the record leads to a decision. • Require supervisor verification of the record, since an unverified utilisation sheet tends to be optimistic.
506 | Projects | Monitor abnormal sound, temperature, leakage and performance | Plant & Equipment Operator | Trigger: When equipment is operating or a performance concern appears. Action: The Plant & Equipment Operator completes “Monitor abnormal sound, temperature, leakage and performance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: utilisation record, monitored condition and reported safety/productivity exception. Control/Handoff: The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When equipment is operating or a performance concern appears. | The Plant & Equipment Operator completes “Monitor abnormal sound, temperature, leakage and performance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | utilisation record, monitored condition and reported safety/productivity exception. | The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: while operating he listens and watches for anything abnormal, such as unusual noise, heat, leaks or loss of performance. • Starts when: continuously while the machine is operating. • How it runs: (1) he watches the gauges and warning lights. (2) He listens for unusual noise or vibration. (3) He watches for leaks, smoke or overheating. (4) He notes any loss of power or slow response. (5) He stops and reports rather than continuing to see if it worsens. • Proof it happened: the defect or observation report and the maintenance record that follows it. • Where it usually breaks: a small symptom is worked through to finish the task, and a cheap repair becomes a major failure. | • List the symptoms that require an immediate stop rather than a report at the end of the shift, since the difference between the two is usually the difference between a seal and an engine. • State that stopping on a symptom is supported even if no fault is found, otherwise the operator carries the blame for lost production and stops reporting. • Require symptoms to be recorded even when the machine keeps working, because that history is what predicts the failure. • Require the maintenance response to be recorded against the report, so operators see that reporting produces action. • Add the rule that warning lights are never overridden or ignored to complete a task.
507 | Projects | Stop equipment on unsafe condition or unauthorised instruction | Plant & Equipment Operator | Trigger: When equipment is operating or a performance concern appears. Action: The Plant & Equipment Operator completes “Stop equipment on unsafe condition or unauthorised instruction” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: utilisation record, monitored condition and reported safety/productivity exception. Control/Handoff: The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When equipment is operating or a performance concern appears. | The Plant & Equipment Operator completes “Stop equipment on unsafe condition or unauthorised instruction” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | utilisation record, monitored condition and reported safety/productivity exception. | The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: if the machine or the situation becomes unsafe, or he is told to do something he is not authorised to do, he stops. • Starts when: the moment the unsafe condition or the unauthorised instruction arises. • How it runs: (1) he stops the machine and makes it safe. (2) He explains why he has stopped. (3) He reports the unsafe condition or the unauthorised instruction. (4) He waits for a competent decision. (5) He resumes only when the condition is corrected or proper authorisation is given. • Proof it happened: the stop work record and the resolution of the reported condition. • Where it usually breaks: he is overruled by someone more senior and carries on, which is exactly the sequence behind most serious plant incidents. | • State that no manager may overrule an operator's stop decision, and name who may authorise a restart. Overruling the operator is the recurring pattern in serious plant incidents, so the SOP must close it explicitly. • Require every stop to be recorded even where work resumes quickly, so the pattern of unsafe conditions becomes visible. • Confirm in writing that the operator is protected for stopping, including where no fault is later found. • List the unauthorised instructions he must refuse, such as exceeding rated capacity, lifting people or removing safety devices. • Add an escalation route he can use when the pressure comes from his own supervisor.
508 | Projects | Report downtime, damage, near miss and productivity constraint | Plant & Equipment Operator | Trigger: When equipment is operating or a performance concern appears. Action: The Plant & Equipment Operator completes “Report downtime, damage, near miss and productivity constraint” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: utilisation record, monitored condition and reported safety/productivity exception. Control/Handoff: The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When equipment is operating or a performance concern appears. | The Plant & Equipment Operator completes “Report downtime, damage, near miss and productivity constraint” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | utilisation record, monitored condition and reported safety/productivity exception. | The Operator stops for unsafe condition, abnormal performance or loss of control and notifies the supervisor. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he reports downtime, damage, near misses and anything holding back his productivity. • Starts when: at the end of the shift, and immediately for damage or a near miss. • How it runs: (1) he reports downtime with the cause and duration. (2) He reports damage to the machine or to other property immediately. (3) He reports near misses even where nothing was damaged. (4) He reports what is limiting his output, such as access, waiting or coordination. (5) The reports are logged and passed on. • Proof it happened: the downtime record, the damage report and the near miss entry. • Where it usually breaks: near misses are never reported because nothing happened, so the warning is lost and the same situation recurs until it does. | • Require near miss reporting with an explicit no blame statement, since near misses are free warnings and they stop the moment reporting carries a cost. • Require downtime to be recorded with a cause category rather than as a total, so recurring causes such as access, fuel or coordination can be addressed. • Require productivity constraints to be reported, because the operator sees the real cause of low output long before the planner does. • Set immediate reporting for damage and same shift reporting for downtime, and say why the two differ. • Require feedback on what was done with the reports, which is what keeps the reporting alive.
509 | Projects | Coordinate preventive maintenance and statutory inspection due dates | Plant & Equipment Operator | Trigger: When maintenance becomes due, a defect is found or the shift ends. Action: The Plant & Equipment Operator completes “Coordinate preventive maintenance and statutory inspection due dates” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: maintained or isolated equipment and completed fuel, care, utilisation and defect records. Control/Handoff: Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When maintenance becomes due, a defect is found or the shift ends. | The Plant & Equipment Operator completes “Coordinate preventive maintenance and statutory inspection due dates” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | maintained or isolated equipment and completed fuel, care, utilisation and defect records. | Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he keeps track of when servicing and statutory inspections are due and makes sure they happen on time. • Starts when: as service or inspection due dates approach. • How it runs: (1) he monitors hours run against the service interval. (2) He notifies the plant coordinator ahead of the due date. (3) The service or inspection is scheduled with the least disruption. (4) The machine is released for it and the record updated. (5) He confirms the machine is not used past a statutory expiry. • Proof it happened: the maintenance schedule, the service records and the valid statutory certificates. • Where it usually breaks: the service is deferred because the machine is needed, until deferral becomes normal and the machine fails at the worst moment. | • Split the rule in two: preventive servicing may be deferred only with recorded authorisation, and statutory inspection may never be exceeded. Treating both as flexible is how uninspected plant ends up working. • Put the monitoring on the plant coordinator with the operator supplying hours, rather than relying on the operator to track dates. • Require an automatic lockout when a statutory certificate expires, so the machine cannot simply keep working. • Require deferrals to be recorded with a reason and a revised date, so the pattern is visible. • Require servicing to be planned around production rather than left until it forces a breakdown.
510 | Projects | Report defects and isolate unsafe equipment from use | Plant & Equipment Operator | Trigger: When maintenance becomes due, a defect is found or the shift ends. Action: The Plant & Equipment Operator completes “Report defects and isolate unsafe equipment from use” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: maintained or isolated equipment and completed fuel, care, utilisation and defect records. Control/Handoff: Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When maintenance becomes due, a defect is found or the shift ends. | The Plant & Equipment Operator completes “Report defects and isolate unsafe equipment from use” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | maintained or isolated equipment and completed fuel, care, utilisation and defect records. | Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he reports defects and physically takes an unsafe machine out of use so nobody else starts it. • Starts when: a defect is found that makes the machine unsafe. • How it runs: (1) he stops and shuts the machine down. (2) He reports the defect to the plant coordinator. (3) He tags the machine as out of service and removes the key or isolates it. (4) He confirms the machine cannot be started by anyone else. (5) It is returned to service only after repair and a recorded check. • Proof it happened: the defect report, the out of service tag and the return to service record. • Where it usually breaks: the machine is only reported and not physically isolated, so the next shift starts it not knowing it is defective. | • Require physical isolation and tagging rather than reporting alone, and require the key to be removed and held by a named person. A defective machine that can still be started will be started. • Name who may remove the tag and return the machine to service, and require a recorded check before it goes back. • Require the out of service status to be visible to all shifts, since night shift is where an untagged defective machine gets used. • Provide a defect list of conditions that require immediate isolation, so the decision is not left to the individual. • Add a check that isolated plant is not cannibalised for parts, which quietly creates a second defective machine.
511 | Projects | Complete authorised refuelling, cleaning and minor daily care | Plant & Equipment Operator | Trigger: When maintenance becomes due, a defect is found or the shift ends. Action: The Plant & Equipment Operator completes “Complete authorised refuelling, cleaning and minor daily care” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: maintained or isolated equipment and completed fuel, care, utilisation and defect records. Control/Handoff: Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When maintenance becomes due, a defect is found or the shift ends. | The Plant & Equipment Operator completes “Complete authorised refuelling, cleaning and minor daily care” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | maintained or isolated equipment and completed fuel, care, utilisation and defect records. | Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: he refuels, cleans and does the small daily care the machine needs, the approved way. • Starts when: daily, and whenever fuel or fluids are needed. • How it runs: (1) he refuels at the designated point with the engine off and no ignition sources. (2) He records the fuel taken. (3) He checks and tops up fluids as permitted. (4) He greases and cleans as per the daily care schedule. (5) He reports anything beyond his authorised daily care. • Proof it happened: the fuel record and the daily care entries in the machine log. • Where it usually breaks: refuelling happens wherever the machine stands, with spillage onto the ground and no record of the quantity. | • Require refuelling at a designated point with spill containment, engine off and no ignition sources. Mobile refuelling causes both fire risk and unrecorded ground contamination. • Require the fuel quantity to be recorded per machine, since fuel that is not recorded per machine cannot be reconciled and is where loss hides. • State clearly what daily care the operator may do and what only a technician may do, so well meant maintenance does not cause damage. • Require the correct fluid specification to be stated, because topping up with the wrong grade is a common and expensive error. • Add a spill response instruction with the kit available at the refuelling point, not in a store.
512 | Projects | Park, secure and submit shift utilisation and defect records | Plant & Equipment Operator | Trigger: When maintenance becomes due, a defect is found or the shift ends. Action: The Plant & Equipment Operator completes “Park, secure and submit shift utilisation and defect records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: maintained or isolated equipment and completed fuel, care, utilisation and defect records. Control/Handoff: Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. Continuity/Escalation: Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. Timing: To be confirmed. | When maintenance becomes due, a defect is found or the shift ends. | The Plant & Equipment Operator completes “Park, secure and submit shift utilisation and defect records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | maintained or isolated equipment and completed fuel, care, utilisation and defect records. | Unsafe equipment is tagged out; only authorised maintenance and release may return it to service. | Only a certified and authorised Operator may provide backup; unsafe equipment or operation remains isolated and escalates to the Supervisor, QHSE and Project Engineer. | To be confirmed. | • In plain words: at the end of the shift he parks the machine safely, secures it and submits his utilisation and defect records. • Starts when: at the end of the shift. • How it runs: (1) he parks in the designated area on firm level ground. (2) He lowers attachments, applies brakes and chocks where needed. (3) He shuts down, isolates and removes the key. (4) He notes any new defect from the shift. (5) He submits the utilisation record and hands the key to the authorised holder. • Proof it happened: the shift utilisation record, the defect notes and the key handover record. • Where it usually breaks: the machine is left with a raised attachment or on a slope, which is a serious hazard to anyone passing after dark. | • State the parking requirements explicitly, including attachments lowered, brakes applied, ground level and chocked where needed. A machine left with a raised attachment is a genuine overnight hazard. • Require the key to be handed to a named holder rather than left in the machine, which is how unauthorised operation and theft occur. • Require a shift end defect note as well as a pre start check, since the pairing is the only way damage can be placed within a shift. • Require records to be submitted the same shift, because utilisation recalled later is unreliable. • Add parking location rules that keep plant clear of access routes, emergency routes and excavation edges.
513 | Projects | Receive the awarded BOQ, estimate, contract and approved budget baseline | Quantity Surveyor | Trigger: When the awarded project and approved commercial handover are received. Action: The Quantity Surveyor completes “Receive the awarded BOQ, estimate, contract and approved budget baseline” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. Control/Handoff: The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the awarded project and approved commercial handover are received. | The Quantity Surveyor completes “Receive the awarded BOQ, estimate, contract and approved budget baseline” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. | The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: the Quantity Surveyor takes over the commercial documents the project has been won on, the priced bill, the estimate, the signed contract and the approved budget, and treats them as the fixed starting point everything is measured against. • Starts when: the project is awarded and handed to the delivery team. • How it runs: (1) he collects the awarded bill of quantities, the winning estimate, the executed contract and the approved budget. (2) He confirms every document is the final awarded version, not a tender draft. (3) He reads the payment, measurement, variation and retention terms so he knows the rules he must work under. (4) He freezes the budget as the baseline. (5) He flags anything missing or contradictory to the COO before work is priced against it. • Proof it happened: a complete commercial handover file, a confirmed budget baseline and a note of the payment and measurement terms. • Where it usually breaks: he starts measuring against the tender bill rather than the awarded one, so every figure after that is against the wrong baseline. | • Name the documents that must be in the commercial handover file and state that measurement does not begin until all of them are received. • Require the awarded version to be identified by date and revision, since tender and awarded bills differ more often than people assume. • Add a contract terms summary sheet covering payment period, measurement method, variation procedure, retention and notice periods, so the terms are usable without rereading the contract. • Fix the baseline formally: once approved it is frozen, and any change needs COO approval with the reason recorded. • Require discrepancies between contract, bill and estimate to be raised in writing before the first valuation, not absorbed.
514 | Projects | Establish project cost codes, quantity control and commitment structure | Quantity Surveyor | Trigger: When the awarded project and approved commercial handover are received. Action: The Quantity Surveyor completes “Establish project cost codes, quantity control and commitment structure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. Control/Handoff: The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the awarded project and approved commercial handover are received. | The Quantity Surveyor completes “Establish project cost codes, quantity control and commitment structure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. | The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he builds the cost structure for the project, the codes that every requisition, invoice and measurement gets booked to, so cost can be tracked by part of the work rather than as one lump. • Starts when: immediately after the commercial baseline is set and before the first purchase is committed. • How it runs: (1) he breaks the project into cost codes that match how the work is actually built and measured. (2) He links each code to its budget value. (3) He sets up the structure in the ERP. (4) He agrees with Procurement and Finance that everything will be booked against these codes. (5) He confirms nothing can be committed against a code that does not exist. • Proof it happened: an approved cost code structure live in the ERP, mapped to the budget. • Where it usually breaks: codes are too broad, so when the project overruns nobody can tell which part of the work caused it. | • Require the cost code structure to match the budget lines one to one, so budget against actual is a direct comparison and not a manual exercise. • Set a rule that no requisition, purchase order or invoice may be raised without a valid cost code, and enforce it in the ERP rather than by instruction. • State who may create or amend a code, since uncontrolled code creation is what makes cost reporting meaningless. • Separate committed cost from spent cost in the structure, because a project can be fully committed while looking underspent. • Require the structure to be issued to the Project Engineer and Procurement so everyone books to the same places.
515 | Projects | Reconcile awarded scope against IFC quantities and estimate assumptions | Quantity Surveyor | Trigger: When the awarded project and approved commercial handover are received. Action: The Quantity Surveyor completes “Reconcile awarded scope against IFC quantities and estimate assumptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. Control/Handoff: The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the awarded project and approved commercial handover are received. | The Quantity Surveyor completes “Reconcile awarded scope against IFC quantities and estimate assumptions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. | The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he compares what the project was paid to do with what the construction drawings now actually show, and works out where the quantities have moved. • Starts when: the construction issue drawings are released, and again at every significant design revision. • How it runs: (1) he remeasures the main quantities from the current drawings. (2) He compares them with the awarded bill and the estimate assumptions. (3) He lists the differences by element with the value effect. (4) He separates genuine scope change, which is recoverable, from estimating error, which is not. (5) He reports the position to the COO and flags variation claims to be raised. • Proof it happened: a scope reconciliation showing awarded quantity against drawing quantity, with the value effect and the claim items identified. • Where it usually breaks: the exercise is left until the project is well underway, by which time the work is built and the notice period for claiming it has expired. | • Set a deadline for this reconciliation, expressed in days from receipt of the construction drawings, because its value falls sharply with time. • Require the output to separate three things clearly: scope increase, design development and estimating error. They have completely different commercial treatment. • Require every recoverable difference to be passed to the variation register immediately with the notice date noted. • Repeat the exercise at every major drawing revision, not only at the start. • Require significant estimate assumption failures to be fed back to Estimating, since this is the only reliable learning loop the company has.
516 | Projects | Prepare project cash-flow, value and commercial milestone schedule | Quantity Surveyor | Trigger: When the awarded project and approved commercial handover are received. Action: The Quantity Surveyor completes “Prepare project cash-flow, value and commercial milestone schedule” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. Control/Handoff: The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the awarded project and approved commercial handover are received. | The Quantity Surveyor completes “Prepare project cash-flow, value and commercial milestone schedule” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. | The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he maps out when the project will earn money and when it will spend it, month by month, so the company can see whether the project funds itself or needs cash injected. • Starts when: the baseline and cost structure are set, then updated monthly. • How it runs: (1) he spreads the value of the work across the programme. (2) He applies the contract payment terms to work out when cash actually arrives. (3) He spreads the committed and expected costs by month. (4) He identifies the months where outgoings exceed receipts. (5) He submits the profile to Finance and the COO with the funding need flagged. • Proof it happened: a project cash flow and value profile with the funding gap months identified. • Where it usually breaks: value earned is treated as cash received, so the gap created by payment terms and retention is invisible until it bites. | • Require value and cash to be shown as two separate lines, with the payment terms and retention applied to the cash line. • Include advance recovery, retention release and any milestone conditions, since these are the items that most distort project cash. • Set the update frequency as monthly and tie it to the certified valuation, so the profile stays anchored to reality. • Require a stated funding requirement figure for the peak month, so Finance is given a number rather than a chart. • Add a rule that a slip in the programme triggers an immediate cash flow update, because delay changes cash far more than it changes value.
517 | Projects | Maintain the project commercial risk, allowance and contingency register | Quantity Surveyor | Trigger: When the awarded project and approved commercial handover are received. Action: The Quantity Surveyor completes “Maintain the project commercial risk, allowance and contingency register” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. Control/Handoff: The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the awarded project and approved commercial handover are received. | The Quantity Surveyor completes “Maintain the project commercial risk, allowance and contingency register” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a reconciled cost baseline, cost-code structure, cash-flow and commercial-risk register. | The Quantity Surveyor records scope and estimate gaps and obtains COO/CTO/CFO direction before changing the baseline. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he keeps a live register of the commercial risks on the project, the money set aside for them, and how much of that cushion has already been used. • Starts when: at project start, updated monthly and whenever a risk materialises. • How it runs: (1) he lists the commercial risks, the priced allowances and the contingency. (2) He puts a value and a likelihood against each. (3) He records every drawdown against contingency with the reason. (4) He reports remaining contingency against remaining risk. (5) He escalates when the cushion no longer covers the exposure. • Proof it happened: a maintained risk and contingency register showing allowance, drawdown and balance. • Where it usually breaks: contingency is spent quietly on early problems, so it is gone by the time the real risks arrive. | • Require contingency drawdown to be approved, not just recorded, and name who approves it. • Make the register show remaining contingency against remaining risk exposure, because the balance alone tells nobody whether it is enough. • Set an escalation trigger, for example when remaining contingency falls below a stated share of remaining exposure, and route it to the COO. • Require closed risks to be marked as closed with the unused allowance released, so the register does not overstate protection. • Keep priced allowances and contingency separate, since spending an allowance is expected and spending contingency is not.
518 | Projects | Verify site requisition quantity against BOQ, budget and installed balance | Quantity Surveyor | Trigger: When a verified site requirement or procurement comparison requires commercial control. Action: The Quantity Surveyor completes “Verify site requisition quantity against BOQ, budget and installed balance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an ERP requisition, budget check, commitment record and remaining-budget status. Control/Handoff: No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a verified site requirement or procurement comparison requires commercial control. | The Quantity Surveyor completes “Verify site requisition quantity against BOQ, budget and installed balance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an ERP requisition, budget check, commitment record and remaining-budget status. | No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: before anything is ordered for site, he checks the quantity being asked for against the bill, the budget and what is already installed or delivered, so the project does not buy more than the work needs. • Starts when: site raises a material or subcontract requisition. • How it runs: (1) he takes the requested quantity. (2) He compares it with the measured quantity for that element. (3) He deducts what has already been delivered or installed. (4) He checks the balance against the budget for that cost code. (5) He approves, reduces or returns the requisition with the reason. • Proof it happened: a verified requisition showing the quantity check and the remaining budget position. • Where it usually breaks: requisitions are passed on the requester's word, and the project quietly buys well past the bill quantity. | • Require the requisition check to show three figures: bill quantity, quantity already procured, and balance remaining. Approval without those figures is not a check. • Set a rule that any requisition exceeding the bill quantity needs a stated reason and higher approval, since this is the earliest visible sign of overrun or waste. • State that wastage allowances are defined by material type in advance rather than argued at each requisition. • Require rejected or reduced requisitions to be recorded with the reason, so patterns of over ordering surface. • Tie the check to the cost code so budget exhaustion is caught before the order, not at invoice stage.
519 | Projects | Create ERP requisitions linked to cost code and required-on-site date | Quantity Surveyor | Trigger: When a verified site requirement or procurement comparison requires commercial control. Action: The Quantity Surveyor completes “Create ERP requisitions linked to cost code and required-on-site date” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an ERP requisition, budget check, commitment record and remaining-budget status. Control/Handoff: No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a verified site requirement or procurement comparison requires commercial control. | The Quantity Surveyor completes “Create ERP requisitions linked to cost code and required-on-site date” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an ERP requisition, budget check, commitment record and remaining-budget status. | No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he raises the formal purchase request in the system, tagged to the right cost code and with a realistic date for when the material must be on site. • Starts when: a site requisition has passed his quantity and budget check. • How it runs: (1) he creates the requisition in the ERP. (2) He attaches the cost code so the spend lands in the right place. (3) He sets the required on site date from the programme, not from the requester's preference. (4) He attaches the specification and drawing reference. (5) He releases it to Procurement and tracks it until an order is placed. • Proof it happened: an ERP requisition carrying cost code, quantity, specification and required date, with an audit trail. • Where it usually breaks: the required date is padded or copied from the last requisition, so Procurement cannot tell what is genuinely urgent. | • Require the required on site date to be derived from the programme activity, with the activity reference recorded, since undisciplined dates destroy Procurement's ability to prioritise. • Make specification and drawing reference mandatory fields, because an unspecified requisition guarantees a wrong or disputed delivery. • State the minimum lead time by material category, so requisitions raised too late are visible as late rather than treated as urgent. • Require the requisition to be traceable to the approved site request, so nothing enters the system without an origin. • Define who may change a released requisition and require the change to be recorded.
520 | Projects | Review procurement comparisons for quantity and scope completeness | Quantity Surveyor | Trigger: When a verified site requirement or procurement comparison requires commercial control. Action: The Quantity Surveyor completes “Review procurement comparisons for quantity and scope completeness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an ERP requisition, budget check, commitment record and remaining-budget status. Control/Handoff: No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a verified site requirement or procurement comparison requires commercial control. | The Quantity Surveyor completes “Review procurement comparisons for quantity and scope completeness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an ERP requisition, budget check, commitment record and remaining-budget status. | No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: when Procurement compares supplier quotations, he checks the commercial side of that comparison, that everyone has quoted the same quantity and the same scope, so the cheapest price is genuinely the cheapest offer. • Starts when: Procurement issues a quotation comparison for a project package. • How it runs: (1) he checks the quantities quoted against the bill and the requisition. (2) He identifies scope each supplier has left out. (3) He adds back the missing items so the comparison is like for like. (4) He confirms the recommended price sits within the budget for that code. (5) He records his commercial comment and returns it. • Proof it happened: a reviewed comparison showing quantity and scope verification and the budget position. • Where it usually breaks: the lowest quotation wins on price alone, and the exclusions turn into variations that cost more than the difference. | • Require the comparison to be normalised before any recommendation, with exclusions priced and added back and the adjustment shown. • Require the budget position for the relevant cost code to appear on the comparison, so an award over budget cannot pass unnoticed. • List the items commonly excluded by category, for example offloading, wastage, testing, commissioning and site attendance, and require each to be confirmed as included or excluded. • State that a commercial review is mandatory above a stated value and cannot be waived for urgency. • Require his comment to be recorded on the comparison itself, so the decision trail is complete.
521 | Projects | Maintain committed-cost and uncommitted-budget tracking | Quantity Surveyor | Trigger: When a verified site requirement or procurement comparison requires commercial control. Action: The Quantity Surveyor completes “Maintain committed-cost and uncommitted-budget tracking” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an ERP requisition, budget check, commitment record and remaining-budget status. Control/Handoff: No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a verified site requirement or procurement comparison requires commercial control. | The Quantity Surveyor completes “Maintain committed-cost and uncommitted-budget tracking” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an ERP requisition, budget check, commitment record and remaining-budget status. | No quantity is requested without BOQ/IFC need and cost code; over-budget or out-of-scope need escalates before commitment. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he tracks the difference between money already committed through orders and subcontracts, and budget that is still free, so the project knows what it has left to spend rather than what it has paid. • Starts when: continuously from the first order, reported monthly. • How it runs: (1) he records every purchase order and subcontract value against its cost code. (2) He adds expected commitments still to come. (3) He compares total commitment with budget by code. (4) He identifies codes where commitment already exceeds budget. (5) He reports the position and stops further commitment on exhausted codes. • Proof it happened: a committed cost and uncommitted budget report by cost code. • Where it usually breaks: only invoices are tracked, so a project looks healthy while it is already committed beyond its budget. | • Define commitment explicitly as order or subcontract value, not invoice value, and require both to be reported side by side. • Require the report to show budget, committed, uncommitted and forecast for every cost code, since a project total hides the problem codes. • Set a hard rule that no new commitment is raised on a code with no uncommitted budget without written approval. • Include expected but unplaced commitments, because those are the overruns that arrive as a surprise. • Require variation approvals to update budget in the same report, so approved extra scope does not look like an overrun.
522 | Projects | Measure completed civil work and maintain quantity records | Quantity Surveyor | Trigger: When work or subcontract progress reaches the measurement cutoff. Action: The Quantity Surveyor completes “Measure completed civil work and maintain quantity records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified measurement sheets, quantity reconciliation and certification status. Control/Handoff: Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When work or subcontract progress reaches the measurement cutoff. | The Quantity Surveyor completes “Measure completed civil work and maintain quantity records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified measurement sheets, quantity reconciliation and certification status. | Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he physically measures the civil work that has actually been completed on site and keeps the records that turn that work into money. • Starts when: at the agreed measurement points in the month, and before every valuation. • How it runs: (1) he takes the current drawings and the bill items. (2) He measures the completed work on site with the site engineer. (3) He records the measurement with location, drawing reference and date. (4) He compares the total with the previous measurement to get the period quantity. (5) He files the sheets as the basis for valuation and cost reporting. • Proof it happened: signed measurement sheets showing quantity, location and drawing reference, with a period comparison. • Where it usually breaks: quantities are taken from the supervisor's percentage estimate instead of measured, and the valuation is then indefensible when the consultant checks it. | • State clearly that measurement means measured quantity, and that a percentage complete supplied by site is not a measurement. • Require joint measurement with the site engineer or consultant where the contract allows, since jointly signed records are far harder to dispute later. • Require location and drawing revision on every measurement sheet, because a quantity without a location cannot be re verified. • Set the measurement method to follow the contract measurement rules, and name those rules in the SOP. • Require work about to be covered to be measured before concealment, as it cannot be measured afterwards.
523 | Projects | Measure completed MEP work and maintain quantity records | Quantity Surveyor | Trigger: When work or subcontract progress reaches the measurement cutoff. Action: The Quantity Surveyor completes “Measure completed MEP work and maintain quantity records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified measurement sheets, quantity reconciliation and certification status. Control/Handoff: Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When work or subcontract progress reaches the measurement cutoff. | The Quantity Surveyor completes “Measure completed MEP work and maintain quantity records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified measurement sheets, quantity reconciliation and certification status. | Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: the same measurement discipline applied to mechanical, electrical and plumbing work, which is harder because much of it is installed above ceilings and inside walls and disappears from view. • Starts when: at monthly measurement points, and before any MEP work is concealed. • How it runs: (1) he takes the MEP drawings and bill items. (2) He measures installed lengths, fittings and equipment with the MEP engineer. (3) He records quantities with zone and drawing reference. (4) He captures anything about to be concealed before it is closed. (5) He files the records for valuation and consumption reconciliation. • Proof it happened: signed MEP measurement records by zone with pre concealment evidence. • Where it usually breaks: services are closed up before measurement, and the quantity becomes a negotiation instead of a fact. | • Tie MEP measurement to the concealment hold point, so nothing is closed before measurement is taken. • Require photographic evidence for concealed services alongside the measurement, because photographs settle disputes that drawings cannot. • Require measurement by zone and system rather than in project totals, since MEP progress claims are usually challenged at zone level. • Distinguish delivered equipment from installed equipment, as they are valued differently under most contracts. • State how testing and commissioning items are measured and when they become payable.
524 | Projects | Verify subcontractor progress measurements and supporting evidence | Quantity Surveyor | Trigger: When work or subcontract progress reaches the measurement cutoff. Action: The Quantity Surveyor completes “Verify subcontractor progress measurements and supporting evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified measurement sheets, quantity reconciliation and certification status. Control/Handoff: Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When work or subcontract progress reaches the measurement cutoff. | The Quantity Surveyor completes “Verify subcontractor progress measurements and supporting evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified measurement sheets, quantity reconciliation and certification status. | Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: when a subcontractor claims progress, he checks that claim against what has actually been done before it turns into a payment. • Starts when: a subcontractor submits a progress measurement or payment application. • How it runs: (1) he receives the claimed quantities. (2) He verifies them against his own measurement and site records. (3) He checks the supporting evidence, approvals and quality records exist. (4) He adjusts the claim to the verified quantity with the reason recorded. (5) He passes the verified position for certification. • Proof it happened: a verified subcontractor measurement showing claimed against verified quantity, with reasons for adjustment. • Where it usually breaks: claims are certified from the subcontractor's own figures under time pressure, and overpayment is discovered only when he has no work left to recover it against. | • Require verification against independent records, and state that a subcontractor's own measurement cannot be certified as submitted. • Require quality acceptance before quantity certification, so defective work is not paid for. • Require every adjustment to be recorded with the reason and communicated, because unexplained cuts create disputes that outlast the project. • Track cumulative certified against subcontract value, since overpayment against remaining scope is the real exposure. • Set a stated turnaround time for verification, as slow certification is a common cause of subcontractor slowdown.
525 | Projects | Reconcile material consumption, installed quantity and site balance | Quantity Surveyor | Trigger: When work or subcontract progress reaches the measurement cutoff. Action: The Quantity Surveyor completes “Reconcile material consumption, installed quantity and site balance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified measurement sheets, quantity reconciliation and certification status. Control/Handoff: Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When work or subcontract progress reaches the measurement cutoff. | The Quantity Surveyor completes “Reconcile material consumption, installed quantity and site balance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified measurement sheets, quantity reconciliation and certification status. | Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he checks that the material bought, the material installed and the material still sitting on site add up. If they do not, something has been wasted, stolen or misused. • Starts when: monthly, and at project completion. • How it runs: (1) he takes the quantity delivered from the store records. (2) He takes the quantity installed from his own measurement. (3) He takes the physical stock balance from the store count. (4) He compares delivered against installed plus balance. (5) He investigates the difference and reports material loss with the cause. • Proof it happened: a material reconciliation by item showing delivered, installed, balance and variance. • Where it usually breaks: the reconciliation is done only at the end, when the material is long gone and no cause can be established. | • Set the reconciliation frequency as monthly for high value and high volume materials, because an annual exercise cannot identify a cause. • Define an acceptable wastage percentage by material type, so variance can be judged rather than merely reported. • Require variance above the allowance to be investigated with a named cause, and route repeat cases to the COO. • Require the physical stock count to be witnessed by someone other than the storekeeper, since a self reported balance closes any gap on paper. • Include material issued to subcontractors as a tracked category, as free issue material is where most unexplained loss sits.
526 | Projects | Maintain measurement sheets, joint records and consultant certification status | Quantity Surveyor | Trigger: When work or subcontract progress reaches the measurement cutoff. Action: The Quantity Surveyor completes “Maintain measurement sheets, joint records and consultant certification status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: verified measurement sheets, quantity reconciliation and certification status. Control/Handoff: Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When work or subcontract progress reaches the measurement cutoff. | The Quantity Surveyor completes “Maintain measurement sheets, joint records and consultant certification status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | verified measurement sheets, quantity reconciliation and certification status. | Measurements require site evidence and responsible engineer confirmation; disputed or unapproved work is separately recorded. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he keeps the measurement paperwork in order and tracks which records the consultant has certified, because uncertified measurement is not yet money. • Starts when: continuously as measurement is carried out. • How it runs: (1) he files every measurement sheet with its reference and date. (2) He identifies which records need consultant signature. (3) He submits them and records the submission date. (4) He tracks certification, query and rejection status. (5) He chases outstanding certifications before the valuation cut off. • Proof it happened: an indexed measurement file and a certification status log showing submitted, certified and pending items. • Where it usually breaks: joint records are taken but never signed, so at final account there is no agreed measurement to rely on. | • Require joint records to be signed at the time of measurement, and state that an unsigned joint record carries no more weight than an internal one. • Keep a certification tracker showing submission date, status and age, because pending certifications are unbilled revenue. • Set an escalation route for records left uncertified beyond a stated number of days. • Require measurement records to be stored in one controlled location, not in personal files, since these are the primary evidence in any final account dispute. • Define the retention period for measurement records in line with the contract limitation period.
527 | Projects | Open and maintain the project variation and additional-work register | Quantity Surveyor | Trigger: When an instruction, scope difference, delay or additional work is identified. Action: The Quantity Surveyor completes “Open and maintain the project variation and additional-work register” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a timely variation/notice record, measured value, substantiation and approval status. Control/Handoff: No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When an instruction, scope difference, delay or additional work is identified. | The Quantity Surveyor completes “Open and maintain the project variation and additional-work register” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a timely variation/notice record, measured value, substantiation and approval status. | No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he opens and maintains the register of every change and extra piece of work on the project, so nothing done outside the original scope is forgotten or given away free. • Starts when: at project start, then at every instruction, drawing change or site direction that alters scope. • How it runs: (1) he opens the register at mobilisation. (2) He records every potential change with its date and origin. (3) He assigns a reference and a status. (4) He notes the notice deadline where the contract requires notification. (5) He reviews the register weekly with the Project Engineer so nothing sits dormant. • Proof it happened: a live variation register with reference, origin, date, status and notice position. • Where it usually breaks: changes are recorded only once they are priced, so the early ones are already time barred by the time anyone claims them. | • Require an entry to be opened the day a potential change is identified, before it is valued or agreed, since the register's purpose is to protect the notice position. • Make the notice deadline a field in the register, with an alert before it expires. This single field prevents most lost entitlement. • Require every entry to record its origin: client instruction, consultant direction, drawing revision, site condition or internal change, as origin decides recoverability. • Include internal changes with no client recovery, so their cost impact is still visible. • Set a weekly review with the Project Engineer as a fixed step, not an option.
528 | Projects | Measure and value instructed variations and scope changes | Quantity Surveyor | Trigger: When an instruction, scope difference, delay or additional work is identified. Action: The Quantity Surveyor completes “Measure and value instructed variations and scope changes” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a timely variation/notice record, measured value, substantiation and approval status. Control/Handoff: No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When an instruction, scope difference, delay or additional work is identified. | The Quantity Surveyor completes “Measure and value instructed variations and scope changes” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a timely variation/notice record, measured value, substantiation and approval status. | No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he measures the extra or changed work and puts a price on it using the contract rates, so the change can be claimed as a proper valued item. • Starts when: a variation is instructed or the work is carried out under direction. • How it runs: (1) he measures the varied work separately from the base scope. (2) He applies the contract rates where they exist. (3) He builds a new rate where none exists, using the contract method. (4) He values time and cost effects where allowed. (5) He submits the valuation into the register with its evidence. • Proof it happened: a variation valuation with measurement, rates applied and rate build ups where new rates were needed. • Where it usually breaks: varied work is measured together with the base work, and afterwards it is impossible to separate what was extra. | • Require varied work to be measured and recorded separately at the time it is executed, since separation after the fact is the single hardest thing to prove. • State the order of preference for rates: contract rate, analogous rate, then new build up, and require the basis to be stated on every valuation. • Require new rate build ups to show labour, material, plant, overhead and profit as separate lines, because a lump sum rate invites rejection. • State whether time related cost is claimed with the variation or separately as delay, so the two are not double counted or lost. • Require the valuation to be prepared within a stated period of instruction, while the cost evidence is still retrievable.
529 | Projects | Prepare variation substantiation, rate build-up and supporting evidence | Quantity Surveyor | Trigger: When an instruction, scope difference, delay or additional work is identified. Action: The Quantity Surveyor completes “Prepare variation substantiation, rate build-up and supporting evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a timely variation/notice record, measured value, substantiation and approval status. Control/Handoff: No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When an instruction, scope difference, delay or additional work is identified. | The Quantity Surveyor completes “Prepare variation substantiation, rate build-up and supporting evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a timely variation/notice record, measured value, substantiation and approval status. | No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he builds the supporting file behind each variation claim, the instruction, the drawings, the measurements, the rates and the photographs, so the claim can survive challenge. • Starts when: a variation is valued and prepared for submission. • How it runs: (1) he assembles the instruction or direction that authorised the work. (2) He attaches the before and after drawings. (3) He includes measurement records and site evidence. (4) He includes the rate build up and cost evidence such as invoices and timesheets. (5) He compiles it as a single submission package. • Proof it happened: a complete substantiation package per variation, indexed and traceable. • Where it usually breaks: the claim is submitted as a price with no evidence, gets rejected, and by the time evidence is gathered the records have gone. | • Set a standard substantiation checklist so every variation is submitted with the same evidence set, and state that incomplete packages are not submitted. • Require the authorising instruction to be identified explicitly. A variation with no traceable instruction is the weakest possible claim. • Require photographic evidence for anything that will be covered or removed, taken before the work is done. • Require cost evidence to be gathered contemporaneously, since timesheets and delivery notes become unobtainable within months. • Keep the package in one controlled folder per variation reference, so it can be reissued in negotiation without rebuilding.
530 | Projects | Track variation submission, negotiation, approval and rejection status | Quantity Surveyor | Trigger: When an instruction, scope difference, delay or additional work is identified. Action: The Quantity Surveyor completes “Track variation submission, negotiation, approval and rejection status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a timely variation/notice record, measured value, substantiation and approval status. Control/Handoff: No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When an instruction, scope difference, delay or additional work is identified. | The Quantity Surveyor completes “Track variation submission, negotiation, approval and rejection status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a timely variation/notice record, measured value, substantiation and approval status. | No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he follows every submitted variation through to a decision, so claims do not sit unanswered and quietly die. • Starts when: a variation is submitted, then continuously until it is approved, rejected or settled. • How it runs: (1) he records the submission date and value. (2) He tracks the client or consultant response. (3) He records queries and resubmissions. (4) He records approval, partial approval or rejection with the value agreed. (5) He escalates items with no response beyond the contract period. • Proof it happened: a status log showing submitted, queried, approved and rejected values with dates and ageing. • Where it usually breaks: nobody chases silence, and unanswered claims are treated as settled at nil at final account. | • Require an ageing view of open variations, since age not value is what predicts a claim being lost. • Set an escalation trigger for no response beyond the contract period, routing to the Project Engineer and COO for a formal notice. • Require approved, rejected and pending values to be reported separately, because a single submitted total overstates the recoverable position. • Require rejections to record the stated reason, so a resubmission can address it rather than repeat it. • Require the forecast to include only approved and probable values, with a stated basis for what counts as probable.
531 | Projects | Maintain delay, disruption and commercial-notice support with the Project Engineer | Quantity Surveyor | Trigger: When an instruction, scope difference, delay or additional work is identified. Action: The Quantity Surveyor completes “Maintain delay, disruption and commercial-notice support with the Project Engineer” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a timely variation/notice record, measured value, substantiation and approval status. Control/Handoff: No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When an instruction, scope difference, delay or additional work is identified. | The Quantity Surveyor completes “Maintain delay, disruption and commercial-notice support with the Project Engineer” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a timely variation/notice record, measured value, substantiation and approval status. | No changed work is treated as commercially approved without written control; material exposure escalates to COO, CLO and CFO. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: when the project is delayed or disrupted by someone else, he supplies the commercial side of the case, the cost of that delay, while the Project Engineer handles the contractual notices. • Starts when: a delay or disruption event occurs, or a notice is being prepared. • How it runs: (1) he identifies the cost effect of the event: standing time, extended preliminaries, idle plant and labour. (2) He gathers the records that prove it, daily reports, timesheets and plant logs. (3) He values the effect. (4) He supplies it to the Project Engineer for the notice within the contract period. (5) He keeps the running cost record as the event continues. • Proof it happened: a valued delay and disruption record with contemporaneous evidence, referenced in the issued notice. • Where it usually breaks: the cost is calculated months later from memory, and the claim fails not on merit but on evidence. | • Require cost capture to start on the day the event starts, running in parallel with the notice, since retrospective reconstruction is what loses these claims. • Name the records that constitute contemporaneous evidence: daily reports, timesheets, plant logs, delivery records and correspondence, and require them to be collected at the time. • Separate prolongation cost from disruption cost, as they are proved in different ways and mixing them weakens both. • Require the notice date and the contract notice period to be recorded against the claim, because entitlement is usually decided there. • Require ongoing events to be valued monthly rather than once at the end.
532 | Projects | Prepare client progress-valuation and invoice-support packages | Quantity Surveyor | Trigger: When a client milestone or supplier/subcontractor payment cutoff is reached. Action: The Quantity Surveyor completes “Prepare client progress-valuation and invoice-support packages” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a certified valuation, invoice-support pack, payment evidence or collection action. Control/Handoff: Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a client milestone or supplier/subcontractor payment cutoff is reached. | The Quantity Surveyor completes “Prepare client progress-valuation and invoice-support packages” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a certified valuation, invoice-support pack, payment evidence or collection action. | Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he prepares the monthly bill to the client, showing the value of work done and the evidence that supports it, so the company gets paid for the period. • Starts when: at the contractual valuation date each month. • How it runs: (1) he takes the measured quantities for the period. (2) He values them at contract rates and adds approved variations. (3) He applies retention, advance recovery and any deductions. (4) He assembles the supporting measurement and certification evidence. (5) He submits the valuation to the client or consultant by the contractual date. • Proof it happened: a submitted valuation package with measurement backup, submitted on the contract date with proof of submission. • Where it usually breaks: the valuation misses the contractual submission date, and payment slips by a full month for no commercial reason. | • Put the contractual valuation and submission dates in the SOP as fixed dates, and make missing them a reportable event, since a missed date costs a month of cash. • Require proof of submission to be retained, because the submission date drives the payment due date. • Standardise the valuation package contents, so the consultant cannot delay certification for missing backup. • Require the certified value from the previous period to be reconciled before the next submission, so disputes are not carried forward silently. • State how work in progress and material on site are treated, as these are the most frequently disputed lines.
533 | Projects | Reconcile certified value, retention, advance recovery and prior billing | Quantity Surveyor | Trigger: When a client milestone or supplier/subcontractor payment cutoff is reached. Action: The Quantity Surveyor completes “Reconcile certified value, retention, advance recovery and prior billing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a certified valuation, invoice-support pack, payment evidence or collection action. Control/Handoff: Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a client milestone or supplier/subcontractor payment cutoff is reached. | The Quantity Surveyor completes “Reconcile certified value, retention, advance recovery and prior billing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a certified valuation, invoice-support pack, payment evidence or collection action. | Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he checks what the client actually certified against what was claimed, and makes sure retention, advance recovery and previous payments have been applied correctly. • Starts when: a payment certificate is received from the client or consultant. • How it runs: (1) he compares the certified value with the claimed value line by line. (2) He identifies and questions every reduction. (3) He verifies retention has been deducted at the contract rate and no more. (4) He verifies advance recovery and previous certified amounts. (5) He records the reconciled position and raises disputes formally. • Proof it happened: a certificate reconciliation showing claimed against certified, with reductions identified and disputed items recorded. • Where it usually breaks: certificates are accepted as received, and cumulative under certification builds into a large loss nobody noticed happening. | • Require line by line reconciliation of every certificate, since silent acceptance of reductions is how projects lose margin without a single decision being taken. • Require reductions to be queried within a stated period, because most contracts limit how long a certificate can be challenged. • Require retention, advance recovery and cumulative certified value to be checked against the contract on every certificate, as arithmetic errors in these lines are common and persistent. • Keep a running record of disputed amounts so they are visible in the forecast rather than written off by default. • Require retention release milestones and dates to be tracked from the start, since unclaimed retention is the most commonly abandoned money in construction.
534 | Projects | Review subcontractor valuation and payment-certificate quantities | Quantity Surveyor | Trigger: When a client milestone or supplier/subcontractor payment cutoff is reached. Action: The Quantity Surveyor completes “Review subcontractor valuation and payment-certificate quantities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a certified valuation, invoice-support pack, payment evidence or collection action. Control/Handoff: Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a client milestone or supplier/subcontractor payment cutoff is reached. | The Quantity Surveyor completes “Review subcontractor valuation and payment-certificate quantities” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a certified valuation, invoice-support pack, payment evidence or collection action. | Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he checks the quantities in subcontractor valuations before payment certificates are issued to them, so the company does not certify more than the work is worth. • Starts when: a subcontractor valuation is received for certification. • How it runs: (1) he verifies the claimed quantities against measurement. (2) He checks retention, advance recovery and previous payments have been applied. (3) He checks deductions for defective work, back charges and free issue material. (4) He confirms the cumulative position against the subcontract value. (5) He issues the certified quantity position for payment. • Proof it happened: a certified subcontractor valuation showing verified quantities, deductions and cumulative position. • Where it usually breaks: back charges and free issue material are never deducted, so the subcontractor is effectively paid twice for the same cost. | • Require a standing deduction checklist on every subcontractor valuation: retention, advance recovery, free issue material, back charges, plant hire and defective work. • Require the cumulative certified value to be tested against the subcontract value plus approved variations, so overcertification is caught before it is paid. • Require back charges to be notified to the subcontractor when incurred, not deducted without warning at the end, since undisclosed deductions lead to disputes and work stoppage. • Set a certification turnaround period, as late certification is a common cause of subcontractor demobilisation. • Require subcontract variations to be approved before they are certified, matching the discipline applied to client variations.
535 | Projects | Verify supplier and subcontractor commercial evidence for payment | Quantity Surveyor | Trigger: When a client milestone or supplier/subcontractor payment cutoff is reached. Action: The Quantity Surveyor completes “Verify supplier and subcontractor commercial evidence for payment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a certified valuation, invoice-support pack, payment evidence or collection action. Control/Handoff: Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a client milestone or supplier/subcontractor payment cutoff is reached. | The Quantity Surveyor completes “Verify supplier and subcontractor commercial evidence for payment” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a certified valuation, invoice-support pack, payment evidence or collection action. | Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: before Finance pays a supplier or subcontractor, he confirms the commercial evidence stacks up: the order, the delivery, the measurement and the rate all agree. • Starts when: an invoice reaches the project for commercial verification. • How it runs: (1) he matches the invoice to the purchase order or subcontract. (2) He matches quantity to the delivery or measurement record. (3) He checks the rate against the agreed rate. (4) He confirms the cost code and available budget. (5) He recommends payment, part payment or rejection with the reason. • Proof it happened: a verified invoice showing the three way match of order, receipt and rate, with a cost code confirmation. • Where it usually breaks: invoices are approved on the strength of the supplier relationship, and price and quantity differences are paid without anyone noticing. | • Make the three way match mandatory: order, receipt or measurement, and invoice. Require all three references to appear on the verification. • State the tolerance for quantity and price differences and require anything outside it to be rejected rather than adjusted informally. • Require the cost code and remaining budget to be confirmed at verification, since this is the last point before the cost is locked in. • Require rejections to be issued in writing with the reason, so the supplier can correct rather than resubmit the same invoice. • Set a verification turnaround period, because slow verification pushes suppliers into stopping supply at the worst moment.
536 | Projects | Track client certification, invoice, collection and commercial actions | Quantity Surveyor | Trigger: When a client milestone or supplier/subcontractor payment cutoff is reached. Action: The Quantity Surveyor completes “Track client certification, invoice, collection and commercial actions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: a certified valuation, invoice-support pack, payment evidence or collection action. Control/Handoff: Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When a client milestone or supplier/subcontractor payment cutoff is reached. | The Quantity Surveyor completes “Track client certification, invoice, collection and commercial actions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | a certified valuation, invoice-support pack, payment evidence or collection action. | Contract terms, prior billing, retention, GRN and approvals are reconciled before Finance processing. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he follows the money from certificate to invoice to collection, and chases the commercial actions needed to get the cash in. • Starts when: a valuation is certified, then continuously until the money is received. • How it runs: (1) he records the certified value and the payment due date. (2) He confirms Finance has invoiced against it. (3) He tracks the receipt against the due date. (4) He identifies overdue payments and the commercial reason behind them. (5) He supplies the evidence Finance or the COO needs to pursue collection. • Proof it happened: a certification and collection tracker showing certified, invoiced, due, received and overdue amounts. • Where it usually breaks: the QS treats his job as finished at certification, and nobody connects a slow payment to the commercial issue actually causing it. | • Require the tracker to run from certification through to receipt, since the QS holds the reason behind most payment delays. • Require an ageing view of overdue receivables by project with the commercial cause noted, because Finance cannot resolve a technical dispute without it. • Set the escalation route and trigger point for overdue amounts, naming the COO and Finance. • Require any contractual remedy for late payment, such as interest or suspension rights, to be identified rather than discovered later. • Require the retention release schedule to sit in the same tracker, as it is otherwise forgotten after project closeout.
537 | Projects | Prepare monthly cost-to-complete and forecast-at-completion | Quantity Surveyor | Trigger: When the monthly forecast, final account, retention or project-closeout cycle becomes due. Action: The Quantity Surveyor completes “Prepare monthly cost-to-complete and forecast-at-completion” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: forecast-at-completion, variance action, final-account status and commercial handover. Control/Handoff: QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the monthly forecast, final account, retention or project-closeout cycle becomes due. | The Quantity Surveyor completes “Prepare monthly cost-to-complete and forecast-at-completion” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | forecast-at-completion, variance action, final-account status and commercial handover. | QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he works out what it will cost to finish the remaining work, and therefore what the project will cost in total when it is done, rather than only what it has cost so far. • Starts when: monthly, at the reporting cut off. • How it runs: (1) he takes the cost incurred to date. (2) He takes the committed cost still to be spent. (3) He estimates the cost of the work not yet committed, using current prices. (4) He adds expected risk drawdown. (5) He reports forecast cost at completion against budget and the resulting margin. • Proof it happened: a monthly cost to complete and forecast at completion report with the margin position. • Where it usually breaks: cost to complete is taken as budget minus spend, which assumes the remaining work will cost exactly what was assumed months ago. | • State explicitly that cost to complete is built from the remaining work at current prices, not from budget minus spend, because that shortcut hides every overrun until the end. • Require the forecast to be built by cost code, so the problem areas are visible rather than netted off against underspends elsewhere. • Require the assumptions behind the forecast to be recorded, so a change in forecast can be explained rather than merely reported. • Require the previous month's forecast to be shown alongside, since the trend matters more than the single figure. • Require approved variations to be added to budget in the same report, otherwise recovered scope reads as overspend.
538 | Projects | Report budget variance, margin exposure and commercial corrective actions | Quantity Surveyor | Trigger: When the monthly forecast, final account, retention or project-closeout cycle becomes due. Action: The Quantity Surveyor completes “Report budget variance, margin exposure and commercial corrective actions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: forecast-at-completion, variance action, final-account status and commercial handover. Control/Handoff: QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the monthly forecast, final account, retention or project-closeout cycle becomes due. | The Quantity Surveyor completes “Report budget variance, margin exposure and commercial corrective actions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | forecast-at-completion, variance action, final-account status and commercial handover. | QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he explains the gap between what the project was meant to cost and what it now looks like it will cost, and says what should be done about it. • Starts when: monthly, once the forecast is prepared. • How it runs: (1) he compares forecast with budget by cost code. (2) He identifies the causes of the variance, quantity, rate, wastage, delay or scope. (3) He quantifies the margin effect. (4) He proposes corrective actions with owners. (5) He presents the position to the Project Engineer and COO and tracks the actions. • Proof it happened: a variance report with causes, margin exposure and named corrective actions with owners and dates. • Where it usually breaks: the report states the numbers without causes, so nothing is actually done and the same variance appears next month. | • Require a stated cause for every variance above a set threshold, because a variance without a cause cannot be acted on. • Require corrective actions to carry an owner and a date, and require last month's actions to be reported closed or open before new ones are added. • Set a margin erosion trigger that forces escalation to the COO, so bad news travels on a rule rather than on judgement. • Require recoverable causes to be cross referenced to the variation or claim register, so a cost problem is pursued as recovery where possible. • Require the report to distinguish one off variances from ones that will repeat every month, since the second type is far more serious.
539 | Projects | Prepare final account, variation reconciliation and retention schedule | Quantity Surveyor | Trigger: When the monthly forecast, final account, retention or project-closeout cycle becomes due. Action: The Quantity Surveyor completes “Prepare final account, variation reconciliation and retention schedule” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: forecast-at-completion, variance action, final-account status and commercial handover. Control/Handoff: QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the monthly forecast, final account, retention or project-closeout cycle becomes due. | The Quantity Surveyor completes “Prepare final account, variation reconciliation and retention schedule” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | forecast-at-completion, variance action, final-account status and commercial handover. | QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: at the end of the project he settles the whole commercial position: every variation, every measurement and the retention still to come, so the project can be closed with an agreed final figure. • Starts when: the works reach practical completion or the contract requires the final account. • How it runs: (1) he compiles final measured quantities for the whole works. (2) He reconciles every variation as approved, rejected or outstanding. (3) He reconciles all certified payments against the final value. (4) He prepares the retention release schedule with dates. (5) He submits the final account and negotiates settlement. • Proof it happened: a submitted final account with full measurement and variation reconciliation, and a retention schedule with release dates. • Where it usually breaks: the final account is prepared long after the team has left, so the knowledge and the records needed to defend it have dispersed. | • Set a deadline for final account preparation, expressed in days from completion, and require it while the delivery team is still assembled. • Require all open variations to be brought to a decision as part of the final account rather than abandoned at nil. • Require the retention schedule to state the release dates and conditions, and require it to be handed to Finance for tracking, since retention is the most commonly forgotten receivable. • Require defect liability obligations and their expiry to be recorded, as retention release usually depends on them. • Require settlement negotiation limits and who may agree them, so the final figure is not conceded below authority.
540 | Projects | Handover final commercial closeout records to Finance and the COO | Quantity Surveyor | Trigger: When the monthly forecast, final account, retention or project-closeout cycle becomes due. Action: The Quantity Surveyor completes “Handover final commercial closeout records to Finance and the COO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: forecast-at-completion, variance action, final-account status and commercial handover. Control/Handoff: QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. Continuity/Escalation: A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. Timing: To be confirmed. | When the monthly forecast, final account, retention or project-closeout cycle becomes due. | The Quantity Surveyor completes “Handover final commercial closeout records to Finance and the COO” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | forecast-at-completion, variance action, final-account status and commercial handover. | QS reconciles with Project Engineer and Finance; unapproved variation, claim, retention or cost exposure remains visible until resolved. | A competent project QS may provide backup with controlled records; budget, claim, variation, margin and certification exceptions escalate to the Project Engineer, COO and CFO. | To be confirmed. | • In plain words: he hands the project's complete commercial record to Finance and the COO, so the company keeps the history after the project team disbands. • Starts when: the final account is settled and the project is being closed. • How it runs: (1) he assembles the final commercial file: budget, final account, variations, measurements and certificates. (2) He confirms the outstanding retention and any open claims are listed with dates. (3) He records the final margin against budget. (4) He hands the file to Finance with the outstanding items named. (5) He submits the commercial lessons learned to the COO. • Proof it happened: a signed commercial closeout handover with the final margin, the outstanding items list and a lessons learned note. • Where it usually breaks: the project closes, the QS moves on and the retention and open claims are left with no owner, so the money is never collected. | • Require a named owner in Finance to accept the outstanding retention and open claims, because these items outlive the project team and need a home. • Require the final margin against budget to be stated with the main causes of the difference, so the estimate and the outcome can be compared. • Require rate and productivity outturn data to be fed back to Estimating, since this is the only way tender prices improve. • List the documents required for closeout and state that the project is not closed until all are handed over. • Require the closeout file to be stored in one controlled location with a retention period matching the contract limitation period.
541 | Projects | Prepare the project HSE plan and site-specific safety arrangements | QHSE Engineer | Trigger: When the project is mobilised or a material QHSE requirement changes. Action: The QHSE Engineer completes “Prepare the project HSE plan and site-specific safety arrangements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. Control/Handoff: QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the project is mobilised or a material QHSE requirement changes. | The QHSE Engineer completes “Prepare the project HSE plan and site-specific safety arrangements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. | QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he writes the safety plan for this particular site, covering the real hazards of this job rather than a generic document. • Starts when: the project is awarded and before anyone mobilises to site. • How it runs: (1) he studies the scope, the site surroundings and the client's safety requirements. (2) He lists the high risk activities this job will actually involve. (3) He sets out the controls, the responsibilities and the reporting lines. (4) He gets it approved by the project manager and the client where required. (5) He briefs the site team on it before work starts. • Proof it happened: an approved project HSE plan with a version and date, and a record of the briefing. • Where it usually breaks: a plan copied from another project is submitted, so it names hazards this site does not have and misses the ones it does. | • Ban plan reuse without revision in the SOP. Require the plan to name this site's actual hazards, neighbours and access constraints. • List the minimum contents: high risk activity list, permit regime, emergency arrangements, welfare, waste, competency requirements and reporting lines. • Require client and authority requirements to be mapped into the plan explicitly, so nothing agreed contractually is left out. • Make the pre mobilisation briefing a condition of work release, not a follow up task. • Set a review trigger: the plan is revised whenever scope, method or site conditions change materially.
542 | Projects | Prepare the project quality plan and inspection-control structure | QHSE Engineer | Trigger: When the project is mobilised or a material QHSE requirement changes. Action: The QHSE Engineer completes “Prepare the project quality plan and inspection-control structure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. Control/Handoff: QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the project is mobilised or a material QHSE requirement changes. | The QHSE Engineer completes “Prepare the project quality plan and inspection-control structure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. | QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he writes how quality will be controlled on this job, meaning who inspects what, when, and against which standard. • Starts when: at project start, alongside the HSE plan and before construction begins. • How it runs: (1) he identifies the work packages and the applicable specifications and codes. (2) He sets the inspection stages for each package. (3) He defines who inspects, who approves and what records are kept. (4) He gets the plan approved by the project manager and consultant. (5) He issues it to the site team and the subcontractors. • Proof it happened: an approved project quality plan with the inspection structure, issued and acknowledged. • Where it usually breaks: the plan exists but the inspection stages are not matched to the actual construction sequence, so inspections are requested after the work is closed. | • Require the inspection stages to be aligned to the construction sequence and to name the hold points where work cannot proceed. • State the standard for each package by specification clause, not by general reference, so acceptance criteria are not arguable. • Define who may accept work internally and who must submit to the consultant, since confusion here causes double handling. • Require subcontractor acknowledgement of the plan, because their work carries the same inspection obligations. • Add a cross reference to the ITP register so the plan and the ITPs cannot drift apart.
543 | Projects | Establish legal, authority, permit and client QHSE requirement registers | QHSE Engineer | Trigger: When the project is mobilised or a material QHSE requirement changes. Action: The QHSE Engineer completes “Establish legal, authority, permit and client QHSE requirement registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. Control/Handoff: QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the project is mobilised or a material QHSE requirement changes. | The QHSE Engineer completes “Establish legal, authority, permit and client QHSE requirement registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. | QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he builds the list of every legal, authority, permit and client requirement the project must satisfy, so nothing is discovered late. • Starts when: at project start, and updated whenever a new requirement or approval appears. • How it runs: (1) he collects the legal, municipal, authority and client QHSE obligations that apply. (2) He records each with its reference, owner and deadline. (3) He identifies which permits must be obtained before which activities. (4) He confirms with the project manager who is responsible for each. (5) He reviews and updates the registers through the project. • Proof it happened: maintained legal, authority, permit and client requirement registers with owners and status. • Where it usually breaks: a permit that is a precondition for an activity is identified only when the activity is due to start. | • Require each permit entry to state the activity it gates and its lead time, so procurement of the permit starts early enough. • Assign a named owner per requirement. A register of obligations with no owners is a list, not a control. • Add an expiry and renewal date field, since lapsed permits and certificates are as damaging as missing ones. • Require the registers to be reviewed at a fixed frequency, with overdue items escalated to the project manager. • Cross check the client contract QHSE section against the register at start, because client specific obligations are the ones most often missed.
544 | Projects | Establish emergency, welfare, environmental and waste-management controls | QHSE Engineer | Trigger: When the project is mobilised or a material QHSE requirement changes. Action: The QHSE Engineer completes “Establish emergency, welfare, environmental and waste-management controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. Control/Handoff: QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the project is mobilised or a material QHSE requirement changes. | The QHSE Engineer completes “Establish emergency, welfare, environmental and waste-management controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. | QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he sets up the arrangements for emergencies, welfare facilities, environmental protection and waste handling on the site. • Starts when: during mobilisation and before the workforce arrives in numbers. • How it runs: (1) he plans the emergency routes, assembly points, first aid and rescue arrangements. (2) He confirms the welfare facilities are provided and sized for the workforce. (3) He sets out the environmental controls, such as dust, noise and spill prevention. (4) He arranges the waste segregation, storage and licensed disposal route. (5) He briefs the site and displays the arrangements. • Proof it happened: emergency plan and layout, welfare provision record, environmental controls and waste disposal arrangements with a licensed contractor. • Where it usually breaks: waste is removed by an unlicensed carrier, which is a legal exposure that surfaces long after disposal. | • Require licensed waste carrier verification with retained disposal receipts, since liability for waste stays with the producer. • Size welfare facilities against the actual peak workforce, and require rechecking when headcount rises. • Require emergency arrangements to be tested rather than displayed. An untested route or muster point is an assumption. • Add the spill kit and containment requirement for fuel and chemical storage, which is the commonest environmental breach on site. • Require the emergency layout to be updated whenever site access or work areas change, because stale routes are dangerous.
545 | Projects | Verify mobilisation and pre-start QHSE readiness before work release | QHSE Engineer | Trigger: When the project is mobilised or a material QHSE requirement changes. Action: The QHSE Engineer completes “Verify mobilisation and pre-start QHSE readiness before work release” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. Control/Handoff: QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the project is mobilised or a material QHSE requirement changes. | The QHSE Engineer completes “Verify mobilisation and pre-start QHSE readiness before work release” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | approved HSE/quality plans, requirement registers, emergency controls and pre-start readiness status. | QHSE Engineer holds mobilisation or work lacking mandatory legal, client, welfare, environmental, safety or quality controls. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: before work is allowed to start, he checks that the safety and quality basics are actually in place on site. • Starts when: at the end of mobilisation, before the first work release. • How it runs: (1) he checks the site set up: access, barricades, signage, welfare, first aid and firefighting provision. (2) He verifies the QHSE documents and registers are in place. (3) He verifies inductions and competency records for the arriving workforce. (4) He records the gaps and gets them closed. (5) He confirms readiness in writing so work can be released. • Proof it happened: a completed pre start QHSE readiness check with gaps closed, and a written readiness confirmation. • Where it usually breaks: work starts under programme pressure with the readiness check open, and the gaps are never closed. | • Make the readiness confirmation a hard gate in the SOP. No work release with open critical items, and list which items are critical. • Name who may authorise a conditional start and require a closure date for each open item. • Include competency and induction verification in the gate, since untrained workers on site is the most common start up breach. • Require the check to be physical, walked on site, and not completed from documents. • Retain the completed check as project evidence, because it is the record that start conditions were controlled.
546 | Projects | Review method statements and task risk assessments before approval | QHSE Engineer | Trigger: When a method, material, high-risk activity, inspection or competency approval is required. Action: The QHSE Engineer completes “Review method statements and task risk assessments before approval” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved method/RA/ITP/submittal, permit control and competency/certification record. Control/Handoff: Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When a method, material, high-risk activity, inspection or competency approval is required. | The QHSE Engineer completes “Review method statements and task risk assessments before approval” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved method/RA/ITP/submittal, permit control and competency/certification record. | Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: before a job method is approved, he reviews how the crew intends to do it and whether the risks have been properly assessed. • Starts when: a method statement or risk assessment is submitted for an activity, and again when the method changes. • How it runs: (1) he reads the proposed method against the actual site conditions. (2) He checks the risk assessment identifies the real hazards and control measures. (3) He verifies the resources, competencies and equipment assumed are available. (4) He returns it with comments or recommends approval. (5) He confirms the approved method is briefed to the crew doing the work. • Proof it happened: reviewed and approved method statements and risk assessments, with the briefing record for the crew. • Where it usually breaks: the method is approved and filed but the crew works to a different sequence, because the briefing never happened. | • Require the briefing to the executing crew as a mandatory step after approval, with signatures, or the approval means nothing. • Require a resubmission when the method, sequence or equipment changes on site, and name who decides that a change is material. • Set a review turnaround time in the SOP, since slow review pushes crews to start without approval. • Require the risk assessment to state residual risk after controls, not just list hazards. • Add a check that the method matches the approved drawings and specification, so safety approval does not endorse a non compliant method.
547 | Projects | Prepare and control inspection and test plans and checklists | QHSE Engineer | Trigger: When a method, material, high-risk activity, inspection or competency approval is required. Action: The QHSE Engineer completes “Prepare and control inspection and test plans and checklists” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved method/RA/ITP/submittal, permit control and competency/certification record. Control/Handoff: Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When a method, material, high-risk activity, inspection or competency approval is required. | The QHSE Engineer completes “Prepare and control inspection and test plans and checklists” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved method/RA/ITP/submittal, permit control and competency/certification record. | Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he prepares the inspection and test plans, the documents that say exactly what gets checked at each stage of the work. • Starts when: before each work package starts, and updated when specifications or methods change. • How it runs: (1) he takes the specification requirements for the package. (2) He sets out each inspection and test stage in sequence. (3) He states the acceptance criteria and the record to be produced for each. (4) He marks which stages are hold points and who witnesses them. (5) He gets the ITP approved by the consultant and issues it for use. • Proof it happened: approved inspection and test plans with acceptance criteria, hold points and witness requirements. • Where it usually breaks: acceptance criteria are written as satisfactory or as per specification, so inspection results become a matter of opinion. | • Require measurable acceptance criteria with values and tolerances. Satisfactory is not an acceptance criterion. • Mark hold points clearly and state that work cannot proceed past them without a signed release. • State the witness requirement per stage: internal, consultant, client or third party, along with the notice period each needs. • Name the record produced at each stage, so the closeout dossier can be assembled from the ITP without reconstruction. • Require ITP approval before the package starts, since retrospective ITPs cannot control work already done.
548 | Projects | Review material submittals, samples and quality-document requirements | QHSE Engineer | Trigger: When a method, material, high-risk activity, inspection or competency approval is required. Action: The QHSE Engineer completes “Review material submittals, samples and quality-document requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved method/RA/ITP/submittal, permit control and competency/certification record. Control/Handoff: Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When a method, material, high-risk activity, inspection or competency approval is required. | The QHSE Engineer completes “Review material submittals, samples and quality-document requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved method/RA/ITP/submittal, permit control and competency/certification record. | Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he checks that the materials being proposed meet the specification, before they are ordered or delivered. • Starts when: a material submittal or sample is prepared, or a substitution is proposed. • How it runs: (1) he compares the proposed material against the specified requirement. (2) He checks the test certificates, compliance documents and any required approvals. (3) He verifies the sample matches the submitted data. (4) He recommends approval or rejection with the reason. (5) He keeps the approved submittal as the reference for checking deliveries. • Proof it happened: reviewed material submittals with certificates, approved samples and a recorded approval status. • Where it usually breaks: a material is ordered before submittal approval, so a rejection becomes a delivery already paid for. | • State in the SOP that ordering before submittal approval is prohibited, and name who may authorise an exception in writing. • Require the approved sample to be retained and labelled, so deliveries can be compared against a physical reference. • Require test certificates to be traceable to the actual batch delivered, not generic type certificates. • Add a substitution route with technical justification, since substitution is where specification compliance quietly fails. • Keep a submittal register with status and turnaround time, because slow approvals become the stated cause of procurement delay.
549 | Projects | Maintain permit-to-work and high-risk activity control registers | QHSE Engineer | Trigger: When a method, material, high-risk activity, inspection or competency approval is required. Action: The QHSE Engineer completes “Maintain permit-to-work and high-risk activity control registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved method/RA/ITP/submittal, permit control and competency/certification record. Control/Handoff: Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When a method, material, high-risk activity, inspection or competency approval is required. | The QHSE Engineer completes “Maintain permit-to-work and high-risk activity control registers” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved method/RA/ITP/submittal, permit control and competency/certification record. | Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he runs the permit system for dangerous work, so activities like hot work, excavation and confined space entry only happen under written authorisation. • Starts when: a high risk activity is planned, and daily for activities in progress. • How it runs: (1) he receives the permit request with the method and precautions. (2) He verifies the controls, isolations, competencies and standby arrangements are in place. (3) He issues the permit with its validity period and conditions. (4) He monitors compliance during the work. (5) He closes the permit when the area is made safe and records the closure. • Proof it happened: a permit register with issued, active and closed permits, each with conditions and closure records. • Where it usually breaks: permits are issued from the office without the site conditions being verified, which makes the permit paperwork rather than protection. | • Require physical verification of conditions before permit issue. A permit issued from a desk is not a control. • Set an explicit validity period per permit type and require reissue rather than verbal extension. • Require formal closure with the area made safe, since open permits accumulate and destroy the credibility of the system. • Name the standby and rescue requirements per activity type, particularly for confined space and hot work. • Add a daily reconciliation of active permits against actual site activity, to catch work proceeding without a permit.
550 | Projects | Verify competency, certification and third-party inspection requirements | QHSE Engineer | Trigger: When a method, material, high-risk activity, inspection or competency approval is required. Action: The QHSE Engineer completes “Verify competency, certification and third-party inspection requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: an approved method/RA/ITP/submittal, permit control and competency/certification record. Control/Handoff: Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When a method, material, high-risk activity, inspection or competency approval is required. | The QHSE Engineer completes “Verify competency, certification and third-party inspection requirements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | an approved method/RA/ITP/submittal, permit control and competency/certification record. | Affected work stays on hold until reviews and approvals are complete; technical issues route to CTO and operational issues to Project Engineer. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he checks that people doing specialised work are actually qualified, and that equipment needing third party inspection has valid certificates. • Starts when: at mobilisation, when new workers or plant arrive, and when certificates approach expiry. • How it runs: (1) he lists the activities and equipment requiring certification. (2) He collects and verifies the certificates for operators, riggers, welders, electricians and inspected equipment. (3) He checks validity dates and the issuing body. (4) He blocks uncertified people and equipment from the relevant work. (5) He tracks upcoming expiries and arranges renewal. • Proof it happened: a competency and certification register with verified certificates, validity dates and blocked entries where applicable. • Where it usually breaks: certificates are collected once at mobilisation and never checked again, so expired ones stay in the file looking valid. | • Require an expiry tracking field with an advance warning period, since expiry is the failure mode, not absence. • Require verification of the issuing body's validity, because forged and unrecognised certificates are common in this area. • State that uncertified personnel and uninspected equipment are physically blocked from the activity, and name who enforces it. • Keep the register aligned with the actual workforce on site, so leavers and new arrivals are reflected. • Add third party inspection scheduling for lifting gear and pressure equipment, with the next due date visible.
551 | Projects | Conduct daily site safety inspection and record corrective actions | QHSE Engineer | Trigger: When daily work proceeds or a planned safety/quality inspection becomes due. Action: The QHSE Engineer completes “Conduct daily site safety inspection and record corrective actions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. Control/Handoff: Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When daily work proceeds or a planned safety/quality inspection becomes due. | The QHSE Engineer completes “Conduct daily site safety inspection and record corrective actions” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. | Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he walks the site every day looking for unsafe conditions and acts, records what he finds and makes sure it gets corrected. • Starts when: daily, and additionally after incidents, weather events or major changes on site. • How it runs: (1) he inspects the work areas, access, edges, plant, storage and housekeeping. (2) He raises the unsafe conditions and acts he finds. (3) He instructs immediate correction where the risk is high. (4) He logs each finding with an owner and a closure date. (5) He verifies the corrections at the next inspection. • Proof it happened: a daily safety inspection record with findings, owners, corrective actions and closure status. • Where it usually breaks: the same finding is recorded day after day without closure, so the inspection becomes a diary rather than a control. | • Add repeat finding detection in the SOP. A finding recorded three times unresolved must escalate to the project manager. • Require a risk rating per finding so immediate danger is separated from housekeeping, and response times differ accordingly. • Require closure verification by re inspection, not by the owner's confirmation alone. • Name what triggers an unscheduled inspection: incident, storm, major lift, new subcontractor or new work area. • Keep the log as the source for the weekly report, so reporting is not a separate reconstruction exercise.
552 | Projects | Conduct planned quality inspections and surveillance | QHSE Engineer | Trigger: When daily work proceeds or a planned safety/quality inspection becomes due. Action: The QHSE Engineer completes “Conduct planned quality inspections and surveillance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. Control/Handoff: Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When daily work proceeds or a planned safety/quality inspection becomes due. | The QHSE Engineer completes “Conduct planned quality inspections and surveillance” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. | Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he inspects completed and in progress work against the specification, to catch quality problems while they can still be fixed cheaply. • Starts when: at the inspection stages set in the ITP, and on a planned surveillance schedule. • How it runs: (1) he inspects the work against the stated acceptance criteria. (2) He records the result with measurements or test values. (3) He accepts, accepts with correction, or rejects the work. (4) He raises the correction or non conformance where needed. (5) He verifies the correction before the stage is released. • Proof it happened: signed inspection records with measured results and a clear accept or reject decision. • Where it usually breaks: inspection is only done when the consultant is coming, so internal quality is unknown until an external inspection fails. | • Separate internal inspection from consultant inspection in the SOP, and require internal acceptance before any external request. • Require recorded measurements rather than tick boxes, since a tick proves attendance and a value proves compliance. • Set a surveillance frequency for ongoing work, not only stage inspections, to catch drift within a package. • Require rejected work to be re inspected against the same criteria and the result recorded, not just verbally cleared. • Track first time pass rate by package and by subcontractor, because that is the number that predicts closeout pain.
553 | Projects | Verify toolbox talks, PPE, access, housekeeping and welfare controls | QHSE Engineer | Trigger: When daily work proceeds or a planned safety/quality inspection becomes due. Action: The QHSE Engineer completes “Verify toolbox talks, PPE, access, housekeeping and welfare controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. Control/Handoff: Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When daily work proceeds or a planned safety/quality inspection becomes due. | The QHSE Engineer completes “Verify toolbox talks, PPE, access, housekeeping and welfare controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. | Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he checks the everyday basics on site: that briefings happen, PPE is worn, access is safe, the site is tidy and welfare is usable. • Starts when: daily as part of routine site presence. • How it runs: (1) he verifies toolbox talks were delivered and understood. (2) He checks PPE compliance and challenges non compliance on the spot. (3) He checks access routes, ladders, edges and lighting. (4) He checks housekeeping, material stacking and waste. (5) He records what he finds and follows up the gaps. • Proof it happened: daily verification records for briefings, PPE, access, housekeeping and welfare, with follow up actions. • Where it usually breaks: PPE non compliance is noted in a report but not challenged at the time, so the standard on site drops. | • Require on the spot challenge and correction, not just recording. An unchallenged breach sets the site standard. • Define the escalation path for repeated PPE non compliance, including removal from site, and state who authorises it. • Require toolbox talk verification by asking workers what the talk covered, since signature sheets prove attendance only. • Add welfare condition checks with a response time, because unusable welfare drives behaviour problems across the site. • Set housekeeping as a supervisor accountability with named areas, so tidiness has an owner rather than being everyone's job.
554 | Projects | Inspect scaffolds, lifting, excavation, hot work and confined-space controls | QHSE Engineer | Trigger: When daily work proceeds or a planned safety/quality inspection becomes due. Action: The QHSE Engineer completes “Inspect scaffolds, lifting, excavation, hot work and confined-space controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. Control/Handoff: Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When daily work proceeds or a planned safety/quality inspection becomes due. | The QHSE Engineer completes “Inspect scaffolds, lifting, excavation, hot work and confined-space controls” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. | Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he inspects the highest risk temporary works and activities on site, scaffolds, lifting operations, excavations, hot work and confined spaces. • Starts when: before first use, at the required inspection frequency, and after any alteration or event that could affect them. • How it runs: (1) he inspects scaffolds and tags them fit or unfit for use. (2) He checks lifting gear certification, rigging and exclusion zones before lifts. (3) He checks excavation support, access and edge protection. (4) He verifies hot work and confined space precautions against the permit. (5) He records each inspection and stops use where the condition is unsafe. • Proof it happened: dated inspection records and scaffold tags, lifting inspection records and permit verification records. • Where it usually breaks: a scaffold is altered by a crew and used before re inspection, which is the single commonest fatal scaffold sequence. | • State that any alteration voids the scaffold tag and use is prohibited until re inspection. Name who may alter scaffolds. • Set the inspection frequency per item type in the SOP, along with the trigger events that force an unscheduled inspection. • Require a documented lift plan for lifts above a stated weight or complexity, with the exclusion zone marked physically. • Require excavation inspection after rain and after any nearby plant movement, since collapse follows ground disturbance. • Keep an unfit for use tagging and isolation procedure, because a defective scaffold that is not tagged will be climbed.
555 | Projects | Issue stop-work instruction for immediate danger or unauthorised activity | QHSE Engineer | Trigger: When daily work proceeds or a planned safety/quality inspection becomes due. Action: The QHSE Engineer completes “Issue stop-work instruction for immediate danger or unauthorised activity” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. Control/Handoff: Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When daily work proceeds or a planned safety/quality inspection becomes due. | The QHSE Engineer completes “Issue stop-work instruction for immediate danger or unauthorised activity” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | inspection evidence, corrective actions, verified toolbox/PPE/access controls or stop-work record. | Immediate danger is stopped; findings receive owners and due dates and overdue/material issues escalate to Project Engineer and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: when he sees immediate danger or work happening without authorisation, he stops it on the spot. • Starts when: he observes immediate danger to life, unauthorised high risk work, or a serious breach of the approved method. • How it runs: (1) he stops the activity and makes the people and area safe. (2) He informs the supervisor and the project manager immediately. (3) He records the reason for the stoppage. (4) He states the conditions to be met before restart. (5) He verifies those conditions and authorises restart in writing. • Proof it happened: a stop work instruction record with the reason, the restart conditions and the written restart authorisation. • Where it usually breaks: the stop is resisted or reversed under programme pressure, which destroys the authority for every future stoppage. | • State in the SOP that a QHSE stop work instruction cannot be overruled by site management, and that only stated restart conditions release the work. • Require written restart authorisation, since verbal restart leaves no record of what was actually fixed. • Require every stoppage to be reported to the project manager and the QHSE function the same day, so the pattern is visible. • Protect the stop decision explicitly, including where the stoppage later proves unnecessary, or the authority will not be used. • Add a review of repeated stoppages by cause, because they point at a systemic failure rather than individual behaviour.
556 | Projects | Review work-inspection requests before consultant submission | QHSE Engineer | Trigger: When material arrives, work reaches inspection/test point or nonconformity is identified. Action: The QHSE Engineer completes “Review work-inspection requests before consultant submission” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: accepted/rejected status, test evidence, NCR record and verified corrective-action closure. Control/Handoff: No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When material arrives, work reaches inspection/test point or nonconformity is identified. | The QHSE Engineer completes “Review work-inspection requests before consultant submission” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | accepted/rejected status, test evidence, NCR record and verified corrective-action closure. | No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: before work is offered to the consultant for inspection, he checks it is genuinely ready, so the company does not fail inspections in front of the client. • Starts when: a crew or supervisor requests that work be submitted for consultant inspection. • How it runs: (1) he verifies the work is complete against the acceptance criteria. (2) He checks the preceding inspections and records are closed. (3) He checks the area is safe and accessible for inspection. (4) He rejects the request internally where it is not ready. (5) He releases the inspection request for submission. • Proof it happened: internally reviewed and released work inspection requests, with rejected requests recorded. • Where it usually breaks: requests are submitted to keep the programme moving, and repeated failures damage the company's credibility with the consultant. | • Make internal release a mandatory precondition for consultant submission, and record internally rejected requests as a measured indicator. • Require preceding stage records to be closed before release, since a missing earlier record invalidates the current inspection. • Set the notice period the consultant requires and build it into the request timing, to avoid disputes over attendance. • Track the inspection pass rate, because a falling rate predicts closeout delay long before it appears in the programme. • Require access and safety readiness as part of release, as an inspection abandoned for access reasons still counts as a failure.
557 | Projects | Verify material receipt, quarantine, rejection and release status | QHSE Engineer | Trigger: When material arrives, work reaches inspection/test point or nonconformity is identified. Action: The QHSE Engineer completes “Verify material receipt, quarantine, rejection and release status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: accepted/rejected status, test evidence, NCR record and verified corrective-action closure. Control/Handoff: No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When material arrives, work reaches inspection/test point or nonconformity is identified. | The QHSE Engineer completes “Verify material receipt, quarantine, rejection and release status” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | accepted/rejected status, test evidence, NCR record and verified corrective-action closure. | No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he controls the quality status of delivered material, what is accepted, what is held, what is rejected and what is released for use. • Starts when: material is delivered to site, and when held material is resolved. • How it runs: (1) he verifies the delivered material against the approved submittal and the certificates. (2) He accepts, quarantines or rejects it. (3) He physically marks and segregates quarantined and rejected material. (4) He arranges removal of rejected material from site. (5) He releases accepted material for use and records the status. • Proof it happened: material receipt inspection records with accept, hold or reject status, and evidence of removal for rejected material. • Where it usually breaks: rejected material stays on site unmarked and is eventually installed, which is the hardest defect to trace afterwards. | • Require physical marking and a segregated quarantine area, because status recorded only on paper does not stop installation. • Set a removal deadline for rejected material with a named owner, so it does not sit on site becoming usable. • Require batch traceability from certificate to delivery to installed location, particularly for structural and fire rated products. • Define who may release held material and on what evidence, since informal release is where control is lost. • Add a check against the approved submittal at delivery, not just against the purchase order, because the order may not match the approval.
558 | Projects | Witness required tests and retain calibrated test evidence | QHSE Engineer | Trigger: When material arrives, work reaches inspection/test point or nonconformity is identified. Action: The QHSE Engineer completes “Witness required tests and retain calibrated test evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: accepted/rejected status, test evidence, NCR record and verified corrective-action closure. Control/Handoff: No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When material arrives, work reaches inspection/test point or nonconformity is identified. | The QHSE Engineer completes “Witness required tests and retain calibrated test evidence” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | accepted/rejected status, test evidence, NCR record and verified corrective-action closure. | No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he attends the tests that must be witnessed, checks the equipment used is calibrated, and keeps the results as evidence. • Starts when: a test is due under the ITP, or a test is requested to resolve a query or non conformance. • How it runs: (1) he confirms the test method, the equipment and the calibration validity. (2) He witnesses the test being carried out. (3) He records the results against the acceptance criteria. (4) He signs the test record and retains the certificate. (5) He raises a non conformance where the result fails. • Proof it happened: witnessed test records with results, acceptance decision and valid calibration certificates for the equipment used. • Where it usually breaks: a test is carried out with uncalibrated equipment, which makes a passing result worthless and often requires the test to be repeated. | • Require calibration validity to be checked and recorded before the test, since an uncalibrated result cannot be defended. • Name which tests must be witnessed and by whom: internal, consultant, client or third party laboratory. • Require failed results to be recorded and raised, not discarded and repeated, because hidden failures reappear at handover. • Set retention requirements for test certificates so they are available for the closeout dossier without a search. • Require the test location and element to be identified on the record, otherwise the result cannot be tied to the work.
559 | Projects | Raise and control NCR, defect and corrective-action records | QHSE Engineer | Trigger: When material arrives, work reaches inspection/test point or nonconformity is identified. Action: The QHSE Engineer completes “Raise and control NCR, defect and corrective-action records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: accepted/rejected status, test evidence, NCR record and verified corrective-action closure. Control/Handoff: No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When material arrives, work reaches inspection/test point or nonconformity is identified. | The QHSE Engineer completes “Raise and control NCR, defect and corrective-action records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | accepted/rejected status, test evidence, NCR record and verified corrective-action closure. | No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: when work or material does not meet requirements, he raises it formally and tracks the correction through to completion. • Starts when: an inspection, test or observation finds work or material that does not conform. • How it runs: (1) he records the non conformance with the requirement breached and the evidence. (2) He notifies the responsible party and the project manager. (3) He obtains the proposed correction and the cause. (4) He agrees the disposition: rework, repair, accept by concession or reject. (5) He tracks it to closure and records the verification. • Proof it happened: a controlled NCR and defect register with disposition, correction evidence and closure verification. • Where it usually breaks: problems are corrected informally without an NCR, so the same defect recurs and there is no record of the cause. | • Define the threshold at which an issue must become a formal NCR, so informal correction cannot be used to avoid the record. • Require the disposition to be decided by the technical authority, particularly where acceptance by concession is proposed. • Require the cause to be recorded, not just the fix, or the register becomes a defect list with no learning value. • Track NCRs by responsible party and recurrence, since repeat NCRs against one subcontractor are a commercial matter. • Require closure evidence to be attached, because a closed NCR with no evidence fails audit and client review.
560 | Projects | Verify corrective-action effectiveness and formally close QHSE findings | QHSE Engineer | Trigger: When material arrives, work reaches inspection/test point or nonconformity is identified. Action: The QHSE Engineer completes “Verify corrective-action effectiveness and formally close QHSE findings” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: accepted/rejected status, test evidence, NCR record and verified corrective-action closure. Control/Handoff: No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When material arrives, work reaches inspection/test point or nonconformity is identified. | The QHSE Engineer completes “Verify corrective-action effectiveness and formally close QHSE findings” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | accepted/rejected status, test evidence, NCR record and verified corrective-action closure. | No concealment or release occurs without required acceptance; failed test and repeated NCR escalate to Project Engineer, CTO and COO. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he checks that corrective actions actually worked rather than just being marked done, and then closes the finding formally. • Starts when: a corrective action reaches its stated completion, and at scheduled review of open findings. • How it runs: (1) he reviews the action taken against what was required. (2) He verifies the effect physically or through records. (3) He checks whether the problem has recurred since. (4) He closes the finding where it is genuinely resolved. (5) He reopens or escalates where it is not. • Proof it happened: closed findings with verification evidence, and reopened findings where verification failed. • Where it usually breaks: closure is granted on the basis of an email saying the action is complete, so unresolved issues disappear from the register. | • Prohibit closure on self declaration. Require verification by the QHSE engineer with evidence recorded. • Distinguish correction from corrective action in the SOP: fixing the instance is not the same as preventing recurrence. • Require a recurrence check over a stated period before permanent closure of systemic findings. • Set an escalation route for actions overdue beyond a stated period, since ageing open actions are the standard audit failure. • Report closure rate and ageing to management, because the number of open findings alone hides how long they have been open.
561 | Projects | Report and coordinate accident, incident and near-miss response | QHSE Engineer | Trigger: When an accident, incident, near miss, emergency or serious unsafe condition occurs. Action: The QHSE Engineer completes “Report and coordinate accident, incident and near-miss response” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled response, notification, evidence, investigation, root cause and closed preventive action. Control/Handoff: Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When an accident, incident, near miss, emergency or serious unsafe condition occurs. | The QHSE Engineer completes “Report and coordinate accident, incident and near-miss response” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled response, notification, evidence, investigation, root cause and closed preventive action. | Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: when an accident, incident or near miss happens, he coordinates the immediate response and gets it reported properly. • Starts when: any accident, injury, dangerous occurrence, environmental release or near miss occurs. • How it runs: (1) he ensures the casualty is treated and the area made safe. (2) He notifies the project manager and the QHSE function immediately. (3) He records the event with the time, place, persons and immediate facts. (4) He arranges medical referral and support where needed. (5) He initiates the investigation and follow up. • Proof it happened: an incident report with time and factual detail, notification records and medical referral evidence where applicable. • Where it usually breaks: near misses are not reported at all, so the warnings that precede a serious accident are invisible. | • Make near miss reporting explicitly blame free in the SOP, and state that reporting one is never a disciplinary matter. • Set the notification timeline in hours for each severity level, and name who must be informed at each level. • Require the initial report to record facts only, since conclusions written in the first hour distort the investigation. • Define the medical referral route and who authorises it, so treatment is never delayed by an approval question. • Track near miss volume as a positive indicator, because a site reporting none is not a safe site, it is a silent one.
562 | Projects | Secure evidence and support incident investigation and root-cause analysis | QHSE Engineer | Trigger: When an accident, incident, near miss, emergency or serious unsafe condition occurs. Action: The QHSE Engineer completes “Secure evidence and support incident investigation and root-cause analysis” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled response, notification, evidence, investigation, root cause and closed preventive action. Control/Handoff: Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When an accident, incident, near miss, emergency or serious unsafe condition occurs. | The QHSE Engineer completes “Secure evidence and support incident investigation and root-cause analysis” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled response, notification, evidence, investigation, root cause and closed preventive action. | Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: after an incident he protects the evidence and helps establish what actually caused it, not just what happened. • Starts when: immediately after an incident, before the scene is disturbed or cleared. • How it runs: (1) he secures the scene and prevents alteration. (2) He photographs and records the conditions, equipment and layout. (3) He collects statements from those involved and witnesses while memory is fresh. (4) He collects the related documents: permits, method statements, inspections and certificates. (5) He supports the investigation to a root cause rather than stopping at the immediate act. • Proof it happened: preserved evidence, photographs, witness statements and a documented root cause analysis. • Where it usually breaks: the area is cleared and returned to work before evidence is recorded, which makes any later investigation guesswork. | • Require the scene to be preserved until released by the investigation lead, and name who may authorise release. • Set an immediate evidence capture list: photographs, equipment condition, permits, method statement and inspection records. • Require statements to be taken the same day, in the person's own words and in a language they are fluent in. • Require root cause analysis to reach system and management factors, since stopping at unsafe act prevents any real correction. • Keep investigation records confidential and controlled, because they carry legal and insurance consequences.
563 | Projects | Notify management and authorities within required thresholds and timing | QHSE Engineer | Trigger: When an accident, incident, near miss, emergency or serious unsafe condition occurs. Action: The QHSE Engineer completes “Notify management and authorities within required thresholds and timing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled response, notification, evidence, investigation, root cause and closed preventive action. Control/Handoff: Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When an accident, incident, near miss, emergency or serious unsafe condition occurs. | The QHSE Engineer completes “Notify management and authorities within required thresholds and timing” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled response, notification, evidence, investigation, root cause and closed preventive action. | Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he makes sure serious events are reported to management and to the authorities within the legally required time. • Starts when: an incident meets a reportable threshold, or a notification is requested by an authority or the client. • How it runs: (1) he assesses the event against the reporting thresholds. (2) He notifies management immediately for reportable events. (3) He prepares the required notification content with the CLO's input where needed. (4) He submits within the prescribed time limit. (5) He records the submission and any authority response or visit. • Proof it happened: notification records with submission dates, authority acknowledgements and the reporting threshold assessment. • Where it usually breaks: the reporting deadline is missed because the threshold was not recognised at site level, which converts a safety event into a legal one. | • Put the reportable thresholds and their time limits in the SOP as a table, so no judgement is needed at the moment of the incident. • Require legal review before submission for serious events, since the wording of a notification has legal consequences. • Name who is authorised to communicate with authorities, and state that others must not. • Require immediate insurer notification alongside authority notification, because late notice can prejudice cover. • Keep a record of every notification and response, as authority follow up visits are usually driven by these submissions.
564 | Projects | Track incident corrective and preventive actions to closure | QHSE Engineer | Trigger: When an accident, incident, near miss, emergency or serious unsafe condition occurs. Action: The QHSE Engineer completes “Track incident corrective and preventive actions to closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled response, notification, evidence, investigation, root cause and closed preventive action. Control/Handoff: Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When an accident, incident, near miss, emergency or serious unsafe condition occurs. | The QHSE Engineer completes “Track incident corrective and preventive actions to closure” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled response, notification, evidence, investigation, root cause and closed preventive action. | Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he makes sure the actions decided after an incident are actually completed, so the same thing does not happen again. • Starts when: an investigation produces corrective and preventive actions. • How it runs: (1) he records each action with an owner and a due date. (2) He tracks progress and chases overdue items. (3) He verifies completion with evidence. (4) He escalates actions that stay overdue. (5) He closes the incident only when the actions are complete and verified. • Proof it happened: an incident action tracker with owners, due dates, verification evidence and closure status. • Where it usually breaks: the investigation report is filed as the end of the process, and the actions in it are never tracked. | • State that an incident is not closed until its actions are verified complete, and separate report closure from incident closure. • Require preventive actions to be applied across the company where relevant, not just on the project where the incident happened. • Set escalation for overdue safety actions at a lower threshold than other actions, given the consequence. • Report open incident actions to management monthly, because these are the actions most likely to be quietly dropped. • Require verification evidence per action, so completion is demonstrated rather than declared.
565 | Projects | Conduct emergency drills and update response arrangements | QHSE Engineer | Trigger: When an accident, incident, near miss, emergency or serious unsafe condition occurs. Action: The QHSE Engineer completes “Conduct emergency drills and update response arrangements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: controlled response, notification, evidence, investigation, root cause and closed preventive action. Control/Handoff: Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When an accident, incident, near miss, emergency or serious unsafe condition occurs. | The QHSE Engineer completes “Conduct emergency drills and update response arrangements” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | controlled response, notification, evidence, investigation, root cause and closed preventive action. | Life safety takes priority; required management and authority notifications follow thresholds and no evidence is altered or omitted. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he runs practice emergencies so people know what to do, and updates the arrangements based on what the drill reveals. • Starts when: at the frequency set in the HSE plan, after significant site changes, and after any real emergency. • How it runs: (1) he plans the drill scenario and informs the necessary parties. (2) He runs the drill and observes the response. (3) He records the evacuation time, headcount and problems observed. (4) He debriefs the site team on what failed. (5) He updates the emergency arrangements and re briefs. • Proof it happened: drill records with timings, headcount reconciliation, observations and the resulting updates to the arrangements. • Where it usually breaks: the drill is recorded as successful without reconciling the headcount, so nobody knows whether everyone actually got out. | • Require headcount reconciliation against the site attendance record as the primary drill outcome, not the evacuation time. • Require at least one unannounced drill per period, since announced drills test compliance rather than readiness. • Vary the scenario across drills: fire, medical, confined space rescue, spill and severe weather. • Require the debrief findings to result in updated arrangements, otherwise the same failures repeat at every drill. • Include subcontractors and visitors in the drill, as they are the group most likely to be unaccounted for.
566 | Projects | Prepare daily and weekly QHSE performance reports | QHSE Engineer | Trigger: When the shift, task or inspection point is completed. Action: The QHSE Engineer completes “Prepare daily and weekly QHSE performance reports” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The QHSE Engineer completes “Prepare daily and weekly QHSE performance reports” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he reports what is happening on safety and quality, daily to the site team and weekly to management. • Starts when: daily and weekly on the reporting schedule, and immediately for serious matters. • How it runs: (1) he compiles the inspections, findings, permits, incidents and inspection results for the period. (2) He states the open items and the ones overdue. (3) He highlights the matters needing management decision. (4) He issues the report to the project manager and the QHSE function. (5) He tracks the actions arising. • Proof it happened: issued daily and weekly QHSE reports with findings, status and escalations, and the resulting actions. • Where it usually breaks: the report becomes a list of activity, so management cannot tell whether risk is rising or falling. | • Require the report to state trend and exception, not activity volume. Numbers of inspections done tell management nothing. • Fix the report template so it is comparable week to week and can be consolidated across projects. • Require overdue and repeat items to be shown separately, since these are the ones management must act on. • Name the escalation items that must be reported immediately rather than waiting for the weekly cycle. • Require the report to be built from the inspection and NCR registers, so the report and the records cannot disagree.
567 | Projects | Maintain QHSE KPIs, audit findings and overdue-action dashboard | QHSE Engineer | Trigger: When the shift, task or inspection point is completed. Action: The QHSE Engineer completes “Maintain QHSE KPIs, audit findings and overdue-action dashboard” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The QHSE Engineer completes “Maintain QHSE KPIs, audit findings and overdue-action dashboard” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he maintains the safety and quality measures for the project, including audit findings and what is overdue. • Starts when: at the reporting cycle, and after each audit or inspection round. • How it runs: (1) he maintains the agreed indicators: incident rates, inspection closure, NCR volumes, first time pass rates and training compliance. (2) He records audit findings with owners and dates. (3) He maintains a visible overdue action list. (4) He reviews the trends with the project manager. (5) He escalates deteriorating indicators. • Proof it happened: a maintained QHSE dashboard with indicators, audit findings and an overdue action list, reviewed with management. • Where it usually breaks: indicators are collected but never reviewed, so the dashboard exists and nothing changes as a result of it. | • Require a scheduled review of the dashboard with the project manager, with decisions recorded. A dashboard with no review is decoration. • Define each indicator's calculation in the SOP, so figures are comparable between projects and periods. • Include leading indicators such as near miss reporting and inspection closure, not only lagging incident counts. • Require an ageing view of overdue actions rather than a count, since age is what indicates loss of control. • Set thresholds that trigger escalation automatically, so deterioration does not depend on someone raising it.
568 | Projects | Compile inspection, test, material and NCR closeout records | QHSE Engineer | Trigger: When the shift, task or inspection point is completed. Action: The QHSE Engineer completes “Compile inspection, test, material and NCR closeout records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The QHSE Engineer completes “Compile inspection, test, material and NCR closeout records” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he assembles all the inspection, test, material and non conformance records the project must hand over at the end. • Starts when: progressively through the project, and intensively as closeout approaches. • How it runs: (1) he collects the records against the ITP and the specification requirements. (2) He checks each record is signed, dated and traceable to the work. (3) He identifies missing records and chases them. (4) He organises the records into the required dossier structure. (5) He verifies completeness against the requirement list before submission. • Proof it happened: a compiled and indexed closeout record set with a completeness check against the requirement list. • Where it usually breaks: compilation only starts at the end, and by then the people who signed the records and the subcontractors who hold them have left. | • Require progressive compilation with a stated completeness percentage reported monthly, since end loading this task is the standard cause of handover delay. • Make record submission a condition of subcontractor payment, because chasing records after demobilisation rarely succeeds. • Require records to be traceable to location and element, otherwise the dossier cannot be verified. • Agree the dossier structure with the client early, so it is not rebuilt at the end to a different format. • Track missing records as a named list with owners rather than as a general gap, so they can actually be closed.
569 | Projects | Support testing, commissioning, snag and final-inspection readiness | QHSE Engineer | Trigger: When the shift, task or inspection point is completed. Action: The QHSE Engineer completes “Support testing, commissioning, snag and final-inspection readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The QHSE Engineer completes “Support testing, commissioning, snag and final-inspection readiness” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he supports the testing, commissioning and snagging stage, making sure the quality and safety side is ready for final inspection. • Starts when: work packages reach completion and testing and commissioning begins. • How it runs: (1) he verifies the pre commissioning checks and prerequisites are complete. (2) He witnesses the required tests and records the results. (3) He raises snags found and tracks their correction. (4) He verifies the closed snags physically. (5) He confirms readiness for final inspection. • Proof it happened: witnessed commissioning test records, a snag list with closure verification and a readiness confirmation for final inspection. • Where it usually breaks: final inspection is requested with snags still open, and the resulting failure delays handover for everyone. | • Require snag closure verification before final inspection is requested, and name who confirms readiness. • Require snags to be raised against a location and a responsible party, since unattributed snags do not get closed. • Verify commissioning prerequisites before tests start, because failed tests due to incomplete prerequisites waste specialist attendance. • Keep a single consolidated snag list, as parallel lists held by different parties always diverge. • Report snag closure rate weekly during closeout, because this is the metric that determines the handover date.
570 | Projects | Handover the approved quality and HSE closeout dossier | QHSE Engineer | Trigger: When the shift, task or inspection point is completed. Action: The QHSE Engineer completes “Handover the approved quality and HSE closeout dossier” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. Output/Evidence: attendance, quantity, status, resource request and work-front handover evidence. Control/Handoff: Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. Continuity/Escalation: A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. Timing: To be confirmed. | When the shift, task or inspection point is completed. | The QHSE Engineer completes “Handover the approved quality and HSE closeout dossier” using approved IFC/contract inputs, project procedures, FirstBit/controlled registers and verified site evidence. | attendance, quantity, status, resource request and work-front handover evidence. | Records are handed to the Site Engineer before cutoff; incomplete or disputed output is checked before inclusion in progress reporting. | A competent authorised QHSE professional may provide backup; imminent danger, serious incident, legal breach, failed critical test or repeated NCR escalates immediately to the Project Engineer and COO. | To be confirmed. | • In plain words: he hands over the completed quality and safety dossier at the end of the project, formally and against a checklist. • Starts when: closeout records are complete and the project is ready for handover. • How it runs: (1) he completes the final completeness check against the requirement list. (2) He obtains internal approval of the dossier. (3) He submits it to the consultant or client for review. (4) He resolves review comments and resubmits where required. (5) He obtains the acknowledgement of acceptance and archives the approved dossier. • Proof it happened: an approved and acknowledged closeout dossier with a completeness checklist and the archived controlled copy. • Where it usually breaks: handover is treated as delivery of files, and the acceptance acknowledgement is never obtained, leaving the obligation technically open. | • Require a written acceptance acknowledgement from the client, since without it the handover obligation stays open and can block final payment. • Require internal approval of the dossier before submission, so review comments are not the company's first quality check. • Keep an archived controlled copy in the company's own records, because dossiers submitted and not retained cannot be produced in a later dispute. • Link dossier acceptance to the final payment and retention release milestones in the SOP, so the commercial value of the task is visible. • Record the closeout lessons for the next project, particularly the records that were hardest to obtain.
571 | Procurement | Set Procurement strategy, policies and annual operating objectives | Chief Procurement Officer (CPO) | Trigger: When the annual planning cycle, policy review, authority review or material control concern requires direction. Action: The Chief Procurement Officer (CPO) completes “Set Procurement strategy, policies and annual operating objectives” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement policy, authority decision, ethical-control action or controlled template. Control/Handoff: The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority review or material control concern requires direction. | The Chief Procurement Officer (CPO) completes “Set Procurement strategy, policies and annual operating objectives” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement policy, authority decision, ethical-control action or controlled template. | The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how the company buys, meaning what procurement is trying to achieve for the year and the rules everyone must follow to get there. • Starts when: the annual planning cycle opens, or the business changes enough that the buying approach no longer fits. • How it runs: (1) he reviews what the business plan will require in materials, subcontracts and services. (2) He sets the sourcing approach and the annual objectives for the function. (3) He drafts or updates the procurement policy. (4) He gets the CEO's approval. (5) He issues it to the team and the departments who raise demand. • Proof it happened: an approved procurement strategy and policy for the year, with objectives and targets stated. • Where it usually breaks: the strategy is written for the function alone and never linked to the project pipeline, so buying is reactive all year. | • Require the strategy to be built from the project pipeline and the budget, so it commits to specific categories and volumes rather than intentions. • Set measurable objectives: savings, on time delivery, cycle time and single source percentage. Objectives without measures cannot be reviewed. • State the policy review frequency and who may propose changes, so the policy does not become stale and worked around. • Require the policy to be issued to requesting departments, not only to procurement, since most breaches start with the requester. • Add a link to the delegation of authority so the strategy and the approval limits are reviewed together.
572 | Procurement | Approve the procurement-control framework, Delegation of Authority and segregation of duties | Chief Procurement Officer (CPO) | Trigger: When the annual planning cycle, policy review, authority review or material control concern requires direction. Action: The Chief Procurement Officer (CPO) completes “Approve the procurement-control framework, Delegation of Authority and segregation of duties” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement policy, authority decision, ethical-control action or controlled template. Control/Handoff: The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority review or material control concern requires direction. | The Chief Procurement Officer (CPO) completes “Approve the procurement-control framework, Delegation of Authority and segregation of duties” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement policy, authority decision, ethical-control action or controlled template. | The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets who can approve what in buying, and makes sure the same person cannot request, approve, order and pay. • Starts when: the authority framework is set up, and whenever roles, limits or the organisation change. • How it runs: (1) he maps the procurement steps from request to payment. (2) He assigns each step to a role and sets the value limits. (3) He checks no single role holds two conflicting steps. (4) He gets the CEO and CFO to approve. (5) He configures the system to enforce it and issues the matrix. • Proof it happened: an approved procurement authority matrix with segregation of duties defined and reflected in the system settings. • Where it usually breaks: the matrix says one thing and the system permissions allow another, so the control exists only on paper. | • Require the system permissions to be reconciled against the approved matrix, with a periodic check. A control not enforced in the system is not a control. • Name the four steps that must never sit with one person: raising demand, approving, ordering and receiving. Add payment release as a fifth held by Finance. • Define the temporary delegation route with an end date and a written record, because absence cover is where segregation quietly collapses. • State the treatment of splitting orders to stay under a limit, and make it an explicit disciplinary matter. • Require an exception log for anything approved outside the matrix, reviewed by the CFO.
573 | Procurement | Approve ethical-sourcing, conflict-of-interest, gifts and anti-bribery controls | Chief Procurement Officer (CPO) | Trigger: When the annual planning cycle, policy review, authority review or material control concern requires direction. Action: The Chief Procurement Officer (CPO) completes “Approve ethical-sourcing, conflict-of-interest, gifts and anti-bribery controls” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement policy, authority decision, ethical-control action or controlled template. Control/Handoff: The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority review or material control concern requires direction. | The Chief Procurement Officer (CPO) completes “Approve ethical-sourcing, conflict-of-interest, gifts and anti-bribery controls” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement policy, authority decision, ethical-control action or controlled template. | The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the rules that keep buying honest, covering conflicts of interest, gifts, hospitality and bribery. • Starts when: the control framework is established, and at least annually thereafter or after any incident. • How it runs: (1) he defines what must be declared and by whom. (2) He sets the gift and hospitality thresholds and the register. (3) He requires annual declarations from everyone involved in sourcing. (4) He gets the CLO and CEO to approve. (5) He briefs the team and the suppliers on the standard expected. • Proof it happened: approved ethical sourcing and anti bribery rules, a declarations register and a gifts and hospitality register. • Where it usually breaks: declarations are collected once at joining and never refreshed, so relationships formed later are never disclosed. | • Require annual re declaration by everyone in a sourcing or approval role, not a one time declaration at joining. • Set a monetary gift threshold and require registration of anything above it, with refusal as the default for tender period gifts. • State that a declared conflict removes the person from that evaluation entirely, rather than being managed informally. • Communicate the standard to suppliers in writing at prequalification, so the expectation is contractual rather than assumed. • Provide a confidential reporting route for suspected corruption, since the people who see it are usually junior to those involved.
574 | Procurement | Approve vendor-governance, prequalification, suspension and blacklisting rules | Chief Procurement Officer (CPO) | Trigger: When the annual planning cycle, policy review, authority review or material control concern requires direction. Action: The Chief Procurement Officer (CPO) completes “Approve vendor-governance, prequalification, suspension and blacklisting rules” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement policy, authority decision, ethical-control action or controlled template. Control/Handoff: The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority review or material control concern requires direction. | The Chief Procurement Officer (CPO) completes “Approve vendor-governance, prequalification, suspension and blacklisting rules” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement policy, authority decision, ethical-control action or controlled template. | The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the rules for who may become a supplier, how they are checked, and how they get suspended or removed if they fail. • Starts when: the vendor governance framework is set up, and when repeated supplier failures force a review. • How it runs: (1) he defines the prequalification criteria by category and risk. (2) He sets the documents required: trade licence, tax registration, insurance, financial and technical evidence. (3) He defines the approval route for adding a vendor. (4) He sets the grounds and process for suspension and blacklisting. (5) He gets approval and issues the rules. • Proof it happened: approved vendor governance rules with prequalification criteria, and a documented suspension and blacklisting process. • Where it usually breaks: vendors are added under time pressure with documents promised later, and the documents never arrive. | • Prohibit provisional vendor creation with documents pending, or state a hard expiry after which the vendor is blocked automatically. • Set differentiated prequalification by risk and value, so low value suppliers are not held to the same burden as structural subcontractors. • Require document expiry tracking for licences, insurance and certifications, since lapsed documents are the common failure rather than missing ones. • Define blacklisting grounds precisely and require CLO review, because a blacklisting decision carries legal exposure. • Require periodic revalidation of active vendors, not just approval at onboarding.
575 | Procurement | Approve standard RFQ, purchase-order, subcontract and procurement-record templates | Chief Procurement Officer (CPO) | Trigger: When the annual planning cycle, policy review, authority review or material control concern requires direction. Action: The Chief Procurement Officer (CPO) completes “Approve standard RFQ, purchase-order, subcontract and procurement-record templates” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement policy, authority decision, ethical-control action or controlled template. Control/Handoff: The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority review or material control concern requires direction. | The Chief Procurement Officer (CPO) completes “Approve standard RFQ, purchase-order, subcontract and procurement-record templates” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement policy, authority decision, ethical-control action or controlled template. | The CPO records decisions, protects competition and segregation of duties, and escalates reserved, related-party or material matters to the CEO, CFO or CLO. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the standard documents the company buys with, so every enquiry and order carries the same protections. • Starts when: the templates are first established, and when law, contract terms or repeated disputes require revision. • How it runs: (1) he identifies the documents needed: RFQ, purchase order, subcontract, evaluation and award records. (2) He works with the CLO on the terms and conditions. (3) He standardises the commercial fields: delivery, payment, warranty and liquidated damages. (4) He approves and issues the templates. (5) He withdraws superseded versions. • Proof it happened: approved and version controlled procurement templates issued for use, with old versions withdrawn. • Where it usually breaks: buyers keep personal copies of old templates, so orders go out with outdated or missing terms. | • Require templates to be issued from a single controlled location and prohibit personal copies, since template drift is invisible until a dispute. • State which fields a buyer may edit and which are locked, particularly the legal terms, and name who may authorise a deviation. • Require the terms and conditions to be attached or referenced on every order, because an order without terms defaults to the supplier's terms. • Set a review cycle with the CLO, so legal and tax changes reach the templates. • Keep a version history, as knowing which terms applied at a given date matters in any claim.
576 | Procurement | Approve project procurement strategy and work-package structure | Chief Procurement Officer (CPO) | Trigger: When a new project, annual category review, procurement-plan update or critical sourcing need is approved. Action: The Chief Procurement Officer (CPO) completes “Approve project procurement strategy and work-package structure” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. Control/Handoff: Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a new project, annual category review, procurement-plan update or critical sourcing need is approved. | The Chief Procurement Officer (CPO) completes “Approve project procurement strategy and work-package structure” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. | Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: for each project he approves how the buying will be broken up into packages and who will be asked to price them. • Starts when: a project is awarded, and again when the scope or programme changes materially. • How it runs: (1) he reviews the project scope, budget and programme with the Project team. (2) He decides the package breakdown: what is bought as material, what is subcontracted, what is self performed. (3) He sets the sourcing route for each package. (4) He confirms the strategy with the COO and the project manager. (5) He issues it as the basis for the procurement schedule. • Proof it happened: an approved project procurement strategy with the package structure and sourcing route per package. • Where it usually breaks: package boundaries leave gaps in scope, and the missing work is discovered on site as a variation with no supplier responsible. | • Require an interface check across package boundaries, with a named owner for every scope element, so gaps are found before award and not on site. • State the decision basis for subcontracting versus self performing, since this is usually decided by habit rather than analysis. • Require the strategy to be signed by both procurement and the project manager, because a strategy imposed by one side is not followed. • Include the client's nominated supplier or approved vendor obligations, as these override the company's own sourcing choices. • Revisit the strategy when scope changes, otherwise the package structure stops matching the work.
577 | Procurement | Approve the programme-linked procurement schedule and long-lead register | Chief Procurement Officer (CPO) | Trigger: When a new project, annual category review, procurement-plan update or critical sourcing need is approved. Action: The Chief Procurement Officer (CPO) completes “Approve the programme-linked procurement schedule and long-lead register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. Control/Handoff: Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a new project, annual category review, procurement-plan update or critical sourcing need is approved. | The Chief Procurement Officer (CPO) completes “Approve the programme-linked procurement schedule and long-lead register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. | Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the buying timetable tied to the construction programme, and the list of items that take a long time to get. • Starts when: at project start once the programme is available, and updated as the programme is revised. • How it runs: (1) he takes the required on site dates from the programme. (2) He works backwards through delivery, manufacture, approval and tender time to set the award dates. (3) He identifies the long lead items and flags the ones already at risk. (4) He agrees the schedule with the project team. (5) He tracks it and escalates slippage. • Proof it happened: an approved procurement schedule aligned to the programme, with a long lead register showing required dates and status. • Where it usually breaks: the schedule is built from procurement's own convenience rather than backwards from site need, so awards happen too late. | • Require every procurement date to be derived backwards from the site requirement date, with each lead time component stated separately. • Require submittal and approval time to be included explicitly, since consultant approval is frequently the longest element and is usually omitted. • Define what qualifies as long lead by weeks, so the register is populated by rule and not by opinion. • Escalate long lead items automatically when float drops below a stated threshold, rather than waiting for a status meeting. • Reissue the schedule whenever the programme is rebaselined, otherwise procurement works to a superseded plan.
578 | Procurement | Approve category, framework, local and international sourcing strategies | Chief Procurement Officer (CPO) | Trigger: When a new project, annual category review, procurement-plan update or critical sourcing need is approved. Action: The Chief Procurement Officer (CPO) completes “Approve category, framework, local and international sourcing strategies” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. Control/Handoff: Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a new project, annual category review, procurement-plan update or critical sourcing need is approved. | The Chief Procurement Officer (CPO) completes “Approve category, framework, local and international sourcing strategies” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. | Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides which categories are bought through framework agreements, which are bought locally, and which are imported. • Starts when: at strategy setting, and when market conditions, prices or supply reliability change. • How it runs: (1) he analyses spend by category and the supply market for each. (2) He decides where framework or annual agreements make sense. (3) He weighs local supply against import on cost, lead time and risk. (4) He gets approval for the agreements that commit the company. (5) He communicates the sourcing route so buyers follow it. • Proof it happened: approved category sourcing strategies and framework agreements, with the sourcing route defined per category. • Where it usually breaks: framework agreements are signed but buyers keep going to their familiar suppliers, so the negotiated rates are never used. | • Require compliance monitoring against framework agreements, reporting off contract spend by buyer, or the agreements deliver nothing. • Include total landed cost for imports: freight, duty, clearance, insurance and inland transport, since unit price comparison misleads badly here. • State the volume commitments and their consequences, because unmet commitments can carry price adjustment clauses. • Set a market review frequency per category, as commodity categories move faster than the strategy cycle. • Require an exit and transition plan for critical framework agreements, so the company is not trapped by its own arrangement.
579 | Procurement | Approve competitive-tender, single-source, sole-source and emergency procurement routes | Chief Procurement Officer (CPO) | Trigger: When a new project, annual category review, procurement-plan update or critical sourcing need is approved. Action: The Chief Procurement Officer (CPO) completes “Approve competitive-tender, single-source, sole-source and emergency procurement routes” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. Control/Handoff: Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a new project, annual category review, procurement-plan update or critical sourcing need is approved. | The Chief Procurement Officer (CPO) completes “Approve competitive-tender, single-source, sole-source and emergency procurement routes” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. | Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides when the company must run a competitive tender and when it may buy from a single supplier, including in emergencies. • Starts when: the framework is set, and each time a request comes for a non competitive route. • How it runs: (1) he sets the value thresholds requiring competition and the minimum number of quotations. (2) He defines the grounds for single source and sole source. (3) He defines the emergency route and who may authorise it. (4) He requires written justification for any non competitive award. (5) He reviews the use of exceptions periodically. • Proof it happened: approved sourcing route rules with thresholds, and justified and approved records for every non competitive award. • Where it usually breaks: emergency procurement becomes routine, and a large share of spend ends up awarded without competition. | • Track the percentage of spend awarded non competitively as a reported measure, since this is the clearest indicator of control loss. • Distinguish single source, meaning a choice, from sole source, meaning no alternative exists, as they need different justification. • Require emergency awards to be ratified afterwards by the normal authority, with the cause of the emergency recorded. • State that poor planning is not a valid emergency ground, because most emergencies are late requests rather than genuine urgency. • Require price reasonableness evidence for non competitive awards, such as a prior price or a benchmark, since competition is absent.
580 | Procurement | Approve Procurement resource, system, capability and annual improvement plans | Chief Procurement Officer (CPO) | Trigger: When a new project, annual category review, procurement-plan update or critical sourcing need is approved. Action: The Chief Procurement Officer (CPO) completes “Approve Procurement resource, system, capability and annual improvement plans” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. Control/Handoff: Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a new project, annual category review, procurement-plan update or critical sourcing need is approved. | The Chief Procurement Officer (CPO) completes “Approve Procurement resource, system, capability and annual improvement plans” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved procurement strategy, package plan, sourcing route, resource plan or long-lead control. | Planning must link IFC/BOQ, budget and required-on-site dates; programme, technical or budget conflicts are resolved with COO, CTO and CFO before commitment. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he plans what the procurement function needs to work properly: people, systems, skills and the improvements for the year. • Starts when: during annual planning, and when workload or capability gaps become visible. • How it runs: (1) he assesses the workload against the project pipeline. (2) He identifies resource and skill gaps. (3) He sets the system and tool needs, including FirstBit. (4) He builds the improvement plan with owners and dates. (5) He gets budget approval and tracks delivery. • Proof it happened: an approved procurement resource and capability plan with an improvement plan showing owners and target dates. • Where it usually breaks: the plan is approved but the improvement actions are the first thing dropped when the workload rises. | • Protect improvement time explicitly, since improvement work is always displaced by transactional workload without a stated allocation. • Base resourcing on transaction volume and package count from the pipeline, not on headcount history. • Include cover and succession for critical roles, because procurement knowledge is concentrated and rarely documented. • Set specific capability targets by category, particularly for technically complex packages where buyers cannot evaluate offers. • Review the improvement plan quarterly with the CEO, so it stays visible above day to day pressure.
581 | Procurement | Approve supplier and subcontractor selections within delegated authority | Chief Procurement Officer (CPO) | Trigger: When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. Action: The Chief Procurement Officer (CPO) completes “Approve supplier and subcontractor selections within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an authorised selection, award, commitment or escalated approval decision. Control/Handoff: No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. | The Chief Procurement Officer (CPO) completes “Approve supplier and subcontractor selections within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an authorised selection, award, commitment or escalated approval decision. | No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he chooses which supplier or subcontractor wins, for awards that fall within the limits he is allowed to approve. • Starts when: an evaluation is complete and a recommendation is submitted for award. • How it runs: (1) he reviews the evaluation against the stated criteria. (2) He checks the commercial comparison is like for like and the qualifications are resolved. (3) He confirms the supplier is prequalified and has capacity. (4) He checks the value is within his authority. (5) He approves the award and records the reason for the choice. • Proof it happened: a signed award recommendation with the evaluation, the comparison and the reason for selection recorded. • Where it usually breaks: the award reason is recorded as lowest price when other factors actually decided it, which makes later challenges hard to defend. | • Require the actual award reason to be recorded, including where the lowest price was not selected, since an unexplained deviation looks like favouritism. • Require the technical evaluation to be completed before commercial offers are opened, so price does not influence technical judgement. • Verify prequalification status and document validity at award, not just at the enquiry stage. • Require capacity confirmation for suppliers already holding several of the company's packages, as concentration causes delivery failure. • Confirm the value against the authority limit including options and contingencies, not just the base amount.
582 | Procurement | Approve purchase orders within delegated authority | Chief Procurement Officer (CPO) | Trigger: When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. Action: The Chief Procurement Officer (CPO) completes “Approve purchase orders within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an authorised selection, award, commitment or escalated approval decision. Control/Handoff: No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. | The Chief Procurement Officer (CPO) completes “Approve purchase orders within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an authorised selection, award, commitment or escalated approval decision. | No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves purchase orders up to his limit, which is the point where the company legally commits its money. • Starts when: a purchase order is prepared and submitted for approval. • How it runs: (1) he checks the order matches the approved requisition and the award. (2) He verifies the prices, terms and delivery match what was agreed. (3) He confirms the budget is available and the value is within his authority. (4) He approves the order for issue. (5) He ensures the order is issued to the supplier and recorded. • Proof it happened: an approved purchase order with the requisition, award and budget confirmation traceable behind it. • Where it usually breaks: an order is raised after the goods have already arrived, so the approval is a formality covering a commitment already made. | • Report retrospective orders as a controlled exception with the requester named, since an order raised after delivery removes all commercial leverage. • Require the order value to be checked against the remaining budget line, not the total budget, before approval. • Require the payment terms on the order to match the agreed terms, because supplier standard terms frequently reappear at order stage. • State the tolerance allowed between requisition and order value, and require reapproval above it. • Require order acknowledgement from the supplier, otherwise delivery dates are assumed rather than confirmed.
583 | Procurement | Approve subcontractor appointments and subcontract awards within delegated authority | Chief Procurement Officer (CPO) | Trigger: When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. Action: The Chief Procurement Officer (CPO) completes “Approve subcontractor appointments and subcontract awards within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an authorised selection, award, commitment or escalated approval decision. Control/Handoff: No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. | The Chief Procurement Officer (CPO) completes “Approve subcontractor appointments and subcontract awards within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an authorised selection, award, commitment or escalated approval decision. | No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the appointment of subcontractors and the contracts they sign, within his authority. • Starts when: a subcontract award is recommended and the contract documents are prepared. • How it runs: (1) he reviews the selection and the commercial terms. (2) He checks the scope, programme and payment terms match the main contract obligations. (3) He confirms the CLO has reviewed the contract wording. (4) He verifies insurance, bonds and guarantees are in place. (5) He approves the appointment and the contract for signature. • Proof it happened: a signed subcontract with legal review evidence, insurance and bond confirmation, and the award approval behind it. • Where it usually breaks: the subcontract is signed without back to back terms, so obligations the company owes the client are not passed down. | • Require a back to back check against the main contract on programme, liquidated damages, defects liability, payment terms and notice periods. • Require insurance and bond verification before mobilisation, not before payment, since an uninsured subcontractor on site is an immediate exposure. • Require CLO review for all subcontracts above a stated value or risk level, and state which clauses may never be amended. • Prohibit mobilisation before contract signature, and name who may authorise an exception in writing with a deadline. • Require the scope to be defined by drawings and specification references, since scope by description alone generates variation claims.
584 | Procurement | Approve material commercial deviations, negotiated terms and award qualifications | Chief Procurement Officer (CPO) | Trigger: When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. Action: The Chief Procurement Officer (CPO) completes “Approve material commercial deviations, negotiated terms and award qualifications” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an authorised selection, award, commitment or escalated approval decision. Control/Handoff: No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. | The Chief Procurement Officer (CPO) completes “Approve material commercial deviations, negotiated terms and award qualifications” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an authorised selection, award, commitment or escalated approval decision. | No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when a supplier will not accept standard terms, he decides whether the change is acceptable and what it costs the company. • Starts when: a supplier submits qualifications, or negotiation produces terms that differ from the standard. • How it runs: (1) he identifies the deviations from standard terms. (2) He assesses the commercial and legal exposure each creates. (3) He takes the CLO's advice on the material ones. (4) He negotiates them out or accepts them with a recorded justification. (5) He records the accepted deviations against the award. • Proof it happened: a recorded schedule of accepted deviations with the justification and the legal advice where taken. • Where it usually breaks: supplier qualifications are attached to the order without being read, so the company unknowingly accepts limited liability or extended delivery. | • Require every supplier qualification to be listed and explicitly accepted or rejected, since silent acceptance is the standard failure here. • Name the terms that may never be conceded without CLO and CFO approval: liability caps, warranty reduction, payment in advance and delivery without penalty. • Require the cost or risk of each accepted deviation to be quantified where possible, so the true award comparison is visible. • Maintain a register of accepted deviations by supplier, because concessions granted once are demanded again. • Require the final order to state the agreed position, so the file does not contain conflicting documents.
585 | Procurement | Approve procurement commitments above authority through the required CEO, CFO or Legal route | Chief Procurement Officer (CPO) | Trigger: When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. Action: The Chief Procurement Officer (CPO) completes “Approve procurement commitments above authority through the required CEO, CFO or Legal route” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an authorised selection, award, commitment or escalated approval decision. Control/Handoff: No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a complete comparison, recommendation, purchase order or subcontract award reaches the approval gate. | The Chief Procurement Officer (CPO) completes “Approve procurement commitments above authority through the required CEO, CFO or Legal route” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an authorised selection, award, commitment or escalated approval decision. | No commitment is released without technical compliance, budget, competition or approved exception, commercial checks and the correct Delegation of Authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when a commitment is bigger than his own authority, he takes it through the proper route to the CEO, CFO or Legal. • Starts when: a procurement commitment exceeds his delegated limit, or falls into a category requiring higher approval. • How it runs: (1) he confirms the value and the applicable authority level. (2) He prepares the submission with the evaluation, the recommendation and the risks. (3) He obtains the CFO's funding confirmation. (4) He obtains the CLO's review where contractual risk requires it. (5) He obtains the approval and only then releases the commitment. • Proof it happened: an approval submission with the recommendation and risks, and the signed higher level approval before commitment. • Where it usually breaks: work starts or an order is issued while the higher approval is still in progress, on the assumption it will be granted. | • State plainly that no commitment may be made in anticipation of approval, and name the consequence, because this is the most common authority breach. • Require the submission to state the risks and the alternatives considered, not only the recommendation, so the approver can actually decide. • Set a service level for approval turnaround, since slow approval is the reason people commit early. • Require aggregate exposure with the same supplier to be shown, as individual orders below the limit can total well above it. • Require the approved value to be recorded against the commitment so subsequent variations are measured from it.
586 | Procurement | Review critical-path procurement status and direct supply-recovery actions | Chief Procurement Officer (CPO) | Trigger: When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. Action: The Chief Procurement Officer (CPO) completes “Review critical-path procurement status and direct supply-recovery actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved recovery, value-engineering, replacement, claim or risk-treatment decision. Control/Handoff: The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. | The Chief Procurement Officer (CPO) completes “Review critical-path procurement status and direct supply-recovery actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved recovery, value-engineering, replacement, claim or risk-treatment decision. | The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he watches the purchases that the construction programme depends on, and pushes to recover any that are running late. • Starts when: at the agreed review frequency, and immediately when a critical delivery is reported at risk. • How it runs: (1) he reviews the critical path items against their required dates. (2) He identifies which are late or at risk. (3) He establishes the cause with the buyer and the supplier. (4) He directs recovery action: expediting, alternative source, partial delivery or air freight. (5) He informs the project team of the revised position. • Proof it happened: a critical procurement status review with recovery actions directed, owners and revised dates. • Where it usually breaks: recovery action is decided but the cost of it is never approved, so the action does not actually happen. | • Require the recovery cost to be quantified and approved as part of the decision, since expediting and air freight need funding to be real. • Require the supplier's revised date to be confirmed in writing, not accepted verbally from a sales contact. • Escalate to the project manager and the COO when a recovery will not restore the required date, so the programme can be replanned. • Track recovery actions to closure, as the status meeting otherwise repeats the same at risk items indefinitely. • Record the cause of each critical delay, because the pattern usually points at late requisitioning rather than supplier failure.
587 | Procurement | Review committed cost, procurement variance, savings and cost-avoidance performance | Chief Procurement Officer (CPO) | Trigger: When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. Action: The Chief Procurement Officer (CPO) completes “Review committed cost, procurement variance, savings and cost-avoidance performance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved recovery, value-engineering, replacement, claim or risk-treatment decision. Control/Handoff: The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. | The Chief Procurement Officer (CPO) completes “Review committed cost, procurement variance, savings and cost-avoidance performance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved recovery, value-engineering, replacement, claim or risk-treatment decision. | The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he checks how procurement is performing against budget, what has been committed, and what savings have actually been achieved. • Starts when: monthly at the reporting cycle, and at project cost review points. • How it runs: (1) he reviews committed cost against budget by category and project. (2) He identifies variances and their causes. (3) He reviews claimed savings against a defined baseline. (4) He challenges savings that are not verifiable. (5) He reports the position and directs corrective action. • Proof it happened: a procurement performance report showing commitment against budget, variance causes and verified savings. • Where it usually breaks: savings are claimed against the first quotation received, which is not a baseline and inflates the reported figure. | • Define the savings baseline precisely: budget, previous price paid or an independent benchmark. Never the first quotation received. • Require the CFO to validate reported savings, because unvalidated savings numbers damage credibility with the whole executive. • Separate cost avoidance from actual savings in reporting, since only one of them reduces spend. • Report committed cost rather than invoiced cost, because commitment is where budget is actually consumed. • Require variance explanations by cause, such as scope change, price movement or specification change, so the response can be targeted.
588 | Procurement | Approve value-engineering and alternative-source recommendations with Technical Engineering | Chief Procurement Officer (CPO) | Trigger: When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. Action: The Chief Procurement Officer (CPO) completes “Approve value-engineering and alternative-source recommendations with Technical Engineering” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved recovery, value-engineering, replacement, claim or risk-treatment decision. Control/Handoff: The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. | The Chief Procurement Officer (CPO) completes “Approve value-engineering and alternative-source recommendations with Technical Engineering” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved recovery, value-engineering, replacement, claim or risk-treatment decision. | The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he works with engineering to find cheaper or better alternatives that still meet the specification. • Starts when: a cost pressure is identified, a specified item is unavailable, or a supplier proposes an alternative. • How it runs: (1) he identifies the high value or problem items worth reviewing. (2) He asks Technical Engineering to assess the proposed alternative. (3) He confirms the alternative meets the specification and any client approval requirement. (4) He quantifies the saving and the risks. (5) He obtains the technical and client approvals before award. • Proof it happened: a value engineering proposal with technical assessment, client approval where required, and the quantified saving. • Where it usually breaks: an alternative is bought on the buyer's judgement of equivalence, and it is rejected on site after delivery. | • State that equivalence is a technical determination only, and that procurement may never accept an alternative on its own judgement. • Require client or consultant approval where the specification is contractual, since technical equivalence does not override a contract requirement. • Require the whole life effect to be considered: maintenance, spares availability and warranty, not just the purchase price. • Set a cut off point in the programme after which alternatives will not be considered, because late substitution causes rework. • Record realised value engineering savings separately, so the effort put into it can be justified.
589 | Procurement | Resolve major supplier, subcontractor, quality, delivery and capacity risks | Chief Procurement Officer (CPO) | Trigger: When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. Action: The Chief Procurement Officer (CPO) completes “Resolve major supplier, subcontractor, quality, delivery and capacity risks” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved recovery, value-engineering, replacement, claim or risk-treatment decision. Control/Handoff: The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. | The Chief Procurement Officer (CPO) completes “Resolve major supplier, subcontractor, quality, delivery and capacity risks” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved recovery, value-engineering, replacement, claim or risk-treatment decision. | The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when a supplier or subcontractor is failing on quality, delivery or capacity, he decides what the company does about it. • Starts when: a material supply risk is reported, or performance monitoring shows a supplier deteriorating. • How it runs: (1) he establishes the facts and the exposure with the buyer and the project team. (2) He assesses the effect on the programme and the cost. (3) He decides the response: pressure, support, dual sourcing or replacement. (4) He assigns the actions and the timeline. (5) He monitors until the risk is closed or the supplier is replaced. • Proof it happened: a supplier risk record with the assessment, the decision taken and the actions tracked to closure. • Where it usually breaks: the company keeps working with a failing supplier because replacement seems slower, until the failure becomes unrecoverable. | • Set trigger thresholds that force a replacement decision, so a failing supplier is not tolerated indefinitely by default. • Require the cost of continuing with a failing supplier to be estimated alongside the cost of replacing, since only the replacement cost is usually visible. • Require contractual notices to be issued as performance deteriorates, because entitlement to recover costs depends on them. • Start alternative sourcing in parallel rather than after termination, as sequential action loses the most time. • Record the root cause, since supplier failure often traces back to the company's own late payment or late information.
590 | Procurement | Approve suspension, termination, replacement or claim strategy for material supply failure | Chief Procurement Officer (CPO) | Trigger: When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. Action: The Chief Procurement Officer (CPO) completes “Approve suspension, termination, replacement or claim strategy for material supply failure” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved recovery, value-engineering, replacement, claim or risk-treatment decision. Control/Handoff: The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly review, critical-path alert, cost variance, vendor failure or supply exception occurs. | The Chief Procurement Officer (CPO) completes “Approve suspension, termination, replacement or claim strategy for material supply failure” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved recovery, value-engineering, replacement, claim or risk-treatment decision. | The CPO balances programme, cost, quality, safety, cash and contract exposure; material cross-functional risk escalates through the executive exception route. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when a supplier fails badly, he decides whether to suspend them, terminate, replace them and pursue a claim. • Starts when: a material supply failure occurs or a supplier breaches the contract seriously. • How it runs: (1) he confirms the breach and gathers the evidence. (2) He obtains the CLO's advice on the contractual position. (3) He decides the route: suspension, termination or negotiated exit. (4) He arranges the replacement supply and quantifies the additional cost. (5) He pursues recovery through bonds, retention or claim. • Proof it happened: a documented breach and decision record with legal advice, notices issued, and the recovery position quantified. • Where it usually breaks: termination happens without the required notices having been served, which destroys the company's ability to recover the extra costs. | • Require the notice sequence in the contract to be followed exactly before termination, since defective notice converts a valid claim into an exposure. • Require the additional cost of replacement to be recorded contemporaneously, as reconstructing it later weakens any recovery. • Check the bond, guarantee and retention position before terminating, because calling security afterwards may not be possible. • Require CLO involvement from the first serious breach, not at termination, when options have already narrowed. • Secure the site position first: materials, equipment and completed work, before the relationship becomes adversarial.
591 | Procurement | Approve strategic-vendor development and performance-improvement actions | Chief Procurement Officer (CPO) | Trigger: When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. Action: The Chief Procurement Officer (CPO) completes “Approve strategic-vendor development and performance-improvement actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved vendor, inventory, compliance, suspension or continuity action. Control/Handoff: Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. | The Chief Procurement Officer (CPO) completes “Approve strategic-vendor development and performance-improvement actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved vendor, inventory, compliance, suspension or continuity action. | Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he invests time in the suppliers the company depends on, helping them improve rather than just replacing them. • Starts when: strategic suppliers are identified, and at scheduled performance reviews. • How it runs: (1) he identifies the suppliers critical to delivery. (2) He reviews their performance data with them openly. (3) He agrees improvement actions on both sides. (4) He commits company side actions such as forecast sharing or payment reliability. (5) He tracks the improvement to the next review. • Proof it happened: supplier development plans with agreed actions on both sides and reviewed performance data. • Where it usually breaks: the review lists only the supplier's failings, so the supplier disengages and nothing improves. | • Require the company's own contribution to be reviewed too: late payment, late information and late requisitions cause much supplier failure. • Base the review on recorded performance data rather than impressions, or the discussion becomes an argument about anecdotes. • Define what strategic means by spend, criticality and switching difficulty, so effort goes to the right suppliers. • Set improvement actions with dates and review them at the next meeting, otherwise the review is a courtesy visit. • Consider volume or term commitments in exchange for improvement, since suppliers invest where they see continuity.
592 | Procurement | Approve vendor master-data control and sensitive bank-detail verification rules | Chief Procurement Officer (CPO) | Trigger: When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. Action: The Chief Procurement Officer (CPO) completes “Approve vendor master-data control and sensitive bank-detail verification rules” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved vendor, inventory, compliance, suspension or continuity action. Control/Handoff: Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. | The Chief Procurement Officer (CPO) completes “Approve vendor master-data control and sensitive bank-detail verification rules” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved vendor, inventory, compliance, suspension or continuity action. | Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he controls who can create or change supplier records, especially bank details, because that is where payment fraud happens. • Starts when: the vendor master rules are set, and whenever a bank detail change is requested. • How it runs: (1) he restricts who may create or amend vendor records. (2) He requires supporting documents for any new vendor. (3) He requires bank detail changes to be verified by callback to a known number, never to details on the request. (4) He requires a second person to approve the change. (5) He keeps an audit trail of every change. • Proof it happened: a controlled vendor master with restricted access, verified bank change records and a full change audit trail. • Where it usually breaks: a bank change email that looks genuine is actioned without independent verification, and a payment is lost. | • Require independent callback verification to a previously known number for every bank detail change, and state that details in the request are never used to verify it. • Require dual approval for bank detail changes, with the second approver outside procurement. • Prohibit vendor master changes by anyone who can also approve payments, as this combination enables undetectable fraud. • Require periodic review of dormant and duplicate vendor records, since these are the accounts used for fraudulent payments. • Log and review all master data changes monthly, because the audit trail only helps if someone looks at it.
593 | Procurement | Approve inventory, stockholding, surplus, scrap and disposal-control principles | Chief Procurement Officer (CPO) | Trigger: When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. Action: The Chief Procurement Officer (CPO) completes “Approve inventory, stockholding, surplus, scrap and disposal-control principles” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved vendor, inventory, compliance, suspension or continuity action. Control/Handoff: Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. | The Chief Procurement Officer (CPO) completes “Approve inventory, stockholding, surplus, scrap and disposal-control principles” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved vendor, inventory, compliance, suspension or continuity action. | Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the principles for what stock is held, how much, and what happens to surplus and scrap. • Starts when: the inventory framework is established, and at periodic stock reviews. • How it runs: (1) he sets which items are held in stock and at what levels. (2) He defines the reorder and minimum stock rules. (3) He sets the treatment of project surplus at closeout. (4) He defines the scrap and disposal route with approval requirements. (5) He requires periodic reconciliation and reporting. • Proof it happened: approved inventory principles with stock levels, surplus treatment rules and an approved disposal process. • Where it usually breaks: project surplus is left on site rather than returned or transferred, so the same material is bought again for the next project. | • Require project surplus to be declared at closeout with a value, and offered to other projects before disposal or new purchase. • Require disposal approval by value band, with independent verification for anything above a threshold, since disposal is a known fraud route. • Set stockholding levels against consumption data rather than intuition, because both overstocking and stockouts trace to guessed levels. • Require periodic physical stock counts reconciled to the system, with variances investigated rather than adjusted away. • Report slow moving and obsolete stock with an ageing view, as it consumes cash silently.
594 | Procurement | Oversee procurement audit, contractual, insurance, tax and regulatory compliance | Chief Procurement Officer (CPO) | Trigger: When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. Action: The Chief Procurement Officer (CPO) completes “Oversee procurement audit, contractual, insurance, tax and regulatory compliance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved vendor, inventory, compliance, suspension or continuity action. Control/Handoff: Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. | The Chief Procurement Officer (CPO) completes “Oversee procurement audit, contractual, insurance, tax and regulatory compliance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved vendor, inventory, compliance, suspension or continuity action. | Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he makes sure the buying function stays within the law and the contract, covering audit, insurance, tax and regulation. • Starts when: at scheduled compliance reviews, at audit, and when regulations or contract terms change. • How it runs: (1) he identifies the compliance obligations affecting procurement. (2) He checks practice against them, including tax treatment and import requirements. (3) He supports internal and external audits. (4) He closes audit findings with corrective actions. (5) He reports the compliance position to the CEO and CFO. • Proof it happened: compliance review records, audit findings with closure evidence and a reported compliance position. • Where it usually breaks: audit findings are answered with a written response rather than a changed process, so the same finding recurs. | • Require corrective actions to change the process or the system setting, not just to answer the finding, and verify the change. • Cover import and customs compliance explicitly, since duty misclassification and incorrect documentation create retrospective liabilities. • Check tax treatment on cross border purchases with Finance, particularly withholding tax and reverse charge obligations. • Verify supplier insurance validity as an ongoing obligation, not a one time check at onboarding. • Track repeat audit findings separately, as a repeat finding is a governance failure rather than a process error.
595 | Procurement | Approve supplier and subcontractor business-continuity and concentration-risk actions | Chief Procurement Officer (CPO) | Trigger: When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. Action: The Chief Procurement Officer (CPO) completes “Approve supplier and subcontractor business-continuity and concentration-risk actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an approved vendor, inventory, compliance, suspension or continuity action. Control/Handoff: Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a vendor, master-data, inventory, audit, insurance or compliance review becomes due. | The Chief Procurement Officer (CPO) completes “Approve supplier and subcontractor business-continuity and concentration-risk actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an approved vendor, inventory, compliance, suspension or continuity action. | Vendor eligibility, bank data, stock disposal and compliance decisions retain independent evidence and the required Finance, Legal, Technical or CEO approval. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he makes sure the company is not dangerously dependent on any one supplier, and knows what to do if a key one fails. • Starts when: at the periodic risk review, and when spend concentration or market conditions change. • How it runs: (1) he analyses spend and dependency by supplier and category. (2) He identifies where a single failure would stop work. (3) He identifies or develops alternative sources for those categories. (4) He requires continuity evidence from critical suppliers. (5) He reports the concentration position and the mitigations. • Proof it happened: a supplier concentration and continuity analysis with identified alternatives and mitigation actions. • Where it usually breaks: an alternative source is named on paper but never trialled, so nobody knows whether it can actually deliver. | • Require alternative sources to be qualified and trialled with at least a small order, since an untested alternative is not a mitigation. • Set a concentration threshold by category that triggers action, rather than reviewing dependency by judgement. • Consider hidden concentration where several suppliers share one manufacturer or one origin, which is the failure people miss. • Require continuity evidence from critical suppliers, including their own dependency on sub suppliers. • Review concentration at least annually and after any major supplier failure in the market.
596 | Procurement | Review the weekly Procurement exception and long-lead dashboard | Chief Procurement Officer (CPO) | Trigger: When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. Action: The Chief Procurement Officer (CPO) completes “Review the weekly Procurement exception and long-lead dashboard” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a verified dashboard, executive decision, continuity arrangement or approved improvement action. Control/Handoff: Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. | The Chief Procurement Officer (CPO) completes “Review the weekly Procurement exception and long-lead dashboard” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a verified dashboard, executive decision, continuity arrangement or approved improvement action. | Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: every week he looks at what is going wrong and what is at risk, rather than at what is going normally. • Starts when: weekly on the reporting cycle. • How it runs: (1) he reviews the exceptions: overdue deliveries, unapproved orders, price escalations and expiring documents. (2) He reviews the long lead items and their float. (3) He identifies items needing his intervention. (4) He directs the actions and owners. (5) He carries unresolved items to the next week with escalation. • Proof it happened: a weekly exception and long lead dashboard with directed actions and their status. • Where it usually breaks: the dashboard reports volume of activity rather than exceptions, so nothing on it demands a decision. | • Define the exception triggers explicitly in the SOP, so the dashboard is generated by rule and not by someone's selection. • Show ageing on unresolved exceptions, because an item appearing for the fifth week needs different treatment from a new one. • Keep the dashboard short and decision focused. A weekly report nobody can act on within its own week is not worth producing. • Generate it from the system rather than compiling it manually, so the review is not delayed by preparation. • Require an action owner and date on every exception raised, otherwise the meeting produces discussion and no change.
597 | Procurement | Review the monthly Procurement performance, savings, exposure and vendor scorecard | Chief Procurement Officer (CPO) | Trigger: When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. Action: The Chief Procurement Officer (CPO) completes “Review the monthly Procurement performance, savings, exposure and vendor scorecard” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a verified dashboard, executive decision, continuity arrangement or approved improvement action. Control/Handoff: Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. | The Chief Procurement Officer (CPO) completes “Review the monthly Procurement performance, savings, exposure and vendor scorecard” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a verified dashboard, executive decision, continuity arrangement or approved improvement action. | Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: monthly he reviews the bigger picture: performance, savings, financial exposure and how suppliers are scoring. • Starts when: monthly at the reporting cycle. • How it runs: (1) he reviews the performance measures against target. (2) He reviews savings and the committed cost position. (3) He reviews the outstanding financial exposure: advances, retentions and open commitments. (4) He reviews the supplier scorecards. (5) He agrees corrective actions and reports upward. • Proof it happened: a monthly procurement performance pack with measures, savings, exposure and vendor scorecards, with actions recorded. • Where it usually breaks: scorecards are produced but never shared with the suppliers, so they cannot act on the assessment. | • Require scorecard results to be shared with the suppliers being scored, since a scorecard the supplier never sees changes nothing. • Define the scorecard measures and weighting in the SOP, so scoring is consistent between buyers and periods. • Include outstanding advance payments and unreconciled retentions in exposure, as these are frequently forgotten money. • Require the pack to show trend rather than a single month, because one month tells management very little. • Tie the scorecard to sourcing decisions explicitly, otherwise poor performers keep receiving awards.
598 | Procurement | Report material procurement commitments, risks and decisions to the CEO | Chief Procurement Officer (CPO) | Trigger: When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. Action: The Chief Procurement Officer (CPO) completes “Report material procurement commitments, risks and decisions to the CEO” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a verified dashboard, executive decision, continuity arrangement or approved improvement action. Control/Handoff: Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. | The Chief Procurement Officer (CPO) completes “Report material procurement commitments, risks and decisions to the CEO” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a verified dashboard, executive decision, continuity arrangement or approved improvement action. | Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he tells the CEO what the company has committed to, what could go wrong, and what he has decided. • Starts when: at the monthly reporting cycle, and immediately for material events. • How it runs: (1) he summarises the material commitments made in the period. (2) He states the significant supply risks and their effect on projects. (3) He reports decisions taken under his authority. (4) He raises matters needing the CEO's decision. (5) He records the CEO's directions and acts on them. • Proof it happened: a reported summary of commitments, risks and decisions, with the CEO's directions recorded. • Where it usually breaks: only good news travels, so the CEO learns about a supply failure when it has already hit the programme. | • Name the events that must be reported immediately rather than in the monthly cycle: supplier insolvency, major delivery failure, fraud suspicion and price shock. • Require risks to be stated with their programme and cost effect, not as general concerns, so the CEO can weigh them. • Require decisions taken under delegated authority to be reported, since delegation without visibility is not oversight. • Keep the format consistent so the CEO can compare periods without re reading the whole pack. • Record the CEO's directions in writing, as verbal directions on procurement matters get remembered differently later.
599 | Procurement | Approve Procurement access-control, backup, delegation and continuity arrangements | Chief Procurement Officer (CPO) | Trigger: When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. Action: The Chief Procurement Officer (CPO) completes “Approve Procurement access-control, backup, delegation and continuity arrangements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a verified dashboard, executive decision, continuity arrangement or approved improvement action. Control/Handoff: Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. | The Chief Procurement Officer (CPO) completes “Approve Procurement access-control, backup, delegation and continuity arrangements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a verified dashboard, executive decision, continuity arrangement or approved improvement action. | Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he makes sure procurement keeps running when people are away and that its records and systems are protected. • Starts when: at the continuity review, on staff changes, and before planned absences. • How it runs: (1) he defines the system access rights per role and reviews them. (2) He names deputies for each critical role. (3) He documents the delegation arrangements for absence. (4) He confirms the backup and record retention arrangements. (5) He tests that a deputy can actually perform the role. • Proof it happened: reviewed access rights, named deputies with written delegations and confirmed backup arrangements. • Where it usually breaks: a deputy is named but has no system access, so the function stops the first day the principal is away. | • Require deputies to hold the necessary system access before the absence begins, and test it, since a delegation without access is symbolic. • Set delegation end dates and require access to be withdrawn on return, otherwise permissions accumulate and segregation erodes. • Review access rights on every leaver and role change, as leaver access is a standard audit finding. • Confirm where procurement records are held and that they are backed up, because contract and award records carry legal weight. • Include the vendor master and approval workflows in the continuity plan, as these block everything when unavailable.
600 | Procurement | Sponsor procurement-process, FirstBit, data-quality and automation improvements | Chief Procurement Officer (CPO) | Trigger: When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. Action: The Chief Procurement Officer (CPO) completes “Sponsor procurement-process, FirstBit, data-quality and automation improvements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a verified dashboard, executive decision, continuity arrangement or approved improvement action. Control/Handoff: Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. Continuity/Escalation: A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the daily/weekly/monthly reporting cycle, access review, absence or process-improvement need occurs. | The Chief Procurement Officer (CPO) completes “Sponsor procurement-process, FirstBit, data-quality and automation improvements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a verified dashboard, executive decision, continuity arrangement or approved improvement action. | Material delay, commitment, vendor, stock or system exceptions have named owners and dates; reserved approvals remain with the CPO or higher authority. | A CEO-approved procurement delegate may coordinate routine matters, but supplier/subcontractor award, major commitment, exception, termination, blacklisting and reserved authority remain with the CPO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sponsors making the buying process better and faster, including how the FirstBit system is used and how clean the data is. • Starts when: when improvement needs are identified, and at the annual planning cycle. • How it runs: (1) he identifies the process pain points and the manual effort. (2) He prioritises the improvements by benefit. (3) He sponsors the system changes and data cleanup with IT and the vendor. (4) He assigns owners and tracks delivery. (5) He confirms the benefit was actually realised. • Proof it happened: an improvement plan with sponsored initiatives, delivery status and evidence of the benefit realised. • Where it usually breaks: system changes are made without cleaning the underlying data, so the reports stay unreliable and nobody trusts the system. | • Require data quality to be addressed before automation, since automating on poor master data multiplies the errors. • Define ownership of the item master and vendor master, as unowned master data degrades continuously. • Require benefit verification after implementation, because improvement projects are usually declared complete at go live rather than at benefit. • Involve the actual users in design, since procurement workarounds exist where the system does not match how work is really done. • Keep a single prioritised improvement list rather than parallel initiatives competing for the same people.
601 | Procurement | Receive and register purchase and subcontract requisitions | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Receive and register purchase and subcontract requisitions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Receive and register purchase and subcontract requisitions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he takes in the requests to buy things and logs them, so every requirement has a reference and a start date. • Starts when: a department or project raises a purchase or subcontract requisition. • How it runs: (1) he receives the requisition through the approved route. (2) He checks it carries the required approval. (3) He registers it with the date received and the requester. (4) He assigns a reference and a buyer. (5) He confirms receipt to the requester. • Proof it happened: a requisition register entry with the date, requester, approval reference and assigned buyer. • Where it usually breaks: requirements arrive by phone or message and are worked on without ever being registered, so nobody can see the real workload or lead time. | • Require every requirement to enter through the registered route, since unregistered requests have no date, no lead time and no traceability. • Record the date received separately from the date required, because the difference is the evidence when a delivery is late. • Confirm receipt with the expected timeline, so requesters do not chase or escalate unnecessarily. • Reject requisitions without approval rather than processing them pending approval. • Report requisitions received with insufficient lead time, as this is the root cause of most emergency buying.
602 | Procurement | Validate IFC, BOQ, specification, approved-brand and revision references | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Validate IFC, BOQ, specification, approved-brand and revision references” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Validate IFC, BOQ, specification, approved-brand and revision references” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks the request refers to the right drawings, bill items, specification and approved brands, at the right revision. • Starts when: a registered requisition is being validated. • How it runs: (1) he checks the drawing and revision quoted against the controlled register. (2) He checks the BOQ item reference matches. (3) He checks the specification and approved brand list. (4) He queries any mismatch with the originator. (5) He records the validated references. • Proof it happened: a validation record confirming the drawing revision, BOQ reference, specification and approved brand. • Where it usually breaks: the requisition quotes a superseded drawing revision, so material is bought to a design that has already changed. | • Check the drawing revision against the controlled register rather than the copy attached to the request, since buying against a superseded revision is the most expensive error this role can make. • Require the approved brand list to be checked, because substitution discovered after delivery is rejected at the company's cost. • Require the specification clause reference rather than a general description. • Return rather than resolve a mismatch, as engineering must confirm what is actually required. • Record the revision bought against, so a later revision change becomes a variation rather than an argument.
603 | Procurement | Validate quantity, budget, project code, cost code and required-on-site date | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Validate quantity, budget, project code, cost code and required-on-site date” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Validate quantity, budget, project code, cost code and required-on-site date” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks the quantity, the budget, the project and cost codes and the date the material is actually needed on site. • Starts when: a requisition is being validated. • How it runs: (1) he checks the quantity against the BOQ and any wastage allowance. (2) He confirms the budget line has funds available. (3) He confirms the project and cost codes are correct. (4) He confirms the required on site date is realistic against lead time. (5) He records the validated data. • Proof it happened: a validation record confirming quantity, budget availability, coding and the required on site date. • Where it usually breaks: the required on site date is copied from the programme without checking the lead time, so the date is already impossible when the requisition is raised. | • Check the required date against the realistic lead time at validation and flag impossible dates immediately, since silence here transfers the blame for a late delivery to procurement. • Confirm budget availability against the remaining line rather than the total budget. • Check the quantity against the BOQ, as over ordering is rarely detected and the surplus is rarely returned. • Verify the cost coding, because miscoded purchases distort project cost reporting permanently. • Require the wastage allowance to be stated rather than built silently into the quantity.
604 | Procurement | Return incomplete, duplicated, unapproved or unclear requisitions for correction | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Return incomplete, duplicated, unapproved or unclear requisitions for correction” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Return incomplete, duplicated, unapproved or unclear requisitions for correction” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: when a request is incomplete, duplicated or unclear, he sends it back rather than guessing. • Starts when: a validation check fails. • How it runs: (1) he identifies the specific deficiency. (2) He checks whether it duplicates an existing requisition. (3) He records the return with the reason. (4) He returns it to the originator with what is required. (5) He tracks the resubmission. • Proof it happened: a return record with the specific reason, notified to the originator, and the resubmission tracked. • Where it usually breaks: procurement completes the missing details itself to save time, so it becomes responsible for a technical decision it is not qualified to make. | • Prohibit procurement from completing technical details on a deficient requisition, since guessing moves responsibility for the error to the wrong function and hides it. • Check for duplicates before returning, as the same requirement raised twice results in double delivery. • State the specific missing items, or the resubmission arrives with the same gaps. • Track return rates by department, since a high rate indicates a training need rather than a procurement problem. • Record the delay caused by the return, so the lead time impact sits with the originator.
605 | Procurement | Split approved requirements into material, equipment and subcontract packages | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Split approved requirements into material, equipment and subcontract packages” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Split approved requirements into material, equipment and subcontract packages” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he breaks the approved requirements into sensible buying packages by type. • Starts when: requisitions are validated and grouped for sourcing. • How it runs: (1) he groups requirements by category and supply market. (2) He separates material supply, equipment and subcontracted work. (3) He considers whether combining increases leverage or risk. (4) He confirms the package boundaries leave no scope gaps. (5) He records the package structure. • Proof it happened: a defined package structure with the requirements allocated and boundaries checked for gaps. • Where it usually breaks: packages are split so finely that no supplier has enough value to care, or combined so broadly that no supplier can cover the whole scope. | • Check package boundaries for scope gaps and overlaps with a named owner per element, since gaps appear on site as unpriced work. • Size packages against the supply market rather than internal convenience, as a package no supplier can fully deliver attracts poor pricing. • State whether supply and install are combined, because split responsibility for the same element causes disputes. • Consider the programme when packaging, since a single large package delays everything within it. • Record the rationale, so the structure can be reviewed when the market response is poor.
606 | Procurement | Maintain the project procurement-package register | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Maintain the project procurement-package register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Maintain the project procurement-package register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he keeps the list of every buying package on the project and where each one stands. • Starts when: packages are defined, and continuously as they progress. • How it runs: (1) he records each package with its scope and value. (2) He records the target award and delivery dates. (3) He records the current stage. (4) He updates it as each stage completes. (5) He reports the status to the project team. • Proof it happened: a package register with scopes, values, target dates and the current stage per package. • Where it usually breaks: the register is updated only before meetings, so between meetings nobody knows the real position. | • Require the register to be updated at each stage change rather than before meetings, since a register refreshed for reporting is always out of date when it matters. • Show the float between the planned award date and the required delivery date, because that is what tells you whether a package is in trouble. • Record the committed value per package, so the project cost position is visible. • Use one register shared with the project team rather than parallel versions. • Highlight packages not yet started against their required award date.
607 | Procurement | Maintain the long-lead, critical-item and client-nominated-supplier register | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Maintain the long-lead, critical-item and client-nominated-supplier register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Maintain the long-lead, critical-item and client-nominated-supplier register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he keeps the list of items that take a long time to get and the ones the client has told the company to use. • Starts when: at project start, and whenever a long lead or nominated item is identified. • How it runs: (1) he identifies items whose lead time threatens the programme. (2) He records the lead time, the required date and the float. (3) He records the client nominated suppliers and any conditions. (4) He flags items already at risk. (5) He reports the register at every review. • Proof it happened: a long lead and nominated supplier register with lead times, required dates, float and risk flags. • Where it usually breaks: client nominated suppliers are treated as normal suppliers, so their poor performance is absorbed rather than reported as a client caused delay. | • Record client nominated suppliers separately and report their performance failures to the client in writing, since their delays are the client's risk and silence transfers it to the company. • Define long lead by weeks so the register is populated by rule, not by opinion. • Show remaining float rather than just the lead time, because float is what determines urgency. • Escalate automatically when float falls below a stated threshold. • Include the submittal and approval time in the lead time, as this is routinely omitted and is often the longest part.
608 | Procurement | Build the procurement schedule backward from required-on-site dates | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Build the procurement schedule backward from required-on-site dates” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Build the procurement schedule backward from required-on-site dates” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he works backwards from when material is needed on site to decide when each order must be placed. • Starts when: the packages are defined and the programme is available. • How it runs: (1) he takes the required on site date from the programme. (2) He subtracts delivery, manufacture, submittal approval and tender time. (3) He sets the enquiry, award and order dates. (4) He identifies packages already past their start date. (5) He issues the schedule and tracks it. • Proof it happened: a procurement schedule derived backwards from site dates, with each lead time component shown. • Where it usually breaks: the schedule is built forward from today, so it shows what is achievable rather than what the programme actually needs. | • Build every date backwards from the required on site date and show each lead time component separately, since a forward built schedule hides the packages that are already late. • Include submittal and consultant approval time explicitly, as this is the most commonly omitted element. • Flag packages whose start date has already passed at the moment the schedule is produced. • Reissue when the programme is rebaselined, or procurement works to a superseded plan. • Share the schedule with the project team so the required dates are jointly owned.
609 | Procurement | Identify market-capacity, lead-time, technical and commercial sourcing constraints | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Identify market-capacity, lead-time, technical and commercial sourcing constraints” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Identify market-capacity, lead-time, technical and commercial sourcing constraints” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he identifies what the market can actually supply, how long it takes, and what will be difficult. • Starts when: sourcing is being planned for a package. • How it runs: (1) he checks the market capacity for the category. (2) He checks current lead times against the requirement. (3) He identifies technical constraints such as limited approved manufacturers. (4) He identifies commercial constraints such as minimum order quantities or price volatility. (5) He records the constraints and their effect. • Proof it happened: a recorded constraint assessment covering capacity, lead time, technical and commercial limitations. • Where it usually breaks: constraints are discovered during the enquiry rather than before it, so the tender period is wasted and has to be restarted. | • Check market capacity and current lead times before issuing the enquiry, since discovering constraints mid tender wastes the tender period and the programme float with it. • Record price volatility for the category, as a fixed price from a volatile market carries either a premium or a future claim. • Identify where only one or two manufacturers are approved, because this removes competition and must be addressed differently. • Report constraints to the project team so the programme can absorb them rather than being surprised. • Check minimum order quantities against the requirement, as these can force over purchasing.
610 | Procurement | Review procurement priorities and constraints with Projects and Technical Engineering | Procurement Lead | Trigger: When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. Action: The Procurement Lead completes “Review procurement priorities and constraints with Projects and Technical Engineering” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. Control/Handoff: The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When an approved project baseline, IFC/BOQ requirement, material request or subcontract need reaches Procurement. | The Procurement Lead completes “Review procurement priorities and constraints with Projects and Technical Engineering” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete requisition, procurement package, long-lead entry and programme-linked sourcing plan. | The Procurement Lead returns uncontrolled scope, missing revisions, absent budget codes or missing required-on-site dates and coordinates correction with Projects, QS and Technical Engineering. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he sits with the project and engineering teams to agree what procurement should tackle first and what is holding it up. • Starts when: at the agreed review frequency, and when priorities shift after a programme change. • How it runs: (1) he brings the package status and the pending items to the review. (2) The project team states which packages the programme now depends on. (3) Engineering states which technical approvals are outstanding. (4) They agree a ranked priority order and who clears each blocker. (5) He records the agreed priorities and works to them. • Proof it happened: a recorded priority review with a ranked package order, identified blockers and named owners. • Where it usually breaks: everything is called urgent, so procurement sets its own order and the site later finds the wrong package was progressed first. | • Require a single ranked priority list agreed at the review, since when everything is urgent procurement sets its own order and the site gets the wrong package first. • Require each blocker to have a named owner and a date, particularly outstanding technical approvals. • Record the agreed priorities in writing, so a later complaint about sequence can be answered. • Hold the review at a fixed frequency rather than only when there is a problem. • Require engineering to attend, because most procurement blockages are technical rather than commercial.
611 | Procurement | Maintain the approved supplier and subcontractor database | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Maintain the approved supplier and subcontractor database” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Maintain the approved supplier and subcontractor database” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he keeps the list of suppliers and subcontractors who are approved to be asked for prices. • Starts when: a supplier is approved, and continuously as documents expire or performance changes. • How it runs: (1) he records each approved supplier with its categories. (2) He records the prequalification status and document validity. (3) He records the performance history. (4) He removes or suspends suppliers who fail. (5) He reviews the database periodically for currency. • Proof it happened: a maintained approved supplier database with categories, valid documents and performance history. • Where it usually breaks: suppliers stay listed as approved with expired licences and insurance, so enquiries go to companies that cannot legally be engaged. | • Track document expiry and block suppliers automatically when documents lapse, since an approved list with expired licences sends enquiries to companies that cannot be engaged. • Record the categories each supplier is approved for, so enquiries are not sent outside their capability. • Record performance history against each entry, and require it to be checked before shortlisting. • Review the database at a set frequency rather than only when adding. • Flag suppliers with no recent activity, as dormant records accumulate and are used for fraud.
612 | Procurement | Create and control supplier and subcontractor master-data requests | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Create and control supplier and subcontractor master-data requests” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Create and control supplier and subcontractor master-data requests” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he raises and controls the requests to create or change supplier records in the system. • Starts when: a new supplier must be created or an existing record changed. • How it runs: (1) he prepares the master data request with the supporting documents. (2) He checks for an existing record first. (3) He submits it through the controlled route. (4) For bank detail changes he follows the independent verification process. (5) He confirms creation and records the reference. • Proof it happened: controlled master data requests with supporting documents, duplicate checks and verification evidence. • Where it usually breaks: bank details are submitted from the supplier's email without independent verification, which is how payment fraud succeeds. | • Require independent callback verification to a previously held number for every bank detail change, and state that the contact details in the request are never used to verify it. • Require a duplicate check before every creation request, as duplicates are the main damage to vendor master quality. • Prohibit the person raising the request from also approving it. • Require supporting documents rather than a supplier's stated details, particularly for tax registration. • Record who requested and who approved each change, since the audit trail is what makes fraud detectable.
613 | Procurement | Collect trade licence, tax, ownership, banking, insurance and capability documents | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Collect trade licence, tax, ownership, banking, insurance and capability documents” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Collect trade licence, tax, ownership, banking, insurance and capability documents” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he collects the licences, tax, ownership, banking, insurance and capability documents from prospective suppliers. • Starts when: a supplier is being prequalified or a document is due for renewal. • How it runs: (1) he issues the document checklist to the supplier. (2) He collects and checks the documents for validity. (3) He checks the ownership details against the declared information. (4) He records the expiry dates. (5) He chases the missing items before approval. • Proof it happened: a completed document set with validity checked, ownership verified and expiry dates recorded. • Where it usually breaks: documents are collected but the expiry dates are never recorded, so lapses are only discovered when a problem arises. | • Record the expiry date of every document at collection and set advance warnings, since lapsed documents are the common failure rather than missing ones. • Verify ownership details, because undeclared common ownership between bidders defeats the entire tender process. • Check insurance covers the work the supplier will actually do, not just that a policy exists. • Verify tax registration independently where possible, as invalid registration affects input tax recovery. • Require the full set before approval rather than approving with documents pending.
614 | Procurement | Perform supplier and subcontractor prequalification due diligence | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Perform supplier and subcontractor prequalification due diligence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Perform supplier and subcontractor prequalification due diligence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks whether a prospective supplier is actually capable and sound before they are approved. • Starts when: a supplier applies or is proposed for prequalification. • How it runs: (1) he reviews the submitted capability and financial information. (2) He assesses the risk based on the category and value involved. (3) He conducts checks proportionate to that risk. (4) He identifies concerns and seeks clarification. (5) He recommends approval, conditional approval or rejection. • Proof it happened: a due diligence record with the checks performed, concerns identified and a recommendation. • Where it usually breaks: due diligence is a document collection exercise, so a supplier with valid paperwork and no capacity is approved. | • Assess actual capacity and financial standing rather than only collecting documents, since valid paperwork proves existence and nothing about ability to deliver. • Scale the depth of diligence to the value and risk, so critical subcontractors are examined properly. • Check financial standing for suppliers requiring advance payment, as insolvency mid order is the largest loss in this area. • Require conditional approvals to state the condition and an expiry. • Record the basis of the decision, so approval can be defended and reviewed.
615 | Procurement | Verify experience, capacity, references, quality, HSE and delivery capability | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Verify experience, capacity, references, quality, HSE and delivery capability” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Verify experience, capacity, references, quality, HSE and delivery capability” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks the supplier's experience, capacity, references, quality, safety and delivery record. • Starts when: prequalification due diligence is being performed. • How it runs: (1) he reviews the stated experience against comparable work. (2) He checks current workload against available capacity. (3) He contacts references and records their responses. (4) He reviews the quality and HSE systems and certifications. (5) He records the assessment against each criterion. • Proof it happened: a capability assessment covering experience, capacity, references, quality and HSE with recorded responses. • Where it usually breaks: references are listed but never contacted, so the assessment rests entirely on the supplier's own claims. | • Contact references and record what they said, since an uncontacted reference list means the assessment rests entirely on the supplier's own account. • Check current workload, because a capable supplier already fully committed will still fail to deliver. • Verify certifications with the issuing body for safety critical work. • Assess experience on comparable scope and scale rather than on years in business. • Require HSE performance data for site based subcontractors, as their incidents become the company's.
616 | Procurement | Screen conflicts, related parties, sanctions, debarment and ethical-sourcing concerns | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Screen conflicts, related parties, sanctions, debarment and ethical-sourcing concerns” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Screen conflicts, related parties, sanctions, debarment and ethical-sourcing concerns” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks for conflicts, related parties, sanctions and past debarment before a supplier is used. • Starts when: prequalification is being completed, and at periodic revalidation. • How it runs: (1) he checks ownership and management against company staff and other bidders. (2) He screens against sanctions and debarment lists. (3) He checks for previous suspension by the company. (4) He checks ethical sourcing concerns in the supply chain. (5) He escalates any finding before approval. • Proof it happened: a screening record covering conflicts, related parties, sanctions, debarment and ethical concerns. • Where it usually breaks: two bidders share ownership, so a tender that looks competitive is not, and the company pays a coordinated price. | • Check ownership across all bidders on the same package, since shared ownership makes a tender look competitive while the prices are coordinated. • Screen against company staff and their declared relations, because an undeclared relationship is a conflict whether or not it is exploited. • Check previously suspended or blacklisted suppliers, as these reappear under new names. • Escalate findings rather than resolving them within procurement. • Repeat the screening at revalidation, since ownership changes.
617 | Procurement | Prepare the technically suitable bidder shortlist | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Prepare the technically suitable bidder shortlist” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Prepare the technically suitable bidder shortlist” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he decides which technically suitable suppliers will actually be invited to price the package. • Starts when: the package is ready for enquiry and a bidder list is needed. • How it runs: (1) he identifies the approved suppliers in the category. (2) He checks their capability against this specific scope. (3) He checks their current performance and capacity. (4) He confirms the minimum number of bidders required. (5) He records the shortlist and the reason for inclusion. • Proof it happened: a recorded shortlist with the selection basis and the required number of bidders confirmed. • Where it usually breaks: the same familiar suppliers are invited every time, so pricing is never tested and the market never widens. | • Require the reason for including each bidder to be recorded, since inviting the same familiar names every time means the price is never actually tested. • Require a minimum number of genuine bidders and record where fewer were available. • Check performance history before inclusion, so poor performers are not reinvited by default. • Include at least one new qualified bidder periodically, to keep the market honest. • Check capacity, because inviting a supplier already loaded with the company's work wastes the enquiry.
618 | Procurement | Prepare complete RFQ and subcontract-enquiry packages | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Prepare complete RFQ and subcontract-enquiry packages” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Prepare complete RFQ and subcontract-enquiry packages” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he prepares the complete enquiry pack so every bidder prices exactly the same thing. • Starts when: the shortlist is agreed and the enquiry is to be issued. • How it runs: (1) he assembles the scope, drawings at current revision and specifications. (2) He prepares the pricing schedule and the required format. (3) He states the commercial terms and the conditions of tender. (4) He states the submission deadline and the required documents. (5) He checks the pack for completeness before issue. • Proof it happened: a complete enquiry pack with scope, current revisions, pricing format, terms and submission requirements. • Where it usually breaks: the pack omits the commercial terms, so bidders price on their own terms and the comparison is meaningless. | • Include the company's commercial terms in every enquiry, since omitting them means bidders price on their own terms and no two offers are comparable. • Require a fixed pricing schedule format, because free format pricing cannot be compared or normalised. • State the drawing revisions issued, so a later revision is identifiable as a change. • List the documents required with the offer, otherwise evaluation stalls chasing them. • Check completeness before issue, as an incomplete pack produces clarification rounds that consume the tender period.
619 | Procurement | Issue controlled RFQs and maintain the bidder and communication log | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Issue controlled RFQs and maintain the bidder and communication log” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Issue controlled RFQs and maintain the bidder and communication log” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he issues the enquiries formally and keeps a record of who was sent what and when. • Starts when: the enquiry pack is complete and ready for issue. • How it runs: (1) he issues the pack to each shortlisted bidder simultaneously. (2) He records the issue date and the contents sent. (3) He obtains acknowledgement of receipt. (4) He logs all communication with each bidder. (5) He maintains the log through to award. • Proof it happened: an issue record per bidder with the date, contents, acknowledgement and a complete communication log. • Where it usually breaks: bidders receive the enquiry at different times, so some have materially less time to price and the tender is open to challenge. | • Issue to all bidders simultaneously and record the time, since staggered issue gives some bidders less time and makes the award challengeable. • Log every communication with every bidder, as informal contact is where tender integrity is lost. • Obtain acknowledgement of receipt, otherwise a bidder can claim never to have received the enquiry. • Record exactly what was sent to each bidder, so it can be shown all priced the same information. • Route all bidder contact through the buyer, not through the project or technical team.
620 | Procurement | Manage bidder clarifications, addenda, site visits and controlled information release | Procurement Lead | Trigger: When a sourcing package or new vendor/subcontractor requirement is approved. Action: The Procurement Lead completes “Manage bidder clarifications, addenda, site visits and controlled information release” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. Control/Handoff: Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a sourcing package or new vendor/subcontractor requirement is approved. | The Procurement Lead completes “Manage bidder clarifications, addenda, site visits and controlled information release” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a controlled vendor record, prequalification decision, bidder shortlist, RFQ and clarification log. | Only eligible and technically suitable bidders receive controlled information; conflicts, sensitive data, insufficient competition and material due-diligence concerns escalate to the CPO. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he handles bidder questions, issues addenda to everyone, and controls site visits. • Starts when: a bidder raises a question or a site visit is required. • How it runs: (1) he receives the query in writing. (2) He obtains the technical answer where needed. (3) He issues the answer as an addendum to all bidders, not just the asker. (4) He arranges site visits with equal access. (5) He records every addendum and attendance. • Proof it happened: an addendum register with answers issued to all bidders, and site visit attendance records. • Where it usually breaks: a question is answered to the bidder who asked, so one bidder prices on better information than the rest. | • Issue every clarification to all bidders regardless of who asked, since answering one bidder privately gives them an advantage and invalidates the comparison. • Prohibit verbal answers entirely during the tender period, as these cannot be evidenced or shared. • Set a clarification cut off date, so late questions do not extend the tender indefinitely. • Number the addenda and require bidders to acknowledge each, otherwise they price on superseded information. • Give all bidders equal site access, because a visit granted to one is a material advantage.
621 | Procurement | Control quotation receipt, tender cutoff, confidentiality and late-bid exceptions | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Control quotation receipt, tender cutoff, confidentiality and late-bid exceptions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Control quotation receipt, tender cutoff, confidentiality and late-bid exceptions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he controls how quotations are received and kept confidential, and how late bids are handled. • Starts when: the submission deadline approaches and offers are received. • How it runs: (1) he specifies the submission route. (2) He records each offer as received with the date and time. (3) He keeps offers unopened or sealed until the deadline. (4) He applies the stated rule on late bids. (5) He records any exception with approval. • Proof it happened: a receipt log with dates and times, controlled confidentiality until the deadline, and approved exceptions recorded. • Where it usually breaks: offers are opened as they arrive, so prices are known before all bids are in and the information can leak. | • Keep all offers sealed until the deadline, since knowing one price before the others are received destroys the integrity of the whole process. • State the late bid rule in the enquiry and apply it consistently, as discretionary acceptance invites challenge. • Require any late bid acceptance to be approved and recorded with the reason. • Record the exact time of receipt, so the deadline can be evidenced. • Restrict access to received offers to the evaluation team only.
622 | Procurement | Check quotation completeness and commercial compliance | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Check quotation completeness and commercial compliance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Check quotation completeness and commercial compliance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks each quotation is complete and actually complies with what was asked. • Starts when: offers are opened for evaluation. • How it runs: (1) he checks each offer covers the full scope. (2) He checks the pricing format was followed. (3) He checks the required documents are attached. (4) He identifies the exclusions and qualifications stated. (5) He records the compliance position per bidder. • Proof it happened: a compliance check per offer covering scope, pricing format, documents, exclusions and qualifications. • Where it usually breaks: exclusions buried in the offer are not extracted, so the cheapest bid is simply the least complete one. | • Extract every exclusion and qualification into the comparison, since the lowest price is usually the least complete offer rather than the best value. • Check scope coverage item by item rather than accepting a total price. • Record non compliance rather than correcting it, and seek clarification formally. • Check the offer validity period, as a short validity can expire before award. • Reject offers that ignore the pricing format, or the comparison cannot be made.
623 | Procurement | Normalise prices, quantities, exclusions, payment terms and delivery assumptions | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Normalise prices, quantities, exclusions, payment terms and delivery assumptions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Normalise prices, quantities, exclusions, payment terms and delivery assumptions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he adjusts the offers so they can be compared fairly, adding back what each has left out. • Starts when: the compliance check is complete. • How it runs: (1) he builds the comparison on a common basis. (2) He prices the exclusions and adds them back to each offer. (3) He adjusts for differing quantities and delivery assumptions. (4) He values the differences in payment terms. (5) He records the normalised comparison and the adjustments made. • Proof it happened: a normalised comparison with each adjustment stated and the basis of normalisation recorded. • Where it usually breaks: only headline prices are compared, so an offer excluding delivery and installation appears cheapest. | • Price and add back every exclusion before comparing, since an offer excluding delivery, offloading or installation looks cheapest and is not. • Value the payment terms difference, because extended terms have real cash value and advance payment has real cost. • Normalise the quantities where bidders have priced differently. • Show each adjustment separately, so the comparison can be checked and defended. • Include the freight, duty and clearance cost for imported offers, as the unit price alone is misleading.
624 | Procurement | Coordinate technical compliance, material-submittal and approved-brand review | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Coordinate technical compliance, material-submittal and approved-brand review” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Coordinate technical compliance, material-submittal and approved-brand review” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he coordinates the technical review of what each bidder has offered, including brands and submittals. • Starts when: offers are received and technical review is required. • How it runs: (1) he issues the technical content to engineering for review. (2) He obtains a technical compliance assessment per bidder. (3) He checks the proposed brands against the approved list. (4) He obtains a view on any proposed alternative. (5) He records the technical position before commercial comparison concludes. • Proof it happened: a technical compliance assessment per bidder with brand and alternative positions recorded. • Where it usually breaks: technical review happens after the commercial recommendation, so a cheaper non compliant offer has already shaped expectations. | • Complete the technical assessment before the commercial recommendation is formed, since a cheap non compliant offer otherwise anchors the expectation and pressure follows. • Require engineering to state compliance explicitly rather than commenting generally. • Require any alternative to be assessed for equivalence by engineering, never accepted on the buyer's judgement. • Check proposed brands against the approved and client accepted lists. • Set a review turnaround, as slow technical review consumes the offer validity period.
625 | Procurement | Evaluate manufacturing capacity, lead time, logistics and programme compliance | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Evaluate manufacturing capacity, lead time, logistics and programme compliance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Evaluate manufacturing capacity, lead time, logistics and programme compliance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks whether each bidder can actually manufacture and deliver in the time the programme needs. • Starts when: offers are being evaluated. • How it runs: (1) he reviews the stated lead time against the required date. (2) He checks the manufacturing capacity and current load. (3) He checks the logistics route and its risks. (4) He checks the delivery programme is credible rather than optimistic. (5) He records the programme compliance position. • Proof it happened: a programme compliance assessment per bidder with lead time, capacity and logistics assessed. • Where it usually breaks: the stated lead time is accepted at face value, so the award goes to a bidder who was simply the most optimistic. | • Test the stated lead time against evidence rather than accepting it, since awarding to the most optimistic bidder is how programmes fail after award. • Check current manufacturing load, because quoted capacity and available capacity are different things. • Assess the logistics route and its risks for imported items, including port and clearance time. • Require the delivery programme to be broken into milestones, so slippage is detectable early. • Weight programme compliance explicitly in the evaluation, or price will always win.
626 | Procurement | Prepare the technical-commercial comparison and deviation register | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Prepare the technical-commercial comparison and deviation register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Prepare the technical-commercial comparison and deviation register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he produces the single comparison showing technical and commercial position plus every open deviation. • Starts when: technical and commercial evaluation are complete. • How it runs: (1) he combines the technical and commercial assessments. (2) He shows the normalised prices with adjustments. (3) He lists the deviations and qualifications per bidder. (4) He identifies the risks each deviation creates. (5) He issues the comparison as the basis for negotiation and award. • Proof it happened: a combined technical and commercial comparison with a deviation register per bidder. • Where it usually breaks: the deviation register is prepared but not carried into the award, so accepted deviations are never recorded anywhere. | • Carry the deviation register through to the award and the order, since deviations identified in evaluation and then forgotten become silently accepted terms. • Show the normalised price alongside the submitted price with adjustments visible. • Present technical and commercial positions together, so the decision is not taken on price in isolation. • Quantify the risk of each open deviation where possible. • Require the comparison to be checked by a second person, as arithmetic errors here decide awards.
627 | Procurement | Prepare and approve the negotiation plan within delegated authority | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Prepare and approve the negotiation plan within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Prepare and approve the negotiation plan within delegated authority” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he plans what he is going to negotiate and gets the plan approved before talking to the supplier. • Starts when: the comparison is complete and negotiation is required. • How it runs: (1) he identifies the negotiation targets: price, terms, delivery and deviations. (2) He sets the opening position and the walk away point. (3) He identifies what the company can offer in return. (4) He obtains approval within his delegated authority. (5) He records the approved plan before negotiating. • Proof it happened: an approved negotiation plan with targets, limits and the concessions available. • Where it usually breaks: negotiation happens without a plan, so concessions are given on terms nobody assessed and only the price is discussed. | • Set the negotiation boundaries on terms as well as price, since without them concessions migrate to whatever was left uncontrolled. • Require the walk away point to be set and approved before negotiation begins. • Identify what the company can offer in return, such as volume or payment terms, so negotiation is not one sided pressure. • Prohibit negotiating below the authority limit without approval, including on terms. • Record the plan, so the outcome can be assessed against the intention.
628 | Procurement | Negotiate price, payment, delivery, warranty, retention and risk terms | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Negotiate price, payment, delivery, warranty, retention and risk terms” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Negotiate price, payment, delivery, warranty, retention and risk terms” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he sits with the supplier and works the price, the payment terms, the delivery dates and the risk terms into something acceptable. • Starts when: the negotiation plan is approved and the bidder is invited to negotiate. • How it runs: (1) he opens on the planned position and states what is required. (2) He works through price, payment, delivery, warranty and retention as a package rather than item by item. (3) He tests every supplier qualification and removes what he can. (4) He confirms each agreed point in writing during the process. (5) He closes with a written summary the supplier confirms. • Proof it happened: a negotiation record with the agreed price, terms and the qualifications removed or accepted, confirmed in writing by the supplier. • Where it usually breaks: the price is agreed verbally and the terms are left for later, so the supplier's own terms reappear at order stage. | • Require the negotiated outcome to be confirmed in writing by the supplier before award, since a verbally agreed position is routinely forgotten at order stage. • Negotiate the terms in the same session as the price, because a price agreed first removes all leverage on the terms. • Require warranty, retention and liquidated damages to be settled explicitly, as these are the clauses suppliers quietly drop. • Prohibit negotiation with more than one bidder on the same round without a formal best and final offer process open to all. • Record who attended and what was agreed, so the file supports the award if it is later questioned.
629 | Procurement | Record negotiated savings, cost avoidance and remaining qualifications | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Record negotiated savings, cost avoidance and remaining qualifications” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Record negotiated savings, cost avoidance and remaining qualifications” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he records what the negotiation actually achieved, and what qualifications the company still has to live with. • Starts when: negotiation concludes, before the recommendation is prepared. • How it runs: (1) he calculates the saving against the defined baseline. (2) He separates real savings from cost avoidance. (3) He lists the qualifications that remain accepted. (4) He quantifies the risk of each remaining qualification where possible. (5) He records the outcome against the package. • Proof it happened: a recorded savings and qualification summary with the baseline stated and remaining risks identified. • Where it usually breaks: savings are claimed against the highest bid received, which makes the figure meaningless and unverifiable. | • Define the savings baseline in the SOP as budget, previous price paid or a benchmark, and never the highest or first quotation received. • Require the remaining qualifications to be listed and carried into the order, otherwise they are accepted silently. • Separate cost avoidance from savings in the record, since only one of them reduces the money actually spent. • Require Finance validation of claimed savings above a threshold, as unverified savings figures undermine every procurement report. • Record the negotiation effort against the result, so the value of negotiating is visible for future packages.
630 | Procurement | Prepare the documented procurement recommendation and approval route | Procurement Lead | Trigger: When the tender cutoff passes and compliant quotations are available for evaluation. Action: The Procurement Lead completes “Prepare the documented procurement recommendation and approval route” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable comparison, negotiated position, savings record and procurement recommendation. Control/Handoff: Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the tender cutoff passes and compliant quotations are available for evaluation. | The Procurement Lead completes “Prepare the documented procurement recommendation and approval route” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable comparison, negotiated position, savings record and procurement recommendation. | Technical approval remains with the authorised Technical/QHSE owner, while commercial evaluation remains controlled by Procurement; deviations and noncompetitive awards require documented approval. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he writes up the case for who should win and takes it to whoever has the authority to approve it. • Starts when: evaluation and negotiation are complete and an award decision is needed. • How it runs: (1) he assembles the comparison, the technical evaluation and the negotiation record. (2) He states the recommendation and the reasons. (3) He states the risks and the accepted deviations. (4) He identifies the correct approval level for the value. (5) He submits it and obtains the signed approval before any commitment. • Proof it happened: a signed procurement recommendation with the supporting evaluation and the approval at the correct authority level. • Where it usually breaks: the recommendation is submitted to whoever is available rather than to the correct authority, so the award is approved without proper authority. | • Require the approval level to be determined by the total committed value including options and contingency, not by the base price. • State the risks and the rejected alternatives in the submission, so the approver is making a decision rather than signing a formality. • Prohibit any commitment, including a verbal indication to the supplier, before the signed approval exists. • Set an approval turnaround expectation, because slow approval is the stated reason people commit early. • Keep the approved recommendation as the reference for the order, so the order cannot differ from what was approved.
631 | Procurement | Prepare the purchase-order award package | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Prepare the purchase-order award package” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Prepare the purchase-order award package” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he prepares the full package of documents needed to issue a purchase order properly. • Starts when: the award is approved and the order is to be raised. • How it runs: (1) he assembles the approved recommendation, the requisition and the budget confirmation. (2) He confirms the supplier record and terms are current. (3) He prepares the order content: scope, quantities, prices, delivery and terms. (4) He attaches the technical references and drawings. (5) He submits the package for order approval. • Proof it happened: a complete award package with the approval, the requisition, the supplier details and the order content ready for issue. • Where it usually breaks: the order is raised from the quotation rather than from the negotiated position, so the negotiated terms are lost. | • Require the order to be built from the approved recommendation and the negotiation record, not from the supplier's quotation. • Require a check that the order value matches the approved value, with reapproval where it differs beyond a stated tolerance. • Attach the technical references and drawing revisions to the order, so the delivery can be checked against the same basis. • Verify the supplier bank and tax details are current at order stage, since these may have changed since prequalification. • Require a second person to check the order against the award before issue, as order errors are expensive to correct after acceptance.
632 | Procurement | Prepare the subcontractor appointment and award package | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Prepare the subcontractor appointment and award package” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Prepare the subcontractor appointment and award package” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he prepares everything needed to formally appoint a subcontractor, which is a heavier package than a purchase order. • Starts when: a subcontract award is approved. • How it runs: (1) he assembles the approval, the scope documents and the agreed commercial terms. (2) He prepares the contract with its schedules and annexures. (3) He confirms insurance, bonds and guarantees are arranged. (4) He arranges legal review where required. (5) He submits the package for signature. • Proof it happened: a complete subcontract appointment package with contract, schedules, security documents and legal review evidence. • Where it usually breaks: the subcontractor mobilises on a letter of intent and the contract is never completed, leaving the company with no enforceable terms. | • Set a hard expiry on any letter of intent with a stated value cap, since an open ended letter of intent leaves the company with obligations and no protection. • Require insurance and bonds to be in place before mobilisation, not before the first payment. • Require the scope schedules to reference specific drawings and specification clauses, because scope described in words generates variation claims. • Require legal review for non standard terms and state which clauses may never be amended. • Track unsigned contracts as a reported exception, as this is a widespread and invisible exposure.
633 | Procurement | Draft the purchase order with controlled scope, quantities, price and revisions | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Draft the purchase order with controlled scope, quantities, price and revisions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Draft the purchase order with controlled scope, quantities, price and revisions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he writes the purchase order itself, making sure the scope, quantities, prices and drawing revisions are exactly right. • Starts when: the award package is ready and the order is being created in the system. • How it runs: (1) he enters the item descriptions, quantities and unit prices. (2) He states the applicable drawing and specification revisions. (3) He states the delivery dates and location. (4) He attaches the terms and conditions. (5) He checks the order against the approved award before submitting it for approval. • Proof it happened: a drafted purchase order with controlled descriptions, revisions, prices and attached terms, matching the approved award. • Where it usually breaks: item descriptions are abbreviated, so the wrong variant is supplied and the order gives no basis to reject it. | • Require full item descriptions including size, grade, standard and brand where specified, since an abbreviated description cannot support a rejection. • Require the drawing revision to be stated on the order, so a later revision change is a variation rather than an argument. • State the delivery location precisely, as deliveries to the wrong site or gate cause loss and double handling. • Require the terms and conditions to be attached rather than referenced only, because an unattached reference is often disputed. • Lock the price and quantity fields after approval so amendments require a controlled revision.
634 | Procurement | Draft the subcontract with BOQ, scope, drawings and specification schedules | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Draft the subcontract with BOQ, scope, drawings and specification schedules” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Draft the subcontract with BOQ, scope, drawings and specification schedules” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he drafts the subcontract, attaching the bill of quantities, the scope, the drawings and the specifications that define the work. • Starts when: the appointment package is being prepared. • How it runs: (1) he drafts the contract using the approved template. (2) He attaches the priced bill of quantities as a schedule. (3) He attaches the drawing register with revisions and the specification sections. (4) He states the scope inclusions and exclusions explicitly. (5) He circulates the draft for review before signature. • Proof it happened: a drafted subcontract with the priced BOQ, drawing register and specification schedules attached and referenced. • Where it usually breaks: drawings are attached without a revision register, so which version was contracted becomes unprovable in a dispute. | • Require a drawing register listing each drawing number and revision as a contract schedule, since this is the single most useful document in a scope dispute. • Require exclusions to be stated explicitly, because anything not excluded and not clearly included becomes a claim. • Attach the priced BOQ as the basis for valuing variations, otherwise variations are negotiated from nothing. • State the order of precedence between the documents, as contradictions between contract, specification and drawings are certain. • Require the subcontractor to sign each schedule, not just the contract cover, so they cannot deny receipt.
635 | Procurement | Define delivery milestones, call-off terms, access and required-on-site obligations | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Define delivery milestones, call-off terms, access and required-on-site obligations” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Define delivery milestones, call-off terms, access and required-on-site obligations” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he sets out when things must be delivered, how deliveries are called off, and what access the supplier will get on site. • Starts when: the order or subcontract is being drafted. • How it runs: (1) he sets the delivery milestones against the programme. (2) He defines the call off mechanism where delivery is phased. (3) He states the notice the supplier must give before delivery. (4) He states the site access, working hours and unloading responsibilities. (5) He states the consequence of late delivery. • Proof it happened: defined delivery milestones, call off terms, notice requirements and access obligations stated in the contract. • Where it usually breaks: delivery is stated as a single date for a large quantity, so everything arrives at once and there is nowhere to store it. | • Require phased delivery with call off for bulk materials, since a single bulk delivery creates storage, damage and cash flow problems. • State the advance notice the supplier must give, because unannounced deliveries cause rejection, standing time and demurrage. • State who unloads and who provides the offloading equipment, as this is the commonest delivery dispute. • State site working hours and access restrictions in the contract, not verbally at delivery. • Link the delivery milestones to the payment terms, so late delivery has a commercial consequence.
636 | Procurement | Define submittal, sample, inspection, quality and acceptance requirements | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Define submittal, sample, inspection, quality and acceptance requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Define submittal, sample, inspection, quality and acceptance requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he sets out what the supplier must submit for approval, what samples are needed, and how the goods will be inspected and accepted. • Starts when: the order or subcontract is being drafted. • How it runs: (1) he lists the submittals required and the deadlines. (2) He states the samples required and who approves them. (3) He states the inspection requirements, including any witnessed tests. (4) He states the acceptance criteria and the rejection consequences. (5) He states that manufacture before submittal approval is at the supplier's risk. • Proof it happened: submittal, sample, inspection and acceptance requirements stated in the contract with deadlines and approval routes. • Where it usually breaks: submittal deadlines are not stated, so the supplier submits late and then blames the approval time for the delay. | • State submittal deadlines in the contract with the approval period allowed, so responsibility for approval delay is clear from the start. • State that manufacture or procurement before submittal approval is at the supplier's own risk, since this is the standard argument after a rejection. • Require samples to be retained and labelled by both parties, as the reference for checking deliveries. • State the witnessed inspection requirements and the notice needed, because missed witness points cause rejection of compliant goods. • State the rejection consequence: replacement at the supplier's cost including transport and delay.
637 | Procurement | Define payment, advance-recovery, retention, tax and invoice-document requirements | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Define payment, advance-recovery, retention, tax and invoice-document requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Define payment, advance-recovery, retention, tax and invoice-document requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he sets the payment terms, how any advance is recovered, the retention held, and the documents needed with an invoice. • Starts when: the order or subcontract is being drafted. • How it runs: (1) he states the payment terms and the trigger for payment. (2) He states any advance payment and the recovery mechanism against deliveries. (3) He states the retention percentage and release conditions. (4) He states the tax treatment and the invoice requirements. (5) He lists the documents that must accompany an invoice. • Proof it happened: payment, advance recovery, retention and invoicing requirements stated in the contract with the required document list. • Where it usually breaks: an advance is paid with no recovery schedule, so it is still outstanding when the supplier stops performing. | • Require every advance payment to have a stated recovery schedule and, above a threshold, an advance payment guarantee, since unrecovered advances are the commonest loss to supplier failure. • State the retention percentage, the release milestones and the release conditions, otherwise retention is either never released or released too early. • List the documents required with an invoice, because incomplete invoice packages are the biggest cause of payment delay and supplier friction. • State the tax treatment explicitly with Finance's input, particularly for cross border purchases. • State when the payment period starts: on invoice receipt or on acceptance, as the difference is significant on both sides.
638 | Procurement | Define warranty, DLP, liquidated-damages, security and insurance requirements | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Define warranty, DLP, liquidated-damages, security and insurance requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Define warranty, DLP, liquidated-damages, security and insurance requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he sets the warranty period, the defects liability, the penalties for lateness and the security the supplier must provide. • Starts when: the order or subcontract is being drafted. • How it runs: (1) he states the warranty period and what it covers. (2) He aligns the defects liability period with the main contract obligation. (3) He states the liquidated damages for delay and the cap. (4) He states the bonds or guarantees required. (5) He states the insurance required and the evidence needed. • Proof it happened: warranty, defects liability, liquidated damages, security and insurance requirements stated in the contract. • Where it usually breaks: the warranty period runs from delivery rather than from handover, so it expires before the building is even occupied. | • Require warranty and defects liability to run from project handover rather than from delivery, since materials delivered early otherwise lose their cover. • Align the defects liability period back to back with the main contract, or the company carries an uncovered gap. • State liquidated damages with the rate and the cap, because an unstated cap is usually challenged and an unstated rate is unenforceable. • Require insurance certificates before mobilisation and track their expiry through the contract period. • State what the bond covers and its validity period, and diarise the expiry so it is extended rather than lapsing.
639 | Procurement | Coordinate Legal review of non-standard or material contractual terms | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Coordinate Legal review of non-standard or material contractual terms” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Coordinate Legal review of non-standard or material contractual terms” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: when the terms differ from the standard or the risk is significant, he gets Legal to review before anything is signed. • Starts when: a supplier proposes non standard terms, or the value or risk crosses the stated threshold. • How it runs: (1) he identifies the terms that deviate from the standard. (2) He summarises the commercial context for Legal. (3) He submits the draft for review with the specific questions. (4) He incorporates the advice or documents why it was not followed. (5) He retains the review evidence with the contract. • Proof it happened: a legal review record with the advice given and evidence of how it was addressed in the final contract. • Where it usually breaks: Legal review is requested on the day of signature, so the advice arrives after the commercial position is already fixed. | • Require legal review before the commercial position is closed, not after, since advice received at signature can no longer be acted on. • Define the thresholds and clause types that trigger mandatory review, so it does not depend on the buyer's judgement. • Require the buyer to summarise the commercial context, because Legal cannot assess risk on wording alone. • Record where legal advice was not followed and who accepted that risk, as this is a governance decision rather than a buyer's choice. • Set a review turnaround service level, otherwise slow review becomes the excuse for skipping it.
640 | Procurement | Route signature, record vendor acceptance and issue the controlled FirstBit commitment | Procurement Lead | Trigger: When the procurement recommendation is approved and commitment documents must be formed. Action: The Procurement Lead completes “Route signature, record vendor acceptance and issue the controlled FirstBit commitment” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. Control/Handoff: Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When the procurement recommendation is approved and commitment documents must be formed. | The Procurement Lead completes “Route signature, record vendor acceptance and issue the controlled FirstBit commitment” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a complete, signed and controlled PO or subcontract recorded as a FirstBit commitment. | Scope, price, revisions, delivery, quality, payment, tax, warranty, retention, securities and approval authority are checked before issue; non-standard terms go to Legal. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he gets the order or contract signed, confirms the supplier has accepted it, and records the commitment in the system. • Starts when: the order or contract is approved and ready for issue. • How it runs: (1) he routes the document for signature by the correct authority. (2) He issues it to the supplier. (3) He obtains the supplier's signed acceptance or written acknowledgement. (4) He records the committed value in FirstBit against the budget. (5) He files the executed document in the controlled record. • Proof it happened: a signed and accepted order or contract, with the commitment recorded in the system and the executed copy filed. • Where it usually breaks: the order is issued but never acknowledged, so the supplier later denies the delivery date or the price. | • Require written supplier acceptance before the order is treated as live, since an unacknowledged order leaves both the price and the date unconfirmed. • Require the commitment to be recorded in the system at issue, not at invoice, because committed cost is what consumes the budget. • Verify that the signed version matches the approved version, as unnoticed changes between approval and signature do occur. • Store the executed document in the controlled record rather than in personal email, since this is the enforceable document. • Set an acknowledgement chase period and escalate where a supplier will not acknowledge.
641 | Procurement | Conduct the supplier or subcontractor post-award kick-off | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Conduct the supplier or subcontractor post-award kick-off” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Conduct the supplier or subcontractor post-award kick-off” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: after the award he holds a start up meeting with the supplier so both sides agree how the job will actually run. • Starts when: immediately after award, before deliveries or site work begin. • How it runs: (1) he arranges the meeting with the supplier and the project team. (2) They confirm scope, programme, submittals and delivery arrangements. (3) They agree communication routes and named contacts. (4) They agree the invoicing and documentation requirements. (5) He issues the minutes and the agreed actions. • Proof it happened: kick off meeting minutes with agreed programme, submittal dates, contacts and actions, issued to both parties. • Where it usually breaks: no kick off is held for material orders, so the first contact after award is a chase call when the delivery is already late. | • Make a kick off mandatory above a value or criticality threshold, since the first weeks after award are when recoverable delays begin. • Agree the submittal dates at the kick off, because submittal delay is the most common cause of late delivery. • Confirm named contacts on both sides, as orders routed to a general email address are the ones that stall. • Confirm the invoicing and documentation requirements at kick off, which prevents most later payment disputes. • Issue minutes with actions and dates, so the meeting produces a record rather than goodwill.
642 | Procurement | Maintain the material-submittal, sample and technical-approval register | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Maintain the material-submittal, sample and technical-approval register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Maintain the material-submittal, sample and technical-approval register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he tracks every material submittal and sample through to technical approval, because nothing can be manufactured until they are approved. • Starts when: the order is placed and submittals become due. • How it runs: (1) he records each required submittal with its due date. (2) He chases the supplier for submission. (3) He routes it for technical and consultant review. (4) He records the outcome: approved, approved with comments or rejected. (5) He chases resubmissions and records final approval. • Proof it happened: a submittal register with dates submitted, reviewed, outcome and final approval status. • Where it usually breaks: the register tracks submission but not approval, so an item sitting rejected for weeks looks the same as an approved one. | • Track approval status rather than submission status, since a submitted and rejected item is no closer to delivery than an unsubmitted one. • Show the ageing of items awaiting review, because approval delay inside the company is a major hidden cause of late delivery. • Record resubmission cycles per item, as repeated rejection points at a supplier who does not understand the specification. • Link the submittal register to the long lead register, so approval delay on critical items is visible in the same place. • Escalate submittals overdue beyond a stated period rather than continuing to chase quietly.
643 | Procurement | Track shop drawings, samples, manufacturing and inspection-release milestones | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Track shop drawings, samples, manufacturing and inspection-release milestones” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Track shop drawings, samples, manufacturing and inspection-release milestones” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he follows the supplier's progress through shop drawings, samples, manufacture and inspection release. • Starts when: submittals are approved and manufacture begins. • How it runs: (1) he agrees the manufacturing milestones with the supplier. (2) He obtains progress updates against them. (3) He arranges inspections at the agreed stages. (4) He obtains the inspection release before dispatch. (5) He records the milestone status and flags slippage. • Proof it happened: milestone tracking records with progress updates, inspection records and dispatch release evidence. • Where it usually breaks: progress is accepted from the supplier's verbal assurance until the delivery date passes and nothing has been made. | • Require evidence of progress such as photographs or an inspection rather than verbal assurance, since suppliers report comfort until the date passes. • Set milestone dates that fall well before the delivery date, so slippage is visible in time to act. • Require pre dispatch inspection and release for critical or imported items, because rejecting goods after arrival is very expensive. • Escalate a missed manufacturing milestone immediately rather than waiting for the delivery date. • Record the actual against planned milestone dates, as the pattern identifies suppliers who consistently overpromise.
644 | Procurement | Expedite long-lead and critical packages against the procurement schedule | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Expedite long-lead and critical packages against the procurement schedule” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Expedite long-lead and critical packages against the procurement schedule” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he chases the long lead and critical items hard, because these are the ones that stop the site if they arrive late. • Starts when: a critical package is awarded, and continuously through manufacture and shipping. • How it runs: (1) he sets a chase frequency for each critical item. (2) He contacts the supplier for status against the milestones. (3) He verifies the status rather than accepting assurances. (4) He escalates within the supplier's organisation where progress stalls. (5) He reports the position and any recovery action needed. • Proof it happened: an expediting log with contacts, verified status, escalations and recovery actions per critical item. • Where it usually breaks: expediting stops once a delivery date is confirmed, and the item slips again unnoticed. | • Set a mandatory chase frequency by criticality, so expediting continues after a date is confirmed rather than stopping at the first assurance. • Require the status to be verified against evidence, since a confirmed date without progress evidence means very little. • Define the escalation path within the supplier's organisation, because buyer to salesperson contact rarely changes a production queue. • Record every contact in the expediting log, as this is the evidence base if a delay claim follows. • Report items where recovery is no longer possible immediately, so the programme can be replanned rather than surprised.
645 | Procurement | Confirm delivery call-offs with Logistics, Store and the Project Engineer | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Confirm delivery call-offs with Logistics, Store and the Project Engineer” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Confirm delivery call-offs with Logistics, Store and the Project Engineer” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he confirms with logistics, the store and the site engineer that a delivery is wanted now, and that there is somewhere to put it. • Starts when: a delivery is due or a call off is being released. • How it runs: (1) he confirms the site actually needs the material on the planned date. (2) He confirms the store has space and handling capability. (3) He confirms transport and access arrangements with Logistics. (4) He releases the call off to the supplier. (5) He confirms the delivery window and notifies all parties. • Proof it happened: a confirmed call off record with site, store and logistics confirmation and a notified delivery window. • Where it usually breaks: material is called off to hit a purchase order date rather than a site need, so it sits in the store deteriorating. | • Require site need to be reconfirmed before every call off, since delivering to a contractual date rather than a site need creates storage loss and damage. • Require the store to confirm space and handling capability, because deliveries with nowhere to go are refused or dumped. • Notify a delivery window rather than a date, as this is what allows the store to plan labour and equipment. • Confirm access restrictions for large or heavy loads in advance, since access failures cause standing time charges. • Record deferred call offs and the reason, so supplier storage or price escalation claims can be assessed.
646 | Procurement | Control purchase-order and subcontract variations, amendments and revised commitments | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Control purchase-order and subcontract variations, amendments and revised commitments” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Control purchase-order and subcontract variations, amendments and revised commitments” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: when the order needs to change, he controls the change formally rather than letting it happen by conversation. • Starts when: scope, quantity, price, specification or delivery needs to change on a live order or subcontract. • How it runs: (1) he receives the change requirement with its justification. (2) He confirms the technical and budget approval for the change. (3) He agrees the commercial effect with the supplier. (4) He issues a formal amendment referencing the original order. (5) He updates the committed value in the system. • Proof it happened: an issued and accepted order amendment with approval evidence and the updated commitment recorded. • Where it usually breaks: changes are agreed verbally on site and only appear as an unexpected invoice at the end. | • State that no variation is valid without a written amendment, and that verbal site instructions to suppliers create no obligation. • Require the amendment to be approved at the authority level for the revised total value, not the incremental value. • Require the commitment in the system to be updated at amendment, so the budget position stays accurate. • Require the programme effect of a variation to be stated, since suppliers routinely claim time as well as money later. • Track variation volume by package and cause, because heavy variation usually indicates a poor original scope definition.
647 | Procurement | Control suspension, cancellation, replacement-source and termination actions | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Control suspension, cancellation, replacement-source and termination actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Control suspension, cancellation, replacement-source and termination actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: when an order has to be stopped, cancelled or moved to another supplier, he manages that properly. • Starts when: a decision is taken to suspend, cancel, replace or terminate. • How it runs: (1) he checks the contractual position and the notice required. (2) He obtains the approval for the action at the correct level. (3) He issues the formal notice with the required wording. (4) He establishes what is owed for work done and materials procured. (5) He arranges the replacement source and records the additional cost. • Proof it happened: formal notices issued, approval evidence, a settlement position for work done and the replacement arrangements recorded. • Where it usually breaks: an order is cancelled by email without checking the cancellation terms, and the supplier claims the full value. | • Require the contractual cancellation and suspension provisions to be checked before any notice, since informal cancellation can trigger the full contract value. • Require CLO review for terminations, because defective notice destroys the company's position. • Establish what the supplier has already committed or manufactured, as this determines the real cost of cancelling. • Secure any materials or work already paid for before the relationship ends. • Record the additional cost of the replacement source, so recovery can be pursued and the decision can be reviewed.
648 | Procurement | Manage supplier and subcontractor claims, disputes and commercial correspondence | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Manage supplier and subcontractor claims, disputes and commercial correspondence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Manage supplier and subcontractor claims, disputes and commercial correspondence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he handles disagreements with suppliers, from a disputed invoice to a formal claim, in writing and on the record. • Starts when: a supplier raises a claim, or the company has a claim against a supplier. • How it runs: (1) he establishes the facts and the contractual position. (2) He gathers the supporting records. (3) He responds within the contractual time limits. (4) He takes CLO advice where the exposure is significant. (5) He negotiates a settlement or escalates, and records the outcome. • Proof it happened: a claim file with the contractual analysis, the correspondence, the evidence and the recorded settlement. • Where it usually breaks: a claim is answered informally and late, so the company loses both the time bar defence and the record of its position. | • Require responses within the contractual time limits, since a late response can concede a claim regardless of its merit. • Require all claim correspondence to go through a single controlled route, because parallel conversations create contradictory positions. • Require the contractual basis to be stated in every response, rather than arguing on fairness. • Involve the CLO above a stated exposure and before any admission is made. • Record claims by cause, as the pattern usually points at a specific weakness in the company's own contract documents.
649 | Procurement | Coordinate rejected-material return, replacement, debit note and credit-note evidence | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Coordinate rejected-material return, replacement, debit note and credit-note evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Coordinate rejected-material return, replacement, debit note and credit-note evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: when material is rejected, he arranges its return or replacement and makes sure the money is recovered. • Starts when: material is rejected at receipt or found defective in use. • How it runs: (1) he obtains the rejection record and the reason from the store or site. (2) He notifies the supplier formally within the contract timeframe. (3) He arranges collection or return and the replacement delivery. (4) He raises the debit note for costs incurred. (5) He obtains the supplier's credit note and confirms the account is corrected. • Proof it happened: a rejection record, supplier notification, return evidence, debit note and the matching credit note. • Where it usually breaks: rejected material is returned but no credit note is obtained, so the company pays for goods it sent back. | • Require the credit note to be tracked to receipt, since returning goods without recovering the money is a straight loss and it happens often. • Notify the supplier within the contractual rejection period, as late rejection can be treated as acceptance. • Require the return to be documented with a gate pass and the supplier's acknowledgement, otherwise the goods disappear and remain payable. • Recover the associated costs such as offloading, storage and demurrage through a debit note, not only the goods value. • Record rejections against the supplier scorecard, as rejection frequency should influence future awards.
650 | Procurement | Verify supplier invoice packages against PO, GRN, delivery and tax requirements | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Verify supplier invoice packages against PO, GRN, delivery and tax requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Verify supplier invoice packages against PO, GRN, delivery and tax requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks the supplier's invoice actually matches the order and what was received before it goes to Finance. • Starts when: a supplier invoice is received for payment. • How it runs: (1) he matches the invoice to the purchase order on price, quantity and terms. (2) He matches it to the goods received note and the delivery documents. (3) He checks the tax treatment and the invoice format requirements. (4) He resolves any mismatch with the supplier before submission. (5) He passes the verified package to Finance. • Proof it happened: a verified invoice package with the three way match between order, receipt and invoice, and the tax compliance check. • Where it usually breaks: invoices are passed for payment on the basis of the order alone, so goods never delivered get paid for. | • Require a three way match of order, goods received note and invoice before submission, since payment on order and invoice alone pays for goods that never arrived. • Require quantity received rather than quantity ordered to drive payment, particularly on partial deliveries. • Check advance recovery and retention deduction on every invoice, as these are routinely forgotten and rarely recovered later. • Verify the tax invoice format meets the legal requirement, because a defective tax invoice can lose the input tax recovery. • Return non compliant invoices promptly with the reason, rather than holding them, since silent holding damages supplier relationships.
651 | Procurement | Verify subcontractor payment packages against certification, retention and contract terms | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Verify subcontractor payment packages against certification, retention and contract terms” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Verify subcontractor payment packages against certification, retention and contract terms” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he checks subcontractor payment applications against what has actually been certified as done, and against the contract terms. • Starts when: a subcontractor submits a payment application. • How it runs: (1) he checks the application against the certified work quantities. (2) He verifies the rates against the contract BOQ. (3) He applies the retention, advance recovery and any deductions. (4) He checks the supporting documents and statutory requirements. (5) He passes the verified package to Finance. • Proof it happened: a verified subcontractor payment package with certified quantities, contract rates, deductions and supporting documents. • Where it usually breaks: payment is made against the subcontractor's claimed progress rather than certified progress, so overpayment builds up quietly. | • Require certified progress from the project team as the basis for payment, since paying claimed progress creates overpayment that is very hard to recover. • Require cumulative tracking so that overpayment against earlier certificates is visible rather than hidden in each period. • Apply retention and advance recovery on every certificate as a system rule rather than a manual step. • Require statutory documents such as wage payment evidence where the contract or law demands them. • Check the position against any pending back charges or defects before certifying payment.
652 | Procurement | Submit complete supplier and subcontractor payment packs to Finance | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Submit complete supplier and subcontractor payment packs to Finance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Submit complete supplier and subcontractor payment packs to Finance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he hands Finance a complete payment pack, so payments are not delayed by missing documents. • Starts when: invoice or payment verification is complete. • How it runs: (1) he assembles the invoice, order, receipt documents and approvals. (2) He includes the deduction and recovery calculations. (3) He confirms the supplier bank details are the verified ones on record. (4) He submits to Finance within the agreed cut off. (5) He tracks the payment and responds to Finance queries. • Proof it happened: a submitted payment pack with all supporting documents, submitted within the cut off and tracked to payment. • Where it usually breaks: packs are submitted incomplete and bounce back and forth, so suppliers are paid late for reasons that have nothing to do with them. | • Define the payment pack contents as a checklist and require completeness before submission, since incomplete packs are the main cause of late payment. • State that bank details are taken from the verified vendor master and never from the invoice, as invoice bank details are a common fraud route. • Set submission cut offs aligned to the Finance payment run, so packs are not held for a full cycle. • Track payment status so procurement can answer supplier queries rather than passing them to Finance. • Report late payment causes, because supplier pricing and cooperation both deteriorate when payment is unreliable.
653 | Procurement | Maintain supplier and subcontractor performance scorecards and corrective actions | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Maintain supplier and subcontractor performance scorecards and corrective actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Maintain supplier and subcontractor performance scorecards and corrective actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he scores how suppliers actually performed and follows up with those who are failing. • Starts when: at the scoring cycle, at package completion, and after any significant failure. • How it runs: (1) he collects the performance data: delivery, quality, documentation and responsiveness. (2) He scores against the defined criteria. (3) He shares the score with the supplier. (4) He agrees corrective actions where performance is poor. (5) He feeds the score into future sourcing decisions. • Proof it happened: completed supplier scorecards with data based scores, shared with suppliers and corrective actions agreed. • Where it usually breaks: scores are based on impressions rather than data, so they are disputed and then ignored. | • Base scores on recorded data such as on time delivery percentage and rejection rate, since impression based scores cannot survive a supplier challenge. • Share the scorecard with the supplier, because a score they never see cannot change their behaviour. • Define the consequence of poor scores explicitly: no invitation, probation or removal, or the scorecard has no effect. • Require the score to be checked before every shortlist, so history influences the next award. • Include the company's own contribution such as late payment, since one sided scoring loses supplier credibility.
654 | Procurement | Prepare weekly and monthly procurement status, commitments and exception reports | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Prepare weekly and monthly procurement status, commitments and exception reports” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Prepare weekly and monthly procurement status, commitments and exception reports” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he reports where procurement stands each week and each month, including what is going wrong. • Starts when: at the weekly and monthly reporting cycles. • How it runs: (1) he compiles the package status from the register. (2) He reports the commitments made in the period. (3) He reports the exceptions: overdue deliveries, pending approvals and at risk items. (4) He states the actions and the owners. (5) He issues the report to the CPO and the project teams. • Proof it happened: issued weekly and monthly procurement reports with status, commitments, exceptions and actions. • Where it usually breaks: the report describes activity rather than exceptions, so the reader cannot see what needs a decision. | • Require the report to lead with exceptions and decisions needed, since a report of completed activity gives management nothing to act on. • Generate it from the package register rather than compiling separately, so the report and the records cannot disagree. • Show committed value against budget by package, because this is the number the project manager actually needs. • Show ageing on overdue items, as an item overdue for two months needs different treatment from one overdue for two days. • Keep the format fixed so periods are comparable and the report can be consolidated across projects.
655 | Procurement | Close purchase orders and subcontracts with final account, retention, warranty and archive records | Procurement Lead | Trigger: When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. Action: The Procurement Lead completes “Close purchase orders and subcontracts with final account, retention, warranty and archive records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. Control/Handoff: Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. Continuity/Escalation: A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. Timing: To be confirmed. | When a PO/subcontract is awarded, a milestone becomes due, an invoice arrives or the package reaches closeout. | The Procurement Lead completes “Close purchase orders and subcontracts with final account, retention, warranty and archive records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an updated expediting record, controlled change, complete payment pack, vendor scorecard or closed procurement file. | Procurement confirms delivery/performance evidence and contract terms; Finance controls payment and Technical/Projects confirm acceptance or progress before liability is released. | A competent authorised procurement professional may provide operational backup; CPO approvals remain reserved and material cost, programme, vendor, contract or compliance exceptions escalate to the CPO. | To be confirmed. | • In plain words: he closes out finished orders and subcontracts properly, settling the account, releasing retention and archiving the records. • Starts when: delivery or subcontract works are complete and the defects period is running or expired. • How it runs: (1) he confirms all deliveries or works are complete and accepted. (2) He agrees the final account including all variations. (3) He confirms warranties, manuals and certificates have been received. (4) He processes the retention release when due. (5) He closes the commitment in the system and archives the file. • Proof it happened: an agreed final account, received warranty documents, retention release evidence and a closed and archived record. • Where it usually breaks: orders are left open in the system after completion, so the committed cost figure stays wrong for months. | • Require open orders to be reviewed and closed at a set frequency, since open commitments distort the committed cost position and hide available budget. • Require warranty documents and manuals to be received before final payment, as they are almost impossible to obtain afterwards. • Diarise retention release dates with an owner, because unclaimed retention is money the company simply loses. • Require the final account to be agreed in writing, so no late claim appears after the file is closed. • Archive the complete package file, since procurement records are the first evidence needed in any later dispute.
656 | Procurement | Create the delivery and transport register from approved purchase orders | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Create the delivery and transport register from approved purchase orders” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Create the delivery and transport register from approved purchase orders” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he builds the list of every delivery that has to happen, taken from the orders that have been placed. • Starts when: purchase orders are issued and deliveries become due. • How it runs: (1) he takes the delivery requirements from each approved order. (2) He records the supplier, material, quantity and required date. (3) He records the delivery location and any special handling. (4) He assigns a delivery reference. (5) He maintains the register as deliveries are planned and completed. • Proof it happened: a delivery and transport register built from the approved orders, with references, dates and locations. • Where it usually breaks: the register is built only for large deliveries, so small ones arrive unannounced with nobody expecting them. | • Build the register from every order rather than only the large ones, since unplanned small deliveries are the ones that arrive with nobody to receive them. • Populate it automatically from the order data where possible, so it cannot drift from what was actually ordered. • Record the special handling requirement at entry, because this determines the equipment and labour needed. • Keep one register shared with the store and the project, not separate copies. • Flag deliveries with no confirmed date, as these are the ones that surprise everyone.
657 | Procurement | Translate required-on-site dates into supplier dispatch and delivery call-offs | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Translate required-on-site dates into supplier dispatch and delivery call-offs” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Translate required-on-site dates into supplier dispatch and delivery call-offs” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he turns the date site needs material into the date the supplier must dispatch it. • Starts when: a delivery is being planned against the required on site date. • How it runs: (1) he takes the required on site date. (2) He subtracts the transit time and any clearance time. (3) He sets the dispatch date and the call off date. (4) He confirms the dates with the supplier. (5) He records the agreed dispatch and delivery dates. • Proof it happened: dispatch and call off dates derived from the required on site date, confirmed with the supplier. • Where it usually breaks: transit and clearance time are underestimated, so dispatch happens on time and delivery is still late. | • Derive the dispatch date backwards from the required on site date including transit and clearance, since on time dispatch does not mean on time delivery. • Use actual historical transit times rather than carrier estimates, particularly for imports. • Confirm the dispatch date with the supplier in writing, as an assumed date is not a commitment. • Build in a buffer for critical items and state it explicitly rather than hiding it. • Reconfirm the required date with site before releasing the call off.
658 | Procurement | Confirm supplier manufacturing, packing and dispatch readiness | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Confirm supplier manufacturing, packing and dispatch readiness” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Confirm supplier manufacturing, packing and dispatch readiness” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he checks the supplier has actually finished making and packing the goods before arranging transport. • Starts when: dispatch is approaching. • How it runs: (1) he contacts the supplier for readiness confirmation. (2) He confirms manufacturing is complete and the goods are packed. (3) He confirms the quantity and packing details. (4) He confirms any pre dispatch inspection is released. (5) He records readiness before booking transport. • Proof it happened: a recorded readiness confirmation covering manufacture, packing and inspection release before transport is booked. • Where it usually breaks: transport is booked on the supplier's promise, and the vehicle arrives to find nothing ready, which is charged in full. | • Require confirmed readiness before booking transport, since a failed collection is charged in full and delays everything behind it. • Require the packed quantity to be confirmed, because partial readiness means a partial load and a second trip. • Confirm any pre dispatch inspection release, as goods dispatched without it may be rejected on arrival. • Record who at the supplier confirmed readiness, so the cost of a failed collection can be recovered. • Reconfirm on the day of collection for long distance movements.
659 | Procurement | Confirm project access, route, gate, work-front and delivery-window restrictions | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Confirm project access, route, gate, work-front and delivery-window restrictions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Confirm project access, route, gate, work-front and delivery-window restrictions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he checks the vehicle can actually get to where the material needs to go, and when. • Starts when: a delivery is being planned. • How it runs: (1) he confirms the site access route and any restrictions. (2) He checks height, width and weight limits on the route. (3) He confirms the gate and the permitted delivery window. (4) He confirms the work front is ready to receive. (5) He records the access arrangements. • Proof it happened: recorded access arrangements covering route, restrictions, gate, delivery window and work front readiness. • Where it usually breaks: an oversize vehicle is dispatched without checking the route, and it is turned back at a bridge or a junction. | • Check route height, width and weight restrictions for every oversize or heavy load, since a vehicle turned back costs the full journey twice and the delay. • Confirm the permitted delivery window with the site and the authority, as deliveries outside permitted hours are refused. • Confirm the work front or store is ready, because a delivery with nowhere to go is the commonest cause of standing time. • Record the access constraints against the site, so they do not have to be rediscovered each time. • Notify the driver of the restrictions in writing, not verbally.
660 | Procurement | Obtain transport or carrier quotations and prepare the logistics recommendation | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Obtain transport or carrier quotations and prepare the logistics recommendation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Obtain transport or carrier quotations and prepare the logistics recommendation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he gets transport prices and recommends which carrier to use. • Starts when: transport is required and not included in the supply. • How it runs: (1) he specifies the movement: load, route, equipment and timing. (2) He obtains quotations from approved carriers. (3) He compares on total cost including waiting and access charges. (4) He checks capability for the specific load. (5) He recommends the carrier with the basis recorded. • Proof it happened: transport quotations compared on a common basis with a recorded recommendation. • Where it usually breaks: only the base rate is compared, so waiting time and access charges make the cheapest quote the most expensive. | • Compare on total cost including waiting time, detention and access charges, since base rate comparison routinely selects the most expensive carrier. • Specify the load and equipment precisely in the enquiry, because a quote for the wrong equipment is worthless. • Check the carrier's capability and insurance for the specific load rather than in general. • Record the free waiting time allowed in each quote, as this is where demurrage claims originate. • Use framework rates for routine movements so each delivery does not need a tender.
661 | Procurement | Arrange vehicle permits, lifting equipment, unloading labour and traffic control | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Arrange vehicle permits, lifting equipment, unloading labour and traffic control” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Arrange vehicle permits, lifting equipment, unloading labour and traffic control” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges the permits, cranes, labour and traffic control the delivery will need. • Starts when: a delivery requires permits or special handling. • How it runs: (1) he identifies the permits required for the vehicle or route. (2) He arranges the lifting equipment appropriate to the load. (3) He arranges the unloading labour. (4) He arranges traffic control where required. (5) He confirms everything is in place before the vehicle is dispatched. • Proof it happened: arranged permits, lifting equipment, labour and traffic control confirmed in place before dispatch. • Where it usually breaks: the crane is booked for the wrong capacity or radius, so the load cannot be lifted when the vehicle arrives. | • Specify lifting equipment by the actual load weight and required radius, since a crane booked on approximate information cannot lift and the whole delivery fails. • Check permit lead times, because oversize and night movement permits are not issued on demand. • Confirm the unloading labour and equipment are actually allocated, not merely requested. • Arrange traffic control where the delivery affects public roads, as this is both a legal and a safety requirement. • Confirm all arrangements before dispatch rather than while the vehicle is en route.
662 | Procurement | Confirm storage space, laydown area, protection and receiving resources | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Confirm storage space, laydown area, protection and receiving resources” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Confirm storage space, laydown area, protection and receiving resources” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he confirms there is somewhere to put the material and someone to receive it. • Starts when: a delivery is being planned. • How it runs: (1) he confirms the storage space or laydown area is available. (2) He confirms the protection needed for the material. (3) He confirms the receiving personnel will be present. (4) He confirms the handling equipment is available. (5) He records the receiving arrangements. • Proof it happened: confirmed storage, protection, receiving personnel and handling equipment before the delivery is released. • Where it usually breaks: material arrives with no protected storage, so it deteriorates before it is ever used. | • Confirm protected storage appropriate to the material before release, since material stored in the open deteriorates and the loss is invisible until installation. • Confirm receiving personnel by name for the delivery window, as a delivery with nobody to receive it is either refused or dumped. • Confirm the handling equipment matches the package weight and dimensions. • Check the laydown area does not obstruct access or work fronts. • Record the arrangements, so responsibility for loss after delivery is clear.
663 | Procurement | Prepare delivery-risk, weather, access and contingency actions | Logistics Coordinator | Trigger: When an approved PO, delivery milestone or project call-off requires logistics planning. Action: The Logistics Coordinator completes “Prepare delivery-risk, weather, access and contingency actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. Control/Handoff: The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When an approved PO, delivery milestone or project call-off requires logistics planning. | The Logistics Coordinator completes “Prepare delivery-risk, weather, access and contingency actions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a delivery plan with confirmed supplier readiness, access, transport, lifting, storage and contingency arrangements. | The Logistics Coordinator does not dispatch until the approved item, destination, date, resources and HSE/access requirements are confirmed with Procurement, Store and Projects. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he thinks through what could go wrong with the delivery and plans for it. • Starts when: a delivery is being planned, particularly a critical or difficult one. • How it runs: (1) he identifies the risks: weather, access, equipment failure and timing. (2) He assesses the consequence of each. (3) He prepares the contingency for the significant ones. (4) He confirms the fallback arrangements. (5) He records the risk and contingency position. • Proof it happened: a delivery risk assessment with contingency actions prepared for the significant risks. • Where it usually breaks: no contingency exists, so a weather delay or an equipment failure turns into a full day of standing time. | • Require a contingency for critical deliveries rather than only a plan, since a single equipment or weather failure otherwise costs a full day of standing time. • Check the weather forecast for lifting operations, as wind limits stop cranes regardless of the schedule. • Identify an alternative access route where the primary route is constrained. • State who decides to postpone and by when, so the decision is not taken at the gate. • Record the cost of failure, as this justifies the contingency effort.
664 | Procurement | Book the approved vehicle, carrier or freight movement | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Book the approved vehicle, carrier or freight movement” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Book the approved vehicle, carrier or freight movement” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he formally books the vehicle or the freight movement once everything is confirmed. • Starts when: readiness, access and receiving are all confirmed. • How it runs: (1) he confirms the carrier, vehicle type and timing. (2) He confirms the rate and the free waiting time. (3) He issues the booking with the collection and delivery details. (4) He obtains the booking confirmation. (5) He records the booking reference and the agreed terms. • Proof it happened: a confirmed booking with the vehicle type, timing, rate and waiting time terms recorded. • Where it usually breaks: the booking is made verbally, so the rate and the waiting time allowance are disputed when the invoice arrives. | • Issue every booking in writing with the rate and free waiting time stated, since verbal bookings produce disputed invoices that cannot be defended. • Record the booking reference, as this is needed for every subsequent query. • Confirm the vehicle type booked matches the load, because a substituted vehicle can be unable to carry or unload. • State the collection and delivery contact details on the booking, so the driver does not call the coordinator for every detail. • Require a cancellation policy in the booking terms.
665 | Procurement | Coordinate supplier collection, release and dispatch authorisation | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Coordinate supplier collection, release and dispatch authorisation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Coordinate supplier collection, release and dispatch authorisation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges for the goods to be released and collected from the supplier. • Starts when: the booking is confirmed and collection is due. • How it runs: (1) he issues the collection authorisation to the supplier. (2) He confirms the vehicle and driver details to the supplier. (3) He confirms the documents to be handed over at collection. (4) He confirms the release is authorised, including payment conditions where relevant. (5) He records the collection. • Proof it happened: an issued collection authorisation with vehicle details, document requirements and the release confirmed. • Where it usually breaks: the supplier holds the goods for payment and nobody knew, so the vehicle arrives and cannot collect. | • Confirm the release is authorised including any payment condition before dispatching the vehicle, since a supplier holding goods for payment turns a collection into a wasted journey. • Notify the supplier of the vehicle and driver details in advance, as unidentified drivers are refused at the gate. • State the documents the supplier must hand over at collection, otherwise they arrive without a packing list or certificate. • Require the supplier to confirm loading is complete before the vehicle departs. • Record the collection time, as this starts the transit clock.
666 | Procurement | Verify packing list, package marking, dimensions, weight and handling requirements | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Verify packing list, package marking, dimensions, weight and handling requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Verify packing list, package marking, dimensions, weight and handling requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he checks the packing list, the markings, the sizes and weights match what is being moved. • Starts when: goods are dispatched or received. • How it runs: (1) he checks the packing list against the order. (2) He checks the package markings identify the contents and the destination. (3) He checks the declared dimensions and weights. (4) He checks the handling requirements are marked. (5) He records any discrepancy before the goods move. • Proof it happened: a verification record covering the packing list, markings, dimensions, weights and handling requirements. • Where it usually breaks: the declared weight is wrong, so the lifting equipment arranged is inadequate and the lift is unsafe. | • Verify the declared weight rather than accepting it, since lifting equipment selected on an understated weight is an immediate safety risk. • Require package markings to identify contents and destination, because unmarked packages are opened on site to identify them and then damaged. • Check the packing list against the order before dispatch, as shortages found on arrival are harder to resolve. • Record handling and orientation requirements, since incorrectly handled goods arrive damaged. • Photograph the loaded condition for high value or fragile items.
667 | Procurement | Verify vehicle, driver, carrier, insurance and statutory transport documents | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Verify vehicle, driver, carrier, insurance and statutory transport documents” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Verify vehicle, driver, carrier, insurance and statutory transport documents” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he checks the vehicle, the driver and the carrier have valid documents before the movement. • Starts when: a movement is being booked or is about to start. • How it runs: (1) he checks the vehicle registration and fitness documents. (2) He checks the driver's licence and permits. (3) He checks the carrier's insurance covers the load. (4) He checks the statutory transport documents required. (5) He records the verification. • Proof it happened: a verification record covering vehicle, driver, carrier insurance and statutory documents. • Where it usually breaks: the carrier's insurance does not cover the load value, so a loss in transit falls entirely on the company. | • Check the carrier's insurance limit against the load value, since carrier liability is usually capped far below the value of what is being moved. • Verify driver licensing for the vehicle class and the load type, particularly for hazardous or oversize movements. • Check the vehicle fitness and permit validity, as an impounded vehicle strands the load. • Record the verification, so responsibility is clear if a document turns out to be invalid. • Require the carrier to notify any vehicle or driver substitution.
668 | Procurement | Prepare import, export and customs documents when cross-border movement applies | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Prepare import, export and customs documents when cross-border movement applies” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Prepare import, export and customs documents when cross-border movement applies” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: for anything crossing a border, he prepares the import and export paperwork. • Starts when: a cross border movement is planned. • How it runs: (1) he identifies the documents required by both jurisdictions. (2) He obtains the commercial invoice, packing list and certificates of origin. (3) He checks the descriptions and values are consistent across documents. (4) He submits or provides them to the broker. (5) He records the document set and the submission. • Proof it happened: a complete import or export document set with consistent descriptions and values, submitted and recorded. • Where it usually breaks: descriptions or values differ between documents, so the shipment is held at customs and storage charges accumulate daily. | • Check descriptions, quantities and values match exactly across every document, since any inconsistency holds the shipment at customs and storage charges accrue daily. • Prepare the documents before dispatch rather than while the shipment is in transit. • Check certificate of origin requirements early, as these cannot be obtained retrospectively. • Confirm who is the importer of record and the responsibility for duty. • Keep the full document set, because customs queries arrive months later.
669 | Procurement | Coordinate HS-code, duty, clearance and broker requirements when applicable | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Coordinate HS-code, duty, clearance and broker requirements when applicable” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Coordinate HS-code, duty, clearance and broker requirements when applicable” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he sorts out the tariff codes, the duty and the customs broker for imported goods. • Starts when: an import is planned or in transit. • How it runs: (1) he obtains the correct HS code for the goods. (2) He establishes the duty rate and any exemption available. (3) He appoints or instructs the broker. (4) He provides the documents and funds required. (5) He tracks clearance and records the duty paid. • Proof it happened: correct HS classification, duty assessed, broker instructed and clearance completed with records. • Where it usually breaks: the goods are misclassified, so the company either overpays duty or faces a retrospective assessment and penalty. | • Confirm the HS code with the broker or a formal ruling rather than estimating, since misclassification produces either overpaid duty or a retrospective penalty. • Check for available exemptions and free zone treatment before clearance, as these cannot be claimed afterwards. • Include duty and clearance in the landed cost comparison at sourcing, not as a surprise at import. • Confirm the funds are available for duty in advance, because shipments sit accruing charges while payment is arranged. • Retain the clearance documents, as these are required for tax recovery and audit.
670 | Procurement | Arrange cargo or transit insurance for controlled high-risk movements | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Arrange cargo or transit insurance for controlled high-risk movements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Arrange cargo or transit insurance for controlled high-risk movements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: for valuable or risky movements he arranges insurance for the goods in transit. • Starts when: a high value or high risk movement is planned. • How it runs: (1) he assesses the value and the transit risk. (2) He checks whether existing cover applies. (3) He arranges specific cargo or transit cover where needed. (4) He confirms the cover is in place before dispatch. (5) He records the policy and the cover period. • Proof it happened: arranged and confirmed transit insurance with the policy, value and period recorded before dispatch. • Where it usually breaks: cover is arranged after dispatch, so the highest risk part of the journey is uninsured. | • Confirm cover is in force before dispatch, since cover arranged in transit leaves the riskiest part of the journey uninsured. • Check whether the existing policy covers the movement before buying separate cover, to avoid paying twice. • Check the cover basis and the excess, because a policy covering only total loss does not respond to damage. • Set a value threshold above which specific cover is mandatory, so the decision is not judgement based. • Record the claim notification requirements, as late notice voids cover.
671 | Procurement | Track shipment, vehicle and consignment location against plan | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Track shipment, vehicle and consignment location against plan” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Track shipment, vehicle and consignment location against plan” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he tracks where the shipment or vehicle actually is against where it should be. • Starts when: a movement is dispatched. • How it runs: (1) he obtains the tracking reference or carrier contact. (2) He checks progress against the planned schedule at set intervals. (3) He identifies deviations early. (4) He escalates where the delivery date is threatened. (5) He records the tracking and the actual arrival. • Proof it happened: a tracking record showing progress against plan with deviations identified and escalated. • Where it usually breaks: tracking is only checked when the delivery is already late, so there is no time left to react. | • Check progress at set intervals during transit rather than at the due date, since a deviation found on the due date leaves no time to react. • Define the escalation trigger, such as a deviation beyond a stated number of hours or days. • Record actual against planned transit times, as this builds the data for future planning. • Notify the site and store of a revised ETA as soon as it is known, so resources are not wasted waiting. • Require the carrier to report exceptions rather than relying only on the company checking.
672 | Procurement | Maintain dispatch evidence and transport-document control | Logistics Coordinator | Trigger: When the approved delivery reaches booking, collection, dispatch or cross-border movement. Action: The Logistics Coordinator completes “Maintain dispatch evidence and transport-document control” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a compliant booking, dispatch file, tracked consignment and controlled transport evidence. Control/Handoff: Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the approved delivery reaches booking, collection, dispatch or cross-border movement. | The Logistics Coordinator completes “Maintain dispatch evidence and transport-document control” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a compliant booking, dispatch file, tracked consignment and controlled transport evidence. | Carrier, vehicle, driver, packing, insurance and customs requirements are verified; missing legal or transport documents block movement and escalate to the Procurement Lead. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he keeps the dispatch and transport documents properly filed and controlled. • Starts when: documents are generated at dispatch and through transit. • How it runs: (1) he collects the dispatch note, packing list and transport documents. (2) He checks each is complete and signed. (3) He files them against the delivery reference. (4) He ensures originals requiring retention are secured. (5) He makes them available to Procurement, Store and Finance. • Proof it happened: a controlled transport document file per delivery, complete, signed and accessible. • Where it usually breaks: documents stay with the driver or in a vehicle, so the delivery cannot be evidenced when the invoice is queried. | • Collect and file the transport documents at delivery, since documents left with the driver cannot be produced when the invoice or a shortage is queried. • Secure original documents required for customs or tax recovery, as copies may not be accepted. • File against the delivery reference so documents can be found from either the order or the delivery. • Check documents are signed and dated, because an unsigned delivery note proves nothing. • Make the file accessible to Finance, so payment is not delayed chasing paperwork.
673 | Procurement | Communicate dispatch, ETA and delivery status to supplier, Store and Projects | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Communicate dispatch, ETA and delivery status to supplier, Store and Projects” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Communicate dispatch, ETA and delivery status to supplier, Store and Projects” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he keeps the supplier, the store and the project informed about dispatch and arrival timing. • Starts when: a movement is dispatched and continues until delivery. • How it runs: (1) he notifies dispatch with the expected arrival. (2) He updates the ETA as it changes. (3) He notifies the store and site of the delivery window. (4) He confirms arrival. (5) He records the communications sent. • Proof it happened: issued dispatch and ETA notifications with the delivery window communicated and arrival confirmed. • Where it usually breaks: the ETA is communicated once and never updated, so resources are mobilised for a delivery that arrives hours later. | • Update the ETA whenever it changes materially, since resources mobilised for a stale ETA are wasted and the delay is blamed on logistics. • Notify a window rather than a precise time, as this is what allows the store to plan. • Include the material, quantity and handling requirement in the notification, not just the timing. • Notify by a recorded route rather than a phone call, so the notification can be evidenced. • Confirm arrival, because an unconfirmed delivery remains open in every register.
674 | Procurement | Book site gate access and confirm authorised delivery personnel | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Book site gate access and confirm authorised delivery personnel” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Book site gate access and confirm authorised delivery personnel” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges gate access for the vehicle and confirms who is authorised to come on site. • Starts when: a delivery is scheduled to a controlled site. • How it runs: (1) he obtains the vehicle and driver details. (2) He submits the access request per the site procedure. (3) He confirms the driver meets the site induction and PPE requirements. (4) He confirms the access approval and the time slot. (5) He notifies the carrier of the arrangements. • Proof it happened: an approved gate access record with vehicle, driver and time slot confirmed and communicated. • Where it usually breaks: the driver arrives without site induction or PPE, so the vehicle is turned away with the load. | • State the site induction and PPE requirement to the carrier in advance, since a driver turned away at the gate wastes the whole journey and the receiving resources. • Submit access requests within the site's stated notice period, because same day requests are routinely refused. • Confirm the time slot, as unslotted deliveries queue and incur waiting charges. • Notify the carrier of the exact gate and contact person. • Record refusals and their causes, so the same failure is not repeated.
675 | Procurement | Coordinate lifting, unloading, traffic and temporary-access arrangements | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Coordinate lifting, unloading, traffic and temporary-access arrangements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Coordinate lifting, unloading, traffic and temporary-access arrangements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he coordinates the lifting, unloading and traffic arrangements at the point of delivery. • Starts when: a delivery requiring these arrangements is due. • How it runs: (1) he confirms the lifting equipment and operator are on site. (2) He confirms the banksman and unloading crew. (3) He confirms the exclusion zone and traffic arrangements. (4) He confirms the sequence with the site. (5) He confirms completion of unloading. • Proof it happened: confirmed lifting, unloading and traffic arrangements in place with the unloading completed and recorded. • Where it usually breaks: unloading starts without an exclusion zone or a banksman, which is where the serious delivery injuries happen. | • Require an exclusion zone and a dedicated banksman before any mechanical unloading begins, since this is where the serious delivery injuries occur. • Require the lift to stop if the arrangements are not as planned, and name who has that authority. • Confirm the crane or forklift capacity against the actual package weight, not the average. • Separate pedestrian and vehicle routes at the unloading area. • Record the arrangements, as a delivery injury investigation will ask for exactly this.
676 | Procurement | Coordinate logistics HSE briefing, method statement and lifting controls | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Coordinate logistics HSE briefing, method statement and lifting controls” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Coordinate logistics HSE briefing, method statement and lifting controls” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he makes sure everyone involved in the delivery has been briefed on how to do it safely. • Starts when: before a delivery involving lifting or significant handling risk. • How it runs: (1) he confirms the method statement for the operation. (2) He arranges the briefing for the driver, crew and operator. (3) He confirms the lifting controls and the plan. (4) He confirms the briefing was delivered and understood. (5) He records the briefing and attendance. • Proof it happened: a delivered HSE briefing with the method statement, lifting controls and attendance recorded. • Where it usually breaks: the driver and the unloading crew are never briefed together, so each assumes the other is controlling the operation. | • Brief the driver and the unloading crew together, since separate briefings leave each assuming the other is in control of the lift. • Require a lift plan for anything above a stated weight or complexity, and require it to be followed. • Take the briefing signatures at the briefing, because a sheet signed afterwards is a false record. • Brief in a language the driver and crew actually understand, particularly for external drivers. • Require the operation to stop if conditions change from those briefed.
677 | Procurement | Coordinate Store, Project and QHSE attendance for receiving inspection | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Coordinate Store, Project and QHSE attendance for receiving inspection” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Coordinate Store, Project and QHSE attendance for receiving inspection” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he makes sure the right people are present to inspect the material when it arrives. • Starts when: a delivery requiring inspection is due. • How it runs: (1) he identifies who must attend: store, project engineer, QHSE. (2) He notifies them of the delivery window. (3) He confirms their attendance. (4) He coordinates the inspection at delivery. (5) He records the attendance and the inspection outcome. • Proof it happened: confirmed attendance of the required parties with the receiving inspection completed and recorded. • Where it usually breaks: nobody technical attends, so material is accepted and signed for before anyone checks it is the right thing. | • Require technical attendance for material needing verification, since accepting and signing before inspection transfers the defect risk to the company. • Notify attendees with enough lead time to be present, and record non attendance. • Define which material categories require QHSE or engineering attendance, so it is not decided per delivery. • Allow the delivery to be held unsigned until inspection is complete. • Record the inspection outcome against the delivery, not only in the store records.
678 | Procurement | Obtain signed delivery note, proof of delivery and receipt evidence | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Obtain signed delivery note, proof of delivery and receipt evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Obtain signed delivery note, proof of delivery and receipt evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he gets the delivery note signed and keeps the proof that the material arrived. • Starts when: material is delivered and received. • How it runs: (1) he ensures the quantity is checked before signing. (2) He ensures any exception is written on the note before signing. (3) He obtains the signed delivery note. (4) He obtains the proof of delivery from the carrier. (5) He files the evidence against the delivery reference. • Proof it happened: a signed delivery note with exceptions noted, plus the carrier's proof of delivery, filed. • Where it usually breaks: the note is signed clean to release the vehicle, so a shortage or damage discovered later cannot be claimed. | • Write every exception on the delivery note before signing, since a clean signature is treated as acceptance and ends the claim. • Prohibit signing before the count is complete, and state that vehicle pressure is not a reason to sign. • Obtain a copy of the signed note at the point of delivery, not later from the carrier. • Photograph the condition on arrival for high value or damage prone goods. • Name who is authorised to sign for deliveries, as anyone signing binds the company.
679 | Procurement | Record waiting time, demurrage, detention and access-delay evidence | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Record waiting time, demurrage, detention and access-delay evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Record waiting time, demurrage, detention and access-delay evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he records the times around a delivery, so waiting charges can be checked or contested. • Starts when: a vehicle arrives and until it departs. • How it runs: (1) he records the arrival time at the gate. (2) He records the time unloading started and finished. (3) He records the departure time. (4) He records the cause of any waiting. (5) He files the record for invoice verification. • Proof it happened: a recorded time log covering arrival, start, finish and departure with the cause of any waiting. • Where it usually breaks: no times are recorded, so a demurrage claim arrives and there is nothing to contest it with. | • Record arrival, start, finish and departure times on every delivery, since without them a demurrage claim cannot be contested and is paid in full. • Record the cause of waiting, as waiting caused by the carrier is not chargeable to the company. • Have both the driver and the receiver sign the time record, so it is not disputed. • Compare claimed demurrage against the free time in the booking terms. • Report recurring waiting causes, because these are usually fixable site issues.
680 | Procurement | Coordinate approved after-hours, urgent and emergency deliveries | Logistics Coordinator | Trigger: When the consignment is dispatched or approaches the project/warehouse delivery window. Action: The Logistics Coordinator completes “Coordinate approved after-hours, urgent and emergency deliveries” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. Control/Handoff: Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When the consignment is dispatched or approaches the project/warehouse delivery window. | The Logistics Coordinator completes “Coordinate approved after-hours, urgent and emergency deliveries” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a safely coordinated arrival with signed delivery, proof-of-delivery and receiving evidence. | Store controls physical receipt, Projects controls site readiness and QHSE controls applicable lifting/inspection requirements; access, safety or work-front failure triggers rescheduling. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges deliveries outside normal hours or at short notice when they are approved. • Starts when: an after hours, urgent or emergency delivery is approved. • How it runs: (1) he confirms the approval and the reason. (2) He checks the permits and site access allow it. (3) He arranges the carrier, labour and equipment for the time required. (4) He confirms the receiving arrangements. (5) He records the cost and the cause. • Proof it happened: an approved out of hours or urgent delivery with permits, arrangements and the cost and cause recorded. • Where it usually breaks: urgent deliveries become routine, so premium transport costs are incurred continuously without anyone noticing. | • Record the cause and the premium cost of every urgent delivery and report the totals, since urgency becomes routine and the premium cost becomes invisible. • Require approval at a stated level for premium movements, so the cost is a decision rather than a default. • Check permits allow the movement, as night and weekend restrictions are enforced. • Confirm receiving resources are available out of hours, otherwise the premium buys nothing. • Analyse the causes, because most urgent deliveries trace to late requisitioning.
681 | Procurement | Escalate late dispatch or delivery and implement the approved recovery plan | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Escalate late dispatch or delivery and implement the approved recovery plan” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Escalate late dispatch or delivery and implement the approved recovery plan” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: when a dispatch or delivery is late he raises it and puts the recovery plan into action. • Starts when: a dispatch or delivery is late or forecast to be late. • How it runs: (1) he establishes the cause and the revised date. (2) He assesses the effect on the site. (3) He escalates to Procurement and the project. (4) He implements the approved recovery: expediting, alternative transport or partial delivery. (5) He tracks recovery to completion. • Proof it happened: an escalation record with the cause, revised date, approved recovery action and its outcome. • Where it usually breaks: lateness is absorbed and managed quietly, so the project is not told until the material is needed and missing. | • Escalate a late dispatch immediately rather than managing it quietly, since the project can only replan if it knows, and silence converts a supply delay into a site delay. • Require the revised date to be confirmed in writing by the supplier or carrier. • Require the recovery cost to be approved, as expediting and premium freight need funding to happen. • Record the cause against the supplier or carrier, so performance scoring reflects it. • Consider partial delivery to release the critical work front rather than waiting for a full load.
682 | Procurement | Record shortage, damage, contamination, temperature or handling exceptions | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Record shortage, damage, contamination, temperature or handling exceptions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Record shortage, damage, contamination, temperature or handling exceptions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he records shortages, damage and other problems found when the material arrives. • Starts when: an exception is identified at receipt. • How it runs: (1) he records the exception with quantities and description. (2) He photographs the condition. (3) He ensures the exception is noted on the delivery note before signing. (4) He notifies Procurement and the supplier within the contractual period. (5) He tracks the resolution. • Proof it happened: an exception record with photographs, the annotated delivery note and notification within the contractual period. • Where it usually breaks: the exception is recorded internally but the supplier is notified late, so the rejection period has expired. | • Notify the supplier and carrier within the contractual rejection period, since a late notification is treated as acceptance whatever the internal record shows. • Photograph the condition before anything is moved, because the evidence disappears as soon as unloading continues. • Annotate the delivery note before signing, as this is the primary evidence. • Record the quantity affected precisely, since approximate claims are reduced. • Quarantine the affected material physically so it is not issued in error.
683 | Procurement | Coordinate rejected-material collection and return to supplier | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Coordinate rejected-material collection and return to supplier” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Coordinate rejected-material collection and return to supplier” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges for rejected material to be collected and sent back to the supplier. • Starts when: material is rejected and must be returned. • How it runs: (1) he confirms the rejection and the supplier's collection instruction. (2) He arranges the gate pass and the return documentation. (3) He arranges the transport or supplier collection. (4) He obtains acknowledgement of the return. (5) He notifies Procurement so the credit can be pursued. • Proof it happened: a documented return with gate pass, transport arrangement and the supplier's acknowledgement of receipt. • Where it usually breaks: material leaves site without a gate pass or acknowledgement, so the supplier denies receiving it and no credit follows. | • Require a gate pass and the supplier's written acknowledgement for every return, since without them the supplier denies receipt and the credit is never issued. • Notify Procurement at the point of return so the credit note is pursued immediately. • Set a deadline for collection, as rejected material left on site is eventually used or lost. • Record the return transport cost for recovery through a debit note. • Keep rejected material segregated until it physically leaves.
684 | Procurement | Coordinate replacement, redelivery and missed-delivery recovery | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Coordinate replacement, redelivery and missed-delivery recovery” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Coordinate replacement, redelivery and missed-delivery recovery” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges the replacement delivery when something has been rejected or a delivery was missed. • Starts when: a replacement or redelivery is required. • How it runs: (1) he confirms the replacement quantity and the revised date with Procurement. (2) He replans the delivery. (3) He confirms readiness, access and receiving again. (4) He arranges the transport. (5) He tracks it to delivery and records the recovery. • Proof it happened: a planned and completed replacement delivery with the revised date and recovery recorded. • Where it usually breaks: the replacement is planned with the same assumptions that failed the first time, so it fails again. | • Address the cause of the original failure before replanning, since repeating the same plan reproduces the same failure. • Confirm the replacement is at the supplier's cost where the rejection was their fault, before arranging transport. • Reconfirm site need, as the work front may have moved on and the material may no longer be wanted immediately. • Record the cost of the redelivery for recovery. • Prioritise replacements affecting critical work fronts over routine deliveries.
685 | Procurement | Coordinate warehouse-to-project material transfers | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Coordinate warehouse-to-project material transfers” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Coordinate warehouse-to-project material transfers” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he moves material from the central warehouse out to the projects that need it. • Starts when: a project requests material held in the warehouse. • How it runs: (1) he confirms the request and the approval. (2) He confirms stock availability with the store. (3) He raises the transfer document. (4) He arranges the transport and the receiving confirmation. (5) He confirms the transfer is recorded in the system at both ends. • Proof it happened: a transfer document with approval, transport arrangement and system records updated at both ends. • Where it usually breaks: material physically moves before the transfer is raised, so both the warehouse and the project show the wrong stock. | • Raise the transfer before the material physically moves, since stock records at both ends are otherwise wrong and the discrepancy is never traced. • Require receiving confirmation at the destination, as a transfer out without a transfer in creates an unexplained loss. • Require approval before transferring material charged to another project, because the cost follows the material. • Check condition at both ends, so damage in transit is attributed correctly. • Reconcile transfers in progress periodically, as these are where stock disappears.
686 | Procurement | Coordinate project-to-warehouse and inter-project material transfers | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Coordinate project-to-warehouse and inter-project material transfers” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Coordinate project-to-warehouse and inter-project material transfers” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he moves material back from projects and between projects. • Starts when: surplus material is returned or transferred between projects. • How it runs: (1) he confirms the material, quantity and condition to be moved. (2) He confirms the approval and the receiving project or warehouse. (3) He raises the transfer document. (4) He arranges the transport. (5) He confirms receipt and the system record at both ends. • Proof it happened: a transfer document with condition recorded, approval, transport and receipt confirmed at both ends. • Where it usually breaks: surplus is left on the finished project rather than returned, so it is written off and the same material is bought again. | • Require surplus to be declared and transferred at project closeout, since material left on a finished site is written off and then purchased again for the next project. • Record the condition at transfer, as material returned damaged should not be valued as new. • Require the receiving project to confirm receipt and the value transferred. • Check the surplus against other projects' requirements before any new purchase. • Report unreturned surplus by project, so the cost sits with the project that caused it.
687 | Procurement | Coordinate rental plant and equipment mobilisation and demobilisation | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Coordinate rental plant and equipment mobilisation and demobilisation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Coordinate rental plant and equipment mobilisation and demobilisation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he arranges hired plant and equipment onto site and off site again. • Starts when: hired plant is required or is no longer needed. • How it runs: (1) he confirms the hire arrangement and the on site date. (2) He arranges transport, access and offloading. (3) He arranges the condition record at delivery. (4) On completion he arranges collection and the off hire confirmation. (5) He records the off hire reference and date. • Proof it happened: mobilisation and demobilisation records with condition reports and a confirmed off hire reference. • Where it usually breaks: the equipment is collected but never formally off hired, so hire charges continue to accrue for weeks. | • Confirm off hire in writing with a reference on the day the plant leaves, since continued hire charges on returned equipment is one of the most common avoidable costs on site. • Record the condition at both delivery and collection, as damage claims otherwise cannot be contested. • Reconcile hire invoices against the off hire dates monthly. • Track idle plant on site, because plant kept for convenience is paid for daily. • Require the hire company's acknowledgement of collection, not just the driver's word.
688 | Procurement | Maintain the daily delivery status and outstanding-logistics action register | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Maintain the daily delivery status and outstanding-logistics action register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Maintain the daily delivery status and outstanding-logistics action register” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he keeps the daily picture of what is arriving and what logistics actions are outstanding. • Starts when: daily, and continuously as deliveries progress. • How it runs: (1) he updates the status of each planned delivery. (2) He records the outstanding actions and their owners. (3) He identifies the deliveries at risk. (4) He circulates the status to the store, project and Procurement. (5) He carries open items forward until closed. • Proof it happened: a daily delivery status and action register circulated, with open items carried forward. • Where it usually breaks: the register lists everything without flagging what is at risk, so the reader cannot see what needs attention. | • Flag the deliveries at risk separately from the routine ones, since a flat list of everything hides the items that need action today. • Show ageing on outstanding logistics actions, as these accumulate quietly. • Circulate to the store, project and Procurement together, so all three plan from one picture. • Update it daily rather than before meetings. • Close items explicitly, otherwise the register grows until it is ignored.
689 | Procurement | Prepare logistics cost, carrier-performance and exception reporting | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Prepare logistics cost, carrier-performance and exception reporting” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Prepare logistics cost, carrier-performance and exception reporting” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he reports what logistics cost, how carriers performed and what went wrong. • Starts when: at the reporting cycle. • How it runs: (1) he compiles the transport and handling costs for the period. (2) He compiles carrier performance: on time, damage and exception rates. (3) He compiles the exceptions and their causes. (4) He identifies the recurring causes. (5) He issues the report with recommendations. • Proof it happened: a logistics cost and carrier performance report with exceptions, causes and recommendations. • Where it usually breaks: cost is reported in total, so the premium spent on urgent and failed deliveries is never visible. | • Report premium and abortive transport cost separately from planned cost, since the total figure hides what late planning and failed deliveries are actually costing. • Report carrier performance by on time percentage and damage rate, and use it in carrier selection. • Report demurrage paid and its causes, as most of it is avoidable. • Show the trend rather than the single period. • Attribute exception causes to the responsible function, because most logistics failures originate upstream.
690 | Procurement | Close each delivery file and hand receipt evidence to Procurement, Store and Finance | Logistics Coordinator | Trigger: When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. Action: The Logistics Coordinator completes “Close each delivery file and hand receipt evidence to Procurement, Store and Finance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. Control/Handoff: No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. Continuity/Escalation: A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. Timing: To be confirmed. | When a delay, damage, rejection, transfer, rental movement or reporting cutoff occurs. | The Logistics Coordinator completes “Close each delivery file and hand receipt evidence to Procurement, Store and Finance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a documented recovery, return, replacement, transfer, delivery closure or logistics performance record. | No unrecorded material movement is allowed; shortage, damage, delay, added cost or loss is evidenced and escalated to the Procurement Lead, Project Engineer and CPO as thresholds require. | A trained authorised logistics backup may coordinate routine movements using the controlled register; carrier appointment, added cost, customs, damage, loss or critical delay exceptions escalate to the Procurement Lead. | To be confirmed. | • In plain words: he closes each delivery off and passes the receipt evidence to the people who need it. • Starts when: a delivery is complete and the documents are collected. • How it runs: (1) he confirms the delivery is complete and any exception is resolved or recorded. (2) He assembles the document set. (3) He passes the receipt evidence to Procurement for invoice verification. (4) He passes the goods received evidence to the Store and Finance. (5) He closes the delivery in the register. • Proof it happened: a closed delivery file with complete documents distributed to Procurement, Store and Finance. • Where it usually breaks: receipt evidence never reaches Finance, so invoices sit unpaid or are paid without a matching receipt. | • Pass the receipt evidence to Finance and Procurement at closure, since a missing goods received record either blocks a valid payment or allows an unverified one. • Require every delivery to be closed explicitly, as open deliveries distort the register and the stock position. • Ensure unresolved exceptions are carried to Procurement rather than closed with the delivery. • File the complete document set against the delivery reference, so any later query can be answered. • Report deliveries closed with open exceptions, as these represent unrecovered money.
691 | Procurement | Prepare the daily receiving plan, unloading zone and storage space | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Prepare the daily receiving plan, unloading zone and storage space” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Prepare the daily receiving plan, unloading zone and storage space” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he plans the day's deliveries, where each one will be unloaded and where the material will go. • Starts when: each morning, and when the delivery schedule changes. • How it runs: (1) he reviews the deliveries expected that day. (2) He plans the unloading zone and the sequence. (3) He confirms the storage space for each item. (4) He confirms the labour and handling equipment. (5) He communicates the plan to the team and Logistics. • Proof it happened: a daily receiving plan with unloading zones, storage allocation and resources confirmed. • Where it usually breaks: no plan is made, so vehicles queue, unloading is improvised and material is placed wherever there is space. | • Require a written daily plan with storage allocated per delivery, since improvised unloading is what causes queuing, damage and material that cannot be found later. • Sequence the deliveries rather than receiving in arrival order, so the difficult ones get the equipment they need. • Confirm space before the vehicle arrives, because a delivery with nowhere to go is either refused or dumped. • Include the handling equipment and labour in the plan, not just the space. • Communicate the plan to Logistics, so delivery windows are set against real capacity.
692 | Procurement | Verify delivery booking, purchase order and authorised supplier or carrier | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Verify delivery booking, purchase order and authorised supplier or carrier” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Verify delivery booking, purchase order and authorised supplier or carrier” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: before unloading he checks the delivery is expected, matches an order and comes from an authorised supplier. • Starts when: a vehicle arrives at the store or site. • How it runs: (1) he checks the delivery against the booking and the delivery register. (2) He matches the delivery note to a live purchase order. (3) He confirms the supplier or carrier is the authorised one. (4) He queries anything unmatched before unloading. (5) He records the verification. • Proof it happened: a verification record matching the delivery to a live order and an authorised supplier before unloading. • Where it usually breaks: material is unloaded first and matched to an order afterwards, so unordered goods end up on site and have to be paid for. | • Verify the delivery against an order in the system before unloading, since material received without an order has no price, no budget and no basis for payment. • Refuse deliveries from unauthorised carriers or suppliers, and record the refusal. • Check the order is still open and not already fully received, as duplicate deliveries do occur. • Require the driver to present the delivery note before unloading starts. • Escalate unplanned deliveries to Procurement rather than accepting them to keep the peace.
693 | Procurement | Receive and segregate incoming materials, equipment and tools | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Receive and segregate incoming materials, equipment and tools” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Receive and segregate incoming materials, equipment and tools” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he receives the goods and separates them by type and status as they come off the vehicle. • Starts when: unloading begins. • How it runs: (1) he supervises safe unloading. (2) He separates materials, equipment and tools. (3) He keeps each delivery separate until it has been checked. (4) He places items in the planned receiving area. (5) He records what was received against the delivery. • Proof it happened: received goods segregated by type and delivery, held in the receiving area pending checking. • Where it usually breaks: deliveries are mixed together on unloading, so a shortage cannot be attributed to a particular delivery or supplier. | • Keep each delivery physically separate until checking is complete, since mixed deliveries make a shortage impossible to attribute to a supplier. • Separate tools and equipment from consumable material, as these need custody records rather than stock records. • Use a defined receiving area rather than unloading directly to storage, so unchecked material cannot be issued. • Supervise unloading rather than leaving it to the driver, because damage occurs during unloading. • Record the delivery reference on the material at receipt, so traceability starts immediately.
694 | Procurement | Count delivered quantities against the delivery note and purchase order | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Count delivered quantities against the delivery note and purchase order” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Count delivered quantities against the delivery note and purchase order” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he counts what actually arrived and compares it to the delivery note and the order. • Starts when: goods are received and being checked. • How it runs: (1) he counts or weighs the delivered quantity. (2) He compares it to the delivery note. (3) He compares it to the purchase order quantity. (4) He records the actual quantity received. (5) He raises any discrepancy before signing. • Proof it happened: a recorded count of actual quantities checked against both the delivery note and the order. • Where it usually breaks: the delivery note is signed before counting because the driver is waiting, so any shortage becomes the company's loss. | • Prohibit signing the delivery note before the count is complete, since a signed note is acceptance and the shortage then belongs to the company. • State that driver or vehicle pressure is not a reason to sign, and give the storekeeper explicit authority to hold the vehicle. • Count against the order as well as the delivery note, because a note matching an over delivery is still wrong. • Require weighing or measuring for bulk items rather than accepting the stated quantity. • Record partial receipts precisely, so the outstanding balance is known.
695 | Procurement | Inspect visible condition, packaging, damage and handling status | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Inspect visible condition, packaging, damage and handling status” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Inspect visible condition, packaging, damage and handling status” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he checks the visible condition and the packaging for damage before accepting. • Starts when: goods are being checked at receipt. • How it runs: (1) he inspects the packaging for damage or tampering. (2) He inspects the visible condition of the goods. (3) He checks for signs of poor handling such as crushing or water marks. (4) He records the condition. (5) He notes any damage on the delivery note before signing. • Proof it happened: a recorded condition inspection with damage noted on the delivery note before signature. • Where it usually breaks: damage inside intact packaging is not checked, so it is discovered at installation when the claim period has long expired. | • Require damage prone items to be opened and checked at receipt rather than at issue, since damage found at installation is outside the claim period and becomes the company's loss. • Note every condition exception on the delivery note before signing, however minor. • Photograph damage before moving the goods, because the evidence is lost once unloading continues. • Check for water and impact marks on packaging, as these indicate hidden damage. • Record condition on receipt even when accepting, so later deterioration is not attributed to delivery.
696 | Procurement | Verify item, model, size, batch and project allocation against the purchase order | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Verify item, model, size, batch and project allocation against the purchase order” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Verify item, model, size, batch and project allocation against the purchase order” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he checks it is actually the right item, model, size and batch, and for the right project. • Starts when: goods are being checked at receipt. • How it runs: (1) he checks the item description against the order. (2) He checks the model, size and grade markings. (3) He records the batch or heat number where applicable. (4) He confirms the project allocation on the order. (5) He records the verification. • Proof it happened: a verification record confirming item, model, size, batch and project allocation against the order. • Where it usually breaks: a similar but different grade or size is accepted because it looks right, and it is only found when it fails an inspection. | • Check the grade and size markings on the material itself rather than relying on the delivery note, since a similar looking wrong grade passes receipt and fails inspection later. • Record the batch or heat number at receipt for structural and certified materials, as traceability cannot be reconstructed. • Confirm the project allocation, because misallocated material distorts both project costs and availability. • Reject rather than accept conditionally where the item differs from the order. • Escalate substitutions to Procurement instead of deciding equivalence at the store.
697 | Procurement | Verify approved submittal, sample, material code and revision status | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Verify approved submittal, sample, material code and revision status” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Verify approved submittal, sample, material code and revision status” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he checks the material matches the approved submittal and the approved revision. • Starts when: goods requiring submittal approval are received. • How it runs: (1) he obtains the approved submittal reference for the item. (2) He compares the delivered material against the approved sample or data. (3) He checks the material code and revision status. (4) He holds the material where it does not match. (5) He records the verification. • Proof it happened: a verification record comparing the delivered material to the approved submittal and revision. • Where it usually breaks: material is accepted before the submittal is approved, so it is installed and later rejected by the consultant. | • Quarantine material delivered before its submittal is approved rather than accepting it, since installed unapproved material is rejected and removed at the company's cost. • Require the approved sample to be retained at the store as the physical reference for comparison. • Check the revision status of the approval, because an approval against a superseded revision is not valid. • Escalate early delivery of unapproved material to Procurement, as this is a supplier control failure. • Record the submittal reference against the GRN, so the approval trail is complete.
698 | Procurement | Capture delivery photographs, signatures and initial receiving evidence | Storekeeper | Trigger: When a booked delivery arrives at the warehouse, yard or project store. Action: The Storekeeper completes “Capture delivery photographs, signatures and initial receiving evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a counted, identified, segregated and evidenced receiving record. Control/Handoff: The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a booked delivery arrives at the warehouse, yard or project store. | The Storekeeper completes “Capture delivery photographs, signatures and initial receiving evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a counted, identified, segregated and evidenced receiving record. | The Storekeeper compares delivery note, PO and approved technical reference; unknown, wrong, damaged or unbooked items remain segregated pending Procurement/Project instruction. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he photographs and records the delivery so there is evidence of what arrived and in what state. • Starts when: goods are received and checked. • How it runs: (1) he photographs the load, the packaging and any damage. (2) He photographs the markings and batch numbers. (3) He obtains the signatures on the delivery documents. (4) He records the receiving details. (5) He files the evidence against the delivery. • Proof it happened: photographs, signed documents and receiving records filed against the delivery reference. • Where it usually breaks: photographs are taken but never filed against the delivery, so they cannot be found when a claim is made. | • File photographs against the delivery reference immediately, since images sitting on a phone cannot be produced when a claim is made weeks later. • Photograph the markings and batch numbers as well as the condition, because these support traceability. • Require photographs as mandatory for damage prone, high value and imported deliveries. • Include something showing scale or the vehicle in the images, so the context is clear. • Retain the evidence for the claim period, not just until the GRN is raised.
699 | Procurement | Coordinate Project and QHSE receiving inspection when required | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Coordinate Project and QHSE receiving inspection when required” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Coordinate Project and QHSE receiving inspection when required” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: for material needing technical checking, he gets the engineer or QHSE to inspect it at receipt. • Starts when: material requiring inspection is received. • How it runs: (1) he identifies material requiring technical or QHSE inspection. (2) He notifies the required inspector. (3) He holds the material pending inspection. (4) He records the inspection outcome. (5) He releases or quarantines based on the result. • Proof it happened: a receiving inspection record with the inspector's outcome, and the material released or quarantined accordingly. • Where it usually breaks: material is stored and issued while inspection is still pending, so unverified material goes into the works. | • Hold material in a physically separate area until inspection is complete, since material stored in the main racks will be issued regardless of its status. • Define which material categories require technical or QHSE inspection at receipt, so it is not decided case by case. • Set a response time for inspectors, as slow inspection is what drives the store to release material anyway. • Record the inspection result against the GRN. • Escalate where inspection is not attended rather than releasing by default.
700 | Procurement | Segregate and quarantine unapproved, damaged or nonconforming material | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Segregate and quarantine unapproved, damaged or nonconforming material” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Segregate and quarantine unapproved, damaged or nonconforming material” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he separates and marks material that is not approved, is damaged or does not conform. • Starts when: material fails a check at receipt or is found defective later. • How it runs: (1) he moves the material to the quarantine area. (2) He marks it clearly as quarantined or rejected. (3) He records the status in the system. (4) He notifies Procurement and the project. (5) He keeps it segregated until the disposition is decided. • Proof it happened: material physically segregated and marked, with the status recorded in the system and notified. • Where it usually breaks: quarantined material is marked in the system but left in the normal racks, so a crew collects and installs it. | • Require physical marking and a segregated quarantine area, since a system status alone does not stop a crew collecting and installing the material. • Use a distinct physical marking that means do not use, and brief the crews on it. • Set a maximum time material may remain in quarantine before the disposition must be decided. • Name who may release material from quarantine, and prohibit anyone else from doing so. • Report quarantine volume and ageing, as accumulating quarantine indicates unresolved supplier issues.
701 | Procurement | Create shortage, excess, damage and discrepancy records | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Create shortage, excess, damage and discrepancy records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Create shortage, excess, damage and discrepancy records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he records the shortages, excesses, damage and differences found at receipt. • Starts when: a discrepancy is identified. • How it runs: (1) he records the discrepancy type and quantity. (2) He records the evidence including photographs. (3) He notes it on the delivery note before signing. (4) He notifies Procurement and Logistics immediately. (5) He tracks it until resolved. • Proof it happened: a discrepancy record with quantities, evidence, the annotated delivery note and notification issued. • Where it usually breaks: small shortages are absorbed rather than recorded, so a supplier who consistently short delivers is never identified. | • Require every discrepancy to be recorded regardless of size, since consistent small shortages are only detectable in the pattern and are otherwise a permanent loss. • Notify Procurement the same day, because the contractual rejection period is short. • Record excess deliveries too, as unrecorded excess is either paid for or later written off. • Report discrepancy rates by supplier, so the scorecard reflects them. • Require the discrepancy to be closed with evidence, not simply left open.
702 | Procurement | Create rejection and supplier-return records | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Create rejection and supplier-return records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Create rejection and supplier-return records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he raises the formal rejection and return record when material is not accepted. • Starts when: material is rejected. • How it runs: (1) he raises the rejection record with the reason and quantity. (2) He attaches the evidence. (3) He records the material as rejected in the system. (4) He arranges segregation pending return. (5) He notifies Procurement so the return and credit can be pursued. • Proof it happened: a rejection and return record with reason, quantity, evidence and Procurement notified. • Where it usually breaks: the rejection is verbal, so the material stays in stock and is eventually issued and installed. | • Require a formal written rejection record, since a verbal rejection leaves the material in stock and it is eventually issued and installed. • Record the rejection in the system so the stock quantity does not show as available. • State the reason precisely with the specification or order reference breached, as vague rejections are disputed. • Set a deadline for the material to leave site, because rejected material on site gets used. • Link the rejection to the credit note tracking, so the money is recovered.
703 | Procurement | Create the FirstBit GRN for accepted quantities | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Create the FirstBit GRN for accepted quantities” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Create the FirstBit GRN for accepted quantities” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he raises the goods received note in the system for the quantities actually accepted. • Starts when: checking is complete and material is accepted. • How it runs: (1) he confirms the accepted quantity. (2) He raises the GRN in FirstBit against the purchase order. (3) He records the batch, location and project allocation. (4) He checks the GRN matches the physical receipt. (5) He confirms the GRN is posted. • Proof it happened: a posted GRN in the system matching the physically accepted quantity, with location and allocation recorded. • Where it usually breaks: the GRN is raised for the ordered quantity rather than the received quantity, so the supplier is paid for goods not delivered. | • Raise the GRN for the quantity physically accepted and never for the ordered quantity, since this is the control that stops payment for undelivered goods. • Raise the GRN on the day of receipt, because delayed GRNs block valid payments and distort stock. • Record the bin location and project allocation on the GRN, so the material can be found and costed. • Prohibit raising a GRN before the physical check is complete. • Require a second check of GRN quantities above a value threshold.
704 | Procurement | Link GRN, delivery note, inspection and project-allocation evidence | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Link GRN, delivery note, inspection and project-allocation evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Link GRN, delivery note, inspection and project-allocation evidence” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he links the receipt record to the delivery note, the inspection and the project it belongs to. • Starts when: the GRN is raised. • How it runs: (1) he attaches the delivery note to the GRN. (2) He attaches the inspection record where applicable. (3) He records the project and cost allocation. (4) He records the submittal or certificate references. (5) He confirms the record set is complete. • Proof it happened: a GRN with the delivery note, inspection record, allocation and certificate references linked. • Where it usually breaks: the GRN stands alone with no supporting documents attached, so Finance cannot verify the invoice without chasing. | • Require the supporting documents to be attached to the GRN at the point it is raised, since a bare GRN forces Finance to chase and delays supplier payment. • Link the material certificates at receipt, as these are required for the closeout dossier and are hardest to obtain later. • Record the project and cost allocation, because reallocating afterwards is rarely done. • Link the inspection record, so the acceptance basis is traceable. • Check the document set is complete before submitting to Procurement.
705 | Procurement | Submit GRN and invoice-support records to Procurement and Finance | Storekeeper | Trigger: When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. Action: The Storekeeper completes “Submit GRN and invoice-support records to Procurement and Finance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accepted GRN or controlled quarantine, discrepancy, rejection and return record. Control/Handoff: GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When the initial receiving check is complete and acceptance, inspection or rejection must be recorded. | The Storekeeper completes “Submit GRN and invoice-support records to Procurement and Finance” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accepted GRN or controlled quarantine, discrepancy, rejection and return record. | GRN records only accepted quantities; QHSE/Project inspection is obtained when required, and discrepancies remain blocked from use and payment until resolved. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he sends the receipt records to Procurement and Finance so invoices can be checked and paid. • Starts when: the GRN and supporting records are complete. • How it runs: (1) he assembles the GRN and supporting documents. (2) He submits them to Procurement for invoice matching. (3) He submits the records Finance requires. (4) He responds to queries on the receipt. (5) He confirms submission in the register. • Proof it happened: submitted GRN and supporting records with the submission recorded and queries answered. • Where it usually breaks: GRNs sit at the store for weeks, so invoices cannot be matched and suppliers chase payment. | • Set a submission deadline in days from receipt, since GRNs held at the store are the main reason valid supplier invoices go unpaid. • Submit the full supporting set rather than the GRN alone, so Procurement can complete the three way match. • Report GRNs not yet submitted as an exception with ageing. • Answer receipt queries promptly, because these hold up the whole payment run. • Reconcile GRNs raised against GRNs submitted monthly.
706 | Procurement | Assign controlled warehouse, yard, rack and bin locations | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Assign controlled warehouse, yard, rack and bin locations” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Assign controlled warehouse, yard, rack and bin locations” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he gives every item a specific place in the store and records where it is. • Starts when: material is accepted and being put away. • How it runs: (1) he identifies the appropriate storage area for the material type. (2) He assigns the rack, bin or yard location. (3) He places the material in that location. (4) He records the location in the system. (5) He verifies the record matches the physical placement. • Proof it happened: assigned and recorded storage locations matching the physical placement of the material. • Where it usually breaks: material is placed wherever there is space without recording it, so it cannot be found and is bought again. | • Require the location to be recorded at put away, since unrecorded material cannot be found and is repurchased while sitting in the store. • Keep one item in one location where possible, because split locations are the main cause of count variances. • Label the locations physically so the system reference means something on the floor. • Assign locations by material type and handling need, not by available space. • Audit location accuracy during cycle counts, as this is what makes the system usable.
707 | Procurement | Label material by project, item, status, batch and ownership | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Label material by project, item, status, batch and ownership” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Label material by project, item, status, batch and ownership” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he labels material with what it is, whose it is, its status and its batch. • Starts when: material is put away. • How it runs: (1) he labels the item with its code and description. (2) He labels the project allocation. (3) He labels the status where it is not free stock. (4) He labels the batch or expiry where applicable. (5) He labels client supplied material distinctly. • Proof it happened: material labelled with item, project, status, batch and ownership information. • Where it usually breaks: client supplied and project allocated material is unlabelled, so it is issued to another project and cannot be replaced. | • Label client supplied and project allocated material distinctly, since issuing it to the wrong project creates a shortage that cannot always be replaced. • Include the batch and expiry on the label for shelf life items, so first expiry first out can actually be applied. • Use a durable label appropriate to the storage conditions, as labels that fall off make stock anonymous. • Label status such as quarantined or reserved, because the physical label is what crews actually see. • Relabel when status changes rather than relying on the system record.
708 | Procurement | Store material to prevent weather, moisture, impact and contamination damage | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Store material to prevent weather, moisture, impact and contamination damage” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Store material to prevent weather, moisture, impact and contamination damage” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he stores things so they do not get wet, knocked, dirty or damaged. • Starts when: material is put away, and continuously while stored. • How it runs: (1) he identifies the protection each material needs. (2) He stores weather sensitive items under cover. (3) He raises material off the ground where moisture is a risk. (4) He protects against impact and contamination. (5) He checks the protection remains effective. • Proof it happened: material stored with appropriate weather, moisture, impact and contamination protection, checked periodically. • Where it usually breaks: material is stored outside because the covered area is full, and it deteriorates silently until it is installed. | • State the protection requirement per material category rather than leaving it to judgement, since material stored inappropriately deteriorates invisibly until installation. • Escalate when covered storage is full instead of storing sensitive material outside. • Require material to be raised off the ground and separated from the walls where moisture matters. • Check the protection after rain and wind, because covers move. • Report storage capacity shortfalls, as these cause losses that are never attributed to storage.
709 | Procurement | Control hazardous material, SDS, ventilation and segregation requirements | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Control hazardous material, SDS, ventilation and segregation requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Control hazardous material, SDS, ventilation and segregation requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he handles hazardous material properly, with the right documents, ventilation and separation. • Starts when: hazardous material is received or stored. • How it runs: (1) he identifies the hazard classification. (2) He obtains and files the safety data sheet. (3) He stores it in the designated area with ventilation. (4) He separates incompatible materials. (5) He confirms spill containment and fire provision are in place. • Proof it happened: hazardous material stored in the designated area with the SDS filed, segregation and containment in place. • Where it usually breaks: incompatible chemicals are stored together because the designated areas are full, which is a fire and reaction risk. | • Require incompatible materials to be separated by the stated distance or barrier, and escalate rather than storing them together when space runs out. • Require the safety data sheet to be on file and accessible before the material is stored, not afterwards. • Require spill containment and the correct fire provision for the hazard class. • Limit the quantity held to the licensed or safe maximum, and record it. • Brief the store team on the hazards they are handling, as this group is routinely uninformed.
710 | Procurement | Control shelf-life, batch, expiry and first-expiry-first-out requirements | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Control shelf-life, batch, expiry and first-expiry-first-out requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Control shelf-life, batch, expiry and first-expiry-first-out requirements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he manages materials that expire, so the oldest usable stock goes out first. • Starts when: shelf life material is received, and continuously while held. • How it runs: (1) he records the batch and expiry date at receipt. (2) He stores it so the earliest expiry is accessible first. (3) He issues on a first expiry first out basis. (4) He monitors approaching expiries. (5) He quarantines expired material and reports it. • Proof it happened: batch and expiry records maintained with first expiry first out applied and expired material quarantined. • Where it usually breaks: newer stock is issued because it is easier to reach, so older stock expires in place and is written off. | • Arrange storage so the earliest expiry is physically the easiest to reach, since issuing what is accessible is what causes older stock to expire in place. • Report approaching expiries early enough for the material to be used or transferred. • Record the expiry at receipt, because it cannot be established later from the packaging alone. • Quarantine expired material immediately, as expired product installed is a defect. • Report expiry write offs with the cause, since these usually trace to over ordering.
711 | Procurement | Secure high-value, controlled, client-supplied and small attractive items | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Secure high-value, controlled, client-supplied and small attractive items” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Secure high-value, controlled, client-supplied and small attractive items” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he locks up the valuable, attractive and client owned items. • Starts when: such items are received or stored. • How it runs: (1) he identifies items requiring secure storage. (2) He stores them in the secure area with controlled access. (3) He records them individually. (4) He controls issue with named authorisation. (5) He counts them more frequently than general stock. • Proof it happened: high value and controlled items in secure storage with individual records and controlled issue. • Where it usually breaks: small attractive items such as tools and fittings are kept in open stock, and losses are only found at the annual count. | • Define small attractive items explicitly and require secure storage, since these are the items that disappear and the loss is only visible at the annual count. • Count high value and attractive items far more frequently than general stock. • Restrict secure area access to named individuals and record every entry. • Require named authorisation for issue of controlled items, not a general material request. • Track client supplied material separately, as loss of it is a contractual issue rather than a cost.
712 | Procurement | Maintain housekeeping, fire access, stacking and safe-load conditions | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Maintain housekeeping, fire access, stacking and safe-load conditions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Maintain housekeeping, fire access, stacking and safe-load conditions” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he keeps the store tidy, safe and accessible, with stacking and fire routes controlled. • Starts when: daily, and continuously. • How it runs: (1) he keeps aisles and fire routes clear. (2) He controls stacking heights and stability. (3) He keeps loads within the rack and floor limits. (4) He keeps the area clean and free of trip hazards. (5) He corrects problems and records the checks. • Proof it happened: maintained housekeeping with clear fire access, controlled stacking and loads within limits, checked and recorded. • Where it usually breaks: stock builds up in the aisles when space is tight, blocking fire routes and making the racking unstable. | • State that fire routes and access aisles may never be used for storage, whatever the space pressure, and name who enforces it. • Mark the maximum stacking height and the rack load limits physically, because these are otherwise judged by eye. • Escalate space shortages rather than absorbing them into the aisles. • Require a daily housekeeping check with the findings recorded. • Include the store in the site safety inspection round, as stores are often excluded.
713 | Procurement | Perform scheduled preservation and storage-condition inspections | Storekeeper | Trigger: When material is accepted into custody or a scheduled preservation check becomes due. Action: The Storekeeper completes “Perform scheduled preservation and storage-condition inspections” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a labelled, safely stored, protected and inspection-ready stock condition. Control/Handoff: Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When material is accepted into custody or a scheduled preservation check becomes due. | The Storekeeper completes “Perform scheduled preservation and storage-condition inspections” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a labelled, safely stored, protected and inspection-ready stock condition. | Storage follows manufacturer, SDS, security, stacking, shelf-life and project-segregation rules; deterioration or unsafe conditions are contained and escalated immediately. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he inspects stored material periodically to check it is still in good condition. • Starts when: at the scheduled inspection frequency. • How it runs: (1) he inspects the stored material for deterioration. (2) He checks the protection is still effective. (3) He checks the storage conditions such as damp and temperature. (4) He records the findings. (5) He acts on deterioration and reports losses. • Proof it happened: scheduled preservation inspection records with findings, actions taken and losses reported. • Where it usually breaks: no inspection happens, so deterioration is discovered when the material is issued and rejected at the work front. | • Set an inspection frequency by material sensitivity, since deterioration discovered at issue has already cost the programme and the material. • Inspect the protection as well as the material, because the cover failing is what causes the loss. • Report deterioration as a loss with the cause, so storage conditions get addressed. • Prioritise long held stock, as this is where deterioration concentrates. • Record the inspection, otherwise there is no evidence the material was cared for.
714 | Procurement | Maintain real-time FirstBit stock and bin-location records | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Maintain real-time FirstBit stock and bin-location records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Maintain real-time FirstBit stock and bin-location records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he keeps the system stock records matching what is physically in the store, in real time. • Starts when: any receipt, issue, transfer or adjustment occurs. • How it runs: (1) he records every movement in the system as it happens. (2) He keeps the bin locations current. (3) He avoids batching entries to the end of the day. (4) He checks the balance after each transaction. (5) He investigates any immediate discrepancy. • Proof it happened: system stock and location records updated in real time and matching the physical position. • Where it usually breaks: transactions are entered at the end of the day or week, so the system is never a reliable picture of what is actually available. | • Require transactions to be entered as they happen rather than batched, since a system updated at the end of the week is never a reliable basis for planning or issuing. • Prohibit physical movement without a system transaction, in either direction. • Keep the bin location current, as an accurate quantity in an unknown location is not usable stock. • Check the balance after each transaction, because errors caught immediately are traceable. • Report transaction backlogs, as these are the root of most stock inaccuracy.
715 | Procurement | Maintain minimum, maximum and reorder-level information | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Maintain minimum, maximum and reorder-level information” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Maintain minimum, maximum and reorder-level information” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he maintains the minimum, maximum and reorder levels for stocked items. • Starts when: the levels are set, and when consumption patterns change. • How it runs: (1) he reviews the consumption history per item. (2) He sets or updates the minimum and maximum levels. (3) He sets the reorder point allowing for lead time. (4) He flags items below minimum. (5) He notifies Procurement for replenishment. • Proof it happened: maintained stock level information with reorder points allowing for lead time, and below minimum items flagged. • Where it usually breaks: reorder levels are set without allowing for lead time, so the reorder is triggered too late and stock runs out anyway. | • Set the reorder point from consumption rate multiplied by lead time plus a buffer, since a level set without lead time triggers the order too late. • Review levels against actual consumption periodically rather than setting them once. • Flag and notify below minimum items automatically, not on inspection. • Set maximum levels too, because overstocking consumes cash and space silently. • Report stockouts with the cause, as most trace to levels never reviewed.
716 | Procurement | Reserve and allocate stock to approved projects and work fronts | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Reserve and allocate stock to approved projects and work fronts” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Reserve and allocate stock to approved projects and work fronts” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he reserves stock for approved projects so it is not issued to someone else. • Starts when: a project requires stock to be allocated in advance. • How it runs: (1) he receives the approved reservation request. (2) He confirms availability. (3) He reserves the quantity in the system. (4) He marks the material physically where practical. (5) He releases it only to the reserving project. • Proof it happened: reserved stock recorded in the system and physically marked, released only to the reserving project. • Where it usually breaks: reserved stock is issued to a more urgent request, so the original project finds nothing when it comes to collect. | • Prohibit issuing reserved stock to another project without the reserving project's written agreement, since silent reallocation leaves the first project short with no warning. • Mark reserved material physically as well as in the system, because crews collect what they can see. • Set an expiry on reservations, otherwise stock is reserved indefinitely and appears unavailable. • Report reserved but uncollected stock, as this ties up both material and cash. • Name who may authorise a reservation and who may override one.
717 | Procurement | Maintain serial-number, batch, warranty and traceability records | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Maintain serial-number, batch, warranty and traceability records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Maintain serial-number, batch, warranty and traceability records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he records serial numbers, batches and warranties so items can be traced later. • Starts when: traceable items are received. • How it runs: (1) he records the serial or batch number at receipt. (2) He records the warranty start date and period. (3) He links the record to the GRN and the certificate. (4) He records the issue destination when it goes out. (5) He maintains the traceability chain. • Proof it happened: serial, batch and warranty records linked to receipt and issue, maintaining the traceability chain. • Where it usually breaks: serial numbers are recorded at receipt but not at issue, so nobody knows which unit went where. | • Record the serial or batch number at issue as well as at receipt, since without the issue record nobody knows which unit was installed where. • Record the warranty start date, as warranty claims fail without evidence of when cover began. • Link the certificate to the batch, because a certificate not tied to installed material proves nothing. • Require traceability for structural, fire rated and pressure items as a minimum. • Make the traceability record available for the closeout dossier.
718 | Procurement | Perform scheduled cycle counts | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Perform scheduled cycle counts” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Perform scheduled cycle counts” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he counts part of the stock regularly rather than everything at once. • Starts when: at the scheduled cycle count frequency. • How it runs: (1) he selects the items due for counting. (2) He counts them physically without reference to the system figure. (3) He compares the count to the system. (4) He investigates variances. (5) He records the count and any adjustment with approval. • Proof it happened: cycle count records with blind counts, variances investigated and approved adjustments. • Where it usually breaks: the counter sees the system figure first, so the count confirms the record rather than testing it. | • Require counts to be blind, with the system quantity hidden from the counter, since a count made against a known figure confirms nothing. • Count high value and fast moving items more frequently than the rest. • Require variances to be investigated before adjustment, not adjusted and forgotten. • Have someone other than the custodian perform the count where possible. • Report count accuracy as a measure, as this is the real indicator of stock control.
719 | Procurement | Perform the monthly physical inventory count | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Perform the monthly physical inventory count” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Perform the monthly physical inventory count” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he runs the full physical stock count every month. • Starts when: at the monthly count date. • How it runs: (1) he prepares the count sheets and freezes movements. (2) He counts all stock physically. (3) He records the counted quantities. (4) He arranges recounts for significant variances. (5) He submits the count for reconciliation. • Proof it happened: a completed monthly physical count with movements frozen, quantities recorded and recounts where needed. • Where it usually breaks: movements continue during the count, so the variance found is a timing difference and the real errors are hidden. | • Freeze all movements during the count, since transactions during counting create timing differences that mask the real errors. • Require a recount of significant variances before any adjustment is proposed. • Include material held at site and in transit, otherwise the count is incomplete by design. • Require independent observation of the count at least periodically. • Record the count date and time, so the position is comparable to the system snapshot.
720 | Procurement | Reconcile physical stock to FirstBit and investigate variances | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Reconcile physical stock to FirstBit and investigate variances” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Reconcile physical stock to FirstBit and investigate variances” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he compares the counted stock to the system and finds out why any differences exist. • Starts when: a count is complete. • How it runs: (1) he compares counted quantities to the system. (2) He lists the variances by value. (3) He investigates each significant variance to its cause. (4) He proposes adjustments with the cause stated. (5) He obtains approval before adjusting. • Proof it happened: a reconciliation with variances listed, causes investigated and approved adjustments recorded. • Where it usually breaks: variances are adjusted as counting errors without investigation, which is exactly how theft and misallocation stay invisible. | • Prohibit adjusting a variance without a documented cause, since writing off differences as counting error is precisely how theft and misallocation stay invisible. • Require approval for adjustments by value band, with Finance involved above a threshold. • Investigate negative and positive variances equally, as offsetting errors indicate misposting. • Track variance trends by item and location, because concentration points at a specific cause. • Report the net and gross variance, not just the net, as netting hides the scale of error.
721 | Procurement | Report slow-moving, obsolete, surplus, damaged and expired stock | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Report slow-moving, obsolete, surplus, damaged and expired stock” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Report slow-moving, obsolete, surplus, damaged and expired stock” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he reports the stock that is not moving, is obsolete, surplus, damaged or expired. • Starts when: at the reporting cycle, and when such stock is identified. • How it runs: (1) he identifies stock with no movement over a stated period. (2) He identifies obsolete and superseded items. (3) He identifies damaged and expired stock. (4) He values each category. (5) He reports with recommendations for transfer, use or disposal. • Proof it happened: a report of slow moving, obsolete, surplus, damaged and expired stock with values and recommendations. • Where it usually breaks: the report is produced but no decision follows, so the stock stays on the shelf for years consuming space and cash. | • Require a decision on each reported item rather than only reporting it, since stock reported and never decided simply ages in place and ties up cash. • Define slow moving by a stated period of no movement, so the list is generated by rule. • Offer surplus to other projects before proposing disposal or new purchase. • Value the categories, because the decision depends on the money involved. • Report the ageing, as stock held for three years needs different treatment from three months.
722 | Procurement | Maintain stock-value, consumption and inventory-exception schedules for review | Storekeeper | Trigger: When a receipt, issue, reservation, count, reorder or inventory-review event occurs. Action: The Storekeeper completes “Maintain stock-value, consumption and inventory-exception schedules for review” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. Control/Handoff: Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When a receipt, issue, reservation, count, reorder or inventory-review event occurs. | The Storekeeper completes “Maintain stock-value, consumption and inventory-exception schedules for review” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | an accurate FirstBit stock record, allocation, count reconciliation and inventory-exception schedule. | Every physical movement has an authorised record; unexplained variance, negative stock, expiry, obsolete stock or value concern is investigated with Procurement and Finance. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he prepares the stock value, consumption and exception figures for management review. • Starts when: at the reporting cycle. • How it runs: (1) he compiles the stock value by category and project. (2) He compiles the consumption for the period. (3) He compiles the exceptions: variances, write offs and slow moving. (4) He reconciles the value to the system. (5) He submits the schedules for review. • Proof it happened: stock value, consumption and exception schedules reconciled to the system and submitted for review. • Where it usually breaks: the schedules do not reconcile to the ledger, so the figures are argued over rather than acted on. | • Reconcile the stock schedules to the ledger before submission, since figures that do not tie cannot be used and destroy trust in the whole report. • Report consumption against project budget, as this is what reveals over issuing. • Report write offs and variances separately from consumption, so losses are visible. • Keep the format consistent so periods are comparable. • State the count date the values are based on.
723 | Procurement | Issue material only against an authorised material request | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Issue material only against an authorised material request” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Issue material only against an authorised material request” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he only gives out material when there is a proper approved request for it. • Starts when: a material request is received at the store. • How it runs: (1) he checks the request is on the approved form. (2) He checks it carries the required authorisation. (3) He checks the requester is entitled to request for that project. (4) He refuses unauthorised requests. (5) He records the request against the issue. • Proof it happened: material issued only against authorised requests, with unauthorised requests refused and recorded. • Where it usually breaks: material is issued on a verbal request to keep work moving, so consumption cannot be attributed and stock records fail. | • Prohibit issuing on a verbal request without exception, since unrecorded issues make both the stock record and the project cost meaningless. • Name who may authorise a material request per project, and keep the list current. • Provide an emergency route with retrospective documentation rather than allowing informal issue. • Record refused requests, as these indicate where the authorisation process is not working. • Require the request to state the work front, not just the project.
724 | Procurement | Verify recipient, project, cost code, quantity and work-front before issue | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Verify recipient, project, cost code, quantity and work-front before issue” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Verify recipient, project, cost code, quantity and work-front before issue” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: before handing material over he checks who is collecting, for what project and for which work front. • Starts when: an authorised request is being fulfilled. • How it runs: (1) he verifies the identity of the person collecting. (2) He confirms the project and cost code. (3) He confirms the quantity against the request. (4) He confirms the work front the material is for. (5) He records the verification before issuing. • Proof it happened: a verification record of recipient, project, cost code, quantity and work front before issue. • Where it usually breaks: the quantity issued exceeds the request because the crew asks for extra at the counter, and the excess is never recorded. | • Issue only the quantity on the request and require a new authorised request for any increase, since counter top increases are never recorded and become unexplained consumption. • Verify the identity of the person collecting, as material issued to an unidentified person cannot be traced. • Confirm the cost code, because miscoded issues distort project cost permanently. • Record the work front, so over consumption can be traced to a location. • Require the recipient to sign at the point of collection.
725 | Procurement | Record material issues, consumption, balances and acknowledgements | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Record material issues, consumption, balances and acknowledgements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Record material issues, consumption, balances and acknowledgements” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he records what went out, to whom, and what balance is left. • Starts when: material is issued. • How it runs: (1) he records the issue in the system against the project. (2) He obtains the recipient's acknowledgement. (3) He updates the stock balance. (4) He records the consumption against the work front. (5) He files the issue record. • Proof it happened: recorded issues with acknowledgements, updated balances and consumption recorded against the project. • Where it usually breaks: issues are recorded on paper and entered into the system days later, so the available stock figure is wrong in between. | • Enter issues into the system at the point of issue, since a delayed entry means the available stock figure is wrong for everyone relying on it. • Require the recipient's signature or system acknowledgement, because an unacknowledged issue is disputed when consumption is questioned. • Record consumption against the work front rather than only the project, so over consumption is locatable. • Reconcile issued quantity against the BOQ quantity periodically, as this is what reveals waste and theft. • Report high consumption against budget by work front.
726 | Procurement | Receive and record unused, excess and returned project material | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Receive and record unused, excess and returned project material” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Receive and record unused, excess and returned project material” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he takes back the material the site did not use and puts it into stock. • Starts when: material is returned from a work front or project. • How it runs: (1) he receives the returned material and counts it. (2) He assesses the condition. (3) He records the return against the original issue and project. (4) He returns it to stock or quarantine depending on condition. (5) He credits the project for the returned quantity. • Proof it happened: recorded returns with quantity, condition, project credit and the material placed back in stock or quarantine. • Where it usually breaks: unused material is left at the work front rather than returned, so it is booked as consumed and quietly corrupts every future estimate. | • Make return of unused material a mandatory step at work front completion, since material never returned is booked as consumed and corrupts every future estimate. • Assess the condition on return and do not credit damaged material as new. • Credit the project for the returned quantity, otherwise crews have no reason to return anything. • Record returns against the original issue, so consumption per work front is accurate. • Report projects with no returns at all, as this is not credible on any real site.
727 | Procurement | Execute authorised warehouse, site and inter-project stock transfers | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Execute authorised warehouse, site and inter-project stock transfers” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Execute authorised warehouse, site and inter-project stock transfers” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he carries out the approved stock transfers between the warehouse, sites and projects. • Starts when: an approved transfer is instructed. • How it runs: (1) he confirms the transfer approval. (2) He confirms availability and condition. (3) He raises the transfer document before the material moves. (4) He arranges the physical movement. (5) He confirms receipt and the system record at both ends. • Proof it happened: an executed transfer with approval, documentation raised before movement and receipt confirmed at both ends. • Where it usually breaks: the material moves first and the paperwork follows later, so both locations show the wrong stock in the meantime. | • Raise the transfer document before the material physically moves, since paperwork that follows the material leaves both locations with wrong stock. • Require receipt confirmation at the destination, as a transfer out with no transfer in is an unexplained loss. • Require approval before transferring material charged to another project, because the cost follows the material. • Record condition at dispatch and receipt, so transit damage is attributed correctly. • Reconcile transfers in transit periodically, as this is where stock disappears.
728 | Procurement | Control tool, equipment and asset issue, return, condition and custody records | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Control tool, equipment and asset issue, return, condition and custody records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Control tool, equipment and asset issue, return, condition and custody records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: he controls the tools and equipment issued to people, and gets them back. • Starts when: a tool or item of equipment is issued or returned. • How it runs: (1) he records the item and its condition at issue. (2) He issues it to a named individual against signature. (3) He records the expected return. (4) He inspects the condition on return. (5) He follows up items not returned. • Proof it happened: tool custody records with named recipients, condition at issue and return, and follow up on outstanding items. • Where it usually breaks: tools are issued to a trade or a gang rather than a named person, so nobody is accountable when they disappear. | • Issue every tool to a named individual and never to a trade or gang, since collective custody means nobody is accountable when the tool disappears. • Record condition at issue and at return, so damage is attributable. • Include tool clearance in the employee exit process, because tools leave with leavers. • Report outstanding tools by holder with ageing, as this is what drives returns. • Set a replacement cost recovery policy and apply it consistently.
729 | Procurement | Report loss, theft, damage and unauthorised stock movement for investigation | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Report loss, theft, damage and unauthorised stock movement for investigation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Report loss, theft, damage and unauthorised stock movement for investigation” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: when stock goes missing or is damaged or moved without authority, he reports it for investigation. • Starts when: a loss, theft, damage or unauthorised movement is identified. • How it runs: (1) he records the facts, quantity and value. (2) He secures any evidence and the area. (3) He reports it immediately to the CPO and the project. (4) He supports the investigation. (5) He records the outcome and the control change. • Proof it happened: a reported loss record with the facts, value, evidence secured and the investigation outcome recorded. • Where it usually breaks: losses are absorbed into count variances rather than reported, so a pattern of theft is never investigated. | • Require every suspected loss or theft to be reported rather than absorbed into a count variance, since absorbing it is what allows a pattern to continue for years. • Secure the evidence and the area before anyone is approached, as early confrontation destroys it. • Report immediately rather than at the next count, because access logs and footage are overwritten. • Require the control weakness to be fixed, not only the incident resolved. • Track losses by item and location, as concentration identifies the route.
730 | Procurement | Close project stock with surplus transfer, approved disposal and archived records | Storekeeper | Trigger: When an authorised material/tool request, return, transfer, loss event or project closeout occurs. Action: The Storekeeper completes “Close project stock with surplus transfer, approved disposal and archived records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. Output/Evidence: a traceable issue, return, custody, transfer, investigation or closed project-stock record. Control/Handoff: The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. Continuity/Escalation: A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. Timing: To be confirmed. | When an authorised material/tool request, return, transfer, loss event or project closeout occurs. | The Storekeeper completes “Close project stock with surplus transfer, approved disposal and archived records” using approved IFC/BOQ, specifications, project programme, budget, vendor records and controlled FirstBit procurement/inventory records. | a traceable issue, return, custody, transfer, investigation or closed project-stock record. | The Storekeeper verifies authority and project/cost allocation before movement; loss, disposal and inter-project transfers require documented approval and FirstBit update. | A trained authorised storekeeper may provide custody backup with controlled system access; GRN correction, stock adjustment, disposal, loss and material exceptions require Procurement Lead or CPO approval. | To be confirmed. | • In plain words: at the end of a project he clears the stock, transfers the surplus and archives the records. • Starts when: a project reaches completion and its stock must be cleared. • How it runs: (1) he counts the remaining project stock. (2) He identifies the surplus and its condition and value. (3) He arranges transfer to other projects or the warehouse. (4) He arranges approved disposal for the rest. (5) He closes the project stock records and archives them. • Proof it happened: a closed project stock position with surplus transferred, approved disposals recorded and records archived. • Where it usually breaks: leftover stock is written off in bulk at closeout, so material that could have been used elsewhere is simply lost. | • Require surplus to be offered to other projects before any disposal or write off, since bulk write off at closeout loses material that is immediately needed elsewhere. • Require disposal approval by value with independent verification above a threshold, as disposal is a known fraud route. • Value the surplus transferred, so the receiving project is charged and the closing project credited. • Close the stock records formally, otherwise the project shows stock indefinitely. • Archive the records for the retention period, as stock records support both claims and audits.
731 | Finance | Set Finance strategy, policies and annual operating objectives | Chief Financial Officer (CFO) | Trigger: When the annual planning cycle, a policy change, control review or material financial event requires direction. Action: The Chief Financial Officer (CFO) completes “Set Finance strategy, policies and annual operating objectives” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved Finance policy, authority decision, KPI framework or controlled risk action. Control/Handoff: The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual planning cycle, a policy change, control review or material financial event requires direction. | The Chief Financial Officer (CFO) completes “Set Finance strategy, policies and annual operating objectives” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved Finance policy, authority decision, KPI framework or controlled risk action. | The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he decides how finance will run for the year, what it is trying to achieve and the rules everyone must follow with money. • Starts when: the annual planning cycle opens, or the business changes enough that the existing rules no longer fit. • How it runs: (1) he reviews what the business plan will demand in funding, reporting and control. (2) He sets the objectives for the function for the year. (3) He drafts or updates the finance policies. (4) He obtains the CEO's approval. (5) He issues them to the departments who spend and commit money. • Proof it happened: approved finance strategy, policies and annual objectives, issued to the business. • Where it usually breaks: the policies are written for the finance team alone, so the departments who actually commit the money never see them. | • Require the policies to be issued to every department that spends or commits money, since most control breaches start outside finance. • Set measurable objectives: close timetable, forecast accuracy, collection days and audit findings. Objectives without measures cannot be reviewed. • State the policy review frequency and who may approve an exception, so exceptions are decided rather than assumed. • Keep the policy set short and readable, because a policy nobody reads is enforced by nobody. • Link the strategy to the delegation of authority, so the rules and the approval limits are reviewed at the same time.
732 | Finance | Approve the financial-control framework, chart-of-account governance and segregation of duties | Chief Financial Officer (CFO) | Trigger: When the annual planning cycle, a policy change, control review or material financial event requires direction. Action: The Chief Financial Officer (CFO) completes “Approve the financial-control framework, chart-of-account governance and segregation of duties” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved Finance policy, authority decision, KPI framework or controlled risk action. Control/Handoff: The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual planning cycle, a policy change, control review or material financial event requires direction. | The Chief Financial Officer (CFO) completes “Approve the financial-control framework, chart-of-account governance and segregation of duties” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved Finance policy, authority decision, KPI framework or controlled risk action. | The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he sets the control framework, the structure of the accounts, and makes sure no one person controls a transaction end to end. • Starts when: the framework is established, and whenever roles, systems or the organisation change. • How it runs: (1) he maps the financial processes from commitment to payment to recording. (2) He assigns each step to a role and sets the limits. (3) He checks no role holds two conflicting steps. (4) He controls who may create or change accounts in the chart of accounts. (5) He configures the system to enforce it and reviews it periodically. • Proof it happened: an approved financial control framework with segregation of duties defined, chart of account controls and matching system settings. • Where it usually breaks: the framework is documented but system permissions allow more than it says, so the control exists only on paper. | • Require system permissions to be reconciled against the approved framework at a set frequency. A control not enforced in the system is not a control. • Name the steps that must never sit with one person: raising, approving, recording, paying and reconciling. • Restrict chart of account changes to named people, since uncontrolled account creation destroys comparability and hides misposting. • Define the temporary delegation route with an end date, because absence cover is where segregation quietly collapses. • Require an exception log for anything processed outside the framework, reviewed by the CEO.
733 | Finance | Approve banking mandates, signatory limits and payment-authority controls | Chief Financial Officer (CFO) | Trigger: When the annual planning cycle, a policy change, control review or material financial event requires direction. Action: The Chief Financial Officer (CFO) completes “Approve banking mandates, signatory limits and payment-authority controls” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved Finance policy, authority decision, KPI framework or controlled risk action. Control/Handoff: The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual planning cycle, a policy change, control review or material financial event requires direction. | The Chief Financial Officer (CFO) completes “Approve banking mandates, signatory limits and payment-authority controls” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved Finance policy, authority decision, KPI framework or controlled risk action. | The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he controls who can move the company's money out of its bank accounts, and up to what value. • Starts when: accounts are opened, mandates are reviewed, or signatories join or leave. • How it runs: (1) he defines the signatory groups and the value limits for each. (2) He requires dual authorisation above stated values. (3) He arranges the bank mandate documentation with the banks. (4) He removes leavers immediately and confirms it with the bank. (5) He reviews the mandates periodically against the actual organisation. • Proof it happened: current bank mandates with signatory limits, dual authorisation rules and confirmation of removals. • Where it usually breaks: a leaver stays on the bank mandate for months because removal was never confirmed with the bank. | • Require bank confirmation of every signatory removal, with the confirmation retained, since an unremoved leaver is a live exposure. • Require dual authorisation above a stated value with the two authorisers from different functions. • Include the leaver process in the HR exit checklist, because finance often learns of a departure after the fact. • Review mandates at a fixed frequency against the current organisation chart, not only when a change is requested. • Cover online banking tokens and device custody explicitly, as these are the practical means of payment rather than the paper mandate.
734 | Finance | Establish financial KPIs, materiality thresholds, reporting standards and closing calendar | Chief Financial Officer (CFO) | Trigger: When the annual planning cycle, a policy change, control review or material financial event requires direction. Action: The Chief Financial Officer (CFO) completes “Establish financial KPIs, materiality thresholds, reporting standards and closing calendar” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved Finance policy, authority decision, KPI framework or controlled risk action. Control/Handoff: The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual planning cycle, a policy change, control review or material financial event requires direction. | The Chief Financial Officer (CFO) completes “Establish financial KPIs, materiality thresholds, reporting standards and closing calendar” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved Finance policy, authority decision, KPI framework or controlled risk action. | The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he sets the numbers the company is measured on, what counts as significant, how things are reported and the closing timetable. • Starts when: at the start of the financial year, and when reporting requirements change. • How it runs: (1) he defines the financial measures and how each is calculated. (2) He sets the materiality thresholds for review and approval. (3) He sets the reporting standards and formats. (4) He publishes the monthly and year end closing calendar. (5) He communicates the requirements to the departments who feed the process. • Proof it happened: defined measures with calculation rules, materiality thresholds, reporting formats and a published closing calendar. • Where it usually breaks: the closing calendar is published to finance only, so the departments who owe accruals and information miss their dates. | • Publish the closing calendar to every department that must submit information, with their specific deadlines named. • Define each measure's calculation in writing, so figures are comparable between periods and cannot be quietly redefined. • Set materiality thresholds that determine what needs review, since without them everything or nothing gets attention. • Fix the report formats so periods are comparable and management is not relearning the layout each month. • State the consequence of a missed submission deadline, otherwise the calendar is advisory.
735 | Finance | Report financial performance, liquidity, compliance and control risk to the CEO | Chief Financial Officer (CFO) | Trigger: When the annual planning cycle, a policy change, control review or material financial event requires direction. Action: The Chief Financial Officer (CFO) completes “Report financial performance, liquidity, compliance and control risk to the CEO” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved Finance policy, authority decision, KPI framework or controlled risk action. Control/Handoff: The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual planning cycle, a policy change, control review or material financial event requires direction. | The Chief Financial Officer (CFO) completes “Report financial performance, liquidity, compliance and control risk to the CEO” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved Finance policy, authority decision, KPI framework or controlled risk action. | The CFO records the decision and maintains segregation of duties; reserved matters and material risk escalate to the CEO or Chairman. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he tells the CEO where the company stands on results, cash, compliance and control weaknesses. • Starts when: at the monthly reporting cycle, and immediately for material events. • How it runs: (1) he reports the performance against budget and forecast. (2) He reports the liquidity position and the runway. (3) He reports compliance and audit matters. (4) He raises control weaknesses and the risks they create. (5) He records the CEO's directions and acts on them. • Proof it happened: a reported financial pack covering performance, liquidity, compliance and control risk, with directions recorded. • Where it usually breaks: control weaknesses are left out because they reflect on finance itself, so the CEO learns about them from the auditor. | • Require control weaknesses and near misses to be reported by the CFO, since an auditor discovering them first is a governance failure. • Name the events that must be reported immediately rather than monthly: covenant breach, suspected fraud, liquidity shortfall and material misstatement. • Report liquidity as a forward runway in weeks, not just a bank balance, because a balance says nothing about what is committed. • Keep the pack format consistent, so the CEO can compare periods without re reading the structure. • Record the CEO's directions in writing, as verbal financial directions are remembered differently later.
736 | Finance | Lead the annual budget and financial operating-plan process | Chief Financial Officer (CFO) | Trigger: When the annual budget, rolling forecast, investment request or material variance cycle becomes due. Action: The Chief Financial Officer (CFO) completes “Lead the annual budget and financial operating-plan process” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved budget, forecast, funding decision, variance action or revised financial baseline. Control/Handoff: Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual budget, rolling forecast, investment request or material variance cycle becomes due. | The Chief Financial Officer (CFO) completes “Lead the annual budget and financial operating-plan process” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved budget, forecast, funding decision, variance action or revised financial baseline. | Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he runs the annual budget process, pulling the departments' plans into one financial plan for the year. • Starts when: at the start of the budget cycle set in the governance calendar. • How it runs: (1) he issues the budget instructions, assumptions and templates. (2) Departments submit their budgets against them. (3) He consolidates, challenges and iterates with each chief. (4) He builds the consolidated plan with cash flow. (5) He takes it through the CEO to ownership approval and baselines it. • Proof it happened: an approved and baselined budget with department submissions, consolidation and the approval trail. • Where it usually breaks: departments submit against different assumptions, so the consolidated plan does not add up and the challenge rounds run out of time. | • Issue the assumptions centrally and require every submission to use them, since inconsistent assumptions make consolidation meaningless. • Publish the calendar working backwards from the ownership approval date, so the challenge rounds have real time. • List the required contents of a submission and return incomplete packs rather than debating them. • Baseline and version the approved budget, so later changes are visible as revisions rather than silent edits. • Require the cash flow to be built with the budget, because a profitable plan that cannot be funded is not a plan.
737 | Finance | Approve departmental budgets, project budgets and cost-control baselines | Chief Financial Officer (CFO) | Trigger: When the annual budget, rolling forecast, investment request or material variance cycle becomes due. Action: The Chief Financial Officer (CFO) completes “Approve departmental budgets, project budgets and cost-control baselines” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved budget, forecast, funding decision, variance action or revised financial baseline. Control/Handoff: Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual budget, rolling forecast, investment request or material variance cycle becomes due. | The Chief Financial Officer (CFO) completes “Approve departmental budgets, project budgets and cost-control baselines” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved budget, forecast, funding decision, variance action or revised financial baseline. | Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves each department's and each project's budget, which becomes the line everyone is measured against. • Starts when: budgets are submitted for approval, and when a project budget is set at award. • How it runs: (1) he reviews the submission against the plan and the assumptions. (2) He challenges the resourcing and the cost assumptions. (3) He confirms the project budget against the tender and the awarded contract. (4) He approves and baselines it. (5) He issues the approved baseline to the owner and locks it in the system. • Proof it happened: approved and baselined department and project budgets, issued and locked in the system. • Where it usually breaks: the project budget is set from the tender rather than the awarded contract, so the baseline is wrong from day one. | • Require project budgets to be set from the awarded contract value and the post award cost plan, not from the tender estimate. • Lock the baseline in the system after approval so variance reporting has a fixed reference. • Require the budget owner to acknowledge the baseline, since a budget nobody accepted is one nobody defends. • State the contingency separately and name who may release it, because contingency absorbed silently hides overruns. • Require any baseline change to go through a documented revision with a reason.
738 | Finance | Approve the rolling forecast, cash-flow forecast and funding plan | Chief Financial Officer (CFO) | Trigger: When the annual budget, rolling forecast, investment request or material variance cycle becomes due. Action: The Chief Financial Officer (CFO) completes “Approve the rolling forecast, cash-flow forecast and funding plan” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved budget, forecast, funding decision, variance action or revised financial baseline. Control/Handoff: Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual budget, rolling forecast, investment request or material variance cycle becomes due. | The Chief Financial Officer (CFO) completes “Approve the rolling forecast, cash-flow forecast and funding plan” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved budget, forecast, funding decision, variance action or revised financial baseline. | Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the updated view of where the year is heading, how cash will flow and how any gap will be funded. • Starts when: at each forecast cycle, and when a material event changes the outlook. • How it runs: (1) he reviews the updated forecast against budget and actuals. (2) He reviews the cash flow forecast including collections and commitments. (3) He identifies any funding gap and the timing. (4) He agrees the funding plan: facilities, timing or deferral. (5) He approves the forecast and reports it. • Proof it happened: an approved rolling forecast with cash flow and a funding plan covering any identified gap. • Where it usually breaks: the forecast is built on optimistic collection dates, so the funding gap appears later and larger than planned. | • Require collections to be forecast on actual client payment behaviour rather than contractual terms, since this is where cash forecasts fail. • Require the forecast to be reconciled to the previous version with the movements explained, so forecast quality is visible. • Show the cash position weekly for the near term and monthly beyond it, because monthly detail hides mid month shortfalls. • Require the funding plan to be arranged before the gap arrives, as facilities negotiated under pressure cost more. • Track forecast accuracy as a measure, otherwise there is no incentive to forecast honestly.
739 | Finance | Review capital expenditure, financing needs and major financial commitments | Chief Financial Officer (CFO) | Trigger: When the annual budget, rolling forecast, investment request or material variance cycle becomes due. Action: The Chief Financial Officer (CFO) completes “Review capital expenditure, financing needs and major financial commitments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved budget, forecast, funding decision, variance action or revised financial baseline. Control/Handoff: Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual budget, rolling forecast, investment request or material variance cycle becomes due. | The Chief Financial Officer (CFO) completes “Review capital expenditure, financing needs and major financial commitments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved budget, forecast, funding decision, variance action or revised financial baseline. | Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he reviews the big spending and borrowing decisions before the company commits to them. • Starts when: a capital request or financing need is raised, or at the scheduled review. • How it runs: (1) he reviews the business case and the cash effect. (2) He tests the assumptions and the payback. (3) He confirms the funding source and the effect on facilities and covenants. (4) He recommends approval, deferral or rejection. (5) He takes it to the CEO or ownership where it exceeds his authority. • Proof it happened: a reviewed capital or financing submission with the funding source, covenant effect and recommendation. • Where it usually breaks: capital is approved on the purchase price alone, with running, maintenance and financing costs never assessed. | • Require whole life cost in every capital case: purchase, financing, running, maintenance and disposal, not just the purchase price. • Require the covenant and facility headroom effect to be stated, since a commitment that breaches a covenant costs far more than its own value. • Require a buy against hire or lease comparison for plant, as this is decided by habit more often than by analysis. • Require post implementation review of major capital, otherwise business cases are never tested against outcomes. • State the authority level by total commitment including financing cost, not by the asset price.
740 | Finance | Approve budget-variance, reforecast and corrective-action decisions | Chief Financial Officer (CFO) | Trigger: When the annual budget, rolling forecast, investment request or material variance cycle becomes due. Action: The Chief Financial Officer (CFO) completes “Approve budget-variance, reforecast and corrective-action decisions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved budget, forecast, funding decision, variance action or revised financial baseline. Control/Handoff: Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the annual budget, rolling forecast, investment request or material variance cycle becomes due. | The Chief Financial Officer (CFO) completes “Approve budget-variance, reforecast and corrective-action decisions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved budget, forecast, funding decision, variance action or revised financial baseline. | Department owners submit evidence; the CFO challenges assumptions and escalates unapproved commitments or material deviations before release. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: when actual results drift from budget, he decides what the new expectation is and what will be done about it. • Starts when: variance reporting shows a material deviation, or at the scheduled reforecast point. • How it runs: (1) he reviews the variance and its cause with the budget owner. (2) He separates timing differences from real overruns. (3) He agrees corrective actions with the owner. (4) He decides whether the budget is reforecast or held. (5) He records the decision and tracks the corrective actions. • Proof it happened: a variance review record with causes, agreed corrective actions and a documented reforecast decision. • Where it usually breaks: every variance is explained as timing, so real overruns are only recognised at year end. | • Require timing explanations to state the period the cost will land in, so a timing claim can be tested next month. • Set a materiality threshold that forces a written explanation, rather than reviewing every line. • Require corrective actions with owners and dates, since a variance meeting without actions changes nothing. • Keep the original baseline visible after a reforecast, or the year's cumulative drift disappears. • Track repeat variances by owner, because a repeatedly missed budget is a planning problem rather than an execution one.
741 | Finance | Approve weekly cash priorities and the controlled payment plan | Chief Financial Officer (CFO) | Trigger: When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. Action: The Chief Financial Officer (CFO) completes “Approve weekly cash priorities and the controlled payment plan” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. Control/Handoff: Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. | The Chief Financial Officer (CFO) completes “Approve weekly cash priorities and the controlled payment plan” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. | Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: every week he decides what gets paid and in what order, because cash is finite and demands exceed it. • Starts when: weekly at the payment planning point, and when a liquidity constraint arises. • How it runs: (1) he reviews the available cash and the expected collections. (2) He reviews the due and overdue payment demands. (3) He prioritises: statutory, payroll, critical suppliers, then the rest. (4) He approves the payment plan for the week. (5) He communicates deferrals so commitments are managed rather than broken silently. • Proof it happened: an approved weekly payment plan with the prioritisation applied and the deferrals identified. • Where it usually breaks: deferred suppliers are not told, so the company loses credit terms and goodwill it did not need to lose. | • State the payment priority order in the SOP: statutory and payroll first, then critical supply, then the rest, so prioritisation is not a weekly argument. • Require deferred suppliers to be informed with a revised date, since silence costs credit terms and future pricing. • Require the plan to be built from confirmed collections rather than hoped for ones. • Protect statutory payments absolutely, as penalties and interest are more expensive than any supplier pressure. • Record repeated deferrals of the same supplier, because that is how supply failures begin.
742 | Finance | Monitor bank balances, liquidity runway, facilities and cash concentration | Chief Financial Officer (CFO) | Trigger: When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. Action: The Chief Financial Officer (CFO) completes “Monitor bank balances, liquidity runway, facilities and cash concentration” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. Control/Handoff: Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. | The Chief Financial Officer (CFO) completes “Monitor bank balances, liquidity runway, facilities and cash concentration” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. | Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he watches the bank balances, how long the cash will last, what facilities are available and where the money is held. • Starts when: daily on balances, and at the weekly and monthly review points. • How it runs: (1) he reviews the balances across all accounts and banks. (2) He calculates the liquidity runway against committed outflows. (3) He reviews the facility utilisation and headroom. (4) He reviews concentration across banks and counterparties. (5) He escalates where the runway falls below the stated threshold. • Proof it happened: a monitored liquidity position with runway, facility headroom and concentration reported against thresholds. • Where it usually breaks: the balance looks healthy while large committed outflows are ignored, so a shortfall appears with no warning. | • Report runway against committed outflows rather than the bank balance, since a healthy balance can be fully committed. • Set a minimum runway threshold that triggers escalation to the CEO automatically. • Monitor facility expiry dates as well as utilisation, because renewal under pressure is expensive or refused. • Review bank concentration, as holding everything with one bank turns a bank problem into a company problem. • Require daily balance reporting to be reconciled to the ledger, so unrecorded transactions are caught quickly.
743 | Finance | Approve bank transfers, foreign-exchange transactions and financing drawdowns | Chief Financial Officer (CFO) | Trigger: When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. Action: The Chief Financial Officer (CFO) completes “Approve bank transfers, foreign-exchange transactions and financing drawdowns” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. Control/Handoff: Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. | The Chief Financial Officer (CFO) completes “Approve bank transfers, foreign-exchange transactions and financing drawdowns” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. | Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves money moving between accounts, currency conversions and drawdowns on borrowing facilities. • Starts when: a transfer, currency transaction or drawdown is required. • How it runs: (1) he confirms the purpose and the amount against the approved plan. (2) He confirms the beneficiary and account details are verified. (3) For currency, he checks the rate and the timing. (4) For a drawdown, he confirms the facility terms and the covenant effect. (5) He approves within his authority or escalates. • Proof it happened: approved transfer, currency and drawdown records with purpose, verified beneficiary details and authority evidence. • Where it usually breaks: an urgent transfer is approved on emailed beneficiary details that were never independently verified. | • Require beneficiary details to be taken from the verified master record and never from the payment request, since this is the primary payment fraud route. • Require dual authorisation for external transfers above a stated value, with the second authoriser independent of the requester. • Require a written purpose for every internal transfer, otherwise inter account movement can be used to disguise misappropriation. • Set a policy on currency exposure and hedging, so rate decisions are not made transaction by transaction on instinct. • Check the covenant effect before every drawdown, as a technical breach can accelerate the whole facility.
744 | Finance | Govern bank guarantees, letters of credit and project security instruments | Chief Financial Officer (CFO) | Trigger: When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. Action: The Chief Financial Officer (CFO) completes “Govern bank guarantees, letters of credit and project security instruments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. Control/Handoff: Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. | The Chief Financial Officer (CFO) completes “Govern bank guarantees, letters of credit and project security instruments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. | Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he controls the guarantees and letters of credit the company gives clients and suppliers, and makes sure they are returned when finished. • Starts when: an instrument is requested, and continuously through its validity period. • How it runs: (1) he reviews the required wording and the exposure it creates. (2) He confirms the facility capacity and the cost. (3) He arranges issue with the bank. (4) He records the instrument with its value, expiry and the obligation it covers. (5) He arranges cancellation and return when the obligation ends. • Proof it happened: a guarantee and letter of credit register with values, expiry dates, covered obligations and cancellation evidence. • Where it usually breaks: instruments stay live long after the obligation has ended, so the company pays charges and ties up facility capacity for nothing. | • Diarise every expiry and require active cancellation and return, since expired obligations with live instruments waste both charges and facility headroom. • Prefer expiry dated instruments over open ended ones, and require CLO review of any open ended wording. • Require the covered obligation to be recorded, so the register shows what can be released rather than only what exists. • Report total contingent exposure to the CEO, because guarantees are real liabilities that sit outside the visible accounts. • Check the wording for unconditional or on demand terms, as these can be called without any proven default.
745 | Finance | Approve emergency liquidity, funding and collection-recovery actions | Chief Financial Officer (CFO) | Trigger: When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. Action: The Chief Financial Officer (CFO) completes “Approve emergency liquidity, funding and collection-recovery actions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. Control/Handoff: Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the cash-planning cutoff, payment cycle, facility requirement or liquidity exception occurs. | The Chief Financial Officer (CFO) completes “Approve emergency liquidity, funding and collection-recovery actions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved cash-priority decision, treasury transaction, facility action or liquidity recovery plan. | Bank access, creation and approval remain segregated; unsupported or out-of-authority treasury actions are blocked and escalated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: when cash gets tight he decides the emergency measures, whether that is funding, collection pressure or deferral. • Starts when: the liquidity runway falls below the threshold, or a major collection fails. • How it runs: (1) he quantifies the shortfall and its timing. (2) He identifies the options: facility drawdown, collection acceleration, deferral or ownership support. (3) He assesses the cost and consequence of each. (4) He obtains CEO or ownership approval where required. (5) He executes and reports the position until it is resolved. • Proof it happened: a documented liquidity action with the options considered, the approval obtained and the resolution tracked. • Where it usually breaks: the shortfall is managed by silently stretching suppliers, so the problem is hidden until supply stops. | • Require any liquidity action beyond a stated threshold to be reported to the CEO, so a shortfall is never managed silently by stretching suppliers. • Prepare the emergency options in advance, since facilities and support arranged during a crisis are the most expensive. • State which payments may never be deferred: payroll, statutory dues and safety critical supply. • Require the root cause to be addressed, as recurring liquidity events usually trace to collection failure rather than to funding. • Record the cost of the action taken, so the true cost of poor collection becomes visible.
746 | Finance | Approve project financial activation and work-before-payment exceptions | Chief Financial Officer (CFO) | Trigger: When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. Action: The Chief Financial Officer (CFO) completes “Approve project financial activation and work-before-payment exceptions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved activation, margin decision, project forecast, provision, credit or recovery action. Control/Handoff: Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. | The Chief Financial Officer (CFO) completes “Approve project financial activation and work-before-payment exceptions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved activation, margin decision, project forecast, provision, credit or recovery action. | Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he decides whether a project may start spending before the client's payment or commitment is secured. • Starts when: a project needs to mobilise before the advance, the contract or the security is in place. • How it runs: (1) he reviews the contractual and payment status. (2) He quantifies the exposure if the project does not proceed. (3) He assesses the client's creditworthiness and payment record. (4) He decides, sets a spending cap and any conditions. (5) He records the exception and monitors it until the position is regularised. • Proof it happened: a documented work before payment exception with the exposure quantified, a spending cap and a review date. • Where it usually breaks: an informal go ahead is given verbally, spending grows past any cap, and there is no record of who authorised the exposure. | • Require every exception to carry a value cap and a review date in writing, since uncapped early spending is how unrecoverable exposure builds. • Require a client credit assessment before the exception, not after, particularly for new clients. • Name who may authorise these exceptions and prohibit verbal authorisation entirely. • Require the position to be regularised or escalated at the review date rather than rolling on by default. • Report open exceptions and their total exposure monthly, as individually small exceptions aggregate into a serious number.
747 | Finance | Approve quotation margins, commercial assumptions and financial deviations | Chief Financial Officer (CFO) | Trigger: When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. Action: The Chief Financial Officer (CFO) completes “Approve quotation margins, commercial assumptions and financial deviations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved activation, margin decision, project forecast, provision, credit or recovery action. Control/Handoff: Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. | The Chief Financial Officer (CFO) completes “Approve quotation margins, commercial assumptions and financial deviations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved activation, margin decision, project forecast, provision, credit or recovery action. | Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the margins and the financial assumptions in quotations before they go to clients. • Starts when: a quotation or tender is prepared and needs financial approval. • How it runs: (1) he reviews the cost build up and the assumptions. (2) He checks the margin against the approved minimum. (3) He reviews the payment terms, retention and cash profile of the offer. (4) He approves, or requires the margin or terms to be corrected. (5) He records any approved deviation from standard. • Proof it happened: an approved quotation with margin, assumptions, payment terms and any recorded deviation. • Where it usually breaks: margin is approved on the price without reviewing the payment terms, so a profitable job consumes cash for a year. | • Require the cash profile of the offer to be reviewed alongside the margin, since a profitable contract with poor terms can still sink the company. • Set minimum margin thresholds by work type and name who may approve anything below them. • Require the assumptions to be listed and carried into the contract, otherwise excluded scope becomes free scope. • Require tax treatment to be confirmed for cross border or unusual arrangements before pricing. • Track won work against approved margin, so the accuracy of the pricing basis is tested rather than assumed.
748 | Finance | Review project committed cost, actual cost, revenue, margin and forecast-at-completion | Chief Financial Officer (CFO) | Trigger: When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. Action: The Chief Financial Officer (CFO) completes “Review project committed cost, actual cost, revenue, margin and forecast-at-completion” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved activation, margin decision, project forecast, provision, credit or recovery action. Control/Handoff: Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. | The Chief Financial Officer (CFO) completes “Review project committed cost, actual cost, revenue, margin and forecast-at-completion” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved activation, margin decision, project forecast, provision, credit or recovery action. | Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he reviews where each project stands financially, including the honest view of where it will finish. • Starts when: at the monthly project review cycle, and when a project reports a material change. • How it runs: (1) he reviews committed cost, actual cost and revenue recognised. (2) He reviews the cost to complete and the forecast at completion. (3) He tests the forecast against the physical progress. (4) He challenges optimistic recovery assumptions. (5) He agrees actions and reports the position. • Proof it happened: a project financial review with committed and actual cost, margin and a challenged forecast at completion. • Where it usually breaks: cost to complete is calculated as budget minus spend, which guarantees the overrun stays hidden until the end. | • Prohibit cost to complete being derived as budget minus spend, and require it to be built from remaining work and current rates. • Require committed cost rather than invoiced cost, since commitment is where the budget is actually consumed. • Require pending variations and claims to be shown separately from certified revenue, so the forecast does not rely on unapproved income. • Reconcile the financial position with the physical progress, as a mismatch is the earliest reliable warning of a problem project. • Track forecast at completion movement month to month, because the direction matters more than the single figure.
749 | Finance | Approve material credit notes, write-offs, provisions and retention strategy | Chief Financial Officer (CFO) | Trigger: When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. Action: The Chief Financial Officer (CFO) completes “Approve material credit notes, write-offs, provisions and retention strategy” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved activation, margin decision, project forecast, provision, credit or recovery action. Control/Handoff: Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. | The Chief Financial Officer (CFO) completes “Approve material credit notes, write-offs, provisions and retention strategy” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved activation, margin decision, project forecast, provision, credit or recovery action. | Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves writing off money the company will not collect, and decides how retentions are pursued. • Starts when: a credit note, write off or provision is proposed, or retention becomes due. • How it runs: (1) he reviews the case and the recovery attempts made. (2) He confirms the commercial and legal position. (3) He decides the provision or write off and the accounting treatment. (4) He obtains higher approval where the value exceeds his authority. (5) He records the decision and the reason. • Proof it happened: approved credit notes, write offs and provisions with recovery evidence and the recorded justification. • Where it usually breaks: write offs are approved without recovery having been genuinely pursued, so collection discipline weakens across the business. | • Require documented evidence of recovery attempts and legal review before any write off, since easy write offs destroy collection discipline. • Set authority thresholds for write offs and require ownership approval above a stated value. • Require write offs to be reported with their cause, as the pattern usually points at contract or certification weaknesses. • Diarise retention due dates with a named owner, because unclaimed retention is the most commonly abandoned money in the business. • Review the provision policy annually, so provisioning is consistent rather than decided case by case.
750 | Finance | Resolve project cost, revenue, cash and collection exceptions with functional chiefs | Chief Financial Officer (CFO) | Trigger: When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. Action: The Chief Financial Officer (CFO) completes “Resolve project cost, revenue, cash and collection exceptions with functional chiefs” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an approved activation, margin decision, project forecast, provision, credit or recovery action. Control/Handoff: Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When a project activation, quotation, cost update, billing event or margin/cash exception requires Finance control. | The Chief Financial Officer (CFO) completes “Resolve project cost, revenue, cash and collection exceptions with functional chiefs” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an approved activation, margin decision, project forecast, provision, credit or recovery action. | Finance reconciles contract, BOQ, certification, cost and cash evidence; material programme, scope or commercial exceptions align with COO, CTO, CPO, CMO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: when a project has a cost, revenue or collection problem, he sorts it out with the chief responsible. • Starts when: an exception is reported, or a review identifies a problem needing cross functional resolution. • How it runs: (1) he establishes the facts with the relevant chief. (2) He identifies whether it is a commercial, delivery or client issue. (3) He agrees the action and who owns it. (4) He sets the timeline and the reporting back point. (5) He tracks it until it is resolved or escalated. • Proof it happened: an exception resolution record with the cause, the agreed action, the owner and the resolution. • Where it usually breaks: the issue is treated as a finance problem, so the department that caused it never changes anything. | • Assign the action to the function that caused the issue rather than to finance, since finance can report a problem but not fix a delivery or certification failure. • Require the root cause to be recorded, as most collection failures trace to incomplete documentation or uncertified work. • Escalate to the CEO where two chiefs cannot agree, rather than letting the exception age. • Set a resolution timeline per exception type, so items do not sit open across reporting cycles. • Report recurring exception causes, because these indicate a process fault rather than isolated events.
751 | Finance | Approve monthly and year-end financial close | Chief Financial Officer (CFO) | Trigger: When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. Action: The Chief Financial Officer (CFO) completes “Approve monthly and year-end financial close” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: approved financial statements, management reporting, tax filing, audit response or investigation action. Control/Handoff: No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. | The Chief Financial Officer (CFO) completes “Approve monthly and year-end financial close” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | approved financial statements, management reporting, tax filing, audit response or investigation action. | No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the closing of the books each month and at year end, confirming the numbers are complete and correct. • Starts when: at each monthly close and at the year end close. • How it runs: (1) he confirms the close checklist is complete. (2) He reviews the reconciliations: bank, receivables, payables and intercompany. (3) He reviews the accruals, provisions and cut off treatment. (4) He reviews the unusual and manual journals. (5) He approves the close and locks the period. • Proof it happened: an approved close with a completed checklist, signed reconciliations and reviewed journals, and the period locked. • Where it usually breaks: the period is closed with reconciliation differences carried forward as unexplained, and they accumulate for months. | • Prohibit closing with unexplained reconciliation differences above a stated threshold, since carried forward differences compound and eventually cannot be resolved. • Require every manual journal above a threshold to be reviewed and approved by someone other than the preparer. • Lock the period after approval and require a documented approval to reopen it. • Require accruals to be supported by evidence such as delivery or progress records, not estimated to fit an expected result. • Track close timeliness and the number of post close adjustments, as these measure the quality of the process.
752 | Finance | Approve management accounts, cash-flow reporting and executive financial pack | Chief Financial Officer (CFO) | Trigger: When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. Action: The Chief Financial Officer (CFO) completes “Approve management accounts, cash-flow reporting and executive financial pack” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: approved financial statements, management reporting, tax filing, audit response or investigation action. Control/Handoff: No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. | The Chief Financial Officer (CFO) completes “Approve management accounts, cash-flow reporting and executive financial pack” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | approved financial statements, management reporting, tax filing, audit response or investigation action. | No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the management accounts and the financial pack that the executive uses to run the business. • Starts when: after the close is approved, at the reporting deadline. • How it runs: (1) he reviews the management accounts against the close. (2) He reviews the cash flow reporting and the forecast. (3) He reviews the commentary for accuracy and balance. (4) He approves the pack for issue. (5) He presents it and records the decisions taken. • Proof it happened: an approved management accounts and executive pack with cash flow reporting, issued with commentary. • Where it usually breaks: the commentary explains the numbers without stating what needs to be decided, so the pack informs but changes nothing. | • Require the commentary to name the decisions needed, not only to explain the variances, so the pack drives action. • Require the pack to reconcile to the closed ledger, since a pack that cannot be tied back destroys trust in every figure. • Fix the format and the issue date, as an unpredictable pack gets read late or not at all. • Include the cash and liquidity position at the front, because it is the constraint that shapes every other decision. • Keep the executive pack short with detail in appendices, so the discussion stays on the issues.
753 | Finance | Approve VAT and corporate-tax returns, positions and payments | Chief Financial Officer (CFO) | Trigger: When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. Action: The Chief Financial Officer (CFO) completes “Approve VAT and corporate-tax returns, positions and payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: approved financial statements, management reporting, tax filing, audit response or investigation action. Control/Handoff: No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. | The Chief Financial Officer (CFO) completes “Approve VAT and corporate-tax returns, positions and payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | approved financial statements, management reporting, tax filing, audit response or investigation action. | No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the tax returns and the positions taken in them, and makes sure the tax is paid on time. • Starts when: at each VAT filing period and at the corporate tax filing cycle. • How it runs: (1) he reviews the return against the underlying records. (2) He reviews the treatment of any uncertain or unusual items. (3) He obtains external advice on material judgement positions. (4) He approves the return and the payment. (5) He ensures filing and payment happen within the deadline and retains the evidence. • Proof it happened: approved and filed returns with the supporting reconciliation, advice on judgement positions and payment evidence. • Where it usually breaks: a filing deadline is missed or a return is filed on incomplete data, and the penalty is far larger than the tax involved. | • Diarise every filing and payment deadline with an owner and an advance warning, since penalties for lateness are avoidable and expensive. • Require the return to be reconciled to the ledger before approval, not filed on extracted data. • Require external advice on material judgement positions and retain it, because a documented position defends against penalty in a challenge. • Check input tax recovery requirements on supplier invoices, as defective tax invoices lose recovery permanently. • Keep a record of positions taken, so filings are consistent between periods.
754 | Finance | Oversee external audit, statutory reporting and regulator or bank submissions | Chief Financial Officer (CFO) | Trigger: When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. Action: The Chief Financial Officer (CFO) completes “Oversee external audit, statutory reporting and regulator or bank submissions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: approved financial statements, management reporting, tax filing, audit response or investigation action. Control/Handoff: No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. | The Chief Financial Officer (CFO) completes “Oversee external audit, statutory reporting and regulator or bank submissions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | approved financial statements, management reporting, tax filing, audit response or investigation action. | No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he manages the external audit and the statutory and bank reporting the company is obliged to produce. • Starts when: the audit cycle begins, and when a statutory or bank submission falls due. • How it runs: (1) he agrees the audit timetable and the information requirements. (2) He ensures the schedules and evidence are prepared. (3) He resolves audit queries and agrees any adjustments. (4) He approves the statutory accounts for signature. (5) He submits the required regulator and bank reporting within the deadlines. • Proof it happened: completed audit with agreed adjustments, signed statutory accounts and evidence of regulator and bank submissions. • Where it usually breaks: audit preparation starts when the auditor arrives, so the audit runs long, costs more and produces avoidable findings. | • Require audit preparation to begin before fieldwork with the schedules agreed in advance, since unprepared audits produce findings that are really preparation failures. • Track bank and covenant reporting deadlines separately, as these carry immediate consequences if missed. • Require management responses to audit findings to change the process, not just answer the point. • Retain the audit evidence file, so next year's audit does not rebuild the same work. • Report repeat audit findings to the CEO, because a repeat finding is a governance issue rather than a technical one.
755 | Finance | Direct response to suspected fraud, financial-control breach and material misstatement | Chief Financial Officer (CFO) | Trigger: When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. Action: The Chief Financial Officer (CFO) completes “Direct response to suspected fraud, financial-control breach and material misstatement” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: approved financial statements, management reporting, tax filing, audit response or investigation action. Control/Handoff: No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When the monthly/year-end close, tax deadline, audit request or material control concern becomes due. | The Chief Financial Officer (CFO) completes “Direct response to suspected fraud, financial-control breach and material misstatement” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | approved financial statements, management reporting, tax filing, audit response or investigation action. | No report or return is issued with unresolved material misstatement; legal, tax, fraud and regulator matters escalate to the CFO and CEO. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: when fraud, a control breach or a material error is suspected, he leads the response. • Starts when: a suspicion is raised, a control breach is detected, or a material misstatement is identified. • How it runs: (1) he secures the records and the system evidence before anything is altered. (2) He restricts the access of the people involved. (3) He informs the CEO and takes CLO advice. (4) He arranges an independent investigation. (5) He implements the control changes and reports the outcome. • Proof it happened: a documented response with evidence secured, access restricted, legal advice taken and the control changes implemented. • Where it usually breaks: the person suspected is questioned before the evidence is secured, and the records are altered or deleted. | • Require evidence and system access to be secured before anyone is approached, since early confrontation destroys the evidence. • Require immediate CEO notification and CLO involvement, and prohibit informal internal resolution of suspected fraud. • Provide a confidential reporting route, as the people who notice are usually junior to those involved. • Require insurer notification where cover may apply, because late notice can void the claim. • Require the control weakness that allowed it to be fixed and verified, not just the individual dealt with.
756 | Finance | Approve supplier, subcontractor and employee-expense payments within authority | Chief Financial Officer (CFO) | Trigger: When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. Action: The Chief Financial Officer (CFO) completes “Approve supplier, subcontractor and employee-expense payments within authority” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an authorised payment, payroll release, final-account decision, retention release or continuity control. Control/Handoff: The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. | The Chief Financial Officer (CFO) completes “Approve supplier, subcontractor and employee-expense payments within authority” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an authorised payment, payroll release, final-account decision, retention release or continuity control. | The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves payments to suppliers, subcontractors and staff expenses up to his authority. • Starts when: a verified payment package is submitted for approval. • How it runs: (1) he checks the payment is supported by an approved commitment and verified receipt. (2) He checks the deductions, advances and retentions are applied. (3) He confirms the beneficiary details match the verified master record. (4) He checks the value is within his authority and cash is available. (5) He approves for release. • Proof it happened: approved payments with the supporting three way match, deduction calculations and verified beneficiary details. • Where it usually breaks: payment is approved on the invoice and approval alone, without evidence that the goods or work were actually received. | • Require evidence of receipt or certified progress for every payment, since approval and invoice alone pays for things never received. • Require beneficiary details to come from the verified master record, never from the invoice or the payment request. • Require the approver to be independent of the person who raised the commitment and the person who recorded the receipt. • Require advance recovery and retention deduction to be applied as a system rule rather than manually. • Set expense payment rules with limits and receipt requirements, as staff expenses are a common small value leakage.
757 | Finance | Approve payroll, WPS, end-of-service and employee-settlement payments | Chief Financial Officer (CFO) | Trigger: When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. Action: The Chief Financial Officer (CFO) completes “Approve payroll, WPS, end-of-service and employee-settlement payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an authorised payment, payroll release, final-account decision, retention release or continuity control. Control/Handoff: The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. | The Chief Financial Officer (CFO) completes “Approve payroll, WPS, end-of-service and employee-settlement payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an authorised payment, payroll release, final-account decision, retention release or continuity control. | The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves payroll and the statutory salary transfer, plus end of service and settlement payments to leavers. • Starts when: at the monthly payroll cycle, and when a settlement is due on a leaver. • How it runs: (1) he reviews the payroll summary against the approved headcount and the previous period. (2) He checks the changes: joiners, leavers, variations and deductions. (3) He verifies the settlement calculations against entitlement and law. (4) He approves the payroll and the transfer file. (5) He confirms the statutory wage transfer was completed within the deadline. • Proof it happened: an approved payroll with the change reconciliation, verified settlement calculations and evidence of the statutory transfer. • Where it usually breaks: payroll is approved on the total value alone, so a duplicated or fictitious employee is never noticed. | • Require period on period reconciliation of payroll by employee count and change reason, since approving a total figure cannot detect a fictitious or duplicated employee. • Require the payroll bank file to be verified against the approved payroll before release, as the file is where amounts can be altered. • Require HR and Finance to be separate: whoever maintains employee records must not also release the payment. • Diarise the statutory wage transfer deadline, because late salary payment carries regulatory consequences beyond the employee relationship. • Require independent recalculation of end of service settlements above a threshold, since these are complex and frequently wrong.
758 | Finance | Approve owner-related, exceptional and restricted payments under delegated authority | Chief Financial Officer (CFO) | Trigger: When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. Action: The Chief Financial Officer (CFO) completes “Approve owner-related, exceptional and restricted payments under delegated authority” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an authorised payment, payroll release, final-account decision, retention release or continuity control. Control/Handoff: The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. | The Chief Financial Officer (CFO) completes “Approve owner-related, exceptional and restricted payments under delegated authority” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an authorised payment, payroll release, final-account decision, retention release or continuity control. | The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the sensitive payments, meaning those involving owners, exceptional items or restricted categories. • Starts when: a payment falls into an owner related, exceptional or restricted category. • How it runs: (1) he confirms the payment's purpose and its basis. (2) He confirms it is within the authority granted for that category. (3) He obtains the specific approval required, including ownership approval where applicable. (4) He confirms the accounting and tax treatment. (5) He records the payment and its authorisation separately for transparency. • Proof it happened: approved sensitive payments with the specific authorisation, the stated basis and the recorded treatment. • Where it usually breaks: owner related payments are processed informally on instruction, with no record of the basis or the approval. | • Require every owner related payment to have a written basis and a specific approval, since informal processing on instruction is indefensible in audit and tax review. • Maintain a separate related party register with the running totals, so the aggregate position is visible. • Require CLO and tax review of the treatment, because related party payments carry both tax and legal exposure. • Define the restricted categories explicitly, so it is clear when this route applies rather than left to judgement. • Report related party transactions to ownership and the auditor, as concealment here is the most damaging governance failure.
759 | Finance | Approve final account, retention release and project financial closeout | Chief Financial Officer (CFO) | Trigger: When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. Action: The Chief Financial Officer (CFO) completes “Approve final account, retention release and project financial closeout” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an authorised payment, payroll release, final-account decision, retention release or continuity control. Control/Handoff: The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. | The Chief Financial Officer (CFO) completes “Approve final account, retention release and project financial closeout” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an authorised payment, payroll release, final-account decision, retention release or continuity control. | The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the final settlement of a project, the release of retention and the closing of its books. • Starts when: the project reaches final account and the retention becomes due. • How it runs: (1) he reviews the final account against the contract and the variations. (2) He confirms all costs are captured and accrued. (3) He confirms the retention release conditions are met. (4) He reviews the final margin against forecast. (5) He approves the closeout and closes the project in the system. • Proof it happened: an approved final account and project closeout with the retention position resolved and the final margin recorded. • Where it usually breaks: projects are closed while supplier retentions and claims remain open, so the final margin is wrong and later costs land in the wrong period. | • Require confirmation that no supplier retentions, claims or warranty obligations remain open before closing, since late costs after closure distort both the project and the current period. • Require the final margin to be compared against the forecast at completion, so the accuracy of project reporting is tested. • Diarise the client retention release date with an owner, because unclaimed retention is money simply lost. • Require closeout lessons to be recorded, particularly where the outcome differed materially from the tender. • Keep the project record archived, as final account and variation records are the first evidence needed in a later dispute.
760 | Finance | Approve Finance continuity, access-control, backup and recovery arrangements | Chief Financial Officer (CFO) | Trigger: When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. Action: The Chief Financial Officer (CFO) completes “Approve Finance continuity, access-control, backup and recovery arrangements” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: an authorised payment, payroll release, final-account decision, retention release or continuity control. Control/Handoff: The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. Continuity/Escalation: A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. Timing: To be confirmed. | When an approved payment batch, payroll file, exceptional transaction or financial-closeout package reaches final authority. | The Chief Financial Officer (CFO) completes “Approve Finance continuity, access-control, backup and recovery arrangements” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | an authorised payment, payroll release, final-account decision, retention release or continuity control. | The CFO approves only complete evidence within delegated authority; preparer, reviewer and bank authoriser remain appropriately segregated. | A CEO-approved finance delegate may coordinate routine matters, but banking authority, tax positions, material payments, funding, financial statements and reserved decisions remain with the CFO or escalate to the CEO. | To be confirmed. | • In plain words: he makes sure finance keeps functioning if people are absent or systems fail, and that the records are protected. • Starts when: at the continuity review, on staff changes, and before planned absences. • How it runs: (1) he defines the system and banking access per role and reviews it. (2) He names deputies for the critical roles including payment approval. (3) He documents the delegation arrangements with limits and end dates. (4) He confirms the backup and record retention arrangements. (5) He tests that the arrangements actually work. • Proof it happened: reviewed access rights, named deputies with written delegations and confirmed and tested backup arrangements. • Where it usually breaks: a deputy is named for payment approval but is not on the bank mandate, so payments stop the first day the CFO is away. | • Require deputies for payment approval to be on the bank mandate before the absence, since a delegation the bank does not recognise is worthless. • Set delegation end dates and withdraw the access on return, otherwise permissions accumulate and segregation erodes. • Test the backup by attempting a restore, because an untested backup is an assumption rather than a control. • Review access on every leaver and role change, as retained leaver access to financial systems is a serious exposure. • Document where banking tokens and credentials are held and who controls them, since this is where continuity actually fails.
761 | Finance | Plan the Finance operating calendar, cutoffs and recurring control timetable | Senior Accountant (Lead) | Trigger: When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. Action: The Senior Accountant (Lead) completes “Plan the Finance operating calendar, cutoffs and recurring control timetable” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled Finance work plan, verified master data, posting review and closed exception record. Control/Handoff: The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. | The Senior Accountant (Lead) completes “Plan the Finance operating calendar, cutoffs and recurring control timetable” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled Finance work plan, verified master data, posting review and closed exception record. | The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she sets the finance timetable for the month, the cut off dates and when each control must be done. • Starts when: at the start of the period, and when the reporting requirements change. • How it runs: (1) she lists the recurring finance tasks and controls. (2) She sets the cut off dates for receipts, invoices and payroll inputs. (3) She sets the date each reconciliation and review is due. (4) She issues the calendar to the team and the departments who feed it. (5) She tracks completion against it. • Proof it happened: a published finance calendar with cut offs and control due dates, tracked against actual completion. • Where it usually breaks: cut offs are published inside finance only, so departments submit late and the close slips every month. | • Publish the cut off dates to every department that submits information, with their own deadlines named, since a calendar known only to finance slips every month. • State what happens to late submissions, such as moving to the next period, or the cut off is advisory. • Include every recurring control on the calendar with a named owner, so nothing depends on memory. • Track completion against the calendar rather than assuming, as missed controls are only found at audit. • Work the calendar backwards from the reporting deadline so the review time is real.
762 | Finance | Control customer, supplier, project, bank and cost-code master-data changes | Senior Accountant (Lead) | Trigger: When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. Action: The Senior Accountant (Lead) completes “Control customer, supplier, project, bank and cost-code master-data changes” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled Finance work plan, verified master data, posting review and closed exception record. Control/Handoff: The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. | The Senior Accountant (Lead) completes “Control customer, supplier, project, bank and cost-code master-data changes” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled Finance work plan, verified master data, posting review and closed exception record. | The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she controls changes to the master records for customers, suppliers, projects, banks and cost codes. • Starts when: a master data change is requested. • How it runs: (1) she receives the change request with supporting documents. (2) She checks for an existing record and validates the data. (3) For bank details she applies the independent verification process. (4) She obtains the second approval. (5) She makes the change and logs it. • Proof it happened: controlled master data changes with supporting documents, verification evidence and a full change log. • Where it usually breaks: cost codes and project codes are created on request without control, so reporting structures fragment and comparability is lost. | • Restrict cost code and project code creation to named people, since uncontrolled code creation fragments reporting and makes period comparison impossible. • Require independent callback verification for every bank detail change, to a previously held number and never to the contact details on the request. • Require dual approval, with the approver different from the person making the change. • Log every change with the requester, approver, before and after values, and review the log monthly. • Prohibit the person who can change master data from also releasing payments.
763 | Finance | Review daily FirstBit posting quality, document completeness and exception status | Senior Accountant (Lead) | Trigger: When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. Action: The Senior Accountant (Lead) completes “Review daily FirstBit posting quality, document completeness and exception status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled Finance work plan, verified master data, posting review and closed exception record. Control/Handoff: The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. | The Senior Accountant (Lead) completes “Review daily FirstBit posting quality, document completeness and exception status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled Finance work plan, verified master data, posting review and closed exception record. | The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks each day that the entries going into the system are correct and properly supported. • Starts when: daily, after the day's postings. • How it runs: (1) she reviews the day's postings for coding and classification errors. (2) She checks each entry has its supporting document attached. (3) She reviews the exception and error reports. (4) She returns incorrect entries for correction. (5) She records the review and the corrections. • Proof it happened: a daily posting quality review with coding checked, documents verified and corrections recorded. • Where it usually breaks: the review happens at month end instead of daily, so hundreds of errors have to be corrected at once under close pressure. | • Require the posting review daily rather than at month end, since errors corrected weeks later are corrected under close pressure and often wrongly. • Require the supporting document to be attached at posting, not promised, because unsupported entries cannot be verified afterwards. • Return incorrect entries to the preparer rather than correcting them, so the error is learned from. • Track error rates by preparer, as this identifies where training is needed. • Review suspense and unallocated accounts daily, since these are where unresolved entries hide.
764 | Finance | Maintain the Finance issue, correction and overdue-action register | Senior Accountant (Lead) | Trigger: When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. Action: The Senior Accountant (Lead) completes “Maintain the Finance issue, correction and overdue-action register” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled Finance work plan, verified master data, posting review and closed exception record. Control/Handoff: The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. | The Senior Accountant (Lead) completes “Maintain the Finance issue, correction and overdue-action register” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled Finance work plan, verified master data, posting review and closed exception record. | The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she keeps the list of finance problems, corrections needed and what is overdue. • Starts when: an issue is identified, and continuously until closed. • How it runs: (1) she records each issue with its owner and due date. (2) She records the correction required. (3) She tracks progress and chases overdue items. (4) She escalates items that remain open. (5) She closes items with evidence. • Proof it happened: an issue and correction register with owners, due dates, escalations and closure evidence. • Where it usually breaks: the register grows without closure, so it becomes too long to use and is abandoned. | • Require closure with evidence rather than a status change, since items marked resolved without evidence are how registers lose credibility and get abandoned. • Show ageing on every item, because an issue open for three months needs escalation rather than another reminder. • Escalate to the CFO on a defined timescale. • Require a named individual owner, as departmental ownership means nobody acts. • Report recurring issue types, since these indicate a process fault rather than isolated errors.
765 | Finance | Allocate accounting work and verify completion of daily Finance controls | Senior Accountant (Lead) | Trigger: When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. Action: The Senior Accountant (Lead) completes “Allocate accounting work and verify completion of daily Finance controls” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled Finance work plan, verified master data, posting review and closed exception record. Control/Handoff: The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily Finance cycle, master-data request, posting review or control-calendar activity becomes due. | The Senior Accountant (Lead) completes “Allocate accounting work and verify completion of daily Finance controls” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled Finance work plan, verified master data, posting review and closed exception record. | The Senior Accountant reviews Accountant work and restricts unauthorised master-data or backdated-period changes; material issues escalate to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she allocates the accounting work and checks the daily controls were actually done. • Starts when: daily, and at the start of each period. • How it runs: (1) she allocates the tasks across the team. (2) She confirms who owns each daily control. (3) She checks each control was performed, not just intended. (4) She follows up incomplete controls the same day. (5) She records the completion. • Proof it happened: allocated work with daily control completion verified and recorded, and gaps followed up. • Where it usually breaks: controls are assumed to have been done because nobody reported a problem, so a missed control is only found at audit. | • Require positive confirmation that each daily control was performed, since assuming completion because nothing was reported is how missed controls reach the auditor first. • Name a deputy for every daily control, so absence does not create a gap. • Record the completion evidence rather than a tick, particularly for reconciliations and bank checks. • Rotate control duties periodically, as this is both a development and a fraud prevention measure. • Report incomplete controls to the CFO rather than carrying them forward silently.
766 | Finance | Verify the project financial-activation file and contractual billing terms | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Verify the project financial-activation file and contractual billing terms” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Verify the project financial-activation file and contractual billing terms” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: before a project can be billed she checks the contract terms and sets up the billing basis correctly. • Starts when: a project is awarded and activated financially. • How it runs: (1) she obtains the contract and its payment terms. (2) She records the billing basis, milestones and rates. (3) She records the retention, advance and tax treatment. (4) She sets up the project in the system with these terms. (5) She confirms the activation file is complete before billing. • Proof it happened: a completed project financial activation file with billing terms, retention, advance and tax treatment recorded. • Where it usually breaks: billing starts from an assumed basis because the contract is not yet available, so the first invoices are wrong and have to be reissued. | • Prohibit billing before the activation file is complete, since invoices issued on an assumed basis are rejected and restart the whole payment cycle. • Extract the payment terms from the executed contract rather than the tender or the award letter. • Record the retention percentage, advance recovery basis and tax treatment at activation, as these are routinely missed on the first invoices. • Record the client's invoicing requirements and submission route, because non compliant invoices are returned unpaid. • Require the project manager to confirm the activation details.
767 | Finance | Review proforma and advance invoices before controlled issue | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Review proforma and advance invoices before controlled issue” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Review proforma and advance invoices before controlled issue” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks proforma and advance invoices before they go to the client. • Starts when: a proforma or advance invoice is required. • How it runs: (1) she confirms the contractual entitlement to the advance. (2) She confirms the amount and the recovery basis. (3) She checks the tax treatment for the advance. (4) She checks the invoice format meets the client's requirements. (5) She approves it for controlled issue. • Proof it happened: reviewed and approved proforma and advance invoices with entitlement, recovery basis and tax treatment confirmed. • Where it usually breaks: the advance is invoiced without recording the recovery schedule, so it is never recovered against progress and sits as an open balance. | • Record the advance recovery schedule at the point of invoicing, since an advance with no recovery mechanism sits unrecovered and distorts both the receivable and the project position. • Confirm the tax treatment of advances specifically, as this differs from progress billing and is commonly wrong. • Confirm the contractual entitlement before issue, because an advance invoiced without entitlement damages credibility with the client. • Check the client's format and submission requirements, as these determine whether it will be processed at all. • Track the advance balance as a separate line rather than netting it into the receivable.
768 | Finance | Prepare progress billing from certified quantities, milestones and contract terms | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Prepare progress billing from certified quantities, milestones and contract terms” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Prepare progress billing from certified quantities, milestones and contract terms” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the progress invoices from what has actually been certified as complete. • Starts when: a progress certificate or milestone is achieved and billing is due. • How it runs: (1) she obtains the certified quantities or milestone confirmation. (2) She applies the contract rates. (3) She applies the retention and advance recovery. (4) She applies the tax treatment. (5) She prepares the invoice with the supporting documents. • Proof it happened: a progress invoice prepared from certified quantities with rates, retention, recovery and tax applied, with supporting documents. • Where it usually breaks: invoices are raised from the project team's claimed progress rather than the client's certified position, so they are rejected and the cash is delayed. | • Bill from the certified position rather than the claimed position, since an invoice ahead of certification is rejected and delays the whole payment cycle. • Attach the supporting documents the contract requires, because incomplete submissions are returned unpaid without comment. • Apply retention and advance recovery as a system rule, as manual application is where these are forgotten. • Track the difference between claimed and certified, since a persistent gap is a commercial issue for the project team. • Submit within the contractual billing window, as late submission moves the payment a full cycle.
769 | Finance | Review tax-invoice and credit-note basis before approval or issue | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Review tax-invoice and credit-note basis before approval or issue” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Review tax-invoice and credit-note basis before approval or issue” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks the basis for tax invoices and credit notes before they are issued or approved. • Starts when: a tax invoice or credit note is prepared. • How it runs: (1) she confirms the transaction basis and the entitlement. (2) She checks the tax treatment and rate. (3) She checks the invoice contains every legally required field. (4) For credit notes she confirms the approval and the reason. (5) She approves for issue and records it. • Proof it happened: reviewed tax invoices and credit notes with the basis, tax treatment and legal format confirmed and approved. • Where it usually breaks: credit notes are issued to fix administrative errors without approval, which is an easy route to concealing revenue adjustments. | • Require approval with a stated reason for every credit note, since unapproved credit notes are the simplest way to conceal a revenue adjustment or a write off. • Check every legally required field on tax invoices, as a defective tax invoice loses the client's recovery and gets returned. • Record credit notes against the original invoice, so the net position is traceable. • Report credit note volume and reasons, because a high volume indicates an upstream billing problem. • Prohibit the person raising an invoice from also approving its credit note.
770 | Finance | Maintain customer receivables, ageing and overdue-invoice status | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Maintain customer receivables, ageing and overdue-invoice status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Maintain customer receivables, ageing and overdue-invoice status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she keeps track of what customers owe, how old the debt is and what is overdue. • Starts when: invoices are issued, and continuously as they age. • How it runs: (1) she maintains the receivables ledger. (2) She produces the ageing analysis. (3) She identifies the overdue invoices and their status. (4) She records the reason each overdue invoice is unpaid. (5) She reports the position for collection action. • Proof it happened: a maintained receivables ledger with ageing analysis and a recorded reason per overdue invoice. • Where it usually breaks: ageing is reported without reasons, so management sees a number and has no idea which debts are actually collectable. | • Record the reason each invoice is unpaid, since an ageing report without reasons tells management nothing about collectability or what action to take. • Separate genuinely disputed invoices from those merely unpaid, as these need completely different action. • Age from the contractual due date rather than the invoice date. • Report the largest overdue items individually rather than only in bands. • Reconcile the ledger to the client's own statement periodically, as unnoticed rejections sit as receivables for months.
771 | Finance | Coordinate client collection follow-up and document payment commitments | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Coordinate client collection follow-up and document payment commitments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Coordinate client collection follow-up and document payment commitments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she chases clients for payment and records what they promise. • Starts when: an invoice becomes due or overdue. • How it runs: (1) she follows up per the collection schedule. (2) She records each contact and the response. (3) She records payment commitments with dates. (4) She escalates where commitments are not met. (5) She involves the project and commercial teams where the issue is contractual. • Proof it happened: a collection log with contacts, responses, recorded payment commitments and escalations. • Where it usually breaks: collection is done by phone with nothing recorded, so a broken promise cannot be evidenced and escalation has no basis. | • Record every payment commitment in writing with the promised date, since a verbal promise that is broken leaves nothing to escalate with. • Escalate on a defined timescale rather than continuing to chase the same contact indefinitely. • Involve the commercial team where the cause is contractual, because finance cannot resolve a certification dispute. • Send a written statement of account periodically, as this surfaces invoices the client never received. • Track the pattern of client payment behaviour, since this is what the cash forecast should be built on.
772 | Finance | Track retention balances, due dates, release conditions and recovery actions | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Track retention balances, due dates, release conditions and recovery actions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Track retention balances, due dates, release conditions and recovery actions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she tracks the retention money held by clients and makes sure it is claimed when due. • Starts when: retention is deducted, and continuously until released. • How it runs: (1) she records the retention held per project and certificate. (2) She records the release conditions and dates. (3) She monitors the approaching release dates. (4) She initiates the claim when conditions are met. (5) She follows up until received. • Proof it happened: a retention register with balances, release conditions and dates, and recovery actions tracked. • Where it usually breaks: retention is never claimed because nobody owns the release date, so the money is quietly abandoned. | • Assign a named owner to every retention release date and diarise it, since unclaimed retention is the most commonly abandoned money in construction. • Record the release conditions, not just the date, because most retention releases depend on a certificate or a defects period ending. • Report the total retention held with ageing to the CFO, as this is a significant asset that receives no attention. • Initiate the claim as soon as conditions are met rather than waiting for the client to offer. • Track the second release separately, as this is the one that is most often lost.
773 | Finance | Reconcile customer accounts, disputed balances and unapplied receipts | Senior Accountant (Lead) | Trigger: When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. Action: The Senior Accountant (Lead) completes “Reconcile customer accounts, disputed balances and unapplied receipts” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. Control/Handoff: Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a project activation, billing milestone, certified quantity, receipt, ageing review or retention date occurs. | The Senior Accountant (Lead) completes “Reconcile customer accounts, disputed balances and unapplied receipts” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice/billing record, receivable schedule, collection action, retention status or customer reconciliation. | Billing links to contract terms and certification; credit notes, write-offs and disputed balances require documented approval before adjustment. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she reconciles customer accounts and sorts out disputed balances and unmatched receipts. • Starts when: at the reconciliation cycle, and when a difference arises. • How it runs: (1) she reconciles the account to the client's statement where available. (2) She identifies unapplied receipts and matches them. (3) She identifies disputed items and their basis. (4) She resolves differences with the client and internally. (5) She records the reconciliation and the remaining differences. • Proof it happened: reconciled customer accounts with receipts applied, disputes identified and remaining differences explained. • Where it usually breaks: receipts are applied to the oldest invoice by default, so a disputed invoice looks paid and the real dispute stays hidden. | • Prohibit default allocation of receipts to the oldest invoice, since this makes a disputed invoice look paid and hides the real dispute from everyone. • Require the client's remittance advice to drive allocation, and chase it where absent. • Clear unapplied receipts within a stated period, as these distort both the ageing and the cash position. • Reconcile to the client's statement rather than only internally, because this is what reveals rejected invoices. • Escalate unresolved differences rather than carrying them forward indefinitely.
774 | Finance | Control the supplier and subcontractor invoice register and period cutoff | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Control the supplier and subcontractor invoice register and period cutoff” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Control the supplier and subcontractor invoice register and period cutoff” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she controls the register of supplier invoices and makes sure they land in the right period. • Starts when: supplier invoices are received, and at each period cut off. • How it runs: (1) she registers each invoice on receipt with the date. (2) She routes it for verification. (3) She tracks its status through to payment. (4) At cut off she ensures invoices for the period are captured or accrued. (5) She reports unregistered and pending invoices. • Proof it happened: a supplier invoice register with receipt dates, status tracking and period cut off applied. • Where it usually breaks: invoices sit in departments before reaching finance, so costs land in the wrong period and the project position is understated. | • Require invoices to be registered centrally on receipt regardless of who received them, since invoices held in departments understate cost and distort every project report. • Record the date received separately from the invoice date, as this is what determines the accrual and the payment period. • Require an accrual for goods and work received but not invoiced at cut off. • Report invoices pending verification with ageing, because these are what cause both late payment and misstated periods. • Reconcile the register to the ledger at each close.
775 | Finance | Review the PO, GRN, invoice and approval three-way match | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Review the PO, GRN, invoice and approval three-way match” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Review the PO, GRN, invoice and approval three-way match” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks the invoice, the order, the receipt record and the approval all agree before payment. • Starts when: a supplier invoice is verified for payment. • How it runs: (1) she matches the invoice to the purchase order on price and terms. (2) She matches it to the goods received note on quantity. (3) She confirms the required approvals are present. (4) She checks the tax treatment and invoice validity. (5) She records the match or the exception. • Proof it happened: a documented three way match between order, receipt and invoice with approval evidence. • Where it usually breaks: payment goes through on the order and the approval alone, so goods that were never received are paid for. | • Require the goods received note as a mandatory element of the match, since paying on order and invoice alone pays for goods that never arrived. • Require quantity received rather than quantity ordered to drive the payable, particularly on partial deliveries. • Set tolerance limits for price and quantity differences and require approval above them. • Check advance recovery and retention on every invoice, as these are routinely omitted. • Report unmatched invoices with ageing, because these represent either missing receipts or invalid claims.
776 | Finance | Review subcontractor certification, retention and advance-recovery calculations | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Review subcontractor certification, retention and advance-recovery calculations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Review subcontractor certification, retention and advance-recovery calculations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks subcontractor payment certificates, retention and advance recovery calculations. • Starts when: a subcontractor certificate or application is submitted for payment. • How it runs: (1) she checks the certified quantities against the project team's certification. (2) She checks the rates against the subcontract. (3) She recalculates the retention and advance recovery. (4) She checks the cumulative position against previous certificates. (5) She records the verification. • Proof it happened: a verified subcontractor certificate with certified quantities, contract rates and recalculated deductions. • Where it usually breaks: each certificate is checked in isolation, so cumulative overpayment builds up unnoticed across the project. | • Check the cumulative position on every certificate, since overpayment builds up across certificates and is invisible when each is checked alone. • Recalculate retention and advance recovery independently rather than accepting the subcontractor's figures. • Require the project team's certification as the basis, not the subcontractor's application. • Check for back charges and pending defects before releasing payment. • Track the total paid against the subcontract value including variations, so the remaining commitment is always visible.
777 | Finance | Validate supplier bank, tax and master-data changes before payment | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Validate supplier bank, tax and master-data changes before payment” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Validate supplier bank, tax and master-data changes before payment” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she verifies changes to supplier bank and tax details before any payment is made to them. • Starts when: a supplier bank or tax detail change is requested, or a first payment is due. • How it runs: (1) she receives the change request. (2) She verifies by independent callback to a previously held number. (3) She checks the supporting documents. (4) She obtains the second approval. (5) She makes the change, logs it and confirms before payment. • Proof it happened: verified bank and tax detail changes with independent callback evidence, documents and dual approval logged. • Where it usually breaks: verification is done by replying to the same email chain, which is exactly what the fraudster controls. | • Verify by callback to a number already held in the master record, and state explicitly that the contact details in the request are never used, since replying to the same chain verifies nothing. • Require dual approval with the second approver outside the team that processes payments. • Require a short hold period before the first payment to changed details, so an anomaly can surface. • Log every change and review the log monthly against payments made. • Brief the team that urgency in a bank change request is itself a warning sign.
778 | Finance | Review expense, petty-cash and employee-reimbursement packages | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Review expense, petty-cash and employee-reimbursement packages” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Review expense, petty-cash and employee-reimbursement packages” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks expense claims, petty cash and staff reimbursements before payment. • Starts when: an expense or reimbursement claim is submitted. • How it runs: (1) she checks the claim is on the approved form with the required approval. (2) She checks each item has a valid receipt. (3) She checks the expense is within policy limits. (4) She checks the coding and project allocation. (5) She approves or returns the claim. • Proof it happened: reviewed expense and petty cash packages with receipts, policy compliance and approvals verified. • Where it usually breaks: claims are paid on approval alone without checking receipts, so unsupported and duplicate claims pass through. | • Require a valid receipt for every item and reject unsupported claims, since approval alone does not evidence that the expense was incurred. • Check for duplicate submission, as the same receipt being claimed twice is a common small value leakage. • Set policy limits per category and apply them consistently rather than case by case. • Require the claimant's manager to approve, and prohibit self approval at any level. • Reconcile petty cash physically at a set frequency, with variances investigated.
779 | Finance | Prepare the payment proposal by due date, priority, cash availability and approval | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Prepare the payment proposal by due date, priority, cash availability and approval” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Prepare the payment proposal by due date, priority, cash availability and approval” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the payment run, ordering it by what is due, what is urgent and what cash is available. • Starts when: at the payment run cycle. • How it runs: (1) she lists the invoices due and overdue. (2) She applies the priority rules. (3) She checks the cash available against the total. (4) She prepares the payment proposal with the deferrals identified. (5) She submits it for approval. • Proof it happened: a payment proposal ordered by due date and priority, matched against available cash, with deferrals identified. • Where it usually breaks: the proposal is built from whoever has chased hardest, so statutory and critical payments are deferred behind noisy suppliers. | • Build the proposal by the stated priority rules rather than by who has chased hardest, since supplier pressure otherwise pushes statutory and critical payments down the list. • Protect statutory and payroll payments absolutely in the rules. • Identify the deferrals explicitly so they are a decision rather than an omission. • Check the cash available against confirmed collections, not expected ones. • Report the deferred total and its ageing, as this is the real measure of payment discipline.
780 | Finance | Review payment vouchers, bank-upload files and authorisation evidence | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Review payment vouchers, bank-upload files and authorisation evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Review payment vouchers, bank-upload files and authorisation evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks the payment vouchers and the bank upload file before the money leaves. • Starts when: the payment proposal is approved and payment is being executed. • How it runs: (1) she checks each voucher against the approved proposal. (2) She checks the beneficiary details against the verified master. (3) She checks the bank upload file totals and beneficiary count. (4) She confirms the authorisation evidence is complete. (5) She releases or submits for release. • Proof it happened: verified payment vouchers and bank upload file checked against the approved proposal with authorisation evidence. • Where it usually breaks: the upload file is edited after approval, so amounts or beneficiaries differ from what was authorised. | • Verify the upload file against the approved proposal on total, count and beneficiaries immediately before release, since post approval editing of the file is the classic payment fraud. • Require the person releasing the payment to be different from the person who prepared the file. • Check beneficiary details against the verified master record, never against the invoice. • Retain the approved proposal and the released file, so any difference can be traced. • Prohibit manual additions to the file after approval, with no exception.
781 | Finance | Reconcile supplier statements, disputed invoices and debit balances | Senior Accountant (Lead) | Trigger: When a supplier, subcontractor, expense or payment package is received or reaches due date. Action: The Senior Accountant (Lead) completes “Reconcile supplier statements, disputed invoices and debit balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. Control/Handoff: No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a supplier, subcontractor, expense or payment package is received or reaches due date. | The Senior Accountant (Lead) completes “Reconcile supplier statements, disputed invoices and debit balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a verified invoice, matched payment package, payment proposal, voucher or supplier reconciliation. | No payment proceeds without PO/contract, GRN/certification, tax document, budget and approval checks; bank-detail changes receive independent verification. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she reconciles supplier statements and resolves disputed invoices and unexplained balances. • Starts when: at the reconciliation cycle, or when a supplier disputes a balance. • How it runs: (1) she obtains the supplier statement. (2) She reconciles it to the ledger. (3) She identifies missing invoices, unrecorded credits and disputed items. (4) She resolves the differences. (5) She records the reconciliation and remaining differences. • Proof it happened: reconciled supplier statements with differences identified, resolved and the remainder explained. • Where it usually breaks: statements are never reconciled, so missing invoices surface as unexpected cost and credit notes due are never claimed. | • Reconcile statements for all significant suppliers at a set frequency, since unreconciled accounts hide both unrecorded costs and credit notes the company is owed. • Investigate debit balances with suppliers, as these usually mean an overpayment or an unclaimed credit. • Chase credit notes due, because these are frequently promised and never issued. • Resolve disputed items rather than leaving them on the ledger, as they block payment and damage relationships. • Record the reconciliation, so the position is defensible at audit.
782 | Finance | Review daily bank, cash, receipt and payment posting status | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Review daily bank, cash, receipt and payment posting status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Review daily bank, cash, receipt and payment posting status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks daily that the bank, cash, receipts and payments have all been posted. • Starts when: daily. • How it runs: (1) she compares the bank statement movements to the postings. (2) She identifies unposted or unmatched items. (3) She checks receipts have been allocated. (4) She checks payments have been recorded. (5) She clears or escalates the differences the same day. • Proof it happened: a daily bank and cash posting review with unmatched items identified and cleared or escalated. • Where it usually breaks: bank movements are only reviewed at month end, so an unauthorised payment could sit unnoticed for weeks. | • Review bank movements daily against postings, since a monthly review means an unauthorised or fraudulent payment can sit undetected for weeks. • Require the review to be performed by someone who cannot make payments. • Clear unmatched items the same day, as these accumulate into an unreconcilable balance. • Post payments from the bank confirmation rather than the payment proposal, so failed payments are not recorded as paid. • Escalate any movement without a matching authorised instruction immediately.
783 | Finance | Prepare and review monthly bank reconciliations | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Prepare and review monthly bank reconciliations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Prepare and review monthly bank reconciliations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares and reviews the monthly bank reconciliations. • Starts when: at each month end for every bank account. • How it runs: (1) she obtains the bank statements for all accounts. (2) She reconciles each to the ledger. (3) She lists and explains every outstanding item. (4) She investigates unexplained differences. (5) She has the reconciliation reviewed and signed. • Proof it happened: signed monthly bank reconciliations for every account with all outstanding items explained. • Where it usually breaks: a balancing figure is used to force the reconciliation, so the real difference is buried and repeats every month. | • Prohibit any balancing or plug figure, since a forced reconciliation buries the real difference and it repeats and grows every month. • Require every outstanding item to be individually listed with its age and reason. • Require review and signature by someone other than the preparer. • Investigate long outstanding cheques and unpresented items, as these often indicate errors or duplicated payments. • Reconcile every account including dormant ones, because dormant accounts are used for fraud.
784 | Finance | Review customer, supplier, employee and related control-account reconciliations | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Review customer, supplier, employee and related control-account reconciliations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Review customer, supplier, employee and related control-account reconciliations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she reviews the reconciliations of the customer, supplier, employee and other control accounts. • Starts when: at each close. • How it runs: (1) she obtains each control account reconciliation. (2) She checks the subledger total agrees to the control account. (3) She reviews the reconciling items for validity. (4) She challenges unexplained differences. (5) She approves or returns the reconciliation. • Proof it happened: reviewed control account reconciliations with subledger agreement confirmed and differences explained. • Where it usually breaks: differences are carried forward as unexplained month after month, until they are too large and old to resolve. | • Prohibit carrying forward unexplained differences above a stated threshold, since these compound and eventually cannot be resolved at all. • Require each reconciling item to state its cause and expected clearance date. • Require reconciliations to be prepared by one person and reviewed by another. • Block direct postings to control accounts, as these are the cause of most differences. • Report ageing of reconciling items, because age indicates loss of control rather than timing.
785 | Finance | Reconcile general-ledger balances to subledgers and supporting schedules | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Reconcile general-ledger balances to subledgers and supporting schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Reconcile general-ledger balances to subledgers and supporting schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she makes sure the general ledger agrees to the detailed records behind it. • Starts when: at each close. • How it runs: (1) she compares each ledger balance to its supporting schedule. (2) She investigates any difference. (3) She confirms each balance is supported by evidence, not just a figure. (4) She clears suspense and clearing accounts. (5) She documents the reconciliation. • Proof it happened: general ledger balances reconciled to subledgers and supporting schedules, with clearing accounts cleared. • Where it usually breaks: a balance sits in a clearing account for months, so offsetting errors in both directions remain hidden. | • Require clearing and suspense accounts to be cleared to near zero each period, since a growing balance hides offsetting errors in both directions. • Require every balance sheet balance to have a supporting schedule, as an unsupported balance cannot be verified or defended. • Review ageing within balances, not only the total, because an old item within a correct total is still an error. • Require the schedule to be prepared from source records rather than from the ledger itself. • Report unreconciled balances to the CFO before close is approved.
786 | Finance | Review accruals, prepayments, provisions and cutoff adjustments | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Review accruals, prepayments, provisions and cutoff adjustments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Review accruals, prepayments, provisions and cutoff adjustments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she reviews the accruals, prepayments, provisions and period cut off adjustments. • Starts when: at each close. • How it runs: (1) she reviews each accrual against the evidence of the obligation. (2) She reviews prepayments and their release. (3) She reviews provisions against their basis. (4) She checks the cut off treatment of receipts and costs. (5) She approves or adjusts the entries. • Proof it happened: reviewed accruals, prepayments and provisions with supporting evidence and cut off applied correctly. • Where it usually breaks: accruals are estimated to produce an expected result rather than from evidence of the obligation. | • Require every accrual to be supported by evidence of the obligation, such as a receipt record or a certificate, since estimating to fit an expected result is manipulation rather than accounting. • Require accruals to be released against the actual invoice and any difference explained. • Review prepayment release schedules, as unreleased prepayments overstate assets. • Require provisions to state their basis and be reviewed each period, not rolled forward. • Check the cut off both ways, since revenue and cost can be misstated in either direction.
787 | Finance | Review project revenue, cost, work-in-progress and margin-recognition schedules | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Review project revenue, cost, work-in-progress and margin-recognition schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Review project revenue, cost, work-in-progress and margin-recognition schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she reviews the project revenue, cost and work in progress figures and the margin recognised. • Starts when: at each close. • How it runs: (1) she reviews the costs recorded against each project. (2) She reviews the revenue recognised against the method. (3) She reviews the work in progress and the accrued or deferred position. (4) She checks the margin against the forecast. (5) She challenges anomalies with the project team. • Proof it happened: reviewed project revenue, cost, work in progress and margin schedules with anomalies challenged. • Where it usually breaks: costs land on the wrong project, so one project looks profitable and another does not, and both figures are wrong. | • Check for misallocated costs between projects at each close, since a miscoded cost makes two projects wrong and the error is almost never found later. • Require the revenue recognition method to be applied consistently and stated per project. • Require pending variations and claims to be excluded from recognised revenue until they are approved. • Reconcile the margin movement month to month and explain the change, as the direction reveals problems earlier than the level. • Require the project manager to confirm the cost position.
788 | Finance | Lead the month-end closing checklist and close unresolved posting exceptions | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Lead the month-end closing checklist and close unresolved posting exceptions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Lead the month-end closing checklist and close unresolved posting exceptions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she runs the month end close checklist and clears the outstanding problems. • Starts when: at the period cut off. • How it runs: (1) she issues the close checklist with owners and dates. (2) She tracks completion of each item. (3) She resolves posting exceptions and unmatched items. (4) She confirms all reconciliations are complete. (5) She submits the close for CFO approval. • Proof it happened: a completed close checklist with exceptions cleared and reconciliations complete before approval. • Where it usually breaks: the close is declared complete with items still open, so the reported numbers rest on unresolved differences. | • Prohibit declaring the close complete with checklist items open, since the reported numbers then rest on unresolved differences nobody has quantified. • Require each checklist item to be signed off by its owner with evidence. • Escalate blocking items to the CFO rather than closing around them. • Track post close adjustments, as a high number indicates the close was premature. • Review the checklist annually against what actually goes wrong, so it covers real risks.
789 | Finance | Prepare the trial balance, financial statements and management-account schedules | Senior Accountant (Lead) | Trigger: When the daily reconciliation or monthly/year-end closing cutoff becomes due. Action: The Senior Accountant (Lead) completes “Prepare the trial balance, financial statements and management-account schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. Control/Handoff: Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the daily reconciliation or monthly/year-end closing cutoff becomes due. | The Senior Accountant (Lead) completes “Prepare the trial balance, financial statements and management-account schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reconciled ledger, approved adjustment, closed checklist, trial balance and financial-statement schedule. | Unreconciled or unsupported balances remain open with owners; the Senior Accountant prevents close until material exceptions are corrected or approved. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the trial balance, the financial statements and the schedules behind them. • Starts when: the close is complete. • How it runs: (1) she extracts the trial balance. (2) She prepares the financial statements from it. (3) She prepares the supporting schedules for each significant balance. (4) She checks the statements agree to the ledger and the schedules. (5) She submits them for review. • Proof it happened: prepared trial balance, financial statements and supporting schedules agreeing to the ledger. • Where it usually breaks: statements are prepared in a spreadsheet that no longer ties to the ledger, so two versions of the truth exist. | • Require the statements to be reconciled to the ledger every period, since a spreadsheet that has drifted from the ledger creates two versions of the truth. • Require a supporting schedule for every significant balance, as unsupported figures fail audit. • Keep the statement format consistent so periods are comparable. • Check the prior period comparatives have not changed, because unexplained restatement destroys credibility. • Retain the working file with the statements for audit.
790 | Finance | Issue the payroll timetable and verify the approved HR-to-Finance handover | Senior Accountant (Lead) | Trigger: When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. Action: The Senior Accountant (Lead) completes “Issue the payroll timetable and verify the approved HR-to-Finance handover” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. Control/Handoff: Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. | The Senior Accountant (Lead) completes “Issue the payroll timetable and verify the approved HR-to-Finance handover” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. | Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she issues the payroll timetable and checks the HR handover is complete and approved. • Starts when: at the start of each payroll cycle. • How it runs: (1) she issues the timetable with the input deadlines. (2) She receives the HR handover of changes. (3) She checks the handover is approved and complete. (4) She checks it covers joiners, leavers, variations and deductions. (5) She confirms receipt and queries gaps. • Proof it happened: an issued payroll timetable and a verified, approved HR handover covering all changes. • Where it usually breaks: changes arrive after the cut off by email, so payroll is processed on incomplete data and corrected the following month. | • Require all payroll changes to arrive through the approved handover before the cut off, since changes accepted by email after cut off cause errors and retrospective corrections. • Require the handover to be approved by HR, not just sent, because unapproved changes have no authorisation behind them. • Reconcile the handover to the previous period's employee list, so missing joiners and leavers are visible. • State that late changes move to the next cycle except in defined cases. • Retain the handover as the authorisation evidence for the payroll.
791 | Finance | Review attendance, overtime, leave, salary and deduction inputs | Senior Accountant (Lead) | Trigger: When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. Action: The Senior Accountant (Lead) completes “Review attendance, overtime, leave, salary and deduction inputs” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. Control/Handoff: Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. | The Senior Accountant (Lead) completes “Review attendance, overtime, leave, salary and deduction inputs” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. | Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks the attendance, overtime, leave and deduction data going into payroll. • Starts when: payroll inputs are received. • How it runs: (1) she reconciles attendance to the employee list. (2) She checks overtime is approved and within policy. (3) She checks leave records against balances. (4) She checks the deductions and their authorisation. (5) She queries anomalies before processing. • Proof it happened: verified payroll inputs with attendance reconciled, overtime approved and deductions authorised. • Where it usually breaks: overtime is paid without approval evidence, so unauthorised hours become a permanent monthly cost. | • Require approval evidence for every overtime claim, since unapproved overtime becomes a permanent monthly cost that nobody ever decided to incur. • Reconcile attendance to the active employee list, which catches both missing employees and records for leavers. • Check manual attendance corrections have supervisor confirmation, as these become payment for time not worked. • Check every deduction has documented authorisation from the employee or the law. • Report unusual patterns such as full overtime for a whole crew, because these indicate a control failure.
792 | Finance | Prepare and review the monthly payroll calculation | Senior Accountant (Lead) | Trigger: When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. Action: The Senior Accountant (Lead) completes “Prepare and review the monthly payroll calculation” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. Control/Handoff: Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. | The Senior Accountant (Lead) completes “Prepare and review the monthly payroll calculation” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. | Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she calculates the payroll and checks it before it goes for approval. • Starts when: the inputs are verified. • How it runs: (1) she processes the payroll calculation. (2) She reconciles the total to the previous period by change reason. (3) She checks the individual variances. (4) She checks the statutory calculations. (5) She submits the payroll with the reconciliation for approval. • Proof it happened: a calculated payroll with a period on period reconciliation by change reason and individual variances checked. • Where it usually breaks: only the total is checked, so a duplicated employee or an inflated individual payment is never noticed. | • Reconcile the payroll period on period by employee count and change reason, since checking only the total cannot reveal a duplicated employee or an inflated payment. • Review individual variances above a threshold rather than the total alone. • Check for duplicate bank details across employees, as this is a common payroll fraud indicator. • Require the preparer and the reviewer to be different people. • Retain the reconciliation as the evidence supporting approval.
793 | Finance | Control employee advances, loans, deductions and recovery balances | Senior Accountant (Lead) | Trigger: When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. Action: The Senior Accountant (Lead) completes “Control employee advances, loans, deductions and recovery balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. Control/Handoff: Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. | The Senior Accountant (Lead) completes “Control employee advances, loans, deductions and recovery balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. | Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she controls employee advances and loans and makes sure they are recovered. • Starts when: an advance or loan is approved, and continuously until recovered. • How it runs: (1) she records the advance with its approval. (2) She sets up the recovery schedule in payroll at the same time. (3) She tracks the outstanding balance per employee. (4) She checks recovery is actually being deducted. (5) She reports outstanding balances and leavers with balances. • Proof it happened: an advance and loan register with approvals, recovery schedules set up and balances tracked. • Where it usually breaks: the advance is paid and the deduction is set up later or never, so the balance is still outstanding when the employee leaves. | • Set up the payroll deduction in the same transaction as the advance payment, since a deduction arranged afterwards is frequently never arranged at all. • Require the employee's written authorisation for the deduction. • Check the outstanding balance before approving any further advance to the same employee. • Report leavers with outstanding balances before the final settlement is released, as recovery afterwards is impossible. • Report total advances outstanding, because this is effectively unsecured lending.
794 | Finance | Prepare end-of-service, leave-salary and final-settlement calculations | Senior Accountant (Lead) | Trigger: When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. Action: The Senior Accountant (Lead) completes “Prepare end-of-service, leave-salary and final-settlement calculations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. Control/Handoff: Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. | The Senior Accountant (Lead) completes “Prepare end-of-service, leave-salary and final-settlement calculations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. | Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she calculates what a leaver is owed, including end of service and leave pay. • Starts when: an employee's departure is confirmed. • How it runs: (1) she obtains the confirmed last working date and the reason. (2) She calculates the end of service entitlement per law and contract. (3) She calculates the leave salary and any other dues. (4) She applies the recoveries and deductions. (5) She submits the settlement for verification and approval. • Proof it happened: a settlement calculation with entitlement basis, leave pay, deductions and recoveries, verified and approved. • Where it usually breaks: the settlement is paid before clearance is complete, so unreturned assets and outstanding advances are never recovered. | • Require the clearance check to be complete before the settlement is released, since assets, access and advances are unrecoverable once the person has been paid and left. • Require independent recalculation of settlements above a threshold, as these are complex and frequently wrong. • State the entitlement basis and the calculation on the settlement, so the employee can see how it was derived. • Check the leave balance against the leave records rather than accepting a stated figure. • Retain the employee's acknowledgement of the settlement.
795 | Finance | Prepare WPS or bank payroll files and reconcile payroll payments | Senior Accountant (Lead) | Trigger: When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. Action: The Senior Accountant (Lead) completes “Prepare WPS or bank payroll files and reconcile payroll payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. Control/Handoff: Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When the monthly payroll cutoff, employee change, leave salary or termination settlement is approved by People & Culture. | The Senior Accountant (Lead) completes “Prepare WPS or bank payroll files and reconcile payroll payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a reviewed payroll, WPS file, employee balance, benefit calculation or settlement schedule. | Finance uses only approved HR inputs; payroll preparation, review and bank release remain segregated and employee confidentiality is protected. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the salary payment file and reconciles that everyone was actually paid. • Starts when: payroll is approved. • How it runs: (1) she prepares the bank or WPS file from the approved payroll. (2) She verifies the file total and record count against the approval. (3) She submits it within the statutory deadline. (4) She confirms the payments were made. (5) She reconciles failures and arranges reissue. • Proof it happened: a submitted payroll file matching the approved payroll, with payments confirmed and failures reconciled. • Where it usually breaks: failed payments are not reconciled, so an employee goes unpaid and only raises it days later. | • Reconcile the payments made against the payroll file after every run, since an unreconciled failure means an employee goes unpaid and finds out before finance does. • Verify the file total and record count against the approved payroll immediately before submission. • Diarise the statutory wage transfer deadline, as late salary payment carries regulatory consequences. • Require the person submitting the file to be different from the person who prepared the payroll. • Investigate returned payments rather than reissuing them blind, as these can indicate incorrect or fictitious accounts.
796 | Finance | Review VAT coding, tax invoices and recoverability documentation | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Review VAT coding, tax invoices and recoverability documentation” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Review VAT coding, tax invoices and recoverability documentation” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she checks the tax coding on transactions and that the documents support tax recovery. • Starts when: transactions are posted, and at each tax period. • How it runs: (1) she reviews the tax coding on sales and purchases. (2) She checks supplier invoices meet the tax invoice requirements. (3) She checks the recoverability of input tax. (4) She corrects miscoded items. (5) She records the review. • Proof it happened: reviewed tax coding with invoice validity and recoverability checked, and corrections recorded. • Where it usually breaks: input tax is claimed on defective invoices, so the recovery is disallowed on review and a penalty follows. | • Check every supplier invoice meets the legal tax invoice requirements before claiming input tax, since a defective invoice loses the recovery permanently and can attract a penalty. • Reject and return non compliant invoices rather than claiming and hoping. • Check the coding of unusual transactions specifically, such as imports, related party and cross border items. • Maintain a record of treatment decisions, so coding is consistent between periods. • Report the value of unrecoverable tax, as this is a real and avoidable cost.
797 | Finance | Prepare VAT reconciliations, return schedules and filing package | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Prepare VAT reconciliations, return schedules and filing package” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Prepare VAT reconciliations, return schedules and filing package” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the tax reconciliations and the filing package for the return. • Starts when: at each tax filing period. • How it runs: (1) she reconciles the tax accounts to the ledger. (2) She prepares the return schedules. (3) She reconciles the return to the underlying transactions. (4) She identifies and explains any difference. (5) She submits the package for CFO approval before filing. • Proof it happened: tax reconciliations and return schedules reconciled to the ledger, submitted for approval before filing. • Where it usually breaks: the return is prepared from an extract that does not tie to the ledger, so the filed figures cannot be supported. | • Reconcile the return to the ledger before filing, since figures that cannot be tied back cannot be supported in a review and invite assessment. • Prepare the filing package early enough for CFO review, as deadline pressure is when errors are filed. • Retain the reconciliation and the supporting schedules for the statutory retention period. • Explain differences rather than adjusting them to match. • Diarise the filing and payment deadlines separately, as both carry penalties.
798 | Finance | Maintain the corporate-tax compliance file and return-support schedules | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Maintain the corporate-tax compliance file and return-support schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Maintain the corporate-tax compliance file and return-support schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she keeps the corporate tax file and the schedules supporting the return. • Starts when: continuously through the year, and at the filing cycle. • How it runs: (1) she maintains the file of items affecting the tax computation. (2) She prepares the supporting schedules. (3) She records the treatment of judgement items. (4) She coordinates with external advisers. (5) She submits the file for review before filing. • Proof it happened: a maintained corporate tax file with supporting schedules and recorded treatment of judgement items. • Where it usually breaks: the file is assembled at filing time, so items arising during the year are reconstructed from memory. | • Maintain the tax file throughout the year rather than assembling it at filing, since items reconstructed from memory months later are the ones challenged. • Record the treatment and the reasoning for every judgement item, as a documented position defends against penalty. • Retain external advice with the file, because this is the evidence the position was taken in good faith. • Keep the schedules reconciled to the ledger as they are built. • Diarise the filing deadline with a margin for review.
799 | Finance | Maintain the fixed-asset register, depreciation and disposal controls | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Maintain the fixed-asset register, depreciation and disposal controls” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Maintain the fixed-asset register, depreciation and disposal controls” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she keeps the asset register, runs depreciation and controls disposals. • Starts when: assets are acquired, and at each close and disposal. • How it runs: (1) she records each asset with its cost, date and location. (2) She applies the depreciation policy. (3) She verifies the asset physically at set intervals. (4) She controls disposals with approval and proceeds recorded. (5) She reconciles the register to the ledger. • Proof it happened: a maintained asset register reconciled to the ledger with depreciation applied and controlled disposals. • Where it usually breaks: assets are never verified physically, so the register contains items that were disposed of or stolen years ago. | • Require periodic physical verification of assets against the register, since a register never verified contains items long since disposed of, scrapped or stolen. • Require approval and recorded proceeds for every disposal, as uncontrolled disposal is a known fraud route. • Record the asset location and custodian, otherwise verification is impossible. • Tag assets physically with the register reference. • Reconcile the register to the ledger every period, and investigate differences.
800 | Finance | Control prepayments, deposits, guarantees and other long-term balance schedules | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Control prepayments, deposits, guarantees and other long-term balance schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Control prepayments, deposits, guarantees and other long-term balance schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she controls the prepayments, deposits, guarantees and other balances that sit on the balance sheet. • Starts when: such a balance arises, and at each close. • How it runs: (1) she records each balance with its basis and expected recovery. (2) She maintains the release or recovery schedule. (3) She checks each balance is still valid and recoverable. (4) She follows up recoveries due. (5) She reconciles the schedules to the ledger. • Proof it happened: maintained schedules for prepayments, deposits and guarantees reconciled to the ledger with recoveries tracked. • Where it usually breaks: deposits and guarantees sit on the balance sheet for years after the underlying arrangement ended, and nobody claims them back. | • Record the expected recovery date and owner for every deposit and guarantee, since these otherwise sit on the balance sheet for years after the arrangement has ended. • Review each balance at least annually for validity and recoverability, and provide where recovery is doubtful. • Chase refundable deposits actively rather than waiting for the counterparty. • Show the ageing of these balances, because age is what indicates a problem. • Reconcile the schedules to the ledger every close.
801 | Finance | Prepare project cost, revenue, margin and forecast-at-completion reporting | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Prepare project cost, revenue, margin and forecast-at-completion reporting” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Prepare project cost, revenue, margin and forecast-at-completion reporting” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the project cost, revenue, margin and expected final outcome reporting. • Starts when: at the monthly reporting cycle. • How it runs: (1) she compiles the committed and actual cost per project. (2) She compiles the revenue recognised and certified. (3) She obtains the cost to complete from the project team. (4) She calculates the forecast at completion and the margin. (5) She issues the report and challenges anomalies. • Proof it happened: project reporting with committed and actual cost, revenue, cost to complete and forecast at completion. • Where it usually breaks: the cost to complete is taken as budget minus spend, so the report shows the budget outcome rather than the real one. | • Reject a cost to complete derived as budget minus spend, since this reports the budget outcome rather than the real one and hides every overrun until the end. • Require committed cost rather than invoiced cost, as commitment is where the budget is consumed. • Require the project manager to sign the cost to complete, so it is owned rather than assumed. • Show the movement in forecast at completion month on month, because the trend reveals problems earlier than the level. • Exclude unapproved variations from forecast revenue.
802 | Finance | Prepare the weekly and monthly company cash forecast | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Prepare the weekly and monthly company cash forecast” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Prepare the weekly and monthly company cash forecast” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the cash forecast for the coming weeks and months. • Starts when: weekly and monthly on the forecasting cycle. • How it runs: (1) she compiles the expected collections with their probability. (2) She compiles the committed and expected outflows. (3) She builds the forecast by week for the near term. (4) She reconciles it to the previous forecast. (5) She reports the position and any shortfall. • Proof it happened: a weekly and monthly cash forecast reconciled to the previous version with shortfalls identified. • Where it usually breaks: collections are forecast on contractual due dates, so the forecast is consistently optimistic and nobody trusts it. | • Forecast collections on actual client payment behaviour rather than contractual due dates, since a consistently optimistic forecast is quickly ignored by everyone. • Reconcile each forecast to the previous one and explain the movements, so forecast quality is visible and improves. • Include committed outflows such as approved orders, not just invoices received. • Forecast weekly for the near term, because monthly buckets hide mid month shortfalls. • Track forecast accuracy as a measure, otherwise there is no incentive to forecast honestly.
803 | Finance | Prepare the monthly Finance management pack and variance commentary | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Prepare the monthly Finance management pack and variance commentary” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Prepare the monthly Finance management pack and variance commentary” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the monthly finance pack and explains the variances. • Starts when: the close is complete. • How it runs: (1) she compiles the results against budget and forecast. (2) She identifies the significant variances. (3) She establishes the cause of each with the responsible department. (4) She writes the commentary. (5) She submits the pack for CFO approval. • Proof it happened: a monthly finance pack with results, variances and commentary explaining the causes. • Where it usually breaks: variance commentary restates the numbers in words rather than explaining what caused them and what will be done. | • Require the commentary to state the cause and the corrective action, since restating the numbers in words adds nothing and management cannot act on it. • Obtain the cause from the responsible department rather than writing it from finance's assumption. • Set a variance threshold that requires explanation, so effort goes where it matters. • Keep the format consistent so periods are comparable. • Show the cash position prominently, as it constrains every other decision.
804 | Finance | Prepare audit schedules and coordinate responses to audit queries | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Prepare audit schedules and coordinate responses to audit queries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Prepare audit schedules and coordinate responses to audit queries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she prepares the audit schedules and handles the auditors' questions. • Starts when: the audit cycle begins. • How it runs: (1) she prepares the schedules on the agreed list. (2) She assembles the supporting evidence. (3) She responds to audit queries with evidence. (4) She coordinates responses from other departments. (5) She records the queries and the resolutions. • Proof it happened: prepared audit schedules with supporting evidence and a record of queries and resolutions. • Where it usually breaks: schedules are prepared during the audit rather than before it, so the audit extends, costs more and finds avoidable issues. | • Prepare the schedules before fieldwork begins, since audits conducted while schedules are being built run longer, cost more and produce avoidable findings. • Keep a query log with the response and the evidence provided, as the same queries recur each year. • Require one coordination point for all auditor requests, so the same question is not answered differently by two people. • Retain the audit file, because next year's audit starts from the same schedules. • Escalate queries that indicate a control weakness rather than only answering them.
805 | Finance | Control final billing, final account, retention and DLP financial tracking | Senior Accountant (Lead) | Trigger: When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. Action: The Senior Accountant (Lead) completes “Control final billing, final account, retention and DLP financial tracking” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. Control/Handoff: The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. Continuity/Escalation: A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. Timing: To be confirmed. | When a tax, fixed-asset, management-reporting, audit or project-closeout cycle becomes due. | The Senior Accountant (Lead) completes “Control final billing, final account, retention and DLP financial tracking” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a tax schedule, asset record, forecast/reporting pack, audit response or final financial-closeout record. | The Senior Accountant reconciles schedules to the ledger and retains evidence; uncertain tax, valuation, asset or project exposure escalates to the CFO. | A competent authorised Senior Accountant may provide operational backup; final CFO approvals remain reserved and material cash, tax, payroll, reporting or control exceptions escalate to the CFO. | To be confirmed. | • In plain words: she controls the final billing, the final account and the money still held after completion. • Starts when: a project reaches final billing and closeout. • How it runs: (1) she confirms all billable work has been invoiced. (2) She prepares the final account reconciliation. (3) She confirms the retention held and the release dates. (4) She records the defects liability period and its financial obligations. (5) She tracks the outstanding balances to recovery. • Proof it happened: a final billing and account reconciliation with retention and defects period obligations recorded and tracked. • Where it usually breaks: the project is closed financially while retention and defects obligations remain, so the balances lose their owner. | • Transfer retention and defects period obligations to a live register with a named owner before closing the project, since balances left with a closed project lose their owner and are never recovered. • Confirm all billable work including variations has been invoiced before final account, as unbilled work is rarely recovered afterwards. • Diarise the retention release dates and the defects period expiry. • Reconcile the final account to the contract value plus approved variations. • Report the total post completion balances outstanding across all closed projects.
806 | Finance | Receive and register Finance documents and transaction requests | Accountant | Trigger: When a Finance transaction or document package is submitted. Action: The Accountant completes “Receive and register Finance documents and transaction requests” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered, coded, complete and traceable posting request or documented rejection. Control/Handoff: The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a Finance transaction or document package is submitted. | The Accountant completes “Receive and register Finance documents and transaction requests” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered, coded, complete and traceable posting request or documented rejection. | The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she receives the finance paperwork and requests coming in and logs them so nothing is lost. • Starts when: a document or transaction request arrives at finance. • How it runs: (1) she receives it through the approved route. (2) She records the date received and the source. (3) She identifies the transaction type. (4) She assigns it to the processing queue. (5) She confirms receipt where a response is expected. • Proof it happened: a register entry with the date received, source and transaction type for every document. • Where it usually breaks: documents are handed directly to individuals, so they are never registered and nobody knows what finance is actually holding. | • Require a single intake route and register everything on receipt, since documents handed to individuals are invisible and the backlog cannot be measured. • Record the date received separately from the document date, as this drives both the accrual and the payment period. • Confirm receipt so departments do not resubmit or escalate unnecessarily. • Report the volume and ageing of the queue, because this is what reveals resourcing problems. • Keep the register sequential, as gaps undermine its reliability.
807 | Finance | Verify required approvals, supporting evidence and FirstBit references | Accountant | Trigger: When a Finance transaction or document package is submitted. Action: The Accountant completes “Verify required approvals, supporting evidence and FirstBit references” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered, coded, complete and traceable posting request or documented rejection. Control/Handoff: The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a Finance transaction or document package is submitted. | The Accountant completes “Verify required approvals, supporting evidence and FirstBit references” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered, coded, complete and traceable posting request or documented rejection. | The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she checks the paperwork has the right approvals and the right system references before anything is processed. • Starts when: a transaction package is being verified. • How it runs: (1) she checks the required approvals are present. (2) She checks the approver's authority for the value. (3) She checks the supporting documents are attached. (4) She checks the system references match. (5) She records the verification or raises the exception. • Proof it happened: a verification record confirming approvals, authority, supporting evidence and system references. • Where it usually breaks: packages are processed with approvals promised to follow, and the approval never arrives. | • Reject packages with missing approvals rather than processing them pending approval, since a transaction processed first and approved later is not controlled at all. • Check the approval is at the correct authority level for the value, not just that someone approved it. • Require the supporting evidence to be attached, because an unsupported entry cannot be verified afterwards. • Verify the system reference exists and matches, as a mismatched reference produces an unreconcilable entry. • Record the verification, so the file shows the check was performed.
808 | Finance | Assign document numbers, project codes, cost codes and filing references | Accountant | Trigger: When a Finance transaction or document package is submitted. Action: The Accountant completes “Assign document numbers, project codes, cost codes and filing references” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered, coded, complete and traceable posting request or documented rejection. Control/Handoff: The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a Finance transaction or document package is submitted. | The Accountant completes “Assign document numbers, project codes, cost codes and filing references” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered, coded, complete and traceable posting request or documented rejection. | The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she assigns the numbers and codes that determine where the transaction lands in the accounts. • Starts when: a verified package is being prepared for posting. • How it runs: (1) she assigns the document number. (2) She assigns the project and cost codes. (3) She checks the codes against the approved structure. (4) She assigns the filing reference. (5) She records the assignment. • Proof it happened: assigned document numbers, project and cost codes checked against the approved structure, with filing references. • Where it usually breaks: cost codes are guessed when the request does not state one, so the cost lands on the wrong project and is never corrected. | • Return packages with no stated cost code rather than guessing, since a guessed code puts cost on the wrong project and is almost never corrected. • Check the code against the approved structure and the project's active codes, not just that it exists. • Never reuse a document number, as historical references become ambiguous. • Record the filing reference at assignment, so the document can be retrieved from the entry. • Report miscoding found later by originating department, to target training.
809 | Finance | Return missing, duplicate, incorrect or unauthorised transaction packages | Accountant | Trigger: When a Finance transaction or document package is submitted. Action: The Accountant completes “Return missing, duplicate, incorrect or unauthorised transaction packages” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered, coded, complete and traceable posting request or documented rejection. Control/Handoff: The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a Finance transaction or document package is submitted. | The Accountant completes “Return missing, duplicate, incorrect or unauthorised transaction packages” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered, coded, complete and traceable posting request or documented rejection. | The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she sends back the packages that are incomplete, duplicated, wrong or unauthorised. • Starts when: a verification check fails. • How it runs: (1) she identifies the specific deficiency. (2) She checks whether it duplicates something already processed. (3) She records the return with the reason. (4) She returns it to the named originator. (5) She tracks the resubmission. • Proof it happened: a return record with the specific reason, notified to the originator and tracked to resubmission. • Where it usually breaks: finance completes the missing information itself to avoid delay, so it owns an error it cannot verify. | • Prohibit finance from completing a deficient package on the originator's behalf, since this moves responsibility for the error to the wrong function and conceals it. • Check for duplicates before returning, as duplicate invoices are a real payment risk. • State the specific missing items, or the resubmission arrives with the same gaps. • Track return rates by department to target training. • Escalate repeated deficient submissions rather than absorbing the rework.
810 | Finance | Maintain the daily posting queue and transaction-completion status | Accountant | Trigger: When a Finance transaction or document package is submitted. Action: The Accountant completes “Maintain the daily posting queue and transaction-completion status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered, coded, complete and traceable posting request or documented rejection. Control/Handoff: The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a Finance transaction or document package is submitted. | The Accountant completes “Maintain the daily posting queue and transaction-completion status” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered, coded, complete and traceable posting request or documented rejection. | The Accountant posts only approved complete documents; duplicates, missing evidence and invalid periods or codes are returned to the requester and Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she keeps the posting queue current so she knows what is done and what is waiting. • Starts when: daily, as transactions are received and processed. • How it runs: (1) she maintains the list of transactions awaiting posting. (2) She records the status of each. (3) She prioritises by cut off and urgency. (4) She clears the queue within the agreed timeframe. (5) She reports the backlog and its ageing. • Proof it happened: a maintained posting queue with statuses, priorities and the backlog reported. • Where it usually breaks: the queue builds up towards period end, so everything is posted in a rush and the error rate rises sharply. | • Set a maximum posting turnaround in days and report the backlog daily, since transactions posted in a period end rush carry a much higher error rate. • Prioritise by cut off date rather than by arrival order. • Report the backlog ageing to the Senior Accountant, because a growing queue means the period end will be wrong. • Keep the queue visible to the team, so work can be reallocated. • Never hold a transaction outside the queue, as unqueued items are forgotten.
811 | Finance | Create the customer and project billing record from approved master data | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Create the customer and project billing record from approved master data” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Create the customer and project billing record from approved master data” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she sets up the billing record for a customer or project from the approved master data. • Starts when: a new customer or project requires a billing record. • How it runs: (1) she obtains the approved master data. (2) She creates the billing record with the terms and tax treatment. (3) She records the billing contact and submission route. (4) She checks the record against the source. (5) She confirms it is ready for invoicing. • Proof it happened: a created billing record matching the approved master data with terms, tax treatment and submission route. • Where it usually breaks: the payment terms in the billing record do not match the contract, so every invoice ages incorrectly. | • Take the payment terms from the executed contract and check them into the billing record, since incorrect terms make every invoice age wrongly and distort the whole receivables position. • Record the client's invoice submission route and required references, as non compliant invoices are returned unpaid. • Verify the legal entity name against the trade licence, because an invoice to the wrong entity is rejected. • Check the record against the source before the first invoice. • Require a second check of tax treatment for cross border clients.
812 | Finance | Create proforma and advance invoices from approved agreements | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Create proforma and advance invoices from approved agreements” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Create proforma and advance invoices from approved agreements” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she creates the proforma and advance invoices from the approved agreement. • Starts when: an advance or proforma invoice is approved for issue. • How it runs: (1) she takes the amount and basis from the approved agreement. (2) She applies the correct tax treatment for an advance. (3) She records the recovery basis. (4) She prepares the invoice in the required format. (5) She issues it and records it. • Proof it happened: an issued proforma or advance invoice matching the approved agreement with tax and recovery basis recorded. • Where it usually breaks: the advance is recorded as revenue rather than as a liability, so the accounts overstate income until it is unwound. | • Record advances as a liability rather than revenue, since treating an advance as income overstates the result and has to be unwound later. • Record the recovery basis at the point of invoicing, otherwise the advance is never recovered against progress. • Apply the specific tax treatment for advances, as this differs from progress billing. • Track the advance balance separately rather than netting it into the receivable. • Require approval before issue, as an advance invoice without entitlement damages client credibility.
813 | Finance | Create tax invoices from approved billing or payment evidence | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Create tax invoices from approved billing or payment evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Create tax invoices from approved billing or payment evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she creates the tax invoices from approved billing or payment evidence. • Starts when: a tax invoice is due to be raised. • How it runs: (1) she confirms the approved basis for the invoice. (2) She applies the correct tax rate and treatment. (3) She includes every legally required field. (4) She checks the invoice against the basis. (5) She issues it and records it in the register. • Proof it happened: an issued tax invoice with the approved basis, correct tax treatment and all required fields. • Where it usually breaks: a required field is missing, so the client rejects the invoice and the payment cycle restarts from zero. | • Check every legally required field before issue, since a defective tax invoice is rejected and the payment cycle restarts from the beginning. • Confirm the approved basis before raising, so invoices are not issued on assumption. • Number invoices sequentially with no gaps, as gaps invite tax authority questions. • Record the issue date and the submission date separately, because the client's clock usually starts at submission. • Retain proof of submission, as clients frequently deny receipt.
814 | Finance | Create progress invoices from certified billing packages | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Create progress invoices from certified billing packages” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Create progress invoices from certified billing packages” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she creates the progress invoices from the certified billing package. • Starts when: a certified billing package is received. • How it runs: (1) she checks the certification and the quantities. (2) She applies the contract rates. (3) She applies the retention, advance recovery and tax. (4) She assembles the required supporting documents. (5) She issues the invoice and records it. • Proof it happened: a progress invoice raised from certification with deductions applied and supporting documents attached. • Where it usually breaks: the invoice is issued without the supporting documents the contract requires, so it is returned unpaid without comment. | • Attach every supporting document the contract requires before issue, since incomplete submissions are returned unpaid and often without explanation. • Bill from the certified position rather than the claimed position. • Apply retention and advance recovery as a system rule, not a manual step. • Submit within the contractual billing window, as late submission loses a full payment cycle. • Record what was submitted and when, because this is the evidence in any payment dispute.
815 | Finance | Prepare credit-note entries from approved supporting documents | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Prepare credit-note entries from approved supporting documents” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Prepare credit-note entries from approved supporting documents” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the credit note entries when they have been approved. • Starts when: an approved credit note is to be raised. • How it runs: (1) she confirms the approval and the stated reason. (2) She identifies the original invoice. (3) She prepares the credit note with the correct tax treatment. (4) She links it to the original invoice. (5) She posts it and records it in the register. • Proof it happened: a posted credit note with approval, stated reason, tax treatment and a link to the original invoice. • Where it usually breaks: credit notes are raised without approval to fix billing errors, which is the easiest route to concealing a revenue adjustment. | • Require documented approval with a stated reason for every credit note, since unapproved credit notes are the simplest way to conceal a revenue adjustment or a write off. • Link every credit note to its original invoice, so the net position is traceable. • Prohibit the person who raised the invoice from also raising its credit note. • Apply the same tax treatment as the original invoice. • Report credit note volume and reasons, as a high volume indicates an upstream billing problem.
816 | Finance | Post customer receipts and retain bank or cash evidence | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Post customer receipts and retain bank or cash evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Post customer receipts and retain bank or cash evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she posts the money received from customers and keeps the bank evidence. • Starts when: a customer receipt appears on the bank or is received in cash. • How it runs: (1) she identifies the receipt from the bank statement. (2) She identifies the paying customer. (3) She posts the receipt to the customer account. (4) She retains the bank credit advice or receipt evidence. (5) She confirms the posting against the bank. • Proof it happened: posted customer receipts with bank or cash evidence retained and reconciled to the bank. • Where it usually breaks: unidentified receipts are posted to a suspense account and never investigated, so customer accounts stay overstated. | • Investigate and clear unidentified receipts within a stated period, since receipts parked in suspense leave customer accounts overstated and the collection effort misdirected. • Post from the bank statement rather than from the customer's advice, so only actual receipts are recorded. • Retain the bank credit advice with the posting, as this is the evidence in any dispute. • Require receipts in cash to be banked promptly and reconciled. • Report suspense balances with ageing at every close.
817 | Finance | Allocate receipts against invoices, advances and project balances | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Allocate receipts against invoices, advances and project balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Allocate receipts against invoices, advances and project balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she matches the money received against the right invoices and balances. • Starts when: a receipt has been posted and needs allocating. • How it runs: (1) she obtains the customer's remittance advice. (2) She allocates the receipt against the specified invoices. (3) She allocates against advances or retention where indicated. (4) She records unallocated amounts. (5) She follows up missing remittance advice. • Proof it happened: receipts allocated per the remittance advice with unallocated amounts recorded and followed up. • Where it usually breaks: receipts are allocated to the oldest invoice by default, so a disputed invoice appears settled and the dispute disappears from view. | • Prohibit default allocation to the oldest invoice, since this makes a disputed invoice look paid and the real dispute becomes invisible to everyone. • Chase the remittance advice where it is missing rather than allocating by assumption. • Record part payments against the specific invoice, so the balance ages correctly. • Clear unallocated receipts within a stated period. • Check allocation against the project, as receipts are frequently allocated to the wrong project on multi project clients.
818 | Finance | Prepare customer statements, collection logs and unapplied-receipt schedules | Accountant | Trigger: When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. Action: The Accountant completes “Prepare customer statements, collection logs and unapplied-receipt schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. Control/Handoff: Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved contract, billing milestone, payment, credit decision or customer-control activity occurs. | The Accountant completes “Prepare customer statements, collection logs and unapplied-receipt schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a controlled invoice, credit entry, receipt allocation, customer statement or collection-support schedule. | Customer and tax data, billing basis and approvals are verified; unapplied receipts or disputed invoices are escalated to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the customer statements, the collection logs and the list of unmatched receipts. • Starts when: at the reporting cycle, and on request. • How it runs: (1) she prepares the statement of account per customer. (2) She updates the collection log with contacts and commitments. (3) She prepares the unapplied receipt schedule. (4) She reconciles the schedules to the ledger. (5) She issues them for collection action. • Proof it happened: customer statements, collection logs and unapplied receipt schedules reconciled to the ledger. • Where it usually breaks: statements are never sent, so invoices the client never received sit as receivables for months. | • Send statements of account at a set frequency, since this is what surfaces invoices the client never received or has rejected without telling anyone. • Reconcile the statement to the ledger before issue, as an incorrect statement damages credibility. • Record every collection contact and commitment in the log, because a verbal promise cannot otherwise be escalated. • Report unapplied receipts with ageing, as these distort both the ageing and the cash picture. • Include the invoice submission date on the statement, since this is what the client's clock runs from.
819 | Finance | Register supplier invoices and verify invoice-control information | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Register supplier invoices and verify invoice-control information” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Register supplier invoices and verify invoice-control information” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she registers the supplier invoices and checks the control details on them. • Starts when: a supplier invoice is received. • How it runs: (1) she registers the invoice with the date received. (2) She checks the invoice number, date and supplier details. (3) She checks it is not a duplicate. (4) She checks the tax invoice validity. (5) She routes it for matching and approval. • Proof it happened: a registered supplier invoice with date received, control details checked and duplicate check performed. • Where it usually breaks: duplicates are not detected because the supplier reissues with a new number, so the same cost is paid twice. | • Check for duplicates on amount, date and reference as well as invoice number, since a reissued invoice with a new number is the standard way a duplicate payment happens. • Record the date received, as this drives the accrual and the payment period. • Check the tax invoice validity at registration rather than at payment, so defective invoices are returned early. • Register centrally regardless of who received the invoice. • Report unregistered invoices found in departments, as these understate cost.
820 | Finance | Match supplier invoices to purchase orders, GRNs and approvals | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Match supplier invoices to purchase orders, GRNs and approvals” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Match supplier invoices to purchase orders, GRNs and approvals” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she matches the supplier invoice to the order, the receipt record and the approval. • Starts when: a registered invoice is being processed. • How it runs: (1) she matches the invoice to the purchase order on price and terms. (2) She matches it to the goods received note on quantity. (3) She confirms the approvals are present. (4) She identifies and records any mismatch. (5) She routes matched invoices for payment and exceptions for resolution. • Proof it happened: a documented three way match with mismatches recorded and routed for resolution. • Where it usually breaks: the goods received note is missing so the invoice is matched to the order alone, which means goods never received get paid for. | • Treat a missing goods received note as a blocking exception rather than matching to the order alone, since this is the control that prevents paying for goods never delivered. • Match on quantity received rather than quantity ordered, particularly on partial deliveries. • Set tolerance limits and require approval for differences above them. • Check retention and advance recovery on every invoice. • Report unmatched invoices with ageing, as these are either missing receipts or invalid claims.
821 | Finance | Post approved purchase invoices to the correct project and cost code | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Post approved purchase invoices to the correct project and cost code” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Post approved purchase invoices to the correct project and cost code” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she posts the approved purchase invoices to the right project and cost code. • Starts when: an invoice is matched and approved. • How it runs: (1) she confirms the project and cost code from the order. (2) She posts the invoice to the ledger. (3) She posts the tax to the correct account. (4) She checks the posting against the invoice. (5) She files the invoice with the posting reference. • Proof it happened: posted purchase invoices with the correct project and cost code, tax treatment and filing reference. • Where it usually breaks: the coding is taken from the invoice rather than the order, so cost lands wherever the supplier happened to reference. | • Take the coding from the purchase order rather than the supplier's invoice, since the supplier's reference is not a reliable basis for allocating the company's cost. • Check the project code is still active and correct for the work. • Post tax separately to the correct account, as mispostings here affect the return. • Check the posting against the invoice before release, because correcting a posted entry is a further transaction. • Report miscoding found later, so the cause can be addressed.
822 | Finance | Record subcontractor invoices, certifications, retention and advances | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Record subcontractor invoices, certifications, retention and advances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Record subcontractor invoices, certifications, retention and advances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she records subcontractor invoices along with the certification, retention and advance recovery. • Starts when: a certified subcontractor application is approved. • How it runs: (1) she confirms the certified value. (2) She records the invoice against the subcontract. (3) She records the retention deducted. (4) She records the advance recovery. (5) She checks the cumulative position against the subcontract value. • Proof it happened: recorded subcontractor invoices with certification, retention and advance recovery, checked cumulatively. • Where it usually breaks: retention is deducted but never recorded as a liability, so the balance owed back to the subcontractor is unknown. | • Record retention deducted as a tracked liability per subcontractor, since a deduction not recorded leaves the company unable to say what it owes back. • Check the cumulative certified value against the subcontract including variations, so overpayment is visible. • Record the advance recovery against the advance balance, not as a general deduction. • Post to the correct project and work package. • Report subcontractors whose cumulative payments approach or exceed their commitment.
823 | Finance | Record approved employee expenses and reimbursement claims | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Record approved employee expenses and reimbursement claims” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Record approved employee expenses and reimbursement claims” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she records the approved staff expense and reimbursement claims. • Starts when: an approved expense claim is received. • How it runs: (1) she checks the approval and the receipts. (2) She checks the coding and project allocation. (3) She checks the tax treatment where recoverable. (4) She posts the claim. (5) She records it for payment. • Proof it happened: posted expense claims with approval, receipts, coding and tax treatment verified. • Where it usually breaks: claims are posted without checking receipts because they are approved, so unsupported and duplicate items pass through. | • Check receipts against every line rather than relying on the approval, since approval confirms authorisation and not that the expense was incurred. • Check for duplicate submission of the same receipt, as this is a common small value leakage. • Check the tax treatment, because expense claims frequently include non recoverable items claimed as recoverable. • Code to the correct project, as expenses are often coded to the department by default. • Report claims returned and their reasons.
824 | Finance | Prepare payment vouchers with the complete supporting package | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Prepare payment vouchers with the complete supporting package” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Prepare payment vouchers with the complete supporting package” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the payment voucher with everything needed to support the payment. • Starts when: an invoice or claim is approved for payment. • How it runs: (1) she prepares the voucher with the payment details. (2) She attaches the invoice, order, receipt and approvals. (3) She includes the deduction and recovery calculations. (4) She confirms the beneficiary details from the verified master. (5) She submits the complete package for approval. • Proof it happened: a complete payment voucher with all supporting documents and verified beneficiary details. • Where it usually breaks: beneficiary details are taken from the invoice rather than the master record, which is exactly how payment fraud succeeds. | • Take beneficiary details only from the verified master record and never from the invoice or the request, since this is the single control that defeats most payment fraud. • Define the voucher contents as a checklist and require completeness before submission. • Include the deduction and recovery calculations on the voucher, so the approver sees the net basis. • Require the preparer and the approver to be different people. • Report incomplete vouchers, as these are the main cause of late payment.
825 | Finance | Post approved bank, cheque and online supplier payments | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Post approved bank, cheque and online supplier payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Post approved bank, cheque and online supplier payments” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she posts the payments once they have actually been made. • Starts when: payments are executed. • How it runs: (1) she obtains the bank confirmation of payment. (2) She posts the payment against the supplier account. (3) She posts any deductions and recoveries. (4) She retains the bank confirmation. (5) She reconciles the posting to the bank movement. • Proof it happened: posted payments matching the bank confirmation with deductions applied and evidence retained. • Where it usually breaks: payments are posted from the proposal rather than the bank confirmation, so failed payments remain recorded as paid. | • Post payments from the bank confirmation rather than the payment proposal, since a failed or returned payment otherwise stays recorded as paid and the supplier remains unpaid. • Reconcile posted payments to bank movements daily. • Retain the bank confirmation with the voucher, as this is the evidence of settlement. • Investigate returned payments rather than reissuing blind, because these can indicate incorrect or fictitious accounts. • Require the person posting to be different from the person releasing the payment.
826 | Finance | Prepare supplier-statement reconciliations and missing-invoice lists | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Prepare supplier-statement reconciliations and missing-invoice lists” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Prepare supplier-statement reconciliations and missing-invoice lists” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she reconciles supplier statements and lists the invoices the company has not received. • Starts when: at the reconciliation cycle, or when a statement is received. • How it runs: (1) she obtains the supplier statement. (2) She reconciles it to the ledger account. (3) She lists the invoices on the statement not in the ledger. (4) She lists the payments not reflected. (5) She reports the reconciliation and the missing invoice list. • Proof it happened: supplier statement reconciliations with missing invoice and unreflected payment lists. • Where it usually breaks: missing invoices are requested but never chased, so the cost lands in a later period and distorts both. | • Chase missing invoices identified on statements rather than only listing them, since uninvoiced cost lands in a later period and distorts both periods. • Accrue for identified missing invoices at the cut off. • Investigate payments the supplier has not reflected, as these can indicate a payment that went astray. • Reconcile all significant suppliers at a set frequency, not only on request. • Escalate suppliers who will not provide statements, since these accounts cannot be verified.
827 | Finance | Prepare debit-note, rejection and invoice-correction entries | Accountant | Trigger: When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. Action: The Accountant completes “Prepare debit-note, rejection and invoice-correction entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. Control/Handoff: PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a supplier/subcontractor invoice, certified expense or approved payment reaches Finance. | The Accountant completes “Prepare debit-note, rejection and invoice-correction entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a registered and correctly posted invoice, payment voucher, payment entry or supplier reconciliation. | PO/contract, GRN/certification, tax treatment, project/cost code and approval evidence are required before posting or payment. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the entries for debit notes, rejections and invoice corrections. • Starts when: a debit note or correction is approved. • How it runs: (1) she confirms the approval and the basis. (2) She identifies the original invoice. (3) She prepares the entry with the correct tax treatment. (4) She links it to the original transaction. (5) She tracks the supplier's credit note. • Proof it happened: posted debit note and correction entries linked to the original transactions, with credit notes tracked. • Where it usually breaks: a debit note is raised but the supplier's credit note is never obtained, so the account stays wrong and the money is not recovered. | • Track every debit note to the receipt of the supplier's credit note, since an unmatched debit note leaves the account wrong and the money unrecovered. • Link corrections to the original transaction, so the net position is traceable. • Apply the same tax treatment as the original entry. • Require approval with a stated basis for every debit note. • Report outstanding debit notes with ageing, as these represent money owed to the company.
828 | Finance | Download or receive bank statements and record bank transactions | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Download or receive bank statements and record bank transactions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Download or receive bank statements and record bank transactions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she gets the bank statements and records the transactions on them. • Starts when: daily, when statements are available. • How it runs: (1) she downloads or receives the statements for every account. (2) She records the transactions in the system. (3) She identifies unrecognised items. (4) She matches transactions to postings. (5) She escalates anything unexplained. • Proof it happened: recorded bank transactions for every account with unrecognised items identified and escalated. • Where it usually breaks: statements are only obtained at month end, so an unauthorised payment could sit undetected for weeks. | • Obtain and review statements daily, since a monthly review means an unauthorised payment can sit undetected for weeks. • Require the person reviewing to be someone who cannot make payments. • Escalate any movement without a matching authorised instruction immediately. • Include all accounts including dormant ones, because dormant accounts are used for fraud. • Retain the statements for the retention period, as these are primary evidence.
829 | Finance | Maintain petty-cash vouchers, limits and replenishment records | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Maintain petty-cash vouchers, limits and replenishment records” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Maintain petty-cash vouchers, limits and replenishment records” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she keeps the petty cash vouchers, the float limits and the replenishment records. • Starts when: petty cash is used or replenished. • How it runs: (1) she records each voucher with its approval and receipt. (2) She checks the expense is within the petty cash policy. (3) She maintains the float balance. (4) She prepares the replenishment against vouchers spent. (5) She retains the vouchers and records. • Proof it happened: petty cash vouchers with approvals and receipts, float balance maintained and replenishment records. • Where it usually breaks: the float is replenished on a stated balance rather than against submitted vouchers, so shortfalls are absorbed unnoticed. | • Replenish only against submitted and approved vouchers, never against a stated balance, since the latter absorbs shortfalls without anyone noticing. • Set a float limit and a maximum single transaction value, and enforce both. • Require a receipt for every voucher regardless of amount. • Prohibit using petty cash to bypass the purchase order process, and state it explicitly. • Require the custodian to be someone who does not also post the entries.
830 | Finance | Record cash receipts, cash payments and controlled cash transfers | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Record cash receipts, cash payments and controlled cash transfers” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Record cash receipts, cash payments and controlled cash transfers” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she records the cash coming in, going out and moving between locations. • Starts when: a cash transaction occurs. • How it runs: (1) she records the receipt or payment with its evidence. (2) She issues or obtains the receipt document. (3) She records cash transfers between custodians or locations. (4) She obtains acknowledgement for transfers. (5) She updates the cash position. • Proof it happened: recorded cash transactions with receipts issued or obtained and transfers acknowledged. • Where it usually breaks: cash transfers between people are made without acknowledgement, so a shortfall cannot be attributed to anyone. | • Require signed acknowledgement for every cash transfer between custodians, since an unacknowledged transfer means a shortfall cannot be attributed to anybody. • Issue a sequentially numbered receipt for every cash receipt, and account for the sequence. • Bank cash receipts promptly rather than using them to fund payments. • Keep cash in a secure location with controlled access, and record who holds keys. • Set a maximum cash holding and enforce it.
831 | Finance | Perform petty-cash and physical-cash counts and reconcile differences | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Perform petty-cash and physical-cash counts and reconcile differences” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Perform petty-cash and physical-cash counts and reconcile differences” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she counts the cash physically and reconciles any difference. • Starts when: at the scheduled count frequency, and on custodian change. • How it runs: (1) she counts the physical cash and the unspent vouchers. (2) She compares the total to the float. (3) She identifies and investigates any difference. (4) She records the count and the cause of any difference. (5) She reports differences for approval and correction. • Proof it happened: physical cash count records reconciled to the float, with differences investigated and reported. • Where it usually breaks: a difference is made good from someone's pocket rather than reported, so a pattern of shortfalls is never seen. | • Require every difference to be reported and approved rather than made good informally, since quietly correcting shortfalls is how a pattern of theft remains invisible. • Count unannounced at least sometimes, as scheduled counts can be prepared for. • Have someone other than the custodian perform the count. • Count on every custodian change, so responsibility transfers cleanly. • Include unspent vouchers in the count, because these form part of the float.
832 | Finance | Prepare bank-reconciliation working papers and unmatched-item schedules | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Prepare bank-reconciliation working papers and unmatched-item schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Prepare bank-reconciliation working papers and unmatched-item schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the working papers for the bank reconciliation and lists the unmatched items. • Starts when: at the reconciliation cycle. • How it runs: (1) she compares the bank statement to the ledger. (2) She lists the items in the bank not in the ledger. (3) She lists the items in the ledger not in the bank. (4) She explains each unmatched item. (5) She submits the working papers for review. • Proof it happened: bank reconciliation working papers with every unmatched item listed and explained. • Where it usually breaks: a balancing figure is used to make it reconcile, so the real difference is hidden and repeats every month. | • Prohibit any balancing figure, since a forced reconciliation hides the real difference and it repeats and grows every month. • List every unmatched item individually with its age and reason. • Investigate long outstanding items, as these often indicate duplicated or failed payments. • Prepare the working papers from source records rather than from the previous month's file. • Submit for independent review rather than self approving.
833 | Finance | Record cheque deposits, returned cheques and bank charges | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Record cheque deposits, returned cheques and bank charges” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Record cheque deposits, returned cheques and bank charges” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she records cheque deposits, bounced cheques and bank charges. • Starts when: such a transaction occurs. • How it runs: (1) she records cheques deposited and tracks clearance. (2) She records returned cheques and reverses the receipt. (3) She notifies collection of returned cheques immediately. (4) She records bank charges and interest. (5) She reconciles these to the bank statement. • Proof it happened: recorded deposits, returned cheques reversed and notified, and bank charges reconciled. • Where it usually breaks: a returned cheque is not reversed promptly, so the customer account shows as paid and collection stops. | • Reverse a returned cheque and notify collection the same day, since an unreversed return leaves the account showing as paid and collection stops entirely. • Track cheques deposited but not cleared, as these are not yet cash. • Review bank charges against the agreed tariff, because incorrect charges are common and rarely challenged. • Escalate repeat returned cheques from the same customer, as this is a credit risk signal. • Record the return reason, since some reasons indicate a fundamental problem.
834 | Finance | Retain payment-file, transfer and bank-confirmation evidence | Accountant | Trigger: When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. Action: The Accountant completes “Retain payment-file, transfer and bank-confirmation evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. Control/Handoff: Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When a bank transaction, cash movement, petty-cash event or reconciliation cutoff occurs. | The Accountant completes “Retain payment-file, transfer and bank-confirmation evidence” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted and evidenced bank/cash transaction, cash count, reconciliation working paper or bank exception. | Cash custody, recording and approval are segregated; loss, unexplained difference, returned cheque or suspicious bank item is immediately escalated. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she keeps the evidence of payment files, transfers and bank confirmations. • Starts when: payments are executed. • How it runs: (1) she retains the approved payment file. (2) She retains the bank confirmation for each payment. (3) She retains the transfer instructions and approvals. (4) She files them against the payment reference. (5) She makes them available for reconciliation and audit. • Proof it happened: retained payment file, transfer and bank confirmation evidence filed against the payment reference. • Where it usually breaks: only the proposal is retained and not the released file, so a difference between the two cannot be detected. | • Retain both the approved proposal and the released bank file, since without both a post approval alteration to the file cannot be detected. • Retain the bank confirmation as the evidence of settlement. • File against the payment reference so evidence can be found from either the invoice or the bank entry. • Restrict access to payment files, as these contain beneficiary bank details. • Retain for the statutory period, because payment queries and audits arrive years later.
835 | Finance | Prepare and post approved journal entries with supporting schedules | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Prepare and post approved journal entries with supporting schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Prepare and post approved journal entries with supporting schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares and posts the approved journal entries with the schedules behind them. • Starts when: a journal entry is required and approved. • How it runs: (1) she prepares the journal with the supporting calculation. (2) She states the reason for the entry. (3) She obtains the approval required. (4) She posts the journal. (5) She files the journal with its schedule. • Proof it happened: posted journals with supporting schedules, stated reasons and documented approval. • Where it usually breaks: journals are posted with no narrative or support, so nobody can tell later what the entry was for. | • Require a narrative and a supporting schedule on every journal, since an unexplained entry cannot be verified or reversed and fails audit immediately. • Require approval by someone other than the preparer for journals above a threshold. • Prohibit journals that bypass the subledgers, as these create control account differences. • Number journals sequentially and account for the sequence. • Review all manual journals at close, because this is where manipulation would occur.
836 | Finance | Post accrual, prepayment and provision entries from approved calculations | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Post accrual, prepayment and provision entries from approved calculations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Post accrual, prepayment and provision entries from approved calculations” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she posts the accrual, prepayment and provision entries from the approved calculations. • Starts when: at each close. • How it runs: (1) she obtains the approved calculations. (2) She posts the entries with their supporting schedules. (3) She sets up the reversal or release where applicable. (4) She checks the entries against the calculations. (5) She files the schedules. • Proof it happened: posted accrual, prepayment and provision entries matching the approved calculations, with schedules filed. • Where it usually breaks: accruals are posted without a reversal, so they remain in the accounts after the invoice arrives and the cost is doubled. | • Set up the reversal at the same time as the accrual, since an unreleased accrual plus the actual invoice doubles the cost and is rarely spotted. • Require the accrual to be supported by evidence of the obligation, not estimated to fit a result. • Release accruals against the actual invoice and explain any difference. • Maintain a prepayment schedule with the release profile, as unreleased prepayments overstate assets. • Review provisions each period rather than rolling them forward.
837 | Finance | Maintain customer, supplier, employee and clearing-account schedules | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Maintain customer, supplier, employee and clearing-account schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Maintain customer, supplier, employee and clearing-account schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she keeps the schedules behind the customer, supplier, employee and clearing accounts. • Starts when: at each close, and continuously as transactions post. • How it runs: (1) she prepares the schedule for each control account. (2) She agrees the schedule total to the ledger. (3) She lists and ages the items within it. (4) She identifies items needing clearance. (5) She submits the schedules for review. • Proof it happened: control account schedules agreeing to the ledger with items listed, aged and clearance identified. • Where it usually breaks: the schedule is a single total rather than an itemised list, so an old item inside a correct total is never found. | • Require the schedule to be itemised and aged rather than a total, since an old or invalid item inside a correct total is otherwise never identified. • Require clearing accounts to be cleared to near zero each period, as a growing balance hides offsetting errors. • Prepare the schedule from source records rather than from the ledger itself. • Flag items needing clearance with an owner and a date. • Submit for independent review at each close.
838 | Finance | Apply correct VAT coding and validate tax-document fields | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Apply correct VAT coding and validate tax-document fields” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Apply correct VAT coding and validate tax-document fields” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she applies the right tax coding and checks the tax documents are valid. • Starts when: transactions are being posted. • How it runs: (1) she determines the correct tax treatment for the transaction. (2) She applies the coding. (3) She checks the supplier invoice contains the required tax fields. (4) She flags invalid documents for return. (5) She records the treatment for unusual items. • Proof it happened: correct tax coding applied with document validity checked and unusual treatments recorded. • Where it usually breaks: tax is coded by habit rather than by the transaction, so imports and related party items are treated incorrectly. | • Check the tax treatment of imports, reverse charge and related party transactions specifically, since habitual coding gets these wrong and the error repeats every period. • Reject invoices missing required tax fields rather than coding around them, as the recovery is lost anyway. • Record the treatment decision for unusual items, so coding is consistent between periods. • Escalate uncertain treatments rather than guessing. • Report the value of unrecoverable tax, as this is a real avoidable cost.
839 | Finance | Prepare VAT input, output and exception schedules | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Prepare VAT input, output and exception schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Prepare VAT input, output and exception schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the input, output and exception schedules for the tax return. • Starts when: at each tax period. • How it runs: (1) she extracts the input and output tax by category. (2) She reconciles them to the ledger accounts. (3) She lists the exceptions and non recoverable items. (4) She explains any difference. (5) She submits the schedules for review. • Proof it happened: input, output and exception schedules reconciled to the ledger with differences explained. • Where it usually breaks: the schedules are built from an extract that does not tie to the ledger, so the return cannot be supported. | • Reconcile the schedules to the ledger tax accounts before submission, since a return that cannot be tied back to the ledger cannot be defended in a review. • List non recoverable and exception items separately with the reason. • Explain differences rather than adjusting to match, as the adjustment hides the underlying error. • Prepare early enough for review, because deadline pressure is when errors are filed. • Retain the schedules for the statutory period.
840 | Finance | Record fixed-asset additions, transfers, disposals and supporting documents | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Record fixed-asset additions, transfers, disposals and supporting documents” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Record fixed-asset additions, transfers, disposals and supporting documents” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she records asset purchases, transfers and disposals with the documents behind them. • Starts when: an asset is acquired, transferred or disposed of. • How it runs: (1) she records the asset with its cost, date and location. (2) She records the tag number and custodian. (3) She records transfers with acknowledgement. (4) She records disposals with the approval and proceeds. (5) She files the supporting documents. • Proof it happened: recorded asset additions, transfers and disposals with approvals, proceeds and supporting documents. • Where it usually breaks: disposals are recorded without approval or proceeds evidence, which is a straightforward route for assets to leave unaccounted. | • Require approval and evidence of proceeds for every disposal, since unapproved disposal with no proceeds record is a direct route for assets to leave the company. • Record the location and custodian, otherwise physical verification is impossible. • Require acknowledgement for transfers between custodians or locations. • Capitalise in line with the policy threshold, and check items are not expensed to avoid the register. • File the purchase invoice with the asset record, as this supports both cost and warranty.
841 | Finance | Post depreciation and fixed-asset reconciliation entries | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Post depreciation and fixed-asset reconciliation entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Post depreciation and fixed-asset reconciliation entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she posts the depreciation and reconciles the asset register to the ledger. • Starts when: at each close. • How it runs: (1) she runs the depreciation calculation. (2) She checks it against the policy and the asset lives. (3) She posts the depreciation entry. (4) She reconciles the register to the ledger. (5) She investigates and explains differences. • Proof it happened: posted depreciation with the register reconciled to the ledger and differences explained. • Where it usually breaks: the register and the ledger drift apart, so the reported asset value cannot be supported by the detail. | • Reconcile the register to the ledger every period, since drift between them leaves the reported asset value unsupported by any detail. • Check depreciation is applied from the correct in service date, not the purchase date. • Check fully depreciated assets are still in use, as these indicate either wrong lives or missing disposals. • Review asset lives periodically against actual usage. • Investigate differences rather than adjusting the ledger to the register or the reverse.
842 | Finance | Reconcile GRN, inventory, advance and deposit clearing accounts | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Reconcile GRN, inventory, advance and deposit clearing accounts” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Reconcile GRN, inventory, advance and deposit clearing accounts” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she reconciles the accounts that hold goods received, inventory, advances and deposits temporarily. • Starts when: at each close. • How it runs: (1) she prepares the schedule for each clearing account. (2) She matches the items within it. (3) She identifies unmatched and aged items. (4) She clears what can be cleared. (5) She reports the remaining balance with reasons. • Proof it happened: clearing account reconciliations with items matched, aged and the remaining balance explained. • Where it usually breaks: the goods received clearing account grows continuously, so unmatched receipts and invoices offset each other invisibly. | • Require the goods received clearing account to be cleared to near zero each period, since a growing balance means unmatched receipts and invoices are offsetting each other invisibly. • Age the items within each clearing account, as an old item in a small net balance is still an error. • Investigate both sides of the balance, because offsetting errors cancel in the total. • Assign an owner to each clearing account. • Escalate clearing balances that do not reduce, as these indicate a process fault.
843 | Finance | Reconcile employee, payroll, loan and advance balances | Accountant | Trigger: When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. Action: The Accountant completes “Reconcile employee, payroll, loan and advance balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a supported ledger entry, tax schedule, asset record and reconciled control-account balance. Control/Handoff: Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When an approved journal, tax transaction, asset event or control-account reconciliation requires posting. | The Accountant completes “Reconcile employee, payroll, loan and advance balances” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a supported ledger entry, tax schedule, asset record and reconciled control-account balance. | Manual journals and corrections require review; unsupported tax, asset, clearing or employee balances remain open and escalate to the Senior Accountant. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she reconciles the employee, payroll, loan and advance balances. • Starts when: at each close. • How it runs: (1) she prepares the schedule of balances per employee. (2) She agrees the total to the ledger. (3) She checks recovery is being deducted as scheduled. (4) She identifies leavers with outstanding balances. (5) She reports the position. • Proof it happened: reconciled employee balances agreeing to the ledger with recovery verified and leaver balances flagged. • Where it usually breaks: leavers with outstanding advances are only identified after the final settlement is paid, so recovery is impossible. | • Flag leavers with outstanding balances before the final settlement is released, since recovery after the person has been paid and left is effectively impossible. • Check the payroll deduction is actually running for every advance, as deductions are frequently set up and then lapse. • Reconcile per employee rather than only in total, because offsetting balances hide problems. • Report the total advances outstanding, as this is effectively unsecured lending. • Require written employee authorisation for every deduction.
844 | Finance | Validate payroll source files and approved employee master-data changes | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Validate payroll source files and approved employee master-data changes” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Validate payroll source files and approved employee master-data changes” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she checks the payroll source files and the approved employee master data changes. • Starts when: payroll inputs are received. • How it runs: (1) she checks the handover is approved and complete. (2) She checks each master data change has authorisation. (3) She reconciles the employee list to the previous period. (4) She checks the bank details against the authorised records. (5) She flags discrepancies before processing. • Proof it happened: validated payroll source files with authorised master data changes and the employee list reconciled. • Where it usually breaks: bank detail changes are accepted by email, so salary can be diverted with no verification at all. | • Require employee bank detail changes to be verified independently and approved, since accepting them by email allows salary to be diverted with no check at all. • Reconcile the employee list period on period, so unauthorised additions are visible. • Check for duplicate bank details across employees, as this is a payroll fraud indicator. • Require every master data change to carry authorisation evidence. • Prohibit the person maintaining employee records from also releasing the payment.
845 | Finance | Post payroll, WPS, benefit, deduction and employer-cost entries | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Post payroll, WPS, benefit, deduction and employer-cost entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Post payroll, WPS, benefit, deduction and employer-cost entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she posts the payroll entries including deductions and the employer's own costs. • Starts when: payroll is approved. • How it runs: (1) she posts the gross pay and the deductions. (2) She posts the employer cost elements. (3) She posts the net payable and the statutory liabilities. (4) She allocates the cost to projects and departments. (5) She reconciles the posting to the approved payroll. • Proof it happened: posted payroll entries reconciled to the approved payroll with cost allocated correctly. • Where it usually breaks: payroll cost is posted to departments only, so project labour cost is understated and project margins look better than they are. | • Allocate payroll cost to projects where the work was performed, since posting only to departments understates project labour and makes margins look better than they are. • Reconcile the posting to the approved payroll total before release. • Post the employer cost elements in the same period, as omitting them understates cost. • Post statutory liabilities to their own accounts so payment obligations are visible. • Restrict access to payroll postings, given the confidentiality involved.
846 | Finance | Record end-of-service and employee final-settlement transactions | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Record end-of-service and employee final-settlement transactions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Record end-of-service and employee final-settlement transactions” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she records the end of service and final settlement transactions for leavers. • Starts when: a settlement is approved. • How it runs: (1) she posts the settlement components. (2) She posts the recoveries and deductions. (3) She releases the end of service provision where held. (4) She records the payment. (5) She reconciles the provision movement. • Proof it happened: posted settlement transactions with recoveries applied and the provision movement reconciled. • Where it usually breaks: the settlement is posted without releasing the provision, so the cost is charged twice. | • Release the end of service provision when the settlement is posted, since failing to release it charges the cost twice and overstates the liability. • Apply all recoveries and deductions before payment, as recovery afterwards is impossible. • Reconcile the provision movement each period, so the balance always reflects actual liability. • Require the clearance check to be complete before the payment is posted. • Retain the employee's acknowledgement of the settlement.
847 | Finance | Prepare monthly ledger, balance-sheet and expense schedules | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Prepare monthly ledger, balance-sheet and expense schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Prepare monthly ledger, balance-sheet and expense schedules” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the monthly ledger, balance sheet and expense schedules. • Starts when: at each close. • How it runs: (1) she prepares the schedules for each significant balance. (2) She agrees each to the ledger. (3) She prepares the expense analysis. (4) She identifies unusual movements. (5) She submits the schedules for review. • Proof it happened: monthly ledger, balance sheet and expense schedules agreeing to the ledger with unusual movements identified. • Where it usually breaks: schedules are rolled forward from the previous month with only the totals updated, so errors are carried forward indefinitely. | • Rebuild the schedules from source records rather than rolling forward and updating totals, since a rolled forward schedule carries its errors indefinitely. • Require each schedule to agree to the ledger and to be itemised. • Flag unusual movements for explanation rather than only presenting the balances. • Compare each balance to the prior period and explain significant changes. • Submit for review rather than filing directly.
848 | Finance | Complete assigned month-end close tasks and correction entries | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Complete assigned month-end close tasks and correction entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Complete assigned month-end close tasks and correction entries” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she completes her allocated close tasks and posts the corrections needed. • Starts when: at the period cut off. • How it runs: (1) she works through her allocated checklist items. (2) She completes each with its evidence. (3) She posts the correction entries identified. (4) She confirms completion to the Senior Accountant. (5) She reports anything she cannot resolve. • Proof it happened: completed close tasks with evidence, corrections posted and completion confirmed. • Where it usually breaks: tasks are reported complete when they are only started, so the close is approved on an incorrect basis. | • Require evidence with every completion confirmation, since a task reported complete but only started means the close is approved on a false basis. • Report items that cannot be resolved rather than leaving them appearing complete. • Require correction entries to be approved, not posted silently. • Track the number of post close corrections, as this measures the quality of the close. • Escalate blocking items immediately rather than at the deadline.
849 | Finance | Prepare documents and schedules requested for audit or management review | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Prepare documents and schedules requested for audit or management review” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Prepare documents and schedules requested for audit or management review” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she prepares the documents and schedules the auditors or management ask for. • Starts when: a request is received from audit or management. • How it runs: (1) she clarifies exactly what is required. (2) She prepares the schedule or retrieves the documents. (3) She checks the information agrees to the ledger. (4) She submits it through the single coordination point. (5) She records what was provided. • Proof it happened: prepared schedules and documents agreeing to the ledger, submitted through the coordination point and recorded. • Where it usually breaks: the same question is answered differently by two people, which raises doubts about the whole set of records. | • Route every audit request through a single coordination point, since two people answering the same question differently casts doubt on all the records. • Check the information agrees to the ledger before submitting, as inconsistencies generate further requests. • Record what was provided and when, because the same items are requested again. • Clarify the request before preparing, to avoid producing the wrong analysis. • Escalate requests that suggest a control weakness rather than only answering them.
850 | Finance | Archive Finance records, approvals, returns and bank evidence by retention rule | Accountant | Trigger: When the payroll posting, month-end, audit request or document-retention activity becomes due. Action: The Accountant completes “Archive Finance records, approvals, returns and bank evidence by retention rule” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. Output/Evidence: a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. Control/Handoff: The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. Continuity/Escalation: A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. Timing: To be confirmed. | When the payroll posting, month-end, audit request or document-retention activity becomes due. | The Accountant completes “Archive Finance records, approvals, returns and bank evidence by retention rule” using approved contracts, certifications, HR/department inputs, FirstBit and controlled Finance records. | a posted payroll/settlement, completed close schedule, audit file or controlled Finance archive. | The Accountant follows the closing checklist and retention rules; unresolved differences or missing documents are reported before period closure. | A trained Accountant may provide transactional backup with controlled access; posting approval, payment authority and material correction remain with the Senior Accountant or CFO. | To be confirmed. | • In plain words: she archives the finance records according to how long each type must be kept. • Starts when: records become inactive, and at the archiving cycle. • How it runs: (1) she identifies the records to be archived. (2) She applies the retention period per record type. (3) She checks for any legal hold before disposal. (4) She archives with an index. (5) She verifies the archive is retrievable. • Proof it happened: archived finance records with retention applied, legal holds checked and retrievability verified. • Where it usually breaks: records are disposed of on schedule without checking for a legal hold, which is a serious exposure. | • Check for a legal hold before every disposal, since destroying records under hold is a severe exposure regardless of the retention schedule. • Retain tax and statutory records for the full legal period, not the convenient one. • Index the archive, as unindexed records cannot be retrieved when an authority or auditor asks. • Verify retrievability by actually retrieving samples, because an archive that cannot be opened is not an archive. • Require approval and a record for every disposal.
851 | Marketing & Sales | Set Marketing & Sales strategy, policies and annual operating objectives | Chief Marketing Officer (CMO) | Trigger: When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. Action: The Chief Marketing Officer (CMO) completes “Set Marketing & Sales strategy, policies and annual operating objectives” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. Control/Handoff: The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. | The Chief Marketing Officer (CMO) completes “Set Marketing & Sales strategy, policies and annual operating objectives” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. | The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how the company wins work for the year, what it is aiming for and the rules the sales team must follow. • Starts when: the annual planning cycle opens, or the market changes enough that the current approach stops working. • How it runs: (1) he reviews the market, the pipeline and what the business plan requires in revenue. (2) He sets the sales and marketing objectives for the year. (3) He drafts or updates the policies covering conduct, pricing boundaries and client engagement. (4) He obtains the CEO's approval. (5) He issues it to the team and the departments who depend on the pipeline. • Proof it happened: an approved marketing and sales strategy with annual objectives and policies, issued to the business. • Where it usually breaks: the revenue target is set without checking the company can actually deliver that volume of work. | • Require the revenue target to be tested against delivery and technical capacity before approval, since selling more than the company can build destroys margin and reputation. • Set measurable objectives: qualified leads, conversion rate, win rate and sales cycle length. Objectives without measures cannot be reviewed. • State the policy review frequency and who may approve an exception, so exceptions are decided rather than assumed. • Issue the conduct and pricing boundaries to everyone client facing, not only to the sales team. • Link the strategy to the delegation of authority, so what may be promised to a client is defined alongside the targets.
852 | Marketing & Sales | Define priority services, sectors, project types, markets and client segments | Chief Marketing Officer (CMO) | Trigger: When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. Action: The Chief Marketing Officer (CMO) completes “Define priority services, sectors, project types, markets and client segments” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. Control/Handoff: The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. | The Chief Marketing Officer (CMO) completes “Define priority services, sectors, project types, markets and client segments” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. | The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides which services, sectors and types of client the company will actively chase. • Starts when: at strategy setting, and when market conditions or capability change. • How it runs: (1) he reviews where the company wins and where it loses money. (2) He assesses the market size and competition per sector. (3) He matches the target segments to the company's actual capability. (4) He sets the priority order. (5) He communicates it so effort is not spread thin. • Proof it happened: defined priority services, sectors, project types and client segments with the basis recorded. • Where it usually breaks: everything is a target, so the team chases every enquiry and wins the ones the company is worst at delivering. | • Base the priorities on where the company actually makes margin rather than on where revenue is largest, since chasing unprofitable sectors is worse than not chasing at all. • State explicitly which segments will not be pursued, as this is what protects focus. • Test the priorities against delivery capability, because winning work the company cannot deliver well destroys the reference value. • Review the priorities annually against win rate and realised margin by segment. • Require deviations from the priority list to be approved, so opportunistic bidding is a decision.
853 | Marketing & Sales | Approve company brand positioning, value proposition and core market messages | Chief Marketing Officer (CMO) | Trigger: When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. Action: The Chief Marketing Officer (CMO) completes “Approve company brand positioning, value proposition and core market messages” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. Control/Handoff: The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. | The Chief Marketing Officer (CMO) completes “Approve company brand positioning, value proposition and core market messages” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. | The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves how the company presents itself and what it claims it is good at. • Starts when: the brand position is set, and when it needs revising. • How it runs: (1) he defines the positioning and what differentiates the company. (2) He defines the value proposition per target segment. (3) He approves the core messages and the claims made. (4) He checks the claims are defensible. (5) He issues the messaging for consistent use. • Proof it happened: approved brand positioning, value proposition and core messages issued for consistent use. • Where it usually breaks: the positioning claims capability the company does not have, so client expectations are set that delivery cannot meet. | • Require every capability claim to be verifiable and agreed with the delivery functions, since claims delivery cannot meet create disputes on the first project. • Check claims for legal and advertising compliance before use, particularly comparative statements. • Require the messaging to be used consistently, as inconsistent positioning across channels undermines credibility. • Review the positioning when the company's capability changes. • Prohibit individuals inventing their own claims in client presentations.
854 | Marketing & Sales | Approve sales governance, Delegation of Authority and ethical-conduct controls | Chief Marketing Officer (CMO) | Trigger: When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. Action: The Chief Marketing Officer (CMO) completes “Approve sales governance, Delegation of Authority and ethical-conduct controls” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. Control/Handoff: The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. | The Chief Marketing Officer (CMO) completes “Approve sales governance, Delegation of Authority and ethical-conduct controls” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. | The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets who may commit the company to a client, up to what value, and how the team must behave. • Starts when: the framework is established, and when roles or limits change. • How it runs: (1) he maps the commitments the sales function can make. (2) He sets the authority limits for price, discount and terms. (3) He sets the conduct rules on gifts, entertainment and client relationships. (4) He obtains approval. (5) He issues it and briefs everyone client facing. • Proof it happened: an approved sales authority matrix and conduct rules, issued and acknowledged by everyone client facing. • Where it usually breaks: a salesperson promises a price or a deadline outside their authority, and the company is held to it commercially. | • State plainly that no price, discount, deadline or term may be communicated to a client without approval, including indicatively, since clients treat any figure given as a commitment. • Set the discount authority by percentage and by value, so both are controlled. • Require acknowledgement of the conduct rules by everyone client facing, because enforcement needs evidence of issue. • Require declaration of any personal relationship with a client contact. • Report commitments made outside authority as exceptions, as the pattern indicates where the limits are wrong.
855 | Marketing & Sales | Approve CRM ownership, data standards, stage definitions and access controls | Chief Marketing Officer (CMO) | Trigger: When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. Action: The Chief Marketing Officer (CMO) completes “Approve CRM ownership, data standards, stage definitions and access controls” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. Control/Handoff: The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, strategy review, policy update or material brand/control issue requires direction. | The Chief Marketing Officer (CMO) completes “Approve CRM ownership, data standards, stage definitions and access controls” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Marketing & Sales strategy, brand decision, governance rule, CRM standard or authority control. | The CMO protects role boundaries: CTO controls technical quotation approval, CLO controls client contracts and Finance controls credit, invoicing and payment activation; reserved matters escalate to the CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides who owns the CRM data, what must be recorded and who can see it. • Starts when: the CRM is established, and when the process or team changes. • How it runs: (1) he defines the mandatory fields per record type. (2) He defines the pipeline stages and what each means. (3) He assigns data ownership. (4) He sets the access permissions. (5) He issues the standards and monitors compliance. • Proof it happened: approved CRM data standards with stage definitions, ownership and access controls applied. • Where it usually breaks: stage definitions are vague, so every salesperson interprets them differently and the pipeline figure means nothing. | • Define each pipeline stage by an objective test such as a submitted proposal or a client confirmation, since subjective stages make the pipeline figure meaningless. • Require the mandatory fields to be completed before a stage advance, so data quality is enforced rather than requested. • State that the CRM is the company's record and client contacts may not be held only personally. • Set access permissions by role, as client and pricing data is commercially sensitive. • Report data quality by owner, because an incomplete CRM makes every forecast unreliable.
856 | Marketing & Sales | Approve annual revenue, qualified-lead, pipeline and conversion targets | Chief Marketing Officer (CMO) | Trigger: When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. Action: The Chief Marketing Officer (CMO) completes “Approve annual revenue, qualified-lead, pipeline and conversion targets” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. Control/Handoff: Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. | The Chief Marketing Officer (CMO) completes “Approve annual revenue, qualified-lead, pipeline and conversion targets” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. | Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the targets for revenue, leads, pipeline and conversion for the year. • Starts when: during annual planning. • How it runs: (1) he works back from the revenue target to the pipeline needed. (2) He applies realistic conversion rates. (3) He sets the lead generation target that supports it. (4) He tests the targets against capacity. (5) He obtains approval and issues the targets. • Proof it happened: approved revenue, lead, pipeline and conversion targets derived from each other and tested against capacity. • Where it usually breaks: the revenue target is set first and the lead target is never derived from it, so the pipeline is structurally too small all year. | • Derive the lead and pipeline targets from the revenue target using actual conversion rates, since a revenue target with no matching pipeline target cannot be achieved. • Use the company's own historical conversion and cycle length rather than assumptions. • Test the target against delivery capacity, because unachievable delivery makes the revenue worthless. • Break the targets down by period, so shortfall is visible early rather than at year end. • Review the targets mid year formally rather than allowing them to drift.
857 | Marketing & Sales | Approve target-account, key-account and relationship-development strategy | Chief Marketing Officer (CMO) | Trigger: When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. Action: The Chief Marketing Officer (CMO) completes “Approve target-account, key-account and relationship-development strategy” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. Control/Handoff: Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. | The Chief Marketing Officer (CMO) completes “Approve target-account, key-account and relationship-development strategy” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. | Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides which clients to invest relationship effort in and how. • Starts when: at strategy setting, and when the client portfolio changes. • How it runs: (1) he identifies the accounts with the greatest potential. (2) He sets the relationship plan per key account. (3) He assigns relationship owners. (4) He sets the contact frequency and the objectives. (5) He reviews progress against the plans. • Proof it happened: approved target and key account strategies with named relationship owners and objectives. • Where it usually breaks: key accounts are named but no relationship activity is planned, so contact only happens when there is a tender. | • Require planned relationship activity independent of live tenders, since contact only at tender time is transactional and wins nothing. • Name a single relationship owner per account, as shared ownership means nobody maintains it. • Require the relationship to extend beyond one contact, because a single relationship is lost when that person moves. • Define what key account means by revenue, potential and strategic value. • Review account health rather than only activity, as activity without progress is not relationship building.
858 | Marketing & Sales | Approve the annual marketing budget and channel allocation | Chief Marketing Officer (CMO) | Trigger: When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. Action: The Chief Marketing Officer (CMO) completes “Approve the annual marketing budget and channel allocation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. Control/Handoff: Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. | The Chief Marketing Officer (CMO) completes “Approve the annual marketing budget and channel allocation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. | Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves how much is spent on marketing and where it goes. • Starts when: during annual budgeting, and when reallocation is needed. • How it runs: (1) he identifies the marketing activity needed to support the targets. (2) He allocates the budget by channel and activity. (3) He states the expected outcome per allocation. (4) He obtains approval. (5) He tracks spend and outcome against the allocation. • Proof it happened: an approved marketing budget allocated by channel with expected outcomes stated and spend tracked. • Where it usually breaks: spend is allocated by habit to the same channels, with no measurement of what any of them actually produced. | • Require the expected outcome to be stated per allocation and measured afterwards, since allocation by habit continues funding channels that produce nothing. • Require lead source to be captured, or channel performance cannot be assessed at all. • Reallocate during the year based on measured performance rather than waiting for the next cycle. • Separate brand spend from lead generation spend, as these are measured differently. • Report cost per qualified lead by channel.
859 | Marketing & Sales | Approve campaign, event, partnership, referral and business-development plans | Chief Marketing Officer (CMO) | Trigger: When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. Action: The Chief Marketing Officer (CMO) completes “Approve campaign, event, partnership, referral and business-development plans” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. Control/Handoff: Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. | The Chief Marketing Officer (CMO) completes “Approve campaign, event, partnership, referral and business-development plans” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. | Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the campaigns, events, partnerships and referral activity. • Starts when: an activity is proposed. • How it runs: (1) he reviews the proposal and its objective. (2) He checks the cost against the expected return. (3) He checks the target audience matches the priority segments. (4) He approves within his authority or escalates. (5) He requires the outcome to be measured and reported. • Proof it happened: approved activity plans with objectives, costs and the measured outcome reported afterwards. • Where it usually breaks: events and campaigns are run and never evaluated, so the same ineffective activity repeats every year. | • Require a post activity evaluation against the stated objective, since unevaluated campaigns and events repeat every year regardless of whether they work. • Require the leads generated to be captured and tracked through to outcome, not just counted. • Check the audience matches the priority segments before approving. • Require referral and partnership arrangements to be reviewed by Legal, as these can create obligations and bribery exposure. • Set a minimum expected return for activity above a cost threshold.
860 | Marketing & Sales | Align sales targets and opportunity priorities with technical, delivery and financial capacity | Chief Marketing Officer (CMO) | Trigger: When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. Action: The Chief Marketing Officer (CMO) completes “Align sales targets and opportunity priorities with technical, delivery and financial capacity” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. Control/Handoff: Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual/quarterly plan, budget, campaign cycle or capacity review becomes due. | The Chief Marketing Officer (CMO) completes “Align sales targets and opportunity priorities with technical, delivery and financial capacity” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | approved revenue and pipeline targets, account priorities, marketing budget, campaign plan and capacity alignment. | Targets must be supported by market evidence and aligned with technical, project-delivery and cash capacity; material resource or budget conflicts escalate to the CEO, CTO, COO or CFO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he checks with the delivery and finance teams that the work being chased can actually be done and funded. • Starts when: at the pipeline review, and before major bid decisions. • How it runs: (1) he reviews the pipeline against technical capability. (2) He reviews it against delivery capacity and timing. (3) He reviews the cash implications with the CFO. (4) He reprioritises where capacity is exceeded. (5) He records the agreed priorities. • Proof it happened: a documented alignment review with technical, delivery and financial capacity assessed and priorities agreed. • Where it usually breaks: sales continues chasing everything, so the company wins more than it can staff and delivery fails on several projects at once. | • Require the pipeline to be reviewed against actual staffed capacity, since winning more than the company can deliver damages several projects at once. • Include the cash requirement of new work in the review, as growth consumes working capital before it produces it. • Require the COO and CFO to participate, not just receive the pipeline. • Deprioritise explicitly rather than pursuing everything at reduced effort. • Record the agreed priorities so bid decisions follow them.
861 | Marketing & Sales | Approve lead-scoring, qualification and opportunity-priority rules | Chief Marketing Officer (CMO) | Trigger: When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. Action: The Chief Marketing Officer (CMO) completes “Approve lead-scoring, qualification and opportunity-priority rules” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. Control/Handoff: No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. | The Chief Marketing Officer (CMO) completes “Approve lead-scoring, qualification and opportunity-priority rules” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. | No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the rules for deciding which leads are worth pursuing and in what order. • Starts when: the qualification framework is established or revised. • How it runs: (1) he defines the qualification criteria. (2) He sets the scoring approach. (3) He defines what makes an opportunity high priority. (4) He sets the disqualification grounds. (5) He issues the rules and monitors their use. • Proof it happened: approved lead scoring and qualification rules with priority definitions, issued and applied. • Where it usually breaks: qualification is subjective, so unfunded and unwinnable enquiries consume the most expensive technical time in the company. | • Require budget confirmation and decision authority to be established before technical resource is committed, since unfunded enquiries consume the most expensive time in the company. • Define the disqualification grounds explicitly, so declining an enquiry is a normal action rather than a failure. • Score against stated criteria rather than enthusiasm, as subjective qualification fills the pipeline with noise. • Require requalification when an opportunity stalls. • Report the volume of disqualified enquiries, because this shows the filter is working.
862 | Marketing & Sales | Make Go, Hold or No-Go decisions for major opportunities | Chief Marketing Officer (CMO) | Trigger: When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. Action: The Chief Marketing Officer (CMO) completes “Make Go, Hold or No-Go decisions for major opportunities” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. Control/Handoff: No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. | The Chief Marketing Officer (CMO) completes “Make Go, Hold or No-Go decisions for major opportunities” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. | No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: for big opportunities he decides whether the company pursues, waits or declines. • Starts when: a major opportunity reaches the decision point. • How it runs: (1) he reviews the client, the scope and the competitive position. (2) He reviews the capability and capacity to deliver. (3) He reviews the commercial and contractual risk. (4) He decides go, hold or no go with the reasons. (5) He records the decision and communicates it. • Proof it happened: a recorded go, hold or no go decision with the assessment and reasons stated. • Where it usually breaks: no go is treated as a failure, so the company bids everything and wins the worst work at the thinnest margin. | • State that a no go is a valid and valuable outcome, since treating it as failure means the company bids everything and wins the worst work. • Require the assessment to cover client payment history and contractual risk, not only the opportunity value. • Record the reasons, so the decision quality can be reviewed against outcomes. • Require the delivery and finance functions to input before a go decision. • Track the win rate on go decisions, as a low rate means the filter is too loose.
863 | Marketing & Sales | Approve tender and bid participation decisions | Chief Marketing Officer (CMO) | Trigger: When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. Action: The Chief Marketing Officer (CMO) completes “Approve tender and bid participation decisions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. Control/Handoff: No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. | The Chief Marketing Officer (CMO) completes “Approve tender and bid participation decisions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. | No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves whether the company submits a tender and on what basis. • Starts when: a tender invitation is received and a decision is needed. • How it runs: (1) he reviews the tender requirements and conditions. (2) He reviews the resource cost of bidding. (3) He reviews the legal and commercial risk flagged. (4) He decides to bid or decline. (5) He records the decision and assigns the bid owner. • Proof it happened: a recorded tender participation decision with the requirements, cost of bidding and risks assessed. • Where it usually breaks: the decision is made without Legal having reviewed the conditions, so the company bids on terms it should have declined. | • Require the legal review of tender conditions before the bid decision, since terms serious enough to decline are otherwise discovered after the company is committed. • Include the cost of bidding in the decision, as bid preparation is a significant unrecovered cost. • Check the realistic probability of winning, because bidding to make up numbers wastes the same effort as bidding to win. • Assign a named bid owner at the decision point. • Track bid cost against win rate by client, as some clients are systematically not worth bidding to.
864 | Marketing & Sales | Approve strategic-client, credit or commercial exceptions through the required authority route | Chief Marketing Officer (CMO) | Trigger: When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. Action: The Chief Marketing Officer (CMO) completes “Approve strategic-client, credit or commercial exceptions through the required authority route” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. Control/Handoff: No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. | The Chief Marketing Officer (CMO) completes “Approve strategic-client, credit or commercial exceptions through the required authority route” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. | No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when a strategic client needs an exception on credit or commercial terms, he takes it through the proper route. • Starts when: an exception is requested for a client. • How it runs: (1) he establishes what exception is being sought and why. (2) He obtains the CFO's view on credit exposure. (3) He obtains the CLO's view on contractual risk. (4) He submits it to the required authority. (5) He records the decision and any conditions. • Proof it happened: an approved exception with credit and legal input, at the correct authority level, with conditions recorded. • Where it usually breaks: exceptions are granted informally to close a deal, so the company carries credit and contractual risk nobody assessed. | • Prohibit informal exceptions entirely, since an exception granted to close a deal leaves the company carrying risk nobody assessed or approved. • Require CFO credit input for every payment or credit exception. • Require CLO input for every contractual exception. • Record the conditions and a review date, so the exception does not become permanent. • Report the aggregate exposure created by open exceptions.
865 | Marketing & Sales | Approve qualified lead handover to Technical Engineering | Chief Marketing Officer (CMO) | Trigger: When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. Action: The Chief Marketing Officer (CMO) completes “Approve qualified lead handover to Technical Engineering” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. Control/Handoff: No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a major lead, tender invitation, bid request, credit concern or technical handover reaches the decision gate. | The Chief Marketing Officer (CMO) completes “Approve qualified lead handover to Technical Engineering” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved Go/Hold/No-Go, bid decision, strategic exception or qualified technical handover. | No technical effort or bid commitment is released without a complete lead record, strategic fit and authority decision; pricing and technical feasibility remain with CTO and financial exceptions with CFO/CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves handing a qualified lead over to engineering to work on. • Starts when: a lead is qualified and needs technical input. • How it runs: (1) he confirms the lead meets the qualification criteria. (2) He confirms the client requirement is documented. (3) He confirms the effort required is justified. (4) He approves the handover. (5) He confirms engineering has accepted it. • Proof it happened: an approved handover with the qualification confirmed and the client requirement documented. • Where it usually breaks: leads are handed over with the requirement described verbally, so engineering designs against a moving brief. | • Require the client requirement to be documented before handover, since a verbal brief means engineering designs against something that changes with every conversation. • Require confirmation of budget and decision authority before committing technical effort. • Require engineering to accept the handover, so the effort is planned rather than imposed. • Define what a complete handover contains as a checklist. • Track technical effort spent on lost opportunities, as this is a real and usually invisible cost.
866 | Marketing & Sales | Approve release of CTO-approved quotations and proposals to clients | Chief Marketing Officer (CMO) | Trigger: When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. Action: The Chief Marketing Officer (CMO) completes “Approve release of CTO-approved quotations and proposals to clients” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. Control/Handoff: Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. | The Chief Marketing Officer (CMO) completes “Approve release of CTO-approved quotations and proposals to clients” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. | Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the quotations and proposals going out to clients once engineering has signed off the technical content. • Starts when: a quotation is technically approved and ready for release. • How it runs: (1) he confirms the technical approval is in place. (2) He confirms the commercial terms and margin are approved. (3) He checks the validity period and the assumptions. (4) He approves release. (5) He records the version issued. • Proof it happened: an approved and released quotation with technical and commercial approvals and the version recorded. • Where it usually breaks: a version is sent that differs from the approved one, so the company is bound to terms nobody signed off. | • Check the document being sent against the approved version immediately before release, since sending an unapproved version binds the company to terms nobody agreed. • Record the version issued and withdraw superseded versions explicitly, as a client holding two versions will sign the favourable one. • Require the assumptions and exclusions to be stated in the proposal, otherwise they are not part of the offer. • State the validity period, as an open ended offer exposes the company to cost movement. • Issue in a non editable format.
867 | Marketing & Sales | Approve client-facing discount, clarification and negotiation boundaries | Chief Marketing Officer (CMO) | Trigger: When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. Action: The Chief Marketing Officer (CMO) completes “Approve client-facing discount, clarification and negotiation boundaries” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. Control/Handoff: Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. | The Chief Marketing Officer (CMO) completes “Approve client-facing discount, clarification and negotiation boundaries” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. | Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets how far the team may go on discounts and negotiation before they must ask. • Starts when: a negotiation is being prepared or a discount is requested. • How it runs: (1) he sets the discount limit per authority level. (2) He sets the boundaries on scope, programme and payment terms. (3) He states what may never be conceded without approval. (4) He briefs the negotiator. (5) He records the approved boundaries. • Proof it happened: approved negotiation boundaries covering discount, scope, programme and payment terms, briefed and recorded. • Where it usually breaks: only the price limit is set, so concessions are made on programme and payment terms instead, which cost more. | • Set boundaries on scope, programme and payment terms as well as price, since concessions migrate to whatever is left uncontrolled and those often cost more. • State the terms that may never be conceded without CLO and CFO approval. • Require every concession to be recorded and carried into the contract, otherwise it is granted twice. • Brief the negotiator in writing, so the boundaries are not misremembered in the room. • Report concessions granted by client, as the pattern shows where the company is being tested.
868 | Marketing & Sales | Lead senior client presentations, relationship meetings and negotiations | Chief Marketing Officer (CMO) | Trigger: When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. Action: The Chief Marketing Officer (CMO) completes “Lead senior client presentations, relationship meetings and negotiations” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. Control/Handoff: Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. | The Chief Marketing Officer (CMO) completes “Lead senior client presentations, relationship meetings and negotiations” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. | Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he leads the important client meetings and negotiations himself. • Starts when: a senior client meeting or negotiation is arranged. • How it runs: (1) he prepares with the bid and delivery teams. (2) He confirms the approved position and boundaries. (3) He leads the meeting or negotiation. (4) He records what was discussed and agreed. (5) He confirms agreed points in writing to the client. • Proof it happened: meeting records with the position taken, points agreed and written confirmation issued to the client. • Where it usually breaks: what was agreed verbally is never confirmed in writing, so each side remembers a different outcome. | • Confirm every agreed point to the client in writing the same day, since verbal agreements are remembered differently by each side and the client's version usually prevails. • Require preparation with the delivery team, as commitments made without them are the ones that fail. • Take an internal record of what was discussed, not only what was agreed. • Confirm the approved boundaries before the meeting rather than judging in the room. • Require any commitment beyond authority to be stated as subject to approval.
869 | Marketing & Sales | Approve changes to client requirements or commitments before downstream handover | Chief Marketing Officer (CMO) | Trigger: When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. Action: The Chief Marketing Officer (CMO) completes “Approve changes to client requirements or commitments before downstream handover” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. Control/Handoff: Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. | The Chief Marketing Officer (CMO) completes “Approve changes to client requirements or commitments before downstream handover” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. | Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when the client changes what they want, he approves the change before it goes to delivery. • Starts when: a client changes a requirement or a commitment before handover. • How it runs: (1) he establishes exactly what has changed. (2) He assesses the effect on price, programme and feasibility. (3) He obtains technical confirmation. (4) He approves or renegotiates. (5) He updates the documented requirement before handover. • Proof it happened: an approved requirement change with the effect assessed and the documentation updated before handover. • Where it usually breaks: the change is accepted verbally and delivery receives the original documentation, so the project starts building the wrong thing. | • Require the documented requirement to be updated before handover, since delivery working from superseded documentation builds the wrong thing at the company's cost. • Require technical confirmation that the change is feasible before accepting it. • Reprice the change rather than absorbing it, as absorbed changes accumulate into a lost margin. • Record the change and the client's acceptance of the revised terms. • Prohibit accepting changes verbally, however minor they appear.
870 | Marketing & Sales | Accept client award evidence and initiate Legal contract finalisation | Chief Marketing Officer (CMO) | Trigger: When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. Action: The Chief Marketing Officer (CMO) completes “Accept client award evidence and initiate Legal contract finalisation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. Control/Handoff: Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When an approved quotation/proposal, client negotiation, requirement change or award decision requires CMO action. | The Chief Marketing Officer (CMO) completes “Accept client award evidence and initiate Legal contract finalisation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a controlled client release, negotiation position, documented requirement decision or contract-finalisation trigger. | Only CTO-approved quotation content is issued, negotiation stays within authority, and client award proceeds to CLO for contract control and Finance for activation. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when the client awards the work he confirms the award and starts the contract process. • Starts when: a client indicates or issues an award. • How it runs: (1) he obtains the award in writing. (2) He compares the award terms against the submitted offer. (3) He identifies any differences. (4) He passes it to Legal for contract finalisation. (5) He records the award and notifies the delivery functions. • Proof it happened: written award evidence compared to the offer, with differences identified and Legal engaged. • Where it usually breaks: the award is accepted as confirmation to start work, so mobilisation happens before the contract terms are settled. | • Compare the client's award against the submitted offer clause by clause, since clients frequently award on their own terms and the difference is only found in a dispute. • Prohibit mobilisation on an award letter alone, and require the legal activation gate to be passed. • Require the award in writing, as a verbal award is not a commitment. • Notify the delivery functions immediately, so planning starts in parallel with contract finalisation. • Record any differences for Legal to resolve rather than assuming they are administrative.
871 | Marketing & Sales | Review the weekly pipeline, probability, value and revenue forecast | Chief Marketing Officer (CMO) | Trigger: When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. Action: The Chief Marketing Officer (CMO) completes “Review the weekly pipeline, probability, value and revenue forecast” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. Control/Handoff: CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. | The Chief Marketing Officer (CMO) completes “Review the weekly pipeline, probability, value and revenue forecast” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. | CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: every week he reviews the pipeline and the revenue it is likely to produce. • Starts when: weekly on the review cycle. • How it runs: (1) he reviews the opportunities by stage and value. (2) He reviews the probability assigned to each. (3) He challenges optimistic probabilities and dates. (4) He calculates the weighted forecast. (5) He directs actions on the key opportunities. • Proof it happened: a weekly pipeline review with stages, values, challenged probabilities and a weighted forecast. • Where it usually breaks: probabilities are set by the owner's optimism, so the forecast is consistently overstated and nobody trusts it. | • Tie probability to objective stage criteria rather than the owner's judgement, since optimism based probability produces a forecast nobody can rely on. • Require the expected close date to be justified, as dates slip silently every week otherwise. • Track forecast accuracy against actual outcomes, because this is what drives honest forecasting. • Review stalled opportunities specifically, as these inflate the pipeline while producing nothing. • Require a next action with a date on every live opportunity.
872 | Marketing & Sales | Review conversion, sales-cycle, win-rate and stalled-opportunity performance | Chief Marketing Officer (CMO) | Trigger: When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. Action: The Chief Marketing Officer (CMO) completes “Review conversion, sales-cycle, win-rate and stalled-opportunity performance” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. Control/Handoff: CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. | The Chief Marketing Officer (CMO) completes “Review conversion, sales-cycle, win-rate and stalled-opportunity performance” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. | CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he reviews how well the company converts opportunities and where they get stuck. • Starts when: at the performance review cycle. • How it runs: (1) he reviews the conversion rate by stage and segment. (2) He reviews the sales cycle length. (3) He reviews the win rate and the loss reasons. (4) He identifies the stalled opportunities and their causes. (5) He directs corrective action. • Proof it happened: a performance review covering conversion, cycle length, win rate and stalled opportunity causes. • Where it usually breaks: losses are all recorded as price, so the company learns nothing and changes nothing. | • Prohibit price as a default loss reason and require the actual cause, since recording every loss as price prevents the company from learning anything at all. • Obtain loss feedback from the client where possible, as the internal explanation is usually wrong. • Analyse conversion by stage to find where opportunities are actually lost. • Review cycle length, because a lengthening cycle predicts a revenue shortfall. • Require stalled opportunities to be closed or reactivated rather than left open indefinitely.
873 | Marketing & Sales | Review campaign, channel, lead-source and marketing-return performance | Chief Marketing Officer (CMO) | Trigger: When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. Action: The Chief Marketing Officer (CMO) completes “Review campaign, channel, lead-source and marketing-return performance” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. Control/Handoff: CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. | The Chief Marketing Officer (CMO) completes “Review campaign, channel, lead-source and marketing-return performance” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. | CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he reviews which marketing activity actually produced business. • Starts when: at the performance review cycle. • How it runs: (1) he reviews the leads generated per channel. (2) He reviews the conversion of those leads. (3) He reviews the cost per qualified lead and per win. (4) He compares channels on return. (5) He reallocates the budget accordingly. • Proof it happened: a channel performance review with leads, conversion, cost per lead and reallocation decisions. • Where it usually breaks: lead source is not captured, so no channel can be evaluated and the budget is allocated on belief. | • Make lead source a mandatory field at creation, since without it no channel can be evaluated and the budget is allocated on belief rather than evidence. • Measure through to won revenue rather than to lead count, as channels producing volume often produce nothing else. • Report cost per qualified lead and cost per win by channel. • Reallocate during the year rather than waiting for the next budget. • Track the time from lead to first contact, because slow response destroys conversion regardless of channel.
874 | Marketing & Sales | Review key-account health, client satisfaction, referrals and repeat-business potential | Chief Marketing Officer (CMO) | Trigger: When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. Action: The Chief Marketing Officer (CMO) completes “Review key-account health, client satisfaction, referrals and repeat-business potential” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. Control/Handoff: CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. | The Chief Marketing Officer (CMO) completes “Review key-account health, client satisfaction, referrals and repeat-business potential” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. | CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he reviews how the important client relationships are actually doing. • Starts when: at the account review cycle. • How it runs: (1) he reviews the activity and outcomes per key account. (2) He reviews client satisfaction and any complaints. (3) He reviews repeat business and referrals. (4) He identifies accounts at risk. (5) He directs relationship actions. • Proof it happened: a key account review with activity, satisfaction, repeat business and at risk accounts identified. • Where it usually breaks: account health is judged from the sales relationship alone, so a client unhappy with delivery looks healthy until they stop calling. | • Assess account health using delivery performance and client satisfaction, not only the sales relationship, since a client unhappy with delivery looks healthy until they simply stop calling. • Require structured client feedback at project completion, as this is the only reliable signal. • Track repeat business rate by client, because this is the real measure of satisfaction. • Identify accounts with declining activity early, as recovery is possible before they are lost. • Involve the delivery functions in the account review.
875 | Marketing & Sales | Resolve material client complaints, pre-contract disputes and reputation risks | Chief Marketing Officer (CMO) | Trigger: When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. Action: The Chief Marketing Officer (CMO) completes “Resolve material client complaints, pre-contract disputes and reputation risks” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. Control/Handoff: CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, client escalation, forecast cutoff or performance exception occurs. | The Chief Marketing Officer (CMO) completes “Resolve material client complaints, pre-contract disputes and reputation risks” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a verified pipeline forecast, performance decision, account action, recovery plan or client-risk resolution. | CRM evidence supports every forecast and decision; stalled, disputed, high-value or reputation-sensitive matters have owners and escalation dates. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he deals with serious client complaints and disputes that arise before a contract is signed. • Starts when: a material complaint, pre contract dispute or reputation risk arises. • How it runs: (1) he establishes the facts. (2) He assesses the commercial and reputational exposure. (3) He takes legal advice where needed. (4) He agrees the response and who delivers it. (5) He records the resolution and the lesson. • Proof it happened: a documented complaint or dispute resolution with the facts, response and outcome recorded. • Where it usually breaks: the complaint is handled by the salesperson who caused it, so the client escalates and the relationship is lost. | • Escalate material complaints away from the person involved, since a client complaint handled by its cause escalates and the relationship is usually lost. • Require the facts to be established before responding, as a defensive first response hardens the position. • Take legal advice before any admission or offer. • Record the root cause and feed it back, because complaints usually indicate a systemic issue. • Set a response timeframe, as delay is what turns a complaint into a dispute.
876 | Marketing & Sales | Approve marketing privacy, consent, copyright, advertising and communication controls | Chief Marketing Officer (CMO) | Trigger: When a compliance review, public statement, absence, access review or improvement need occurs. Action: The Chief Marketing Officer (CMO) completes “Approve marketing privacy, consent, copyright, advertising and communication controls” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. Control/Handoff: Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a compliance review, public statement, absence, access review or improvement need occurs. | The Chief Marketing Officer (CMO) completes “Approve marketing privacy, consent, copyright, advertising and communication controls” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. | Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the controls on privacy, consent, copyright and what the company may claim in its advertising. • Starts when: the framework is set, and when law or practice changes. • How it runs: (1) he identifies the applicable privacy and advertising obligations. (2) He sets the consent requirements for marketing contact. (3) He sets the rules on using client names, images and third party content. (4) He obtains CLO review. (5) He issues the controls and monitors compliance. • Proof it happened: approved privacy, consent, copyright and advertising controls with legal review, issued to the team. • Where it usually breaks: client project photographs and names are used without permission, which most construction contracts actually prohibit. | • Require written client permission before using any project image, name or reference, since most construction contracts prohibit this and breach damages the relationship immediately. • Require consent evidence for marketing contact, as unconsented contact is both unlawful and damaging. • Require licensing evidence for third party images and content, because infringement claims are expensive and avoidable. • Maintain a register of permissions obtained with their expiry. • Require CLO review of comparative and superlative claims.
877 | Marketing & Sales | Approve crisis, public-statement and reputation-response actions | Chief Marketing Officer (CMO) | Trigger: When a compliance review, public statement, absence, access review or improvement need occurs. Action: The Chief Marketing Officer (CMO) completes “Approve crisis, public-statement and reputation-response actions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. Control/Handoff: Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a compliance review, public statement, absence, access review or improvement need occurs. | The Chief Marketing Officer (CMO) completes “Approve crisis, public-statement and reputation-response actions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. | Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when something goes publicly wrong he controls what the company says and who says it. • Starts when: an incident, allegation or media enquiry creates reputational risk. • How it runs: (1) he establishes the facts with the relevant functions. (2) He takes CLO advice on what may be said. (3) He prepares the statement or the holding position. (4) He confirms the single authorised spokesperson. (5) He records what was issued and monitors the response. • Proof it happened: an approved public statement or holding position with legal review and a named authorised spokesperson. • Where it usually breaks: employees comment individually before any position is agreed, and those comments become the company's official position. | • Name a single authorised spokesperson and instruct everyone else not to comment, since uncontrolled employee comment becomes the company's official position. • Require CLO review before any public statement, as statements made in the first hours create legal exposure. • Prepare holding statements in advance for foreseeable events, because drafting under pressure produces admissions. • Include social media in the instruction, as this is where the first comments appear. • Record what was issued and when, for the investigation record.
878 | Marketing & Sales | Approve Marketing & Sales access, delegation, backup and continuity arrangements | Chief Marketing Officer (CMO) | Trigger: When a compliance review, public statement, absence, access review or improvement need occurs. Action: The Chief Marketing Officer (CMO) completes “Approve Marketing & Sales access, delegation, backup and continuity arrangements” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. Control/Handoff: Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a compliance review, public statement, absence, access review or improvement need occurs. | The Chief Marketing Officer (CMO) completes “Approve Marketing & Sales access, delegation, backup and continuity arrangements” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. | Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he makes sure the function keeps working when people are away and the client data is protected. • Starts when: at the continuity review, on staff changes, and before planned absences. • How it runs: (1) he defines the CRM and system access per role. (2) He names deputies for client relationships and approvals. (3) He documents the delegations with limits and end dates. (4) He confirms the CRM and client records are backed up. (5) He reviews access on every leaver. • Proof it happened: reviewed access rights, named deputies with written delegations and confirmed backup of client records. • Where it usually breaks: client relationships and contacts sit with one individual, so when they leave the relationship and the information go with them. | • Require client contacts and relationship history to be held in the CRM rather than personally, since otherwise both the relationship and the information leave with the individual. • Revoke CRM access at the exit moment, as client data is the easiest thing for a leaver to take. • Name a deputy relationship owner for every key account. • Set delegation end dates for approval authority. • Back up the CRM, because it holds the pipeline and the client history.
879 | Marketing & Sales | Sponsor FirstBit CRM, analytics, workflow and sales-process improvements | Chief Marketing Officer (CMO) | Trigger: When a compliance review, public statement, absence, access review or improvement need occurs. Action: The Chief Marketing Officer (CMO) completes “Sponsor FirstBit CRM, analytics, workflow and sales-process improvements” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. Control/Handoff: Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a compliance review, public statement, absence, access review or improvement need occurs. | The Chief Marketing Officer (CMO) completes “Sponsor FirstBit CRM, analytics, workflow and sales-process improvements” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. | Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sponsors improving the CRM and the sales process so the function works better. • Starts when: improvement needs are identified, and at annual planning. • How it runs: (1) he identifies where the process or system slows the team down. (2) He prioritises the improvements. (3) He sponsors the system changes with IT and R&D. (4) He assigns owners and tracks delivery. (5) He confirms the benefit was realised. • Proof it happened: an improvement plan with sponsored initiatives, delivery tracked and the benefit confirmed. • Where it usually breaks: CRM changes are made without fixing the data, so the reports stay unreliable and the team continues working outside the system. | • Address CRM data quality before adding functionality, since unreliable reports drive the team to work outside the system entirely. • Involve the sales team in design, because workarounds exist where the system does not match how selling actually works. • Require adoption to be measured after each change, not assumed. • Confirm the benefit rather than declaring completion at go live. • Keep a single prioritised improvement list.
880 | Marketing & Sales | Report performance, forecast, risks and corrective actions to the CEO | Chief Marketing Officer (CMO) | Trigger: When a compliance review, public statement, absence, access review or improvement need occurs. Action: The Chief Marketing Officer (CMO) completes “Report performance, forecast, risks and corrective actions to the CEO” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. Control/Handoff: Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. Continuity/Escalation: A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a compliance review, public statement, absence, access review or improvement need occurs. | The Chief Marketing Officer (CMO) completes “Report performance, forecast, risks and corrective actions to the CEO” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved privacy/communication control, reputation action, continuity arrangement, system improvement or CEO report. | Consent, confidentiality, intellectual property and approved communication rules are preserved; crisis and material reputation matters escalate immediately to the CMO, CLO and CEO. | A CEO-approved commercial delegate may coordinate routine matters, but bid/no-bid, major client negotiation, material commercial exception, public statement, award acceptance and reserved decisions remain with the CMO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he tells the CEO how the pipeline and revenue are tracking, what the risks are and what he is doing about them. • Starts when: at the monthly reporting cycle, and immediately for material events. • How it runs: (1) he reports performance against the revenue and lead targets. (2) He reports the pipeline and the weighted forecast. (3) He states the risks: lost accounts, competitive pressure and forecast shortfalls. (4) He states the corrective actions and their owners. (5) He records the CEO's directions and acts on them. • Proof it happened: a reported performance and forecast pack with risks and corrective actions, and the CEO's directions recorded. • Where it usually breaks: the shortfall is reported late in the year when there is no longer time to act on it. | • Require an early warning when the forecast falls below target by a stated margin, since a shortfall reported late in the year cannot be recovered. • Require the forecast to show the movement from the previous report, so the direction is visible rather than the single figure. • Name the events that must be reported immediately: loss of a key account, a major bid loss and a significant client complaint. • Require corrective actions with owners and dates, not general intentions. • Keep the format consistent so the CEO can compare periods and challenge the trend rather than the presentation.
881 | Marketing & Sales | Research construction-market sectors, demand, client needs and opportunity trends | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Research construction-market sectors, demand, client needs and opportunity trends” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Research construction-market sectors, demand, client needs and opportunity trends” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she studies the market to find out where the work is and what clients are actually asking for. • Starts when: at the research cycle, and when entering a new sector or market. • How it runs: (1) she gathers information on sector activity and demand. (2) She identifies the project types being tendered. (3) She identifies what clients are prioritising. (4) She assesses where the company's capability fits. (5) She reports the findings with recommendations. • Proof it happened: market research records with demand, client needs and opportunity trends, and recommendations reported. • Where it usually breaks: research is collected but never turned into a recommendation, so it informs nobody and changes nothing. | • Require every research output to end in a specific recommendation, since research that stops at information changes nothing and is not worth doing. • Use sources that can be cited, as unattributed market claims are challenged and then ignored. • Focus on the priority sectors rather than covering everything superficially. • Include the company's own win and loss data, which is usually more useful than external market data. • Set a review frequency, because market research ages quickly.
882 | Marketing & Sales | Maintain competitor, pricing-position, service and market-intelligence records | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Maintain competitor, pricing-position, service and market-intelligence records” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Maintain competitor, pricing-position, service and market-intelligence records” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps records on competitors, their pricing position and the market generally. • Starts when: continuously, and after each significant bid. • How it runs: (1) she gathers publicly available competitor information. (2) She records their apparent service range and positioning. (3) She records pricing indications from bid outcomes. (4) She identifies their strengths and weaknesses. (5) She maintains the records for bid strategy use. • Proof it happened: maintained competitor and market intelligence records from lawful sources, used in bid strategy. • Where it usually breaks: competitor pricing is assumed from rumour, so bids are discounted against a competitor's price that nobody actually knows. | • Record competitor information only from public and lawful sources, and state this in the SOP, since improperly obtained information creates legal exposure. • Focus on competitor positioning and typical pricing level rather than speculation. • Update after each significant bid loss, as this is when the best information becomes available. • Keep the records controlled, because competitor analysis is commercially sensitive. • Prohibit using information obtained from a client in confidence.
883 | Marketing & Sales | Build and maintain the target-account and market-segment database | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Build and maintain the target-account and market-segment database” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Build and maintain the target-account and market-segment database” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she builds and maintains the database of the clients the company wants to work for. • Starts when: the target list is established, and continuously as it changes. • How it runs: (1) she identifies the organisations in the priority segments. (2) She records the contacts and their roles. (3) She records the activity and the relationship status. (4) She keeps the contact data current. (5) She maintains it in the CRM rather than separately. • Proof it happened: a maintained target account database in the CRM with current contacts and relationship status. • Where it usually breaks: contacts are held on personal phones and in personal email, so the database is incomplete and leaves with the person. | • Require all client contacts to be held in the CRM rather than personally, since a database held on personal devices is incomplete and leaves with the individual. • Record the contact's role and decision authority, not just their name. • Review and clean the data periodically, as contacts move and records decay quickly. • Record consent status for marketing contact, which is a legal requirement. • Record more than one contact per account, so the relationship survives a departure.
884 | Marketing & Sales | Monitor tender portals, referrals, networks and opportunity sources | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Monitor tender portals, referrals, networks and opportunity sources” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Monitor tender portals, referrals, networks and opportunity sources” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she watches the tender portals and other sources for opportunities. • Starts when: daily, and continuously. • How it runs: (1) she checks the tender portals on the defined schedule. (2) She reviews referrals and network sources. (3) She identifies opportunities matching the priority segments. (4) She records them for qualification. (5) She flags deadlines immediately. • Proof it happened: a monitoring log with opportunities identified, recorded for qualification and deadlines flagged. • Where it usually breaks: a tender is found too late to prepare properly, so the company either declines or submits something weak. | • Check the portals daily and flag the submission deadline immediately on identification, since a tender found late produces either a decline or a weak submission. • Record the source of every opportunity, so effective sources can be identified. • Set the minimum lead time the company needs, and state that anything shorter requires a specific decision. • Register every opportunity even where a decline is likely, as the record shows market activity. • Name a deputy for monitoring, so absence does not create a gap.
885 | Marketing & Sales | Prepare the annual and quarterly Marketing & Sales operating plan | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Prepare the annual and quarterly Marketing & Sales operating plan” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Prepare the annual and quarterly Marketing & Sales operating plan” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she prepares the plan for what marketing and sales will actually do in the year and quarter. • Starts when: at the annual and quarterly planning cycles. • How it runs: (1) she takes the approved targets and priorities. (2) She plans the activity needed to support them. (3) She allocates the budget and resources. (4) She sets the milestones and measures. (5) She obtains approval and issues the plan. • Proof it happened: an approved operating plan with activity, budget, milestones and measures for the period. • Where it usually breaks: the plan lists activity without linking it to the lead or revenue target, so nobody can tell whether it is enough. | • Link each planned activity to the lead or revenue target it supports, since a plan of activity with no connection to the target cannot be assessed as sufficient. • Include the expected lead volume per activity, so shortfall is predictable rather than discovered. • Plan within the approved budget rather than planning first and seeking funding later. • Set quarterly milestones, as annual plans drift without checkpoints. • Review actual against planned activity each quarter.
886 | Marketing & Sales | Maintain the campaign, content, event and client-engagement calendar | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Maintain the campaign, content, event and client-engagement calendar” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Maintain the campaign, content, event and client-engagement calendar” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the calendar of campaigns, content, events and client engagement. • Starts when: the plan is approved, and continuously as activity is scheduled. • How it runs: (1) she schedules the planned activity across the year. (2) She checks for clashes and gaps. (3) She aligns it with industry events and client cycles. (4) She keeps it updated as things change. (5) She circulates it to the team and stakeholders. • Proof it happened: a maintained engagement calendar with activity scheduled, clashes checked and circulated. • Where it usually breaks: activity clusters around a few months, so there are long periods with no client contact at all. | • Check the calendar for gaps as well as clashes, since clustered activity leaves long periods with no client contact and the pipeline reflects it months later. • Align activity with client budget and tender cycles rather than the company's convenience. • Include lead time for content and approvals in the calendar, as these are what cause activity to slip. • Circulate to the delivery functions, because their input is needed for credentials and case studies. • Update the calendar when things change rather than keeping a stale version.
887 | Marketing & Sales | Prepare campaign briefs with audience, message, budget, channel and KPI | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Prepare campaign briefs with audience, message, budget, channel and KPI” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Prepare campaign briefs with audience, message, budget, channel and KPI” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she writes the brief for each campaign, stating who it targets, what it says and how success is measured. • Starts when: a campaign is planned. • How it runs: (1) she defines the target audience precisely. (2) She defines the message and the call to action. (3) She sets the budget and the channels. (4) She sets the measures of success. (5) She obtains approval before execution. • Proof it happened: an approved campaign brief with audience, message, budget, channels and measures defined. • Where it usually breaks: no measure is set, so the campaign cannot be judged and the same approach is repeated regardless of result. | • Require a measurable success criterion in every brief, since a campaign with no measure cannot be judged and the same approach repeats regardless of result. • Define the audience specifically rather than by broad sector, as broad targeting produces unqualified volume. • State the call to action, because a campaign with no next step generates awareness and nothing else. • Require the lead capture and attribution method to be defined before launch. • Obtain approval before any spend is committed.
888 | Marketing & Sales | Coordinate approved marketing-spend commitments with Procurement and Finance | Marketing Manager (Lead) | Trigger: When the planning cycle, market change, campaign request or new opportunity source requires analysis. Action: The Marketing Manager (Lead) completes “Coordinate approved marketing-spend commitments with Procurement and Finance” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. Control/Handoff: Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When the planning cycle, market change, campaign request or new opportunity source requires analysis. | The Marketing Manager (Lead) completes “Coordinate approved marketing-spend commitments with Procurement and Finance” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated market view, target-account database, marketing plan, calendar, campaign brief and approved spend route. | Assumptions, data sources, dates and campaign KPIs are recorded; unapproved spend or unsupported market claims are blocked and escalated to the CMO. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she arranges the marketing purchases properly through procurement and finance. • Starts when: marketing spend is approved and needs committing. • How it runs: (1) she confirms the approval and the budget line. (2) She raises the requisition through the normal route. (3) She works with Procurement on supplier selection. (4) She confirms the commitment is recorded. (5) She tracks the spend against the allocation. • Proof it happened: marketing commitments raised through the approved route with budget confirmed and spend tracked. • Where it usually breaks: agencies and suppliers are engaged directly and the paperwork follows, so the company is committed before anyone approved it. | • Prohibit engaging marketing suppliers before the commitment is approved, since retrospective approval of a committed cost is not a control at all. • Route marketing spend through the normal procurement process, as marketing is frequently treated as an exception. • Confirm the budget line has funds before committing, not at invoice. • Require contracts for recurring agency arrangements rather than rolling on informally. • Track spend against the allocation monthly, because marketing overspend is usually only found at year end.
889 | Marketing & Sales | Maintain brand guidelines and the controlled marketing-asset library | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Maintain brand guidelines and the controlled marketing-asset library” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Maintain brand guidelines and the controlled marketing-asset library” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the brand guidelines and the library of approved marketing materials. • Starts when: the guidelines are set, and continuously as assets are created. • How it runs: (1) she maintains the brand guidelines document. (2) She maintains the library of approved logos, images and templates. (3) She controls versions and withdraws superseded assets. (4) She provides access to those who need it. (5) She checks usage for compliance. • Proof it happened: maintained brand guidelines and a controlled asset library with versions controlled and superseded assets withdrawn. • Where it usually breaks: old logos and templates stay in circulation on personal drives, so inconsistent materials go to clients. | • Require assets to be used from the controlled library only and withdraw superseded versions explicitly, since old logos and templates on personal drives reach clients. • Keep the guidelines short and practical, as a long brand manual is not followed. • Control who may create new client facing materials. • Check usage periodically, particularly on documents produced by other departments. • Retain licensing evidence for stock images in the library.
890 | Marketing & Sales | Prepare the content plan and production schedule | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Prepare the content plan and production schedule” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Prepare the content plan and production schedule” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she plans what content will be produced and when. • Starts when: the operating plan is approved. • How it runs: (1) she identifies the content needed to support the plan. (2) She sets the production schedule with lead times. (3) She identifies who provides the technical input. (4) She schedules the approval time. (5) She tracks production against the schedule. • Proof it happened: a content plan and production schedule with input owners, approval time and progress tracked. • Where it usually breaks: the schedule allows no time for technical input and approval, so content is either late or published unapproved. | • Build the technical input and approval time into the schedule explicitly, since omitting it means content is either late or published without approval. • Name who provides the technical input per item and agree it with them in advance. • Prioritise content that supports live opportunities over general material. • Set a realistic volume, as an over ambitious content plan produces nothing. • Track what was actually published against the plan.
891 | Marketing & Sales | Prepare approved project credentials, case studies and reference material | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Prepare approved project credentials, case studies and reference material” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Prepare approved project credentials, case studies and reference material” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she prepares the project credentials and case studies used to win work. • Starts when: a project completes, and when credentials are needed for a bid. • How it runs: (1) she gathers the project information and outcomes. (2) She obtains the technical review for accuracy. (3) She obtains the client's consent to use the project. (4) She prepares the credential or case study. (5) She maintains it in the controlled library. • Proof it happened: approved project credentials and case studies with technical review and documented client consent. • Where it usually breaks: a project is used as a credential without the client's permission, which most construction contracts prohibit. | • Require documented client consent before any project is used as a credential, since most construction contracts prohibit this and breach damages the relationship immediately. • Require technical review for factual accuracy, as overstated credentials are checked by clients and destroy credibility. • Capture the project information at completion while the team is still available. • Record what the consent permits and its expiry. • Keep credentials current, because dated credentials suggest no recent work.
892 | Marketing & Sales | Maintain company profiles, capability statements and prequalification content | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Maintain company profiles, capability statements and prequalification content” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Maintain company profiles, capability statements and prequalification content” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the company profiles and prequalification content up to date and ready to use. • Starts when: a prequalification is required, and at the review cycle. • How it runs: (1) she maintains the capability statement and company profile. (2) She maintains the standard prequalification responses. (3) She keeps the certificates, licences and financial information current. (4) She checks accuracy with the relevant functions. (5) She uses them for prequalification submissions. • Proof it happened: current company profiles and prequalification content with certificates and information verified. • Where it usually breaks: prequalification is submitted with expired certificates, so the submission is rejected and the opportunity is lost outright. | • Check every certificate and licence is current before any prequalification submission, since expired documents cause outright rejection and the opportunity is simply lost. • Maintain a standard response library so submissions are not written from scratch under deadline pressure. • Verify financial and insurance information with Finance rather than reusing last year's figures. • Keep a tracker of prequalification expiry dates with clients, because these lapse. • Check the profile claims against actual current capability.
893 | Marketing & Sales | Maintain approved website service, project and contact information | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Maintain approved website service, project and contact information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Maintain approved website service, project and contact information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the website content accurate, including services, projects and contact details. • Starts when: content requires updating, and at the review cycle. • How it runs: (1) she reviews the website content for accuracy. (2) She obtains approval for changes. (3) She updates the services and project information. (4) She verifies the contact information works. (5) She records what was changed and when. • Proof it happened: updated and approved website content with contact information verified and changes recorded. • Where it usually breaks: the contact form or phone number is broken and nobody notices, so enquiries are lost silently for months. | • Test the enquiry form, phone number and email route at a set frequency, since a broken contact route loses enquiries silently and nobody notices for months. • Require approval for content changes, particularly capability claims. • Check that project and client references on the site have consent. • Review the site for outdated information at a set frequency. • Confirm every enquiry from the site reaches the CRM.
894 | Marketing & Sales | Maintain the approved social-media publishing calendar | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Maintain the approved social-media publishing calendar” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Maintain the approved social-media publishing calendar” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the calendar of what will be posted on social media and when. • Starts when: the content plan is approved. • How it runs: (1) she schedules the approved content. (2) She checks each item has approval before scheduling. (3) She avoids posting during sensitive periods. (4) She monitors the posts and responses. (5) She records what was published. • Proof it happened: a publishing calendar with approved content scheduled, published and recorded. • Where it usually breaks: scheduled content publishes automatically during an incident or a sensitive period, which reads as insensitive or misleading. | • Require scheduled content to be reviewed and suspended during any incident or sensitive period, since automatic publishing at the wrong moment reads as insensitive and is widely noticed. • Require approval before scheduling, not after publication. • Name who may respond to comments and require client matters to be routed rather than answered. • Hold account credentials centrally, as accounts controlled by one person are lost when they leave. • Record deletions and corrections with approval, because silent deletion of a live post looks like concealment.
895 | Marketing & Sales | Execute approved digital, email, social, print and direct-marketing campaigns | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Execute approved digital, email, social, print and direct-marketing campaigns” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Execute approved digital, email, social, print and direct-marketing campaigns” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she runs the approved campaigns across the chosen channels. • Starts when: a campaign is approved and due to launch. • How it runs: (1) she prepares the campaign materials from approved content. (2) She sets up the lead capture and tracking. (3) She launches across the approved channels. (4) She monitors performance during the campaign. (5) She records the results against the brief. • Proof it happened: an executed campaign with lead capture in place, performance monitored and results recorded against the brief. • Where it usually breaks: lead capture is not tested before launch, so enquiries generated by the campaign are lost entirely. | • Test the lead capture and attribution end to end before launch, since a campaign that generates enquiries nobody receives is a complete waste of the budget. • Confirm the consent basis for email and direct marketing, as unconsented contact is unlawful. • Monitor during the campaign so a failing campaign can be stopped rather than completed. • Record results against the brief's stated measures. • Set the response commitment for leads generated, because slow response destroys conversion.
896 | Marketing & Sales | Coordinate exhibitions, industry events, client visits and promotional activities | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Coordinate exhibitions, industry events, client visits and promotional activities” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Coordinate exhibitions, industry events, client visits and promotional activities” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she organises the exhibitions, events and client visits. • Starts when: an event is approved. • How it runs: (1) she plans the logistics, materials and attendance. (2) She confirms who will represent the company and briefs them. (3) She prepares the lead capture method. (4) She runs the event. (5) She follows up every lead captured and reports the outcome. • Proof it happened: an organised event with attendance briefed, leads captured and followed up, and the outcome reported. • Where it usually breaks: leads collected at the event are never followed up, so the entire cost produces nothing. | • Require every lead captured at an event to be entered in the CRM and followed up within a stated period, since uncontacted event leads make the whole cost worthless. • Brief the attending team on the message and who they should target, as unbriefed attendance is just presence. • Set a lead target for the event so its value can be assessed. • Prepare the lead capture method in advance rather than collecting business cards loosely. • Evaluate the event afterwards against its cost.
897 | Marketing & Sales | Coordinate approved agencies, designers, photographers, media and marketing suppliers | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Coordinate approved agencies, designers, photographers, media and marketing suppliers” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Coordinate approved agencies, designers, photographers, media and marketing suppliers” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she manages the agencies, designers and other marketing suppliers. • Starts when: a supplier is engaged and while work is in progress. • How it runs: (1) she briefs the supplier against the approved brief. (2) She agrees the deliverables and deadlines. (3) She reviews the work against the brief. (4) She approves or returns deliverables. (5) She confirms the invoice matches the agreed scope. • Proof it happened: supplier briefs, agreed deliverables, reviewed work and invoices matched to agreed scope. • Where it usually breaks: scope creeps through informal requests, so the invoice exceeds the approved amount and there is no basis to challenge it. | • Require every scope addition to be approved before the supplier starts it, since informal requests produce invoices above the approved amount with no basis to challenge. • Brief in writing against the approved brief, as verbal briefs produce rework. • Require the intellectual property and usage rights in the supplier agreement. • Check the invoice against the agreed deliverables before approval. • Require photographers to obtain site and personnel consents.
898 | Marketing & Sales | Control content approval, client consent, copyright and publication evidence | Marketing Manager (Lead) | Trigger: When an approved content, campaign, event, website, social-media or supplier activity becomes due. Action: The Marketing Manager (Lead) completes “Control content approval, client consent, copyright and publication evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an approved and traceable brand asset, campaign, event record or published communication with consent evidence. Control/Handoff: Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When an approved content, campaign, event, website, social-media or supplier activity becomes due. | The Marketing Manager (Lead) completes “Control content approval, client consent, copyright and publication evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an approved and traceable brand asset, campaign, event record or published communication with consent evidence. | Every external asset uses approved branding, current facts, client consent and copyright clearance; agencies and spend follow Procurement and Finance controls. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she controls that content is approved, consents are held and copyright is respected before publishing. • Starts when: content is prepared for publication. • How it runs: (1) she confirms the content has the required approval. (2) She confirms client consent where a project or name is used. (3) She confirms licensing for third party images and content. (4) She retains the evidence. (5) She releases for publication. • Proof it happened: publication records with approval, client consent and licensing evidence retained. • Where it usually breaks: a stock image is used without a licence, and an infringement claim arrives with a demand attached. | • Retain licensing evidence for every third party image and asset, since infringement claims arrive with a demand and are difficult to defend without it. • Retain client consent evidence with the published content, not separately. • Check personnel consent for identifiable people in photographs. • Require approval evidence before release, and prohibit publishing on verbal approval. • Keep a publication register, so what has been published and on what basis is known.
899 | Marketing & Sales | Monitor email, phone, WhatsApp, website, social, portal, referral and repeat-client enquiries | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Monitor email, phone, WhatsApp, website, social, portal, referral and repeat-client enquiries” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Monitor email, phone, WhatsApp, website, social, portal, referral and repeat-client enquiries” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she watches every channel enquiries come in on, so none are missed. • Starts when: continuously, across all channels. • How it runs: (1) she monitors email, phone, messaging, website, social, portals and referrals. (2) She identifies genuine enquiries. (3) She captures the details. (4) She passes them into the registration process. (5) She reports channel volumes. • Proof it happened: monitored channels with enquiries captured from each and passed into registration. • Where it usually breaks: enquiries arriving on a personal phone or messaging account are never captured, so they are invisible and sometimes lost. | • Require business messaging to run through a company account rather than personal numbers, since enquiries on a personal phone are invisible and are lost when that person is unavailable. • Monitor every channel including the ones nobody thinks about, such as portal messages and social direct messages. • Set a maximum response time and measure it, because response speed is the strongest conversion factor. • Capture enquiries even where they will be declined, as the volume data matters. • Name a deputy for monitoring during absence.
900 | Marketing & Sales | Register each enquiry in FirstBit CRM and assign a unique Lead ID | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Register each enquiry in FirstBit CRM and assign a unique Lead ID” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Register each enquiry in FirstBit CRM and assign a unique Lead ID” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she registers every enquiry in the CRM with its own reference. • Starts when: an enquiry is received. • How it runs: (1) she creates the CRM record. (2) She assigns the unique lead reference. (3) She records the date, channel and source. (4) She records the client and contact details. (5) She confirms the record is complete for qualification. • Proof it happened: a CRM record per enquiry with a unique reference, date, channel and source recorded. • Where it usually breaks: registration happens days later when the enquiry is already being worked on, so the response time measure and the source attribution are both wrong. | • Register the enquiry before any work is done on it, since late registration corrupts both the response time measure and the source attribution. • Require the source channel as a mandatory field, as this is what makes channel evaluation possible. • Register every enquiry including those likely to be declined. • Never reuse a lead reference. • Report unregistered work as an exception, because this is where enquiries disappear.
901 | Marketing & Sales | Identify and merge duplicate client, contact and opportunity records | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Identify and merge duplicate client, contact and opportunity records” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Identify and merge duplicate client, contact and opportunity records” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she finds and merges duplicate client and opportunity records. • Starts when: at the data review cycle, and when a duplicate is spotted. • How it runs: (1) she searches for duplicates on name, contact and project. (2) She confirms they are the same entity or opportunity. (3) She identifies the record to retain. (4) She merges, preserving the history. (5) She records the merge. • Proof it happened: identified and merged duplicate records with history preserved and the merge recorded. • Where it usually breaks: duplicates are left in place, so two people pursue the same client separately and the client notices. | • Run a duplicate check at enquiry registration, since two people pursuing the same client separately is visible to the client and damages credibility immediately. • Search on near matches and alternative spellings, not exact matches alone. • Preserve the activity history when merging, as this is the relationship record. • Record the merge so the retained reference is traceable. • Report duplicate volumes, because a high rate indicates a registration discipline problem.
902 | Marketing & Sales | Record campaign, channel, referral and lead-source attribution | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Record campaign, channel, referral and lead-source attribution” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Record campaign, channel, referral and lead-source attribution” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she records where each lead actually came from. • Starts when: at enquiry registration. • How it runs: (1) she establishes the source from the enquiry itself. (2) She records the campaign or channel where applicable. (3) She records the referrer where it is a referral. (4) She avoids recording a default value. (5) She maintains the attribution through the opportunity. • Proof it happened: recorded lead source attribution per enquiry, maintained through the opportunity lifecycle. • Where it usually breaks: source is recorded as other or left as a default, so no channel can ever be evaluated. | • Prohibit a default or other value for source and require the actual origin, since a defaulted field makes the entire marketing spend unevaluable. • Ask the client directly where the enquiry originated, as assumptions are usually wrong. • Record the referrer's name for referrals, so the relationship can be acknowledged and repeated. • Maintain the attribution through to won revenue, not just at the lead stage. • Report revenue by source annually, because this is what should drive the budget.
903 | Marketing & Sales | Collect client identity, contact, KYC and communication-consent information | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Collect client identity, contact, KYC and communication-consent information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Collect client identity, contact, KYC and communication-consent information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she collects the client's identity, contact and consent information. • Starts when: an enquiry is being qualified. • How it runs: (1) she collects the legal entity name and registration details. (2) She collects the contact details and roles. (3) She records the communication consent. (4) She collects the client verification information required. (5) She records it in the CRM. • Proof it happened: collected client identity, contact and consent information recorded in the CRM. • Where it usually breaks: the trading name is recorded rather than the legal entity, so the eventual contract and invoices are addressed to an entity that does not exist. | • Record the legal entity name and registration rather than the trading name, since contracts and invoices addressed to a non existent entity are unenforceable and unpayable. • Record the communication consent basis, as this is a legal requirement for marketing contact. • Collect the client verification information required before significant effort is committed. • Record the contact's role and authority, not just their name. • Flag new clients for a credit check before any commitment.
904 | Marketing & Sales | Collect client brief, drawings, photographs, location and available site information | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Collect client brief, drawings, photographs, location and available site information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Collect client brief, drawings, photographs, location and available site information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she collects the client's brief and whatever drawings, photographs and site information exist. • Starts when: an enquiry requires technical assessment. • How it runs: (1) she requests the brief and available documents. (2) She collects drawings, photographs and location details. (3) She records the site access and condition information. (4) She identifies what is missing. (5) She confirms the pack is sufficient for assessment. • Proof it happened: a collected client brief with drawings, photographs and site information, and gaps identified. • Where it usually breaks: technical assessment starts on an incomplete brief, so the estimate is based on assumptions that later prove wrong. | • Define the minimum information required before technical assessment starts, since an estimate built on assumptions is either lost on price or won at a loss. • Record what the client could not provide, so the assumptions are visible in the offer. • Request the information in one structured list rather than piecemeal. • Record the site access and condition information, as these drive significant cost. • Escalate where a client refuses to provide basic information, because this predicts how the project will run.
905 | Marketing & Sales | Qualify service need, scope, budget, timing, stakeholders and decision process | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Qualify service need, scope, budget, timing, stakeholders and decision process” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Qualify service need, scope, budget, timing, stakeholders and decision process” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she establishes what the client actually needs, their budget, timing and who decides. • Starts when: an enquiry is being qualified. • How it runs: (1) she establishes the service need and the scope. (2) She establishes the budget range and how it is funded. (3) She establishes the required timing. (4) She identifies the stakeholders and the decision process. (5) She records the qualification findings. • Proof it happened: a qualification record covering need, scope, budget, timing, stakeholders and decision process. • Where it usually breaks: budget is not asked about because it feels awkward, so unfunded enquiries consume weeks of design effort. | • Require the budget question to be asked at first contact, since avoiding it is what lets unfunded enquiries consume weeks of the company's most expensive time. • Identify the decision maker and the approver separately, as the contact is frequently neither. • Establish the decision timeline and the process, because a client with no process will not decide. • Record the qualification findings rather than holding them in the salesperson's head. • Requalify when the enquiry stalls, as circumstances change.
906 | Marketing & Sales | Apply the approved lead score, status, priority and qualification outcome | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Apply the approved lead score, status, priority and qualification outcome” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Apply the approved lead score, status, priority and qualification outcome” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she applies the score and status that determine how the enquiry is treated. • Starts when: qualification is complete. • How it runs: (1) she applies the approved scoring criteria. (2) She sets the status and priority. (3) She records the qualification outcome. (4) She disqualifies where the criteria are not met. (5) She records the reason for the outcome. • Proof it happened: an applied lead score, status and priority with the qualification outcome and reason recorded. • Where it usually breaks: everything is scored as high priority, so prioritisation means nothing and resources go to whoever shouts loudest. | • Apply the scoring criteria mechanically rather than by judgement, since scoring everything as high priority means resources go to whoever pushes hardest. • Require disqualification to be recorded with a reason, so declining is a visible normal outcome. • Set the proportion of leads that can be high priority, because an unlimited high priority list is not a priority list. • Requalify stalled leads rather than leaving their original score. • Report score distribution, as this shows whether the criteria are being applied.
907 | Marketing & Sales | Acknowledge the enquiry and communicate the controlled next action | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Acknowledge the enquiry and communicate the controlled next action” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Acknowledge the enquiry and communicate the controlled next action” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she acknowledges the enquiry and tells the client what happens next. • Starts when: an enquiry is registered. • How it runs: (1) she issues the acknowledgement within the stated timeframe. (2) She states the next step and who will make contact. (3) She states the expected timeline. (4) She avoids committing to anything not approved. (5) She records the acknowledgement. • Proof it happened: an issued acknowledgement with the next action and timeline stated, and the communication recorded. • Where it usually breaks: the acknowledgement promises a proposal by a date that was never agreed internally, so the company misses its own commitment. | • Prohibit committing to a date in the acknowledgement unless it has been agreed internally, since a missed self imposed deadline damages credibility before any work is done. • Set a maximum acknowledgement time and measure it, as response speed is the strongest conversion factor. • Use a controlled template, so no price or capability commitment is made inadvertently. • Name the person who will make contact, because a general acknowledgement invites chasing. • Record the acknowledgement in the CRM.
908 | Marketing & Sales | Assign the qualified lead to the Business Development Executive with response SLA | Marketing Manager (Lead) | Trigger: When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. Action: The Marketing Manager (Lead) completes “Assign the qualified lead to the Business Development Executive with response SLA” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. Control/Handoff: Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a new enquiry, referral, tender invitation, campaign response, portal lead or repeat-client opportunity arrives. | The Marketing Manager (Lead) completes “Assign the qualified lead to the Business Development Executive with response SLA” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a unique, complete and qualified FirstBit CRM lead with source, priority, owner, response and next action. | Duplicates are merged, missing data is pursued, consent and KYC are recorded, and no lead advances without a documented qualification result. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she assigns the qualified lead to a business development executive with a response deadline. • Starts when: a lead is qualified. • How it runs: (1) she selects the owner based on sector and workload. (2) She assigns the lead in the CRM. (3) She sets the response deadline. (4) She confirms the assignment with the owner. (5) She tracks whether the deadline is met. • Proof it happened: an assigned lead with a named owner, response deadline set and adherence tracked. • Where it usually breaks: leads are assigned to whoever is available without checking workload, so they sit unworked past the deadline. | • Check the owner's current workload before assigning, since a lead assigned to an overloaded person sits unworked and the response deadline passes. • Require the owner to accept the assignment, so it is not merely allocated in the system. • Track deadline adherence by owner and report it. • Reassign automatically where the deadline passes without contact. • Assign by sector knowledge where it matters, because a poor first conversation loses the opportunity.
909 | Marketing & Sales | Complete the qualified-lead checklist and controlled handover pack | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Complete the qualified-lead checklist and controlled handover pack” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Complete the qualified-lead checklist and controlled handover pack” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she completes the handover pack so the next person has everything they need. • Starts when: a lead is being handed over. • How it runs: (1) she completes the qualified lead checklist. (2) She assembles the client brief, documents and qualification findings. (3) She records the consents and identity information. (4) She confirms the pack is complete. (5) She hands it over and records the handover. • Proof it happened: a completed checklist and handover pack with the brief, documents and qualification findings. • Where it usually breaks: the handover is a verbal summary, so the receiving person re asks the client questions already answered. | • Require a documented handover pack rather than a verbal briefing, since re asking the client questions already answered signals disorganisation and costs credibility. • Define the pack contents as a checklist and require completeness before handover. • Include what the client has not provided, so assumptions are visible. • Require the receiving owner to confirm the pack is sufficient. • Record the handover date, as this starts the next response clock.
910 | Marketing & Sales | Create the FirstBit technical pre-assessment handover task for the CTO | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Create the FirstBit technical pre-assessment handover task for the CTO” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Create the FirstBit technical pre-assessment handover task for the CTO” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she raises the task for the CTO to carry out the technical pre assessment. • Starts when: a qualified lead needs technical assessment. • How it runs: (1) she creates the handover task in the system. (2) She attaches the client brief and documents. (3) She states the assessment required and the deadline. (4) She notifies the CTO. (5) She confirms the task was received. • Proof it happened: a created technical pre assessment task with the brief attached, requirement stated and receipt confirmed. • Where it usually breaks: the task is raised with an unrealistic deadline, so it is either rejected or done superficially. | • Agree the assessment deadline with the CTO rather than imposing it, since an imposed unrealistic deadline produces either a rejection or a superficial assessment. • Attach the complete brief to the task, as a task requiring the technical team to chase information stalls immediately. • State what specifically is required from the assessment. • Confirm receipt, because a task raised in the system and unseen achieves nothing. • Track the technical effort committed per opportunity.
911 | Marketing & Sales | Track CTO acceptance, return, clarification and technical-owner assignment | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Track CTO acceptance, return, clarification and technical-owner assignment” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Track CTO acceptance, return, clarification and technical-owner assignment” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she tracks whether the technical team accepted the task and who owns it. • Starts when: a technical task is raised. • How it runs: (1) she monitors the task status. (2) She records acceptance and the assigned technical owner. (3) She records any return or clarification request. (4) She resolves clarifications with the client. (5) She escalates where the task stalls. • Proof it happened: tracked technical task status with acceptance, owner, clarifications and escalations recorded. • Where it usually breaks: a clarification request sits unanswered, so the assessment stalls and the client hears nothing for weeks. | • Treat an open clarification request as a blocking item with a deadline, since an unanswered clarification stalls the assessment and the client hears nothing. • Record the assigned technical owner, so the opportunity has a named technical contact. • Escalate stalled tasks rather than continuing to wait. • Keep the client informed while the assessment is in progress, as silence loses opportunities. • Report technical assessment turnaround, because this is often the longest stage.
912 | Marketing & Sales | Coordinate site-visit access, client attendance and requirement confirmation | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Coordinate site-visit access, client attendance and requirement confirmation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Coordinate site-visit access, client attendance and requirement confirmation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she arranges the site visit, gets the client there and confirms what they actually want. • Starts when: a site visit is required for assessment. • How it runs: (1) she arranges access with the client. (2) She confirms who will attend from both sides. (3) She confirms the purpose and what will be examined. (4) She records the findings and the requirement confirmation. (5) She issues the record to both sides. • Proof it happened: a site visit record with attendance, findings and the requirement confirmed to the client. • Where it usually breaks: the visit findings are not written up, so different attendees remember different requirements. | • Issue a written record of the visit findings and requirement confirmation to the client, since unrecorded visits leave every attendee remembering something different. • Require the client decision maker to attend where possible, as a visit with a junior contact requires repeating. • Confirm access arrangements in advance, because a failed visit wastes senior time on both sides. • Photograph the site conditions, as these drive significant cost. • Record what could not be examined, so the assumptions are visible.
913 | Marketing & Sales | Maintain the client clarification, requirement and decision log | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Maintain the client clarification, requirement and decision log” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Maintain the client clarification, requirement and decision log” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the log of client questions, requirements and decisions. • Starts when: an enquiry is active, and continuously through it. • How it runs: (1) she records each client clarification and the answer given. (2) She records requirement changes with dates. (3) She records client decisions. (4) She keeps the log current. (5) She carries the log into the handover. • Proof it happened: a maintained clarification, requirement and decision log carried into the handover. • Where it usually breaks: the log stays with the salesperson, so delivery inherits the proposal without any of the agreed clarifications. | • Require the clarification log to travel with the handover, since a delivery team working from the proposal alone misses everything agreed after it was written. • Record the date of each requirement change, as this determines what was priced. • Record client decisions distinctly from discussion. • Keep the log in the CRM rather than in personal notes. • Confirm material clarifications to the client in writing.
914 | Marketing & Sales | Coordinate the preliminary concept and indicative-budget presentation | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Coordinate the preliminary concept and indicative-budget presentation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Coordinate the preliminary concept and indicative-budget presentation” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she arranges the presentation of the initial concept and the rough budget. • Starts when: the concept and indicative budget are approved for presentation. • How it runs: (1) she confirms the concept and budget have the required approval. (2) She arranges the meeting with the decision makers. (3) She prepares the presentation from approved material. (4) She records the client's reaction and questions. (5) She confirms the next step in writing. • Proof it happened: a presentation delivered from approved material with the client's response and next step recorded. • Where it usually breaks: an indicative budget is presented without stating its basis, so the client treats it as a fixed price. | • Label every indicative figure with its basis, exclusions and validity in writing, since clients treat any number presented as a commitment. • Require the figure to be approved before presentation, including indicative ones. • Present to the decision maker, as a concept presented to an intermediary is rarely understood correctly. • Record the client's reaction, because this shapes the formal proposal. • Confirm the agreed next step in writing the same day.
915 | Marketing & Sales | Coordinate the CTO-approved detailed-design quotation or agreement process | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Coordinate the CTO-approved detailed-design quotation or agreement process” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Coordinate the CTO-approved detailed-design quotation or agreement process” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she coordinates the detailed design quotation or agreement process. • Starts when: the client wants to proceed to detailed design. • How it runs: (1) she obtains the CTO approved design fee and scope. (2) She prepares the quotation or agreement. (3) She confirms the commercial terms are approved. (4) She issues it and tracks the client's response. (5) She records the outcome. • Proof it happened: an issued design quotation or agreement with technical and commercial approval, tracked to outcome. • Where it usually breaks: design work starts on a verbal go ahead, so the fee is never agreed and the client disputes it later. | • Prohibit design work starting before a signed agreement or written acceptance, since a fee never agreed in writing is disputed and frequently unrecovered. • State the design scope and the number of revisions included, as unlimited revisions consume the fee entirely. • State what happens to the design fee if the client proceeds to construction. • State the intellectual property position on the design. • Require approval of both the fee and the scope before issue.
916 | Marketing & Sales | Coordinate release of the CTO-approved construction quotation and commercial offer | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Coordinate release of the CTO-approved construction quotation and commercial offer” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Coordinate release of the CTO-approved construction quotation and commercial offer” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she coordinates issuing the construction quotation once it is approved. • Starts when: the construction quotation is technically and commercially approved. • How it runs: (1) she confirms the technical approval. (2) She confirms the commercial approval and margin. (3) She assembles the offer with assumptions and exclusions. (4) She issues the approved version. (5) She records the version and tracks the response. • Proof it happened: an issued construction quotation with both approvals, assumptions stated and the version recorded. • Where it usually breaks: an earlier draft is issued by mistake, so the company is exposed to a price or scope it never approved. | • Verify the document being sent against the approved version immediately before release, since issuing an earlier draft exposes the company to a price it never approved. • State the assumptions, exclusions and validity in the offer, otherwise they are not part of it. • Issue in a non editable format. • Record the version and the issue date, as this is the reference for any negotiation. • Withdraw superseded versions explicitly.
917 | Marketing & Sales | Control proposal revisions, assumptions, exclusions and client-facing versions | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Control proposal revisions, assumptions, exclusions and client-facing versions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Control proposal revisions, assumptions, exclusions and client-facing versions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she controls the proposal versions and what each one says. • Starts when: a proposal is revised. • How it runs: (1) she records each version with its changes. (2) She updates the assumptions and exclusions. (3) She obtains approval for the revision. (4) She issues the new version and withdraws the old. (5) She records which version the client holds. • Proof it happened: controlled proposal versions with changes recorded, approvals obtained and the client's held version known. • Where it usually breaks: the client holds two versions and signs the one more favourable to them, which the company never approved. | • Withdraw superseded versions explicitly and confirm which version is current, since a client holding two versions will sign the one that favours them. • Require approval for every revision, not only the first issue. • Number the versions clearly on the document face. • Record what changed between versions, as this is what the negotiation turns on. • Carry the assumptions and exclusions forward into every revision.
918 | Marketing & Sales | Coordinate client feedback and approved technical or commercial clarifications | Marketing Manager (Lead) | Trigger: When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. Action: The Marketing Manager (Lead) completes “Coordinate client feedback and approved technical or commercial clarifications” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. Control/Handoff: CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a qualified lead is ready for technical review, site assessment, concept, design offer or construction quotation. | The Marketing Manager (Lead) completes “Coordinate client feedback and approved technical or commercial clarifications” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete technical handover, coordinated visit, controlled proposal version and documented client clarification. | CMO remains the client/commercial interface while CTO controls technical scope and quotation approval; any revision or commitment is recorded before client release. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she handles the client's feedback and gets the technical or commercial answers. • Starts when: the client responds with questions or requested changes. • How it runs: (1) she records the feedback precisely. (2) She routes technical questions to engineering and commercial ones for approval. (3) She obtains the approved response. (4) She communicates it to the client. (5) She records the exchange. • Proof it happened: recorded client feedback with approved technical and commercial responses communicated and logged. • Where it usually breaks: a technical question is answered by sales to keep momentum, and the answer turns out to be wrong. | • Prohibit sales answering technical questions directly, since an incorrect technical answer given to maintain momentum becomes a commitment the company cannot meet. • Require commercial concessions to be approved before they are communicated, including indicatively. • Record the client's exact wording, as paraphrasing loses the point being made. • Set a response timeframe, because slow responses lose opportunities. • Confirm every answer in writing.
919 | Marketing & Sales | Maintain opportunity stage, probability, value, expected close date and next action | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Maintain opportunity stage, probability, value, expected close date and next action” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Maintain opportunity stage, probability, value, expected close date and next action” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps each opportunity's stage, value and next action current in the CRM. • Starts when: an opportunity is created, and continuously. • How it runs: (1) she updates the stage as the opportunity progresses. (2) She updates the value and probability. (3) She updates the expected close date. (4) She records the next action with a date. (5) She reviews opportunities with no recent activity. • Proof it happened: current opportunity records with stage, value, probability, close date and next action. • Where it usually breaks: records are updated only before the pipeline meeting, so between meetings the pipeline is fiction. | • Require updates as events occur rather than before the pipeline meeting, since a pipeline refreshed for reporting is fiction the rest of the time. • Require a next action with a date on every live opportunity, as opportunities without one are dormant. • Require the stage to meet its objective criteria before it can be advanced. • Flag opportunities with no activity for a stated period. • Require the close date to be justified rather than rolled forward.
920 | Marketing & Sales | Review daily overdue lead, proposal and client-follow-up actions | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Review daily overdue lead, proposal and client-follow-up actions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Review daily overdue lead, proposal and client-follow-up actions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: every day she checks what follow ups and proposals are overdue. • Starts when: daily. • How it runs: (1) she reviews the overdue lead responses. (2) She reviews the overdue proposal issues. (3) She reviews the overdue client follow ups. (4) She chases the owners. (5) She escalates items overdue beyond a stated period. • Proof it happened: a daily overdue action review with owners chased and items escalated. • Where it usually breaks: the review produces a list nobody acts on, so items stay overdue indefinitely. | • Escalate items overdue beyond a stated period rather than re listing them daily, since a list that never triggers escalation is ignored. • Send each owner their own overdue items, not just the full list. • Show ageing, because a lead overdue by three weeks is effectively lost. • Report overdue volumes by owner, as this is what drives behaviour. • Prioritise overdue first responses, since these are the most damaging.
921 | Marketing & Sales | Prepare the weekly pipeline, conversion and revenue forecast | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Prepare the weekly pipeline, conversion and revenue forecast” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Prepare the weekly pipeline, conversion and revenue forecast” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she prepares the weekly pipeline and revenue forecast. • Starts when: weekly on the reporting cycle. • How it runs: (1) she compiles the opportunities by stage and value. (2) She applies the probabilities. (3) She calculates the weighted forecast. (4) She reconciles it to the previous week. (5) She issues it with the significant movements explained. • Proof it happened: a weekly pipeline and forecast reconciled to the previous week with movements explained. • Where it usually breaks: the forecast is issued without explaining what moved, so nobody can see whether the position improved or deteriorated. | • Reconcile each forecast to the previous week and explain the movements, since the movement is what reveals whether the position is improving or deteriorating. • Show wins, losses and slipped dates separately, as these have different causes. • Generate the forecast from the CRM rather than compiling separately. • Show the unweighted and weighted values, because both are needed. • Track forecast accuracy over time.
922 | Marketing & Sales | Prepare campaign, funnel, lead-source and conversion-performance reporting | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Prepare campaign, funnel, lead-source and conversion-performance reporting” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Prepare campaign, funnel, lead-source and conversion-performance reporting” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she reports how campaigns, channels and the sales funnel are performing. • Starts when: at the reporting cycle. • How it runs: (1) she compiles the leads by source and campaign. (2) She compiles the conversion at each funnel stage. (3) She compiles the cost per lead and per win. (4) She identifies the weak points. (5) She issues the report with recommendations. • Proof it happened: campaign, funnel and conversion reporting with cost per lead and identified weak points. • Where it usually breaks: conversion is reported overall rather than by stage, so where opportunities are actually lost is never identified. | • Report conversion at each funnel stage rather than overall, since an overall rate cannot show where opportunities are actually being lost. • Report cost per qualified lead and per win by channel, not cost per enquiry. • Include the time at each stage, as delay is a major loss cause. • Make recommendations rather than only presenting data. • Keep the format consistent so periods are comparable.
923 | Marketing & Sales | Maintain controlled pre-contract client communication and approval evidence | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Maintain controlled pre-contract client communication and approval evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Maintain controlled pre-contract client communication and approval evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she keeps the record of pre contract communication and approvals with the client. • Starts when: an opportunity is active. • How it runs: (1) she records all significant client communication. (2) She records what was offered and approved internally. (3) She records the client's responses and commitments. (4) She keeps the evidence in one controlled place. (5) She carries it into the handover. • Proof it happened: controlled pre contract communication and approval evidence retained and carried into handover. • Where it usually breaks: communication sits in individual mailboxes, so the company cannot evidence what was actually offered. | • Hold all pre contract communication in one controlled location rather than in individual mailboxes, since the company otherwise cannot evidence what it actually offered. • Record the internal approval alongside what was communicated, so unauthorised commitments are visible. • Retain the evidence beyond the award, as it is needed in any scope dispute. • Carry it into the handover pack. • Record verbal conversations in a note the same day.
924 | Marketing & Sales | Coordinate proposal presentations and negotiation meetings | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Coordinate proposal presentations and negotiation meetings” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Coordinate proposal presentations and negotiation meetings” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she arranges the proposal presentations and negotiation meetings. • Starts when: a presentation or negotiation is required. • How it runs: (1) she arranges the meeting with the right attendees. (2) She prepares the material from approved content. (3) She briefs the internal team on the approved position. (4) She records what was discussed and agreed. (5) She confirms agreed points to the client in writing. • Proof it happened: arranged meetings with approved material, the position briefed and agreed points confirmed in writing. • Where it usually breaks: the internal team is not briefed, so different people give the client different answers in the same meeting. | • Brief the internal team on the approved position before the meeting, since different answers from different people in one meeting destroys client confidence. • Confirm agreed points to the client in writing the same day. • Require the decision maker to attend, as a presentation to an intermediary is rarely conveyed accurately. • State clearly what is approved and what is subject to approval. • Take an internal record of the discussion, not only the outcome.
925 | Marketing & Sales | Capture written client approval, letter of intent, award and decision evidence | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Capture written client approval, letter of intent, award and decision evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Capture written client approval, letter of intent, award and decision evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she captures the client's written approval, letter of intent or award. • Starts when: the client indicates a decision. • How it runs: (1) she requests the decision in writing. (2) She records exactly what has been awarded or approved. (3) She compares it to the submitted offer. (4) She identifies differences. (5) She records the evidence and notifies the next functions. • Proof it happened: captured written award or approval evidence compared to the offer with differences identified. • Where it usually breaks: a verbal award is treated as confirmation, so mobilisation starts on something that was never committed. | • Require the decision in writing before anything is treated as won, since a verbal award is not a commitment and mobilising on one is unrecoverable if it evaporates. • Compare the award against the submitted offer clause by clause, as clients frequently award on their own terms. • Record exactly what was awarded, including scope and value. • Notify Legal, Finance and Technical immediately. • Treat a letter of intent as a partial commitment requiring a cap and an expiry.
926 | Marketing & Sales | Hand won opportunities to Legal, Finance and Technical Engineering | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Hand won opportunities to Legal, Finance and Technical Engineering” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Hand won opportunities to Legal, Finance and Technical Engineering” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she hands the won work over to Legal, Finance and Engineering. • Starts when: an award is captured. • How it runs: (1) she assembles the complete opportunity file. (2) She passes the contract documents to Legal. (3) She passes the commercial and billing terms to Finance. (4) She passes the technical requirement to Engineering. (5) She confirms each has accepted the handover. • Proof it happened: a completed handover to Legal, Finance and Engineering with acceptance confirmed by each. • Where it usually breaks: only the proposal is handed over, so the clarifications and agreed changes never reach the delivery team. | • Require the clarification log and agreed changes to be handed over with the proposal, since delivery working from the proposal alone builds what was originally offered rather than what was agreed. • Require each receiving function to confirm acceptance, so gaps are found immediately. • Define the handover contents per function as a checklist. • Include the client's own terms and any accepted deviations. • Record the handover date, as this starts the activation clock.
927 | Marketing & Sales | Track contract and financial-activation status before downstream release | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Track contract and financial-activation status before downstream release” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Track contract and financial-activation status before downstream release” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she tracks whether the contract and the financial setup are complete before work is released. • Starts when: the handover is made. • How it runs: (1) she tracks the contract finalisation status with Legal. (2) She tracks the financial activation with Finance. (3) She identifies what is blocking activation. (4) She chases the outstanding items. (5) She confirms activation before downstream release. • Proof it happened: tracked contract and financial activation status with blockers identified and activation confirmed. • Where it usually breaks: the project mobilises while the contract is still unsigned, so the company performs work with no enforceable terms. | • Report unsigned contracts where work has started as an exception, since performing under an unexecuted contract leaves the company without enforceable terms or entitlement. • Track the specific blocker rather than a general status. • Escalate where activation is delayed beyond a stated period. • Confirm the advance payment has been received where it is a condition precedent. • Notify the client's obligations that remain outstanding.
928 | Marketing & Sales | Record Hold, No-Go and lost opportunities with standard reason codes | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Record Hold, No-Go and lost opportunities with standard reason codes” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Record Hold, No-Go and lost opportunities with standard reason codes” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she records the opportunities that were held, declined or lost, with a proper reason. • Starts when: an opportunity is held, declined or lost. • How it runs: (1) she establishes the actual outcome and reason. (2) She applies the standard reason code. (3) She records any client feedback. (4) She closes the opportunity in the CRM. (5) She retains the record for analysis. • Proof it happened: closed opportunities with standard reason codes and any client feedback recorded. • Where it usually breaks: everything is coded as price, so the company learns nothing about why it actually loses. | • Prohibit price as a default loss code and require the actual reason, since coding every loss as price prevents the company from learning anything at all. • Obtain client feedback where possible, as the internal explanation is usually wrong. • Distinguish held from lost, because held opportunities can be reactivated. • Close opportunities rather than leaving them open, as an inflated pipeline misleads everyone. • Report loss reasons by segment, since the pattern is what informs strategy.
929 | Marketing & Sales | Perform win-loss analysis and maintain corrective-action records | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Perform win-loss analysis and maintain corrective-action records” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Perform win-loss analysis and maintain corrective-action records” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she analyses why the company wins and loses and follows up the actions. • Starts when: at the analysis cycle, and after significant wins or losses. • How it runs: (1) she analyses the outcomes by reason, segment and value. (2) She identifies the recurring causes. (3) She distinguishes controllable from uncontrollable causes. (4) She agrees corrective actions with owners. (5) She tracks the actions and the effect. • Proof it happened: win loss analysis with recurring causes identified, corrective actions assigned and tracked. • Where it usually breaks: the analysis is produced but no action follows, so the same losses repeat every year. | • Require corrective actions with owners outside marketing where the cause sits elsewhere, since analysis without action means the same losses repeat every year. • Separate controllable causes from market factors, so effort goes where it can change the outcome. • Analyse wins as well as losses, because what works is usually undocumented. • Track whether the corrective actions changed the outcome. • Report to the CMO and the CEO, as most causes are cross functional.
930 | Marketing & Sales | Coordinate client satisfaction, referral and repeat-opportunity follow-up | Marketing Manager (Lead) | Trigger: When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. Action: The Marketing Manager (Lead) completes “Coordinate client satisfaction, referral and repeat-opportunity follow-up” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. Control/Handoff: Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. Continuity/Escalation: A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. Timing: To be confirmed. | When a CRM update, daily follow-up, weekly forecast, client decision, award or post-interaction review becomes due. | The Marketing Manager (Lead) completes “Coordinate client satisfaction, referral and repeat-opportunity follow-up” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an accurate pipeline, forecast, client record, award handover, loss reason, corrective action or repeat-opportunity record. | Won work transfers with complete evidence to CLO, Finance and Technical Engineering; no downstream release occurs before contract and financial gates are visible. | A competent authorised marketing professional may provide operational backup; CMO approvals remain reserved and material brand, spend, client, pipeline, privacy or proposal exceptions escalate to the CMO. | To be confirmed. | • In plain words: she follows up with clients after delivery to check satisfaction and find more work. • Starts when: a project completes, and at the follow up cycle. • How it runs: (1) she contacts the client for structured feedback. (2) She records the satisfaction and any concerns. (3) She asks for referrals where appropriate. (4) She identifies repeat opportunities. (5) She records the outcome and routes concerns for resolution. • Proof it happened: client satisfaction follow up records with feedback, referrals and repeat opportunities identified. • Where it usually breaks: follow up only happens when there is something to sell, so dissatisfaction is discovered when the client goes elsewhere. | • Require structured feedback at project completion regardless of whether there is a sales opportunity, since dissatisfaction is otherwise discovered when the client simply goes elsewhere. • Route concerns raised for resolution rather than only recording them. • Ask for referrals explicitly, as satisfied clients rarely offer them unprompted. • Record the feedback against the account for the health review. • Feed recurring delivery complaints back to the COO, because these affect every future opportunity.
931 | Marketing & Sales | Maintain the assigned target-account and prospect list | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Maintain the assigned target-account and prospect list” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Maintain the assigned target-account and prospect list” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he keeps his own list of the clients he is responsible for chasing. • Starts when: accounts are assigned, and continuously as the list changes. • How it runs: (1) he records each assigned account in the CRM. (2) He records the contacts and their roles. (3) He records the last contact and the next planned action. (4) He keeps the information current. (5) He reviews the list with the Marketing Manager. • Proof it happened: a maintained target account list in the CRM with contacts, last contact and next action recorded. • Where it usually breaks: the real list is in his head and his phone, so nobody else can see the position and it leaves with him. | • Require the account list and all contacts to live in the CRM rather than on a personal phone, since a list held privately is invisible to the company and leaves with the individual. • Require a next action with a date on every assigned account, as accounts without one go dormant. • Record the last contact date, so gaps are visible. • Review the list periodically and release accounts with no realistic potential. • Record more than one contact per account, because a single relationship is lost when that person moves.
932 | Marketing & Sales | Research client organisations, decision makers, influencers and project interests | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Research client organisations, decision makers, influencers and project interests” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Research client organisations, decision makers, influencers and project interests” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he researches the client organisation to find out who decides and what they are planning. • Starts when: an account is assigned or an opportunity emerges. • How it runs: (1) he researches the organisation, its activity and its projects. (2) He identifies the decision makers and the influencers. (3) He identifies their current project interests. (4) He identifies the route into the organisation. (5) He records the findings in the CRM. • Proof it happened: research records identifying decision makers, influencers and project interests, recorded in the CRM. • Where it usually breaks: the relationship is built with a single friendly contact who has no authority, so the effort produces nothing. | • Identify the decision maker and the budget approver separately from the day to day contact, since building the whole relationship with someone who cannot decide is the commonest wasted effort in this role. • Record the decision structure in the CRM, not just contact names. • Use lawful public sources only, and state this in the SOP. • Identify who influences the decision as well as who signs it. • Update the research when contacts change, as these moves are frequent.
933 | Marketing & Sales | Verify prospect contact details, relevance and communication consent | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Verify prospect contact details, relevance and communication consent” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Verify prospect contact details, relevance and communication consent” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he checks the contact details are right, the contact is relevant and consent exists to contact them. • Starts when: a prospect is added or contacted. • How it runs: (1) he verifies the contact details. (2) He confirms the contact's role is relevant. (3) He checks the communication consent status. (4) He records the verification. (5) He removes contacts who are no longer relevant. • Proof it happened: verified contact details with relevance and consent status recorded. • Where it usually breaks: marketing contact is made without consent, which is unlawful and damages the company's standing with the client. | • Check the consent basis before any marketing contact, since unconsented contact is unlawful and creates a poor first impression with the client. • Verify the contact's role and authority, as contacting the wrong person wastes the approach. • Record consent withdrawal immediately and honour it across all channels. • Clean out contacts who have left, because these distort every activity measure. • Distinguish a business enquiry response from marketing outreach, as the consent rules differ.
934 | Marketing & Sales | Identify planned villas, warehouses, retrofit and design-and-build opportunities | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Identify planned villas, warehouses, retrofit and design-and-build opportunities” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Identify planned villas, warehouses, retrofit and design-and-build opportunities” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he looks for the specific project types the company wants: villas, warehouses, retrofits and design and build work. • Starts when: continuously, and when monitoring the market. • How it runs: (1) he monitors the sources for these project types. (2) He identifies the client and the stage the project is at. (3) He assesses whether it fits the company's capability. (4) He records the opportunity. (5) He plans the approach. • Proof it happened: identified opportunities in the target project types recorded with client, stage and fit assessment. • Where it usually breaks: opportunities are identified only once they are formally tendered, which is too late to influence anything. | • Target opportunities before they reach formal tender, since by tender stage the specification is set and the company competes on price alone. • Record the project stage, so the approach can be matched to it. • Assess capability fit before investing effort, as chasing unsuitable work displaces suitable work. • Record opportunities that are too early, so they can be revisited at the right time. • Report opportunity volume by type against the priority segments.
935 | Marketing & Sales | Monitor assigned tender portals, notices and invitation sources | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Monitor assigned tender portals, notices and invitation sources” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Monitor assigned tender portals, notices and invitation sources” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he watches the tender portals and notices he is responsible for. • Starts when: daily. • How it runs: (1) he checks his assigned portals and sources. (2) He identifies relevant notices. (3) He records the submission deadline immediately. (4) He passes them for qualification. (5) He flags short deadlines for a decision. • Proof it happened: a monitoring log with relevant notices identified, deadlines recorded and passed for qualification. • Where it usually breaks: a notice is spotted but the deadline is not recorded, so it is missed while the company is still deciding. | • Record the submission deadline the moment a notice is identified, since a tender lost to a missed deadline is the most avoidable loss possible. • Check the portals daily rather than when convenient. • Flag short deadlines immediately for a bid or no bid decision, so the choice is deliberate. • Record every relevant notice even where a decline is likely. • Name a deputy for portal monitoring during absence.
936 | Marketing & Sales | Build approved referral, consultant, partner and professional-network relationships | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Build approved referral, consultant, partner and professional-network relationships” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Build approved referral, consultant, partner and professional-network relationships” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he builds relationships with consultants, partners and professionals who refer work. • Starts when: referral relationships are being developed. • How it runs: (1) he identifies the consultants and professionals who influence work. (2) He makes contact within the approved conduct rules. (3) He maintains regular contact. (4) He records the relationship and any referrals. (5) He acknowledges referrals received. • Proof it happened: recorded referral relationships with contact history and referrals tracked and acknowledged. • Where it usually breaks: an informal commission arrangement is agreed with a referrer, which is a serious bribery exposure for the company. | • Prohibit any commission or payment arrangement with a referrer without a written agreement approved by the CLO, since informal arrangements are a serious bribery exposure for the company and the individual. • Require every referral relationship to be recorded, so it belongs to the company rather than the individual. • Apply the gifts and hospitality rules to referrer relationships explicitly. • Acknowledge referrals received, as unacknowledged referrers stop referring. • Track the conversion of referred work, because this justifies the effort.
937 | Marketing & Sales | Prepare daily and weekly prospecting, meeting and follow-up plans | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Prepare daily and weekly prospecting, meeting and follow-up plans” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Prepare daily and weekly prospecting, meeting and follow-up plans” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he plans his own week: who he will contact, meet and follow up. • Starts when: at the start of each day and week. • How it runs: (1) he reviews his accounts and opportunities. (2) He plans the outreach and meetings. (3) He plans the follow ups due. (4) He records the plan in the CRM. (5) He reviews achievement against the plan. • Proof it happened: a recorded prospecting and follow up plan with achievement reviewed against it. • Where it usually breaks: the day is spent responding to whatever arrives, so planned prospecting never happens and the pipeline dries up. | • Protect planned prospecting time explicitly, since a day spent responding to whatever arrives produces no new pipeline and the shortfall appears months later. • Plan from the account and opportunity list rather than from memory. • Set a minimum weekly outreach volume and measure it. • Review achievement against the plan, not just activity volume. • Prioritise overdue follow ups over new outreach, as these are closer to revenue.
938 | Marketing & Sales | Submit new market, client, competitor and opportunity signals to the Marketing Manager | Business Development Executive | Trigger: When the approved account plan, prospecting cycle, tender alert or market signal requires action. Action: The Business Development Executive completes “Submit new market, client, competitor and opportunity signals to the Marketing Manager” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: an updated prospect/account record, research note, relationship lead, activity plan or market signal. Control/Handoff: The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the approved account plan, prospecting cycle, tender alert or market signal requires action. | The Business Development Executive completes “Submit new market, client, competitor and opportunity signals to the Marketing Manager” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | an updated prospect/account record, research note, relationship lead, activity plan or market signal. | The Business Development Executive uses approved target criteria and records sources; confidential, unsuitable or conflict-sensitive prospects are escalated to the Marketing Manager. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he passes what he learns about the market and competitors back to the Marketing Manager. • Starts when: he learns something relevant from the market. • How it runs: (1) he notes the signal: client plans, competitor activity or market movement. (2) He records the source and the reliability. (3) He submits it to the Marketing Manager. (4) He avoids submitting rumour as fact. (5) He records it in the CRM where it relates to an account. • Proof it happened: submitted market and competitor signals with the source recorded and reliability indicated. • Where it usually breaks: market information stays in conversations and is never recorded, so the company learns nothing collectively. | • Require market signals to be recorded rather than shared in conversation, since information that stays verbal is lost and the company learns nothing collectively. • Distinguish confirmed information from rumour, as acting on rumour damages bid strategy. • Record the source, so reliability can be judged. • Prohibit using information received from a client in confidence. • Feed significant signals to the CMO promptly rather than at the next review.
939 | Marketing & Sales | Conduct approved calls, emails, WhatsApp messages, visits and networking outreach | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Conduct approved calls, emails, WhatsApp messages, visits and networking outreach” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Conduct approved calls, emails, WhatsApp messages, visits and networking outreach” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he makes the calls, sends the messages, visits and networks to generate interest. • Starts when: per his prospecting plan. • How it runs: (1) he makes contact through the approved channels. (2) He uses the approved introduction and message. (3) He listens for the need rather than presenting. (4) He agrees a next step where there is interest. (5) He records the outcome in the CRM. • Proof it happened: recorded outreach activity with the approach used, the response and the agreed next step. • Where it usually breaks: business conversations happen on a personal number and messaging account, so the company has no record of what was said or promised. | • Require business messaging and calls to run through company accounts and numbers, since conversations on a personal number are not recoverable and are not the company's record. • Record the outcome of every contact attempt, including no response, as this is what shows effort and pattern. • Require the approved message to be used, so capability is not overstated. • Agree an explicit next step, because outreach with no next step produces nothing. • Respect the stated contact preferences and consent.
940 | Marketing & Sales | Use only approved scripts, credentials, presentations and company information | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Use only approved scripts, credentials, presentations and company information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Use only approved scripts, credentials, presentations and company information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he only uses the approved scripts, presentations and company information. • Starts when: preparing for any client contact. • How it runs: (1) he takes the material from the controlled library. (2) He checks it is the current version. (3) He uses the approved claims and credentials only. (4) He avoids creating his own material. (5) He requests new material through the Marketing Manager. • Proof it happened: client contact made using current approved material from the controlled library. • Where it usually breaks: individually created presentations overstate capability, and the client holds the company to the claim. | • Prohibit individually created client facing material, since self made presentations overstate capability and the client holds the company to the claim. • Take material from the controlled library each time rather than reusing an old copy. • Request new material through the proper route rather than improvising. • Check credentials have client consent before presenting them. • Never quote a price or a programme not approved, including as an illustration.
941 | Marketing & Sales | Schedule introductory, discovery and follow-up meetings | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Schedule introductory, discovery and follow-up meetings” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Schedule introductory, discovery and follow-up meetings” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he arranges the introductory, discovery and follow up meetings. • Starts when: a client agrees to meet. • How it runs: (1) he agrees the date, time and attendees. (2) He confirms the purpose and the agenda. (3) He confirms internal attendance where needed. (4) He confirms the meeting in writing. (5) He records it in the CRM. • Proof it happened: scheduled meetings with purpose, attendees and confirmation issued, recorded in the CRM. • Where it usually breaks: the meeting is arranged without confirming who will attend from the client, so it happens with someone who cannot decide anything. | • Confirm who will attend from the client side before arranging internal attendance, since a technical team attending a meeting with a junior contact is expensive wasted time. • State the purpose in the confirmation, as an unpurposed meeting achieves nothing. • Confirm in writing, because unconfirmed meetings are the ones that do not happen. • Record the meeting in the CRM so the account history is complete. • Request the decision maker's attendance explicitly where a decision is sought.
942 | Marketing & Sales | Record each outreach attempt, response and agreed next action in FirstBit CRM | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Record each outreach attempt, response and agreed next action in FirstBit CRM” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Record each outreach attempt, response and agreed next action in FirstBit CRM” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he records every contact attempt, what came back and what was agreed. • Starts when: any client contact occurs. • How it runs: (1) he records the contact with the date and channel. (2) He records the response, including no response. (3) He records what was agreed. (4) He sets the next action with a date. (5) He keeps the record current. • Proof it happened: CRM records of every contact attempt, the response and the agreed next action with a date. • Where it usually breaks: only successful contacts are recorded, so the effort put into an account and the pattern of non response are both invisible. | • Record unsuccessful contact attempts as well as successful ones, since without them the real effort on an account and the pattern of non response are both invisible. • Require a next action with a date on every record, as this is what prevents opportunities going quiet. • Record what was agreed in the client's own terms rather than a summary. • Record the contact the same day, because detail is lost quickly. • Report accounts with no contact for a stated period.
943 | Marketing & Sales | Respond to assigned enquiries within the approved service level | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Respond to assigned enquiries within the approved service level” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Respond to assigned enquiries within the approved service level” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he responds to the enquiries assigned to him within the agreed time. • Starts when: an enquiry is assigned. • How it runs: (1) he acknowledges the assignment. (2) He makes first contact within the service level. (3) He records the contact and the outcome. (4) He agrees the next step with the client. (5) He escalates where he cannot meet the deadline. • Proof it happened: enquiry responses within the service level with contact and next step recorded. • Where it usually breaks: the first response takes days, and by then the client has already engaged someone else. | • Set the first response service level in hours and measure it, since response speed is the single strongest predictor of conversion in construction enquiries. • Require escalation where the deadline cannot be met, so the enquiry is reassigned rather than delayed. • Acknowledge immediately even where a full response takes longer. • Report response times by owner. • Reassign automatically where no contact is made within the service level.
944 | Marketing & Sales | Collect initial project type, location, scope, budget and timing information | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Collect initial project type, location, scope, budget and timing information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Collect initial project type, location, scope, budget and timing information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he collects the basic facts about the project: type, place, size, budget and timing. • Starts when: an enquiry is being developed. • How it runs: (1) he establishes the project type and location. (2) He establishes the scope and scale. (3) He establishes the budget range. (4) He establishes the required timing. (5) He records it in the CRM. • Proof it happened: recorded initial project information covering type, location, scope, budget and timing. • Where it usually breaks: budget and timing are not established because they feel intrusive, so the opportunity is worked without knowing whether it is real. | • Require budget and timing to be established at first contact, since without them the opportunity is being worked with no idea whether it is real. • Ask for a range rather than an exact figure, as this is easier for the client to give. • Record what the client could not answer, so the gaps are visible. • Establish the funding source for private clients, because this determines whether the project proceeds. • Record the information in the CRM rather than retaining it personally.
945 | Marketing & Sales | Identify decision makers, approval stakeholders and procurement route | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Identify decision makers, approval stakeholders and procurement route” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Identify decision makers, approval stakeholders and procurement route” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he works out who actually decides and how the client will buy. • Starts when: an enquiry is being qualified. • How it runs: (1) he identifies who will make the decision. (2) He identifies who approves the budget. (3) He identifies any consultant or adviser involved. (4) He establishes the procurement route. (5) He records the decision structure. • Proof it happened: a recorded decision structure with decision maker, budget approver, advisers and procurement route. • Where it usually breaks: the contact is assumed to be the decision maker, and the proposal is later rejected by someone never met. | • Establish the decision maker and the budget approver explicitly rather than assuming the contact is both, since a proposal rejected by someone never met is the standard late stage loss. • Identify any consultant involved, as they often control the specification and the shortlist. • Establish the procurement route, because a negotiated approach and a formal tender need entirely different effort. • Record the decision timeline and the process. • Seek access to the decision maker rather than relying on the contact to relay.
946 | Marketing & Sales | Flag duplicate, unsuitable, suspicious or out-of-strategy enquiries for review | Business Development Executive | Trigger: When an assigned prospect or enquiry reaches the outreach and first-response stage. Action: The Business Development Executive completes “Flag duplicate, unsuitable, suspicious or out-of-strategy enquiries for review” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. Control/Handoff: Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an assigned prospect or enquiry reaches the outreach and first-response stage. | The Business Development Executive completes “Flag duplicate, unsuitable, suspicious or out-of-strategy enquiries for review” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a compliant outreach record, scheduled meeting, captured initial requirement and qualification flag. | Only approved material and channels are used; no price, scope, programme or contractual promise is made outside delegated authority. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he flags the enquiries that are duplicated, unsuitable or look suspicious. • Starts when: an enquiry raises a concern. • How it runs: (1) he identifies the concern: duplicate, unsuitable, suspicious or outside strategy. (2) He records the specific reason. (3) He flags it to the Marketing Manager. (4) He does not commit effort pending review. (5) He records the outcome of the review. • Proof it happened: flagged enquiries with the specific concern recorded and the review outcome noted. • Where it usually breaks: a suspicious enquiry is worked anyway because it looks like revenue, and the company invests effort in something that was never real. | • Require effort to stop pending review on a flagged enquiry, since working a suspicious enquiry because it looks like revenue invests real cost in something that was never real. • List the warning signs explicitly: unverifiable client, unusual urgency, reluctance to meet and requests for pricing without scope. • Require duplicates to be checked before any effort is committed. • Escalate anything suggesting fraud rather than simply declining it. • Record the outcome, so the same enquiry is not reworked later.
947 | Marketing & Sales | Prepare the client and opportunity briefing before each meeting | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Prepare the client and opportunity briefing before each meeting” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Prepare the client and opportunity briefing before each meeting” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: before every meeting he prepares by reading up on the client and the opportunity. • Starts when: a meeting is scheduled. • How it runs: (1) he reviews the account and opportunity history. (2) He reviews the client's business and recent activity. (3) He prepares his objectives for the meeting. (4) He prepares the questions to ask. (5) He briefs any internal attendees. • Proof it happened: a prepared briefing with account history, objectives and questions, and internal attendees briefed. • Where it usually breaks: he arrives having read nothing, so the meeting is spent on questions already answered in the file. | • Require the account history to be reviewed before every meeting, since asking questions already answered in the file tells the client the company is not paying attention. • Set a specific objective for each meeting, as an unfocused meeting produces no next step. • Brief internal attendees, so the client does not receive conflicting messages. • Prepare the questions rather than improvising, because the quality of questions determines the quality of qualification. • Know what has already been committed or offered.
948 | Marketing & Sales | Conduct the approved discovery meeting and record complete meeting notes | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Conduct the approved discovery meeting and record complete meeting notes” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Conduct the approved discovery meeting and record complete meeting notes” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he runs the discovery meeting and writes down what was actually said. • Starts when: at the meeting. • How it runs: (1) he follows the approved discovery approach. (2) He listens and asks rather than presenting. (3) He records the client's requirements in their own words. (4) He confirms his understanding back to the client. (5) He writes up the notes the same day. • Proof it happened: complete meeting notes recording the client's requirements, confirmed understanding and agreed next steps. • Where it usually breaks: notes are written days later from memory, so requirements are recorded inaccurately and the design is wrong from the start. | • Write up meeting notes the same day, since notes reconstructed days later lose the detail and the design or estimate is then built on an inaccurate requirement. • Record requirements in the client's own words rather than interpreted, as the interpretation is frequently wrong. • Confirm understanding back to the client in the meeting and again in writing. • Record what the client did not want as well as what they did. • Record the notes in the CRM rather than in a personal notebook.
949 | Marketing & Sales | Capture client business need, required service, scope and expected outcome | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Capture client business need, required service, scope and expected outcome” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Capture client business need, required service, scope and expected outcome” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he captures what the client is actually trying to achieve and what service they need. • Starts when: during and after the discovery meeting. • How it runs: (1) he records the business need behind the request. (2) He records the specific service required. (3) He records the scope as the client describes it. (4) He records the outcome the client expects. (5) He confirms it with the client in writing. • Proof it happened: recorded client need, required service, scope and expected outcome, confirmed in writing. • Where it usually breaks: the stated request is recorded without the underlying need, so the company proposes the wrong solution to the right problem. | • Record the underlying business need as well as the stated request, since proposing exactly what was asked for often solves the wrong problem and loses to a better proposal. • Record the expected outcome, as this is what the client will judge the result against. • Confirm the scope understanding in writing, because this becomes the baseline for every variation. • Record the client's own priorities between cost, time and quality. • Distinguish requirements from preferences.
950 | Marketing & Sales | Confirm indicative budget, target programme, decision date and selection criteria | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Confirm indicative budget, target programme, decision date and selection criteria” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Confirm indicative budget, target programme, decision date and selection criteria” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he confirms the budget, the programme, when they will decide and how they will choose. • Starts when: during qualification. • How it runs: (1) he confirms the indicative budget and its status. (2) He confirms the target programme. (3) He confirms the decision date. (4) He establishes the selection criteria. (5) He records all four in the CRM. • Proof it happened: recorded budget, programme, decision date and selection criteria. • Where it usually breaks: selection criteria are never asked about, so the proposal is built on price when the client is actually deciding on programme. | • Ask the client directly what will decide the award, since a proposal optimised for price when the client is deciding on programme loses for no reason. • Confirm whether the budget is approved or aspirational, as these are entirely different situations. • Confirm the decision date and who is involved, because a client with no date will not decide. • Record the competition where the client will say. • Update these four items whenever they change.
951 | Marketing & Sales | Coordinate site-visit timing, access, attendance and available documents | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Coordinate site-visit timing, access, attendance and available documents” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Coordinate site-visit timing, access, attendance and available documents” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he arranges the site visit and makes sure the right people and documents are there. • Starts when: a site visit is needed. • How it runs: (1) he agrees the timing and access with the client. (2) He confirms who will attend from both sides. (3) He requests the available documents in advance. (4) He confirms the arrangements in writing. (5) He confirms the visit took place as planned. • Proof it happened: an arranged site visit with access, attendance and documents confirmed in writing. • Where it usually breaks: the technical team attends and the client's decision maker does not, so the requirement is never confirmed with the person who matters. | • Request the decision maker's attendance at the site visit, since a visit without them means the requirement is confirmed with somebody who cannot confirm it. • Request the available drawings and documents before the visit, so the time is used effectively. • Confirm access arrangements in writing, because a failed visit wastes senior time on both sides. • Confirm what will be examined, so the right people attend. • Record who attended, as this determines whose confirmation was obtained.
952 | Marketing & Sales | Record site access information, photographs, drawings and client-provided evidence | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Record site access information, photographs, drawings and client-provided evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Record site access information, photographs, drawings and client-provided evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he records what he found on site, with photographs and whatever the client provided. • Starts when: at the site visit. • How it runs: (1) he records the access and site conditions. (2) He photographs the relevant conditions. (3) He collects the drawings and documents the client provides. (4) He records what was not available. (5) He files everything against the opportunity. • Proof it happened: recorded site information with photographs, client documents and gaps noted, filed against the opportunity. • Where it usually breaks: photographs stay on a personal phone, so the technical team estimates without ever seeing the site conditions. | • Upload site photographs to the opportunity record the same day, since images left on a personal phone mean the technical team estimates without seeing the site. • Photograph access routes and constraints as well as the work area, because access drives significant cost. • Record what could not be examined or was not provided, so assumptions are visible in the offer. • Record measurements and observations rather than relying on recall. • Note anything suggesting hidden conditions such as damp, movement or previous repairs.
953 | Marketing & Sales | Raise missing-information and clarification requests through the Marketing Manager | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Raise missing-information and clarification requests through the Marketing Manager” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Raise missing-information and clarification requests through the Marketing Manager” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: when information is missing he raises the request properly rather than chasing informally. • Starts when: missing information is identified. • How it runs: (1) he identifies exactly what is missing. (2) He raises the request through the Marketing Manager. (3) He communicates it to the client as a single list. (4) He tracks the responses. (5) He escalates where information is not provided. • Proof it happened: raised clarification requests with the items listed, tracked to response and escalated where unanswered. • Where it usually breaks: information is requested piecemeal over weeks, so the client becomes frustrated and the assessment stalls repeatedly. | • Request missing information as one consolidated list rather than piecemeal, since repeated requests frustrate the client and stall the assessment each time. • Set a response deadline and escalate rather than chasing indefinitely. • Record what remains unanswered, so it becomes a stated assumption in the offer. • Route requests through the agreed channel, as parallel requests from several people look disorganised. • Report opportunities stalled on missing information.
954 | Marketing & Sales | Confirm the client’s next action, Sevents owner and follow-up date | Business Development Executive | Trigger: When an approved discovery meeting or site visit is scheduled. Action: The Business Development Executive completes “Confirm the client’s next action, Sevents owner and follow-up date” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. Control/Handoff: Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When an approved discovery meeting or site visit is scheduled. | The Business Development Executive completes “Confirm the client’s next action, Sevents owner and follow-up date” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | complete meeting/site evidence, clarified needs, stakeholders, decision criteria and documented next action. | Client-provided information is labelled and protected; technical conclusions remain subject to CTO review and missing or conflicting requirements are escalated. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he confirms what the client will do next, who owns it here and by when. • Starts when: at the end of every client interaction. • How it runs: (1) he agrees the client's next action. (2) He confirms the company's next action and owner. (3) He agrees the date for each. (4) He confirms it in writing. (5) He records it in the CRM as the next action. • Proof it happened: an agreed and confirmed next action on both sides with dates, recorded in the CRM. • Where it usually breaks: the meeting ends with a general intention to be in touch, so the opportunity goes quiet and neither side moves. | • Require a dated next action on both sides at the end of every interaction, since ending on a general intention to be in touch is how opportunities go quiet. • Confirm the next action in writing the same day. • Record it in the CRM as the next action with its date. • Name the owner on the company side, so the client knows who to expect. • Follow up on the agreed date rather than waiting for the client.
955 | Marketing & Sales | Support preparation of the qualified-lead handover to Technical Engineering | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Support preparation of the qualified-lead handover to Technical Engineering” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Support preparation of the qualified-lead handover to Technical Engineering” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he helps put together the handover pack for engineering. • Starts when: a lead is ready for technical handover. • How it runs: (1) he assembles his meeting notes and the client brief. (2) He provides the site information and photographs. (3) He provides the qualification findings. (4) He identifies the gaps and assumptions. (5) He confirms the pack with the Marketing Manager. • Proof it happened: a contributed handover pack with meeting notes, site information, qualification findings and gaps identified. • Where it usually breaks: the handover omits what the client said informally, so the technical team misses requirements the client considers agreed. | • Include informal client statements and preferences in the handover, since the client considers these agreed and the technical team never hears them otherwise. • State the assumptions and the gaps explicitly, so they can be qualified in the offer. • Include the site photographs and access information. • Confirm the pack is complete before handover rather than sending supplements afterwards. • Remain available to the technical team for clarification.
956 | Marketing & Sales | Follow up missing drawings, briefs, KYC and decision information | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Follow up missing drawings, briefs, KYC and decision information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Follow up missing drawings, briefs, KYC and decision information” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he chases the client for the drawings, information and details still outstanding. • Starts when: information remains outstanding. • How it runs: (1) he tracks what is outstanding. (2) He follows up on the agreed schedule. (3) He records each follow up and the response. (4) He escalates where it is not provided. (5) He confirms receipt and passes it on. • Proof it happened: follow up records with outstanding items tracked, escalations and receipt confirmed. • Where it usually breaks: chasing stops after two attempts, so the opportunity stalls without ever being formally closed or progressed. | • Set a follow up schedule with an escalation point, since chasing that simply stops leaves the opportunity neither progressed nor closed. • Record every follow up attempt, as this is the evidence of effort and the basis for escalation. • Escalate to the Marketing Manager rather than abandoning the opportunity. • Consider proceeding on stated assumptions where information will not come, with approval. • Report opportunities stalled on client information, as the volume matters.
957 | Marketing & Sales | Support approved concept, capability, proposal and quotation presentations | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Support approved concept, capability, proposal and quotation presentations” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Support approved concept, capability, proposal and quotation presentations” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he supports the presentations of concepts, capability and proposals. • Starts when: a presentation is arranged. • How it runs: (1) he confirms the material is approved and current. (2) He arranges the meeting and the attendees. (3) He supports the presentation. (4) He records the client's reaction and questions. (5) He confirms the next step in writing. • Proof it happened: supported presentations using approved material with the client's reaction and next step recorded. • Where it usually breaks: he answers a pricing or technical question off the cuff, and the answer becomes a commitment. | • Prohibit answering pricing or technical questions in the room without approval, since an off the cuff answer becomes a commitment the company must honour. • State clearly what is indicative and what is firm. • Record the client's questions and objections, as these shape the final proposal. • Use approved material only. • Confirm the next step in writing the same day.
958 | Marketing & Sales | Issue only approved and revision-controlled client documents | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Issue only approved and revision-controlled client documents” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Issue only approved and revision-controlled client documents” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he only sends the client documents that are approved and version controlled. • Starts when: a document is to be sent to a client. • How it runs: (1) he confirms the document is approved. (2) He confirms it is the current version. (3) He sends it through the recorded route. (4) He records what was sent and when. (5) He confirms client receipt. • Proof it happened: client documents sent from approved current versions with the issue recorded and receipt confirmed. • Where it usually breaks: an older version is sent from a personal folder, so the client holds terms the company never approved. | • Send documents from the controlled location only and never from a personal folder, since an older version reaching the client creates terms the company never approved. • Record what was sent and when, as this is the evidence of the offer. • Confirm receipt, because clients frequently deny receiving proposals. • Send in a non editable format. • Confirm which version is current when a revision is issued.
959 | Marketing & Sales | Record client feedback, questions, objections and clarification requests | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Record client feedback, questions, objections and clarification requests” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Record client feedback, questions, objections and clarification requests” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he records what the client says back, including objections and questions. • Starts when: the client responds to a proposal or presentation. • How it runs: (1) he records the feedback precisely. (2) He records the objections raised. (3) He records the clarifications requested. (4) He passes them to the Marketing Manager for response. (5) He records the response given. • Proof it happened: recorded client feedback, objections and clarification requests with the responses given. • Where it usually breaks: objections are not recorded because they are uncomfortable, so the same objection loses the next bid as well. | • Require objections to be recorded exactly as raised, since unrecorded objections lose the next bid in the same way and the company never learns. • Record the client's exact wording rather than a softened summary. • Pass technical and commercial clarifications for proper response rather than answering directly. • Record the response given, so the position stays consistent. • Report recurring objections, as these indicate a real weakness in the offer.
960 | Marketing & Sales | Follow up quotation, design-agreement, award and contract decisions | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Follow up quotation, design-agreement, award and contract decisions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Follow up quotation, design-agreement, award and contract decisions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he follows up on the quotation and chases the decision. • Starts when: a quotation or agreement is with the client. • How it runs: (1) he confirms the client received it. (2) He follows up on the agreed schedule. (3) He establishes where the decision stands. (4) He identifies and addresses any blocker. (5) He records each follow up and the position. • Proof it happened: follow up records with receipt confirmed, decision status established and blockers identified. • Where it usually breaks: follow up consists of asking whether there is any news, which gives the client no reason to engage. | • Require each follow up to add something rather than asking for news, since a contentless chase gives the client no reason to respond and trains them to ignore contact. • Establish where the decision actually stands and what is blocking it. • Confirm the client received the document, as proposals are frequently not received. • Set the follow up schedule at the time of issue. • Escalate where the client has gone silent rather than continuing indefinitely.
961 | Marketing & Sales | Support negotiations only within CMO-approved boundaries | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Support negotiations only within CMO-approved boundaries” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Support negotiations only within CMO-approved boundaries” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he only negotiates within the limits he has been given. • Starts when: a negotiation arises. • How it runs: (1) he confirms the approved boundaries before engaging. (2) He negotiates within them. (3) He refers anything outside them for approval. (4) He records what was discussed and offered. (5) He confirms the agreed position in writing. • Proof it happened: negotiation records within the approved boundaries with anything outside referred for approval. • Where it usually breaks: a concession is offered verbally to keep momentum, and the company is then held to it. | • Prohibit offering any concession verbally, even indicatively, since the client treats it as given and the company is held to it. • Confirm the boundaries in writing before engaging, so they are not misremembered under pressure. • Refer anything outside the boundaries rather than assuming it would be approved. • Record what was offered and by whom. • Require concessions to be traded rather than given.
962 | Marketing & Sales | Convert verbal client commitments into written confirmation and CRM evidence | Business Development Executive | Trigger: When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. Action: The Business Development Executive completes “Convert verbal client commitments into written confirmation and CRM evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a complete support record, controlled client document, feedback log, follow-up result or written commitment. Control/Handoff: Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When the opportunity requires technical handover, proposal presentation, quotation follow-up, negotiation support or written confirmation. | The Business Development Executive completes “Convert verbal client commitments into written confirmation and CRM evidence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a complete support record, controlled client document, feedback log, follow-up result or written commitment. | Only approved revisions are shared and negotiation remains within CMO authority; technical, legal, pricing or payment changes route to CTO, CLO or CFO. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: when the client agrees something verbally he gets it in writing. • Starts when: a client makes a verbal commitment. • How it runs: (1) he records what was said and when. (2) He writes to the client confirming his understanding. (3) He requests written confirmation. (4) He records the confirmation received. (5) He treats it as committed only once confirmed. • Proof it happened: verbal commitments confirmed in writing to the client with the written confirmation recorded. • Where it usually breaks: a verbal award is reported internally as a win, so mobilisation begins on something that was never committed. | • Confirm verbal client commitments in writing the same day and treat nothing as committed until confirmed, since mobilising on a verbal award is unrecoverable if it evaporates. • Prohibit reporting verbal commitments as won in the CRM. • Record what was said and by whom, so the position can be evidenced. • Request written confirmation explicitly rather than hoping it follows. • Escalate where the client will not confirm in writing, as this is itself a signal.
963 | Marketing & Sales | Maintain current CRM stage, notes, contacts, tasks and next-action dates | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Maintain current CRM stage, notes, contacts, tasks and next-action dates” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Maintain current CRM stage, notes, contacts, tasks and next-action dates” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he keeps his CRM records current on stage, contacts, tasks and next actions. • Starts when: continuously as things happen. • How it runs: (1) he updates the stage when it changes. (2) He updates the contacts and their roles. (3) He records the tasks and their dates. (4) He records the next action. (5) He keeps the notes current. • Proof it happened: current CRM records with stage, contacts, tasks and next action dates maintained. • Where it usually breaks: the CRM is updated once a week from memory, so the dates and details are wrong and the pipeline is unreliable. | • Require CRM updates at the time of the event rather than weekly from memory, since reconstructed records carry wrong dates and details and the pipeline built on them is unreliable. • Require a next action date on every live opportunity. • Update contacts when people change roles, as stale contacts waste every future approach. • Record enough detail that a colleague could pick the opportunity up. • Report records not updated within a stated period.
964 | Marketing & Sales | Update opportunity probability, value, expected close date and decision status | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Update opportunity probability, value, expected close date and decision status” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Update opportunity probability, value, expected close date and decision status” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he keeps the probability, value and expected close date honest. • Starts when: at each opportunity review, and when the position changes. • How it runs: (1) he assesses the probability against the stage criteria. (2) He updates the value as the scope firms up. (3) He updates the expected close date with a justification. (4) He records the decision status. (5) He explains changes at the pipeline review. • Proof it happened: updated probability, value, close date and decision status with changes explained. • Where it usually breaks: the close date is rolled forward every week without explanation, so the forecast is permanently one month away. | • Require a justification whenever a close date is moved, since a date rolled forward each week keeps the forecast permanently one month away and useless. • Tie probability to the stage criteria rather than to confidence. • Require the value to be updated as scope changes, in both directions. • Require opportunities with repeated date slips to be reviewed or closed. • Track his own forecast accuracy, as this is what improves honesty.
965 | Marketing & Sales | Report daily and weekly pipeline movement, delays and support requirements | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Report daily and weekly pipeline movement, delays and support requirements” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Report daily and weekly pipeline movement, delays and support requirements” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he reports what moved in his pipeline, what is stuck and what help he needs. • Starts when: daily and weekly on the reporting cycle. • How it runs: (1) he reports the movements: advances, wins, losses and slips. (2) He reports the delays and their causes. (3) He identifies where he needs support. (4) He states his planned actions. (5) He records the reporting. • Proof it happened: reported pipeline movement, delays and support requirements with planned actions stated. • Where it usually breaks: support is requested too late, so an opportunity is lost for want of technical or commercial help that was available. | • Require support needs to be raised as soon as identified rather than at the weekly review, since opportunities are lost for want of help that was available all along. • Report movement rather than the static position, as movement is what management can act on. • Report the cause of each delay, particularly internal causes. • State planned actions with dates. • Report honestly on opportunities that have gone quiet.
966 | Marketing & Sales | Maintain the approved client relationship and communication cadence | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Maintain the approved client relationship and communication cadence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Maintain the approved client relationship and communication cadence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he keeps in regular contact with his clients at the agreed frequency. • Starts when: the contact plan is set, and continuously. • How it runs: (1) he follows the agreed contact frequency per account. (2) He makes contact with something of value rather than just checking in. (3) He records each contact. (4) He updates the account information. (5) He reviews accounts with no recent contact. • Proof it happened: maintained contact cadence per account with each contact recorded. • Where it usually breaks: contact only happens when there is something to sell, so the client only hears from the company when it wants something. | • Require contact independent of live opportunities, since a client who only hears from the company when it wants something does not build a relationship. • Require each contact to carry something of value rather than a check in. • Set the cadence by account priority, as not every account warrants the same frequency. • Report accounts with no contact for a stated period. • Record the contact in the CRM so the account history is complete.
967 | Marketing & Sales | Coordinate client satisfaction, referral and repeat-business discussions | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Coordinate client satisfaction, referral and repeat-business discussions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Coordinate client satisfaction, referral and repeat-business discussions” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he talks to clients after delivery about satisfaction, referrals and further work. • Starts when: a project completes, and at the follow up cycle. • How it runs: (1) he contacts the client for feedback. (2) He records the satisfaction and any concerns. (3) He asks about further requirements. (4) He asks for referrals where appropriate. (5) He routes concerns for resolution. • Proof it happened: post delivery discussions with feedback, further requirements and referrals recorded, concerns routed. • Where it usually breaks: concerns raised are not passed on, so the client repeats them to somebody else and the company never addresses them. | • Route every concern raised for resolution and confirm back to the client, since unaddressed concerns are repeated to others and cost future work. • Ask for referrals explicitly, as satisfied clients rarely offer them unprompted. • Conduct the conversation regardless of whether there is an immediate opportunity. • Record the feedback against the account. • Ask what the company could have done better, because this is the most useful question.
968 | Marketing & Sales | Record no-response, Hold, No-Go and loss reasons accurately | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Record no-response, Hold, No-Go and loss reasons accurately” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Record no-response, Hold, No-Go and loss reasons accurately” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he records honestly why an opportunity went nowhere. • Starts when: an opportunity is held, declined or lost. • How it runs: (1) he establishes the actual reason. (2) He seeks the client's explanation where possible. (3) He applies the correct reason code. (4) He records any client feedback. (5) He closes the opportunity in the CRM. • Proof it happened: closed opportunities with accurate reason codes and any client feedback recorded. • Where it usually breaks: price is recorded by default because it is the least uncomfortable answer, so the company never learns the real cause. | • Prohibit price as a default reason and require the actual cause, since price is the least uncomfortable answer and recording it every time teaches the company nothing. • Ask the client why, as the internal assumption is usually wrong. • Distinguish no response from a decision, because these need different follow up. • Close opportunities rather than leaving them open to inflate the pipeline. • State clearly that recording a loss honestly is expected and not penalised.
969 | Marketing & Sales | Capture competitor, client, price-position and market intelligence | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Capture competitor, client, price-position and market intelligence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Capture competitor, client, price-position and market intelligence” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he passes on what he learns about competitors, clients and pricing. • Starts when: he learns something relevant. • How it runs: (1) he records what he learned and from where. (2) He distinguishes fact from impression. (3) He submits it to the Marketing Manager. (4) He records it against the account where relevant. (5) He avoids passing on confidential client information. • Proof it happened: recorded market and competitor intelligence with sources and reliability indicated. • Where it usually breaks: information received from one client in confidence is used with another, which is a real confidentiality breach. | • State explicitly that information received from a client in confidence may not be used with another client, since this is a genuine confidentiality breach that is often treated as harmless. • Distinguish confirmed facts from impressions, as acting on impressions damages bid strategy. • Record the source so reliability can be judged. • Gather competitor information from lawful public sources only. • Submit intelligence promptly, because its value decays quickly.
970 | Marketing & Sales | Protect confidential information and escalate complaints, conflicts or ethical concerns | Business Development Executive | Trigger: When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. Action: The Business Development Executive completes “Protect confidential information and escalate complaints, conflicts or ethical concerns” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. Output/Evidence: a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. Control/Handoff: CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. Continuity/Escalation: A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. Timing: To be confirmed. | When a client interaction, task due date, pipeline cutoff, relationship review or market observation occurs. | The Business Development Executive completes “Protect confidential information and escalate complaints, conflicts or ethical concerns” using approved client information, market evidence, company credentials, project records, authority limits and controlled FirstBit CRM/client-folder records. | a current CRM record, pipeline update, relationship action, loss reason, intelligence note or escalated concern. | CRM must reflect the real status and next action; material complaints, confidentiality breaches, conflicts or misleading information are escalated immediately. | A trained authorised Business Development Executive may provide activity backup using controlled CRM access; client commitments, pricing, scope, contract, credit and material complaint decisions escalate to the Marketing Manager or CMO. | To be confirmed. | • In plain words: he protects confidential information and reports complaints, conflicts and ethical concerns. • Starts when: continuously, and when a concern arises. • How it runs: (1) he keeps client and company information confidential. (2) He declares any personal relationship with a client contact. (3) He refuses gifts outside the policy. (4) He escalates complaints and ethical concerns immediately. (5) He records the escalation. • Proof it happened: confidentiality maintained, declarations made and complaints or concerns escalated and recorded. • Where it usually breaks: a gift or hospitality is accepted during a live tender, which compromises the whole process even if nothing improper follows. | • State that gifts and hospitality must be refused during a live tender regardless of value, since acceptance compromises the process whether or not anything improper follows. • Require declaration of any personal relationship with a client contact, and record it. • Require immediate escalation of complaints rather than handling them personally. • Provide a confidential route for reporting ethical concerns about colleagues. • Require confidential client information to be held in the controlled system, not personally.
971 | People & Culture | Set workforce organisation and People & Culture strategy | Chief People & Culture Officer (CPCO) | Trigger: At the annual planning cycle or a material organisation change. Action: Define the approved organisation structure, workforce principles, departmental objectives and People & Culture priorities. Output/Evidence: The recorded approved organisation and workforce plan. Control/Handoff: Responsibilities are cascaded to the HR & Admin Lead. Continuity/Escalation: An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. Timing: To be confirmed. | At the annual planning cycle or a material organisation change. | Define the approved organisation structure, workforce principles, departmental objectives and People & Culture priorities. | The recorded approved organisation and workforce plan. | Responsibilities are cascaded to the HR & Admin Lead. | An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. | To be confirmed. | • In plain words: he decides how the company is organised in terms of people, and what the company is trying to be as a place to work. • Starts when: the annual planning cycle opens, or the business changes enough that the current structure no longer fits. • How it runs: (1) he reviews what the business plan will require in people and skills. (2) He designs the organisation structure and reporting lines. (3) He sets the people objectives for the year. (4) He obtains the CEO's approval. (5) He issues the structure and the policies to the chiefs. • Proof it happened: an approved organisation structure and people strategy with annual objectives, issued to the business. • Where it usually breaks: the structure on paper does not match how work actually flows, so people report to one person and take instructions from another. | • Require the structure to state a single reporting line per role, since dual reporting without a stated priority is the commonest source of conflict and inaction. • Set measurable people objectives: turnover, time to fill, training completion and absence. Objectives without measures cannot be reviewed. • Require the structure to be reissued when it changes, as an outdated chart is used to justify decisions long after it is wrong. • Link the structure to the delegation of authority, so each role's decision rights are defined alongside its position. • Require the chiefs to confirm their own structure, otherwise the chart reflects intention rather than reality.
972 | People & Culture | Approve manpower plan, recruitment and compensation proposals | Chief People & Culture Officer (CPCO) | Trigger: When departments submit validated manpower needs. Action: Review business need, budget, grade, recruitment route and proposed compensation, then approve, reject or return the manpower plan. Output/Evidence: The retained manpower plan decision record. Control/Handoff: The decision record is retained before recruitment begins. Continuity/Escalation: An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. Timing: To be confirmed. | When departments submit validated manpower needs. | Review business need, budget, grade, recruitment route and proposed compensation, then approve, reject or return the manpower plan. | The retained manpower plan decision record. | The decision record is retained before recruitment begins. | An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. | To be confirmed. | • In plain words: he approves how many people will be hired, how they will be recruited and what they will be paid. • Starts when: the manpower plan is prepared, or a recruitment or pay proposal is raised. • How it runs: (1) he reviews the manpower requirement against the business plan. (2) He checks the cost against the approved budget. (3) He reviews the recruitment approach and the sources. (4) He reviews the compensation proposal against the internal structure. (5) He approves or escalates beyond his authority. • Proof it happened: approved manpower plan, recruitment approach and compensation proposals with budget confirmed. • Where it usually breaks: salaries are agreed individually to close a hire, so the internal pay structure becomes inconsistent and unmanageable. | • Require every offer to be checked against the internal pay structure, since salaries agreed individually to close a hire create inconsistencies that surface as grievances and unplanned cost. • Require the manpower plan to be checked against approved budget and the project pipeline, not against current workload alone. • Require the full employment cost to be assessed, including visa, insurance, accommodation and end of service accrual. • State who may approve an offer above the band, and require it in writing. • Review pay structure annually, as a structure never reviewed is worked around continuously.
973 | People & Culture | Approve employment, salary, leave and termination decisions | Chief People & Culture Officer (CPCO) | Trigger: When a controlled employment decision exceeds routine processing. Action: Verify the complete recommendation, authority level, budget and supporting evidence. Output/Evidence: The recorded approval or rejection. Control/Handoff: HR changes the employee record or communicates the decision only after the approval is recorded. Continuity/Escalation: An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. Timing: To be confirmed. | When a controlled employment decision exceeds routine processing. | Verify the complete recommendation, authority level, budget and supporting evidence. | The recorded approval or rejection. | HR changes the employee record or communicates the decision only after the approval is recorded. | An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. | To be confirmed. | • In plain words: he approves the decisions that affect someone's employment: hiring, pay, leave and termination. • Starts when: such a decision is proposed. • How it runs: (1) he reviews the proposal and its basis. (2) He checks the legal and contractual position. (3) He checks the consistency with previous decisions. (4) He checks the cost and the approvals required. (5) He approves, refers or rejects and records the decision. • Proof it happened: approved employment decisions with the basis, legal position and consistency recorded. • Where it usually breaks: a termination is approved without the process having been followed, so the decision is procedurally unfair regardless of its merits. | • Require confirmation that the disciplinary or performance process was followed before approving any termination, since a procedurally defective dismissal creates liability regardless of how justified it was. • Require CLO review for terminations above a stated risk, and for any dismissal for cause. • Check consistency with previous similar decisions, as inconsistency is the basis of most discrimination claims. • Require the documented performance or conduct history to be attached. • Record the reasoning, because these decisions are challenged months later.
974 | People & Culture | Review performance, capability and succession risks | Chief People & Culture Officer (CPCO) | Trigger: Quarterly and annually. Action: Review appraisal results, critical-role coverage, capability gaps, probation outcomes and succession risks. Output/Evidence: Issued approved development, replacement or succession actions with named owners and deadlines. Control/Handoff: Named owners deliver the approved actions by the stated deadlines. Continuity/Escalation: An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. Timing: To be confirmed. | Quarterly and annually. | Review appraisal results, critical-role coverage, capability gaps, probation outcomes and succession risks. | Issued approved development, replacement or succession actions with named owners and deadlines. | Named owners deliver the approved actions by the stated deadlines. | An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. | To be confirmed. | • In plain words: he reviews how people are performing, what skills are missing and who could replace key people. • Starts when: at the review cycle, and when a key role becomes at risk. • How it runs: (1) he reviews the performance outcomes across the company. (2) He identifies the capability gaps. (3) He identifies the roles with no successor. (4) He agrees development and succession actions with the chiefs. (5) He reports the risks to the CEO. • Proof it happened: a documented review of performance, capability and succession with identified risks and agreed actions. • Where it usually breaks: succession is discussed but nothing is done, so a key departure leaves the company with no cover at all. | • Require a named successor or a stated plan for every critical role, since succession discussed without action leaves the company exposed the day someone resigns. • Identify single points of failure explicitly, including roles where knowledge is undocumented. • Require development actions with dates rather than general intentions. • Review capability against the future plan, not only current performance. • Report unmitigated succession risk to the CEO, as this is a business risk rather than an HR matter.
975 | People & Culture | Govern employee relations, discipline and grievance cases | Chief People & Culture Officer (CPCO) | Trigger: When a grievance, misconduct or material employee-relations issue is raised. Action: Ensure fair fact-finding, controlled documentation, appropriate consultation and an authorised decision. Output/Evidence: The complete retained case record. Control/Handoff: Confidentiality is protected and the case record is released only to authorised parties. Continuity/Escalation: An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. Timing: To be confirmed. | When a grievance, misconduct or material employee-relations issue is raised. | Ensure fair fact-finding, controlled documentation, appropriate consultation and an authorised decision. | The complete retained case record. | Confidentiality is protected and the case record is released only to authorised parties. | An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. | To be confirmed. | • In plain words: he oversees how employee relations, discipline and grievances are handled. • Starts when: a case is raised or escalated. • How it runs: (1) he confirms the process to be followed. (2) He confirms the investigator is independent. (3) He reviews the findings and the proposed outcome. (4) He checks consistency and legal compliance. (5) He approves the outcome and records it. • Proof it happened: governed cases with the process followed, independent investigation and the outcome approved and recorded. • Where it usually breaks: the manager complained about investigates the complaint, so the outcome is invalid however correct it may be. | • Require the investigator to be independent of both the complainant and the reporting line complained about, since a manager investigating their own case invalidates the outcome however correct it is. • Require the process and timeline to be stated to both parties at the outset. • Require findings to be recorded with the evidence relied on, not just the conclusion. • Check consistency against previous similar cases. • Provide a confidential route for grievances about senior staff, as these are otherwise never raised.
976 | People & Culture | Report workforce cost, compliance and People & Culture KPIs | Chief People & Culture Officer (CPCO) | Trigger: At the approved monthly and quarterly reporting cadence. Action: Review headcount, attendance, turnover, recruitment, overtime, leave, payroll exceptions, expiry exposure and open employee actions. Output/Evidence: The verified People & Culture dashboard and corrective actions. Control/Handoff: The verified dashboard and corrective actions are submitted to the CEO. Continuity/Escalation: An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. Timing: To be confirmed. | At the approved monthly and quarterly reporting cadence. | Review headcount, attendance, turnover, recruitment, overtime, leave, payroll exceptions, expiry exposure and open employee actions. | The verified People & Culture dashboard and corrective actions. | The verified dashboard and corrective actions are submitted to the CEO. | An authorised CEO-approved delegate may act only within the approved Delegation of Authority; reserved or material decisions escalate to the CEO. | To be confirmed. | • In plain words: he reports the workforce cost, the compliance position and the people measures to the CEO. • Starts when: at the reporting cycle, and immediately for material issues. • How it runs: (1) he reports the headcount and workforce cost against budget. (2) He reports the compliance position on visas, permits and labour law. (3) He reports the people measures: turnover, absence and training. (4) He raises the risks and the decisions needed. (5) He records the CEO's directions. • Proof it happened: a reported people pack with workforce cost, compliance position, measures and risks. • Where it usually breaks: compliance exposures are omitted because they reflect on the function, so the CEO learns of them from an inspection. | • Require compliance exposures to be reported by the CPCO, since an inspection discovering them first is a governance failure and the penalties fall on the company. • Report workforce cost including the full employment cost, not basic salary alone. • Name the events requiring immediate report: labour inspection, serious grievance, visa lapse and any allegation against a senior employee. • Report turnover by department and reason, as this is where the real signal is. • Keep the format consistent so the CEO can see the trend.
977 | People & Culture | Evaluate and shortlist candidates | HR & Admin Lead | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Lead completes the work item “Evaluate and shortlist candidates” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Lead completes the work item “Evaluate and shortlist candidates” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she assesses the candidates and decides who should be interviewed or offered. • Starts when: applications are received for an approved vacancy. • How it runs: (1) she assesses each candidate against the stated requirements. (2) She checks the screening findings. (3) She prepares the comparison for the hiring manager. (4) She agrees the shortlist. (5) She records the assessment and the reasons. • Proof it happened: a candidate evaluation and shortlist with assessments against the stated requirements recorded. • Where it usually breaks: shortlisting is done on impression, so the decision cannot be explained and unsuccessful candidates have grounds to complain. | • Require the assessment to be recorded against the stated requirements, since a shortlist based on impression cannot be explained and is the basis of most recruitment complaints. • Use the same criteria for every candidate for a role, so the comparison is fair. • Require the hiring manager to participate in the decision rather than receiving it. • Record why unsuccessful candidates were not progressed. • Retain the assessment records for the retention period, as recruitment decisions are challenged.
978 | People & Culture | Confirm approved salary package and joining date | HR & Admin Lead | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Lead completes the work item “Confirm approved salary package and joining date” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Lead completes the work item “Confirm approved salary package and joining date” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she confirms the pay package and the start date with the selected candidate. • Starts when: a candidate is selected and the offer is approved. • How it runs: (1) she confirms the approved package. (2) She confirms the joining date and the notice position. (3) She communicates the offer clearly. (4) She obtains the candidate's acceptance in writing. (5) She records the accepted terms. • Proof it happened: a written offer accepted in writing with the approved package and joining date recorded. • Where it usually breaks: the package is discussed verbally and remembered differently, so the first payslip produces a dispute. | • Issue the offer in writing with every element of the package itemised, since verbal discussion is remembered differently and the first payslip becomes a dispute. • Obtain written acceptance before proceeding to visa or onboarding. • Confirm the package matches the approved authority, as verbal negotiation drifts above it. • State clearly which elements are fixed and which are variable or discretionary. • Record the accepted terms as the basis for the contract.
979 | People & Culture | Deliver company induction and policy briefing | HR & Admin Lead | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Lead completes the work item “Deliver company induction and policy briefing” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Lead completes the work item “Deliver company induction and policy briefing” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she runs the induction so a new joiner understands the company and its rules. • Starts when: an employee joins. • How it runs: (1) she delivers the company induction. (2) She briefs the policies that apply to the role. (3) She covers the safety and conduct requirements. (4) She obtains acknowledgement of the policies. (5) She records the induction and the acknowledgements. • Proof it happened: a delivered induction with policies briefed and acknowledged, recorded against the employee. • Where it usually breaks: induction is a document handover, so nothing is understood and the acknowledgement is meaningless. | • Require the induction to be delivered rather than handed over as documents, since an acknowledgement of policies never explained is worthless in any later disciplinary case. • Require acknowledgement of the specific policies with disciplinary consequences. • Deliver in a language the employee understands, particularly for site staff. • Include the safety induction before any site access is granted. • Record the induction date and content, as this is the evidence the employee was informed.
980 | People & Culture | Introduce employee to team and reporting line | HR & Admin Lead | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Lead completes the work item “Introduce employee to team and reporting line” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Lead completes the work item “Introduce employee to team and reporting line” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she introduces the new joiner to the team and confirms who they report to. • Starts when: on the joining date. • How it runs: (1) she introduces the employee to the team and the manager. (2) She confirms the reporting line explicitly. (3) She confirms the role and the immediate expectations. (4) She confirms the workplace arrangements. (5) She records the introduction. • Proof it happened: a recorded introduction with the reporting line and immediate expectations confirmed. • Where it usually breaks: the reporting line is left ambiguous, so the employee takes instructions from several people and satisfies none. | • Confirm a single reporting line in writing on day one, since ambiguity here means the employee takes instructions from several people and satisfies none of them. • Require the manager to be present for the introduction, as an introduction by HR alone signals nothing. • Confirm the immediate expectations for the first weeks, because this is when most early leavers decide to leave. • Confirm workplace, equipment and access arrangements are ready before arrival. • Record the introduction, so the reporting line is evidenced.
981 | People & Culture | Collect first-week performance and onboarding feedback | HR & Admin Lead | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Lead completes the work item “Collect first-week performance and onboarding feedback” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Lead completes the work item “Collect first-week performance and onboarding feedback” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: after the first week she asks the new joiner and the manager how it is going. • Starts when: at the end of the first week. • How it runs: (1) she meets the new employee. (2) She asks about the onboarding experience and any problems. (3) She obtains the manager's early view. (4) She resolves the issues raised. (5) She records the feedback. • Proof it happened: recorded first week feedback from the employee and the manager with issues resolved. • Where it usually breaks: no check happens, so a joiner with a practical problem such as no access or no equipment struggles silently. | • Make the first week check mandatory, since a joiner without access, equipment or a clear task struggles silently and often leaves within months. • Ask about practical obstacles specifically, as these are easy to fix and are the commonest complaint. • Obtain the manager's early view, because a mismatch identified now can still be corrected. • Resolve the issues raised rather than only recording them. • Track early leaver reasons, as these usually trace to onboarding.
982 | People & Culture | Confirm departmental work handover | HR & Admin Lead | Trigger: When a resignation, termination or employee exit is formally approved. Action: The HR & Admin Lead completes the work item “Confirm departmental work handover” using approved records and systems. Output/Evidence: a completed clearance file covering handover, access, assets, government cancellation and employee records. Control/Handoff: The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When a resignation, termination or employee exit is formally approved. | The HR & Admin Lead completes the work item “Confirm departmental work handover” using approved records and systems. | a completed clearance file covering handover, access, assets, government cancellation and employee records. | The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she confirms the departmental handover has actually happened for the role. • Starts when: a joiner replaces someone, or a role changes hands. • How it runs: (1) she confirms the handover requirement with the department. (2) She confirms what must be handed over. (3) She confirms the handover took place. (4) She records any gaps. (5) She escalates where the handover was not completed. • Proof it happened: a confirmed departmental handover with the content recorded and gaps identified. • Where it usually breaks: the leaver departs before the handover, so the incoming person reconstructs the role from scratch. | • Require the handover to be completed before the leaver's last day and evidenced, since a role reconstructed from scratch costs months of productivity. • Define what a handover must contain per role type, including files, contacts, ongoing matters and system access. • Require the receiving person to confirm the handover was sufficient. • Record gaps, so the incoming person's difficulties are understood rather than judged. • Include the handover in the exit clearance checklist.
983 | People & Culture | Coordinate staff accommodation and requirements | HR & Admin Lead | Trigger: When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. Action: The HR & Admin Lead completes the work item “Coordinate staff accommodation and requirements” using approved records and systems. Output/Evidence: an updated visa, permit, travel, accommodation or PRO transaction record with evidence. Control/Handoff: The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. | The HR & Admin Lead completes the work item “Coordinate staff accommodation and requirements” using approved records and systems. | an updated visa, permit, travel, accommodation or PRO transaction record with evidence. | The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she arranges accommodation and the practical needs of staff who require them. • Starts when: an employee requires accommodation or related support. • How it runs: (1) she confirms the entitlement per the policy. (2) She arranges the accommodation. (3) She confirms the standard and the condition. (4) She records the allocation. (5) She handles the ongoing issues raised. • Proof it happened: arranged accommodation with the entitlement confirmed, standard checked and allocation recorded. • Where it usually breaks: accommodation standards are not checked, so conditions fall below the legal requirement and the exposure is on the company. | • Inspect accommodation against the legal minimum standard and record it, since substandard worker accommodation is a serious regulatory and reputational exposure for the company. • Check occupancy against the permitted capacity, as overcrowding is the commonest breach. • Record the allocation per employee, so the cost and the responsibility are traceable. • Set a route for residents to raise conditions issues, and respond to them. • Inspect at a set frequency rather than only on complaint.
984 | People & Culture | Prepare warning letters and disciplinary memos | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Prepare warning letters and disciplinary memos” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Prepare warning letters and disciplinary memos” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she prepares the warning letters and disciplinary memos. • Starts when: a disciplinary outcome requires a written warning. • How it runs: (1) she confirms the process was followed. (2) She states the specific incident, date and evidence. (3) She states the required improvement and the timeframe. (4) She states the consequence of repetition. (5) She obtains approval and issues it against acknowledgement. • Proof it happened: an issued warning letter stating the incident, evidence, required improvement and consequence, acknowledged. • Where it usually breaks: the letter describes general dissatisfaction, so it cannot support a later dismissal at all. | • Require the letter to state the specific incident, date and evidence, since a letter describing general dissatisfaction cannot support a later dismissal. • State the required improvement and the review timeframe, so the employee has a defined opportunity to correct. • Require the employee's acknowledgement of receipt, and record a refusal to sign. • Require CLO review for final warnings. • State the validity period of the warning, as an indefinite warning is unenforceable.
985 | People & Culture | Draft employment contracts | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Draft employment contracts” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Draft employment contracts” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she drafts the employment contracts. • Starts when: an offer is accepted. • How it runs: (1) she prepares the contract using the approved template. (2) She enters the agreed terms from the offer. (3) She checks the terms comply with the law. (4) She obtains review for any non standard term. (5) She routes it for signature. • Proof it happened: a drafted employment contract matching the accepted offer, using the approved template with non standard terms reviewed. • Where it usually breaks: the contract terms differ from the offer, and the employee only notices when a benefit is denied. | • Check the contract against the accepted offer term by term, since a difference between them is discovered when a benefit is refused and becomes a dispute. • Use the approved template only and require review for any deviation. • State the probation period, notice period and end of service basis explicitly. • Require the contract to be signed before or on the first working day. • Issue a copy to the employee and record that it was issued.
986 | People & Culture | Coordinate employee performance appraisals | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Coordinate employee performance appraisals” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Coordinate employee performance appraisals” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she coordinates the performance appraisal process across the company. • Starts when: at the appraisal cycle. • How it runs: (1) she issues the appraisal timetable and forms. (2) She briefs the managers on the process. (3) She tracks completion. (4) She reviews the completed appraisals for consistency. (5) She records the outcomes and the development actions. • Proof it happened: a completed appraisal cycle with forms issued, completion tracked and outcomes recorded. • Where it usually breaks: appraisals are completed as a formality with no specific content, so they support neither development nor any later performance decision. | • Require specific examples in every rating, since a formulaic appraisal supports neither development nor any later performance decision. • Require development actions with dates rather than general comments. • Review rating distribution across managers, as inconsistency here undermines the whole process. • Require the employee to see and acknowledge the appraisal. • Escalate performance concerns as they arise rather than saving them for the appraisal.
987 | People & Culture | Issue and track quarterly appraisal forms | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Issue and track quarterly appraisal forms” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Issue and track quarterly appraisal forms” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she issues the quarterly appraisal forms and chases them. • Starts when: at each quarterly cycle. • How it runs: (1) she issues the forms with the deadline. (2) She tracks who has submitted. (3) She chases the outstanding ones. (4) She escalates persistent non completion. (5) She records the completion position. • Proof it happened: issued quarterly forms with completion tracked, chased and escalated where outstanding. • Where it usually breaks: forms are chased for weeks and eventually abandoned, so the process quietly lapses. | • Escalate non completion to the department chief rather than chasing indefinitely, since an abandoned appraisal cycle means the process lapses and cannot be relied on later. • Report completion rates by department, as this is what drives compliance. • Keep the form short enough to be completed, because length is the main reason for non completion. • Require completion before any pay or promotion decision for that employee. • Record the completion position so gaps are visible.
988 | People & Culture | Update ERP timesheets and verify payroll inputs | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Update ERP timesheets and verify payroll inputs” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Update ERP timesheets and verify payroll inputs” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she updates the timesheets in the system and checks the payroll inputs. • Starts when: at the payroll input cycle. • How it runs: (1) she enters or verifies the timesheet data. (2) She reconciles it to attendance. (3) She checks the overtime approvals. (4) She checks the leave records. (5) She confirms the inputs for payroll. • Proof it happened: updated timesheets reconciled to attendance with overtime approvals and leave verified. • Where it usually breaks: timesheet corrections are made on assumption because the supervisor is unavailable, which becomes payment for time not worked. | • Require supervisor confirmation for every timesheet correction, since assumed corrections become payment for time not worked and the pattern is never detected. • Reconcile timesheets to the biometric attendance record rather than accepting them. • Check overtime approval evidence exists before processing. • Reconcile the employee list to payroll, so leavers and joiners are correct. • Report the volume of manual corrections, as a high volume indicates a control problem.
989 | People & Culture | Administer employee medical and workers compensation insurance | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Administer employee medical and workers compensation insurance” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Administer employee medical and workers compensation insurance” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she manages the medical and workers compensation insurance for employees. • Starts when: an employee joins or leaves, and at policy renewal. • How it runs: (1) she adds joiners to the policies within the insurer's timeframe. (2) She removes leavers. (3) She issues the cards or evidence to employees. (4) She handles claims and queries. (5) She coordinates the renewal. • Proof it happened: current insurance registers with joiners added and leavers removed within the required timeframe. • Where it usually breaks: a joiner is added late, so an incident during the gap is uninsured and the cost falls entirely on the company. | • Add joiners within the insurer's stated timeframe and confirm cover is active, since an incident during an uninsured gap falls entirely on the company. • Remove leavers promptly, as the company continues paying premiums otherwise. • Reconcile the insured list to the payroll list at a set frequency, which catches both gaps and overpayment. • Diarise the renewal with enough lead time, because a lapse leaves the whole workforce uncovered. • Issue the cover evidence to employees, as they cannot use cover they do not know they have.
990 | People & Culture | Follow up approved People & Culture payments with Accounts | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Follow up approved People & Culture payments with Accounts” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Follow up approved People & Culture payments with Accounts” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she follows up with accounts on the people related payments that have been approved. • Starts when: an approved payment is pending. • How it runs: (1) she confirms the payment is approved and submitted. (2) She tracks it with Finance. (3) She responds to Finance queries. (4) She confirms the payment was made. (5) She informs the employee or vendor. • Proof it happened: tracked people related payments with Finance queries answered and payment confirmed. • Where it usually breaks: an incomplete submission bounces between HR and Finance, and the employee is the one left unpaid. | • Define the required submission contents as a checklist, since incomplete submissions bounce between functions and the employee is the one left unpaid. • Track the payment to completion rather than assuming submission is the end. • Inform the employee of the expected date, as uncertainty drives escalation. • Prioritise employee payments over vendor payments in the follow up. • Report late employee payments and their causes.
991 | People & Culture | Process salary advance requests for approval | HR & Admin Lead | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Lead completes the work item “Process salary advance requests for approval” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Lead completes the work item “Process salary advance requests for approval” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she processes salary advance requests for approval. • Starts when: an employee requests a salary advance. • How it runs: (1) she checks the request against the policy. (2) She checks the employee's outstanding balance. (3) She prepares the recovery schedule. (4) She obtains approval. (5) She confirms the deduction is set up before payment. • Proof it happened: processed advance requests with policy compliance, outstanding balance checked and recovery set up. • Where it usually breaks: the advance is paid and the deduction is arranged afterwards, so it is frequently never arranged at all. | • Require the payroll deduction to be set up before the advance is paid, since a deduction arranged afterwards is frequently never arranged and the balance is lost. • Check the existing outstanding balance before approving a further advance. • Require the employee's written authorisation for the deduction. • Set a maximum advance and a maximum recovery period in the policy. • Report total advances outstanding, as this is effectively unsecured lending.
992 | People & Culture | Coordinate People & Culture requirements with site engineers | HR & Admin Lead | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Lead completes the work item “Coordinate People & Culture requirements with site engineers” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Lead completes the work item “Coordinate People & Culture requirements with site engineers” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she coordinates the people requirements with the site engineers. • Starts when: a site has a manpower or personnel requirement. • How it runs: (1) she receives the requirement from the site. (2) She confirms the approval and the budget. (3) She coordinates the mobilisation or resolution. (4) She confirms the arrangements with the site. (5) She records the outcome. • Proof it happened: coordinated site personnel requirements with approvals confirmed and arrangements recorded. • Where it usually breaks: site requests are taken verbally with no approval, so people are mobilised against no budget. | • Require site manpower requests to be approved in writing before mobilisation, since verbally mobilised workers arrive against no budget and nobody owns the cost. • Confirm accommodation, transport and induction are arranged before mobilisation. • Confirm the certification requirements for the trade before mobilising. • Record the requirement and the response, so demobilisation is also managed. • Report mobilisation lead times, as unrealistic requests are the common cause of failure.
993 | People & Culture | Prepare and control company policies for management approval | HR & Admin Lead | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Lead completes the work item “Prepare and control company policies for management approval” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Lead completes the work item “Prepare and control company policies for management approval” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she prepares and controls the company policies for management approval. • Starts when: a policy is created or requires revision. • How it runs: (1) she drafts or updates the policy. (2) She obtains input from the affected functions. (3) She obtains legal review where needed. (4) She routes it for management approval. (5) She issues it, withdraws the previous version and records acknowledgements. • Proof it happened: an approved and issued policy with version control, previous version withdrawn and acknowledgements recorded. • Where it usually breaks: the old policy version stays in circulation, so employees comply with rules the company has already changed. | • Withdraw the previous version explicitly and notify everyone bound by it, since compliance with a withdrawn policy is a real and common failure. • Require acknowledgement for policies with disciplinary consequences, as enforcement needs evidence of issue. • Require legal review for policies affecting employment terms. • Set a review frequency, because a policy referencing outdated law is worse than none. • Keep policies short and in plain language, as unread policies are enforced by nobody.
994 | People & Culture | Prepare company event communications and announcements | HR & Admin Lead | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Lead completes the work item “Prepare company event communications and announcements” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Lead completes the work item “Prepare company event communications and announcements” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she prepares the announcements and communications for company events. • Starts when: an announcement or event communication is required. • How it runs: (1) she drafts the communication. (2) She obtains approval of the content. (3) She confirms the distribution list. (4) She issues it through the approved channel. (5) She records what was issued. • Proof it happened: issued communications with approved content and the distribution recorded. • Where it usually breaks: announcements go out with information that was not meant to be public, such as individual pay or personal circumstances. | • Require approval before any announcement referring to an individual, since personal information released in a company communication cannot be withdrawn. • Check the distribution list, as internal announcements sent externally cause real problems. • Prohibit including salary, medical or disciplinary information in any announcement. • Obtain the individual's consent before announcing anything personal. • Record what was issued and to whom.
995 | People & Culture | Coordinate contractor's all-risk insurance for projects | HR & Admin Lead | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Lead completes the work item “Coordinate contractor's all-risk insurance for projects” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Lead completes the work item “Coordinate contractor's all-risk insurance for projects” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she arranges the contractor's all risk insurance for projects. • Starts when: a project requires the insurance. • How it runs: (1) she obtains the project details and values. (2) She confirms the contractual insurance requirements. (3) She obtains quotations and arranges the cover. (4) She confirms the cover is in place before work starts. (5) She files the policy and tracks the expiry. • Proof it happened: arranged project insurance matching the contractual requirement, confirmed in place before work starts. • Where it usually breaks: work starts before the policy is active, so the riskiest early period is uninsured. | • Confirm the policy is active before any work starts on site, since the early construction period is high risk and an uninsured incident falls entirely on the company. • Check the cover against the contractual requirement clause by clause, as a policy that does not meet the contract is a breach. • Check the sum insured against the actual contract value including variations. • Diarise the expiry against the programme, because projects overrun and cover lapses. • File the policy where the project team can produce it on request.
996 | People & Culture | Prepare and route project undertakings for approval | HR & Admin Lead | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Lead completes the work item “Prepare and route project undertakings for approval” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Lead completes the work item “Prepare and route project undertakings for approval” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she prepares the project undertakings and routes them for approval. • Starts when: an undertaking is required for a project or authority. • How it runs: (1) she obtains the required wording. (2) She checks what the company is committing to. (3) She obtains legal review where the commitment is material. (4) She routes it for authorised signature. (5) She records the issued undertaking. • Proof it happened: an approved and signed undertaking with legal review where material, recorded. • Where it usually breaks: an undertaking is signed without anyone reading what it commits the company to. | • Require the commitment in every undertaking to be identified and reviewed before signature, since undertakings are signed routinely and can create significant unlimited obligations. • Require legal review above a stated materiality. • Confirm the signatory has the authority for the commitment being made. • Maintain a register of undertakings given, as these are obligations the company has forgotten. • Record the expiry or discharge conditions.
997 | People & Culture | Coordinate approved vendors for systems, uniforms, software and supplies | HR & Admin Lead | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Lead completes the work item “Coordinate approved vendors for systems, uniforms, software and supplies” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Lead completes the work item “Coordinate approved vendors for systems, uniforms, software and supplies” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she coordinates the approved suppliers for systems, uniforms, software and supplies. • Starts when: such a requirement arises. • How it runs: (1) she confirms the requirement and the approval. (2) She raises it through Procurement. (3) She coordinates delivery or provision. (4) She confirms receipt and quality. (5) She records the arrangement. • Proof it happened: coordinated supplier arrangements raised through Procurement with receipt and quality confirmed. • Where it usually breaks: suppliers are engaged directly because the requirement is small, so spend accumulates outside any control. | • Route every purchase through Procurement regardless of size, since small direct engagements accumulate into significant uncontrolled spend. • Confirm the approval and budget before committing. • Require software purchases to be checked for licensing and data protection compliance. • Check receipt and quality before approving payment. • Report recurring small purchases, as these usually justify a framework arrangement.
998 | People & Culture | Validate manpower requisition and budget before recruitment | HR & Admin Lead | Trigger: When a department requests manpower. Action: Verify the approved position, job requirements, headcount plan, budget, reporting line, urgency and requested start date. Output/Evidence: A complete requisition record; incomplete requests are returned. Control/Handoff: Only a complete requisition is released for CPCO approval and recruitment. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When a department requests manpower. | Verify the approved position, job requirements, headcount plan, budget, reporting line, urgency and requested start date. | A complete requisition record; incomplete requests are returned. | Only a complete requisition is released for CPCO approval and recruitment. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: before recruiting she checks the request is genuine, approved and funded. • Starts when: a manpower requisition is received. • How it runs: (1) she checks the requisition is complete and approved. (2) She checks the position exists in the approved structure. (3) She checks the budget covers it. (4) She confirms the role requirements are defined. (5) She releases it for recruitment or returns it. • Proof it happened: a validated requisition with approval, structure position and budget confirmed before recruitment starts. • Where it usually breaks: recruitment starts on a verbal request, so a hire is made for a position that was never approved or funded. | • Prohibit starting recruitment without an approved and funded requisition, since a hire made against no approved position creates a permanent unbudgeted cost. • Check the position exists in the approved structure rather than only that someone approved the request. • Require the role requirements to be defined before sourcing, as recruiting against a vague brief wastes everyone's time. • Confirm the full employment cost against the budget, not just the salary. • Return incomplete requisitions rather than starting and clarifying later.
999 | People & Culture | Manage formal offer approval and issuance | HR & Admin Lead | Trigger: After candidate selection. Action: Prepare the offer package using the approved grade, salary, benefits, notice period and joining conditions. Output/Evidence: The issued controlled offer and retained candidate acceptance or rejection. Control/Handoff: CPCO and Finance approval is obtained where required before the offer is issued. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | After candidate selection. | Prepare the offer package using the approved grade, salary, benefits, notice period and joining conditions. | The issued controlled offer and retained candidate acceptance or rejection. | CPCO and Finance approval is obtained where required before the offer is issued. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she manages getting the offer approved and issued properly. • Starts when: a candidate is selected. • How it runs: (1) she prepares the offer with the proposed package. (2) She checks it against the approved band and the requisition. (3) She obtains the required approval. (4) She issues the offer in writing. (5) She obtains written acceptance and records it. • Proof it happened: an approved and issued written offer with the package checked against authority, accepted in writing. • Where it usually breaks: the package is discussed with the candidate before approval, so the company is committed to something it has not approved. | • Prohibit discussing any specific package with a candidate before it is approved, since the candidate treats it as an offer and withdrawal damages the company's reputation. • Check the package against the approved band and the requisition before issue. • Issue the offer in writing with every element itemised and a validity period. • State the conditions such as background checks and document verification. • Obtain written acceptance before starting visa or onboarding activity.
1000 | People & Culture | Process employee transfers, promotions and salary changes | HR & Admin Lead | Trigger: When an authorised employee-change request is received. Action: Verify the business justification, effective date, reporting line, budget and approvals, then update the contract/addendum, ERP and payroll instructions. Output/Evidence: The updated contract/addendum, ERP record and payroll instruction. Control/Handoff: The controlled change is communicated to the employee and affected departments. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an authorised employee-change request is received. | Verify the business justification, effective date, reporting line, budget and approvals, then update the contract/addendum, ERP and payroll instructions. | The updated contract/addendum, ERP record and payroll instruction. | The controlled change is communicated to the employee and affected departments. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she processes the transfers, promotions and pay changes. • Starts when: such a change is proposed and approved. • How it runs: (1) she checks the change is approved at the right level. (2) She checks the new package against the structure. (3) She prepares the letter and the contract amendment. (4) She updates the employee record and payroll. (5) She confirms the change with the employee. • Proof it happened: processed changes with approval, documentation issued and the employee record and payroll updated. • Where it usually breaks: the change is made in payroll but never documented, so there is no record of the agreed new terms. | • Require a letter or contract amendment for every change, since a change made in payroll without documentation leaves no record of the agreed terms. • Check the new package against the pay structure, as promotions are where inconsistency creeps in. • Require approval at the correct level for the new total cost. • Update the reporting line and the authority matrix where the role changes. • Record the effective date, as retrospective changes cause payroll corrections.
1001 | People & Culture | Manage grievance and disciplinary case workflow | HR & Admin Lead | Trigger: When a complaint, policy breach or disciplinary concern is reported. Action: Open a confidential case, gather evidence and coordinate hearings and consultation. Output/Evidence: The authorised decision documented in the confidential case record. Control/Handoff: Corrective actions or appeals are tracked to closure. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When a complaint, policy breach or disciplinary concern is reported. | Open a confidential case, gather evidence and coordinate hearings and consultation. | The authorised decision documented in the confidential case record. | Corrective actions or appeals are tracked to closure. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she manages the grievance and disciplinary cases through the proper process. • Starts when: a grievance or disciplinary matter is raised. • How it runs: (1) she records the matter and the date raised. (2) She confirms the process and the timeline. (3) She arranges an independent investigation. (4) She records the findings and the outcome. (5) She issues the outcome and records the case file. • Proof it happened: a documented case with the process followed, independent investigation, findings and outcome recorded. • Where it usually breaks: the process is compressed to reach a quick outcome, so the decision is procedurally unfair and cannot be defended. | • Require the full process to be followed regardless of how clear the outcome seems, since a procedurally defective decision creates liability however justified it was. • Require the investigator to be independent of both parties. • State the timeline to both parties and keep to it, as delay itself is a ground for complaint. • Allow the employee to respond before any decision is taken. • Keep the case file confidential and controlled, as these documents are disclosable.
1002 | People & Culture | Coordinate exit clearance, final settlement and exit interview | HR & Admin Lead | Trigger: When an employee exit is approved. Action: Issue the clearance checklist, coordinate manager handover, IT access closure, asset recovery, visa cancellation and Finance settlement, and conduct the exit interview. Output/Evidence: The completed exit clearance and interview record. Control/Handoff: The employee file is closed only when all evidence is complete. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | When an employee exit is approved. | Issue the clearance checklist, coordinate manager handover, IT access closure, asset recovery, visa cancellation and Finance settlement, and conduct the exit interview. | The completed exit clearance and interview record. | The employee file is closed only when all evidence is complete. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she manages the exit process: clearance, settlement and the exit interview. • Starts when: a departure is confirmed. • How it runs: (1) she issues the clearance checklist. (2) She confirms assets, access and documents are returned. (3) She confirms outstanding balances are identified. (4) She coordinates the final settlement. (5) She conducts the exit interview and records the feedback. • Proof it happened: a completed clearance with assets returned, balances identified, settlement processed and exit feedback recorded. • Where it usually breaks: the settlement is released before clearance is complete, so assets, access and advances are never recovered. | • Require clearance to be fully complete before the settlement is released, since assets, access and unrecovered advances are gone once the person has been paid and left. • Include IT access revocation in the clearance, timed to the exit moment. • Conduct the exit interview independently of the line manager, as this is where the real reason emerges. • Report exit reasons by department, because the pattern is the useful information. • Confirm the handover is complete as part of clearance.
1003 | People & Culture | Maintain employee training and competency plan | HR & Admin Lead | Trigger: At onboarding, appraisal or when a competency gap is identified. Action: Define the required training, approval, provider, schedule and assessment. Output/Evidence: Maintained attendance and competency evidence. Control/Handoff: Overdue or ineffective training actions are reported. Continuity/Escalation: The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. Timing: To be confirmed. | At onboarding, appraisal or when a competency gap is identified. | Define the required training, approval, provider, schedule and assessment. | Maintained attendance and competency evidence. | Overdue or ineffective training actions are reported. | The trained HR & Admin Assistant may prepare records as operational backup, but approvals and material exceptions escalate to the CPCO. | To be confirmed. | • In plain words: she keeps track of what training people need, what they have completed, and what is expiring. • Starts when: at the training planning cycle, on joining, and when certifications approach expiry. • How it runs: (1) she identifies the mandatory and role specific training per position. (2) She records what each employee has completed. (3) She tracks the certification expiry dates. (4) She schedules the training and the renewals. (5) She reports the completion and the gaps. • Proof it happened: a training and competency record per employee with completion status, certification validity and the scheduled plan. • Where it usually breaks: the record shows attendance rather than valid certification, so expired certificates look the same as current ones. | • Track certification validity with expiry dates and advance warnings, not just attendance, since an expired certificate means the person cannot legally do the work. • Define the mandatory training per role in the SOP, so the requirement is not decided case by case. • Block deployment to a role where the required training or certification is missing, and name who enforces it. • Require the training plan to be funded in the budget, otherwise it is deferred every year. • Report training gaps for critical and certified roles to the CPCO, as these carry legal and operational consequence.
1004 | People & Culture | Pre-screen white-collar candidates through approved recruitment channels | HR & Admin Assistant | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Assistant completes the work item “Pre-screen white-collar candidates through approved recruitment channels” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Assistant completes the work item “Pre-screen white-collar candidates through approved recruitment channels” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she does the first filter on office and professional candidates, so only people who actually fit reach an interview. • Starts when: an approved vacancy is released for recruitment. • How it runs: (1) she takes the role requirements from the approved job description. (2) She sources candidates through the approved channels only. (3) She screens the applications against the stated requirements. (4) She holds a short screening call to check availability, salary expectation and visa status. (5) She passes the shortlist to the hiring manager with her notes. • Proof it happened: a screening record per candidate with the source, the assessment against requirements and the shortlist passed on. • Where it usually breaks: candidates are shortlisted on the CV alone without a screening call, so interviews are spent discovering salary or visa problems. | • Require a screening call before shortlisting to confirm salary expectation, notice period and visa status, since these three eliminate most candidates and waste the most interview time. • State the approved sourcing channels and prohibit others, because unvetted channels create both quality and data protection problems. • Require the screening assessment to be recorded against the stated requirements, so shortlisting decisions can be explained. • Set a response commitment to all applicants, as silence damages the company's ability to hire later. • Require candidate data to be held only in the approved system, not in personal email or spreadsheets.
1005 | People & Culture | Pre-screen blue-collar candidates through approved recruitment channels or agencies | HR & Admin Assistant | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Assistant completes the work item “Pre-screen blue-collar candidates through approved recruitment channels or agencies” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Assistant completes the work item “Pre-screen blue-collar candidates through approved recruitment channels or agencies” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she does the same first filter for site and trade workers, usually through agencies or approved suppliers. • Starts when: an approved manpower requirement is released. • How it runs: (1) she takes the trade, quantity, skill level and mobilisation date required. (2) She approaches the approved agencies or channels. (3) She checks the candidates against the trade and certification requirements. (4) She arranges trade testing where required. (5) She passes the qualified candidates for selection. • Proof it happened: a screening record per worker with the trade, certification status and the source, and the trade test results. • Where it usually breaks: workers are mobilised on the agency's claim of skill level, and the shortfall is only discovered on site. | • Require a trade test before mobilisation for skilled trades, since an agency's stated skill level is unverified and remobilising is expensive. • Require certification verification for certified trades at screening, not on arrival at site. • Use only approved agencies with a contract in place, because informal supply arrangements create labour law exposure. • Record the source per worker, so agencies delivering poor quality can be identified and dropped. • Confirm the mobilisation date and the readiness of accommodation and transport before committing to a start.
1006 | People & Culture | Schedule and prepare candidate interviews | HR & Admin Assistant | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Assistant completes the work item “Schedule and prepare candidate interviews” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Assistant completes the work item “Schedule and prepare candidate interviews” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she arranges the interviews and makes sure the interviewers actually have what they need before the candidate arrives. • Starts when: a shortlist is agreed and interviews are to be arranged. • How it runs: (1) she agrees the panel and the timing with the interviewers. (2) She schedules the candidate and confirms the arrangements. (3) She circulates the CV, the job description and the assessment form in advance. (4) She prepares the room or the video link. (5) She collects the completed assessments after the interview. • Proof it happened: scheduled interviews with confirmations, circulated candidate packs and collected interview assessment records. • Where it usually breaks: interviewers receive the CV as the candidate walks in, so the interview is unstructured and produces no comparable assessment. | • Require the candidate pack to be circulated a stated period in advance, since an interviewer reading the CV in the room cannot assess against requirements. • Require a completed assessment form per interviewer, because verbal impressions cannot be compared between candidates. • Confirm interviews in writing with both sides, as no show interviews damage the company's reputation with candidates. • Require the same core questions across candidates for a role, so the comparison is fair and defensible. • Collect the assessments before the decision meeting, otherwise the decision is made on recollection.
1007 | People & Culture | Complete background checks for locally hired employees | HR & Admin Assistant | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Assistant completes the work item “Complete background checks for locally hired employees” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Assistant completes the work item “Complete background checks for locally hired employees” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she checks that what a local candidate has claimed is actually true, before an offer is confirmed. • Starts when: a candidate is selected and before the offer is finalised. • How it runs: (1) she obtains the candidate's consent for the checks. (2) She verifies the employment history with previous employers. (3) She verifies the qualifications and certifications claimed. (4) She checks for any restriction such as a labour ban. (5) She records the outcome and reports any discrepancy before the offer. • Proof it happened: completed background check records with consent, verification responses and the discrepancies noted. • Where it usually breaks: the offer is issued before checks are complete, so a discrepancy found later means withdrawing an accepted offer. | • Complete the checks before the offer is issued, or state that the offer is conditional on them in writing, since withdrawing an accepted offer creates legal exposure. • Require written candidate consent before any check, as unconsented enquiries breach data protection. • Verify certifications with the issuing body for safety critical and certified roles, because forged certificates are common. • Check for labour bans and visa restrictions early, as these can prevent employment entirely. • Record what was verified and by whom, so the file shows the check happened rather than being assumed.
1008 | People & Culture | Collect and verify pre-employment documents | HR & Admin Assistant | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Assistant completes the work item “Collect and verify pre-employment documents” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Assistant completes the work item “Collect and verify pre-employment documents” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she collects the documents a new joiner must provide and checks they are genuine and complete. • Starts when: an offer is accepted and before the joining date. • How it runs: (1) she issues the document checklist to the candidate. (2) She collects the passport, visa, qualifications, certificates and photographs. (3) She verifies the documents against the originals. (4) She chases the missing items before the joining date. (5) She files them in the employee file. • Proof it happened: a completed document checklist with verified copies filed and the outstanding items recorded. • Where it usually breaks: the employee starts with documents missing, and they are never collected once work has begun. | • Require the document checklist to be complete before the start date, since documents not collected before joining are rarely collected afterwards. • Require verification against the original, with the verifier named, rather than accepting emailed copies. • State which documents legally must be held before work can begin, and block the start where they are missing. • Set an expiry tracking requirement for visas, permits and certificates at the point of filing. • State how documents are stored and who may access them, since these files contain sensitive personal data.
1009 | People & Culture | Maintain candidate follow-up until joining | HR & Admin Assistant | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The HR & Admin Assistant completes the work item “Maintain candidate follow-up until joining” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The HR & Admin Assistant completes the work item “Maintain candidate follow-up until joining” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she stays in contact with the candidate between offer and joining, so they actually turn up. • Starts when: an offer is accepted, and continues until the joining date. • How it runs: (1) she confirms the joining date and the arrangements in writing. (2) She keeps in contact through the notice period. (3) She tracks the visa or permit progress where applicable. (4) She confirms the joining arrangements shortly before the date. (5) She escalates immediately where the candidate goes quiet or delays. • Proof it happened: a candidate follow up record with contact dates, confirmed arrangements and escalations where needed. • Where it usually breaks: contact stops after the offer is accepted, and the candidate accepts another offer without the company knowing until the start date. | • Require scheduled contact through the notice period, since candidate drop out between offer and joining is common and almost always preceded by silence. • Require immediate escalation where a candidate goes quiet, so recruitment can restart rather than discovering a no show on the day. • Confirm the joining arrangements in writing shortly before the date, including reporting time, location and documents to bring. • Track visa and permit progress separately, as this is the usual cause of a delayed start. • Record drop out reasons, because the pattern usually points at slow processing or an uncompetitive offer.
1010 | People & Culture | Obtain signed employment agreement | HR & Admin Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Assistant completes the work item “Obtain signed employment agreement” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Assistant completes the work item “Obtain signed employment agreement” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she gets the employment contract signed, which is what makes the employment terms enforceable on both sides. • Starts when: the offer is accepted and the joining date is confirmed. • How it runs: (1) she prepares the agreement using the approved template and the approved terms. (2) She has it reviewed where the terms are non standard. (3) She issues it to the employee for signature. (4) She obtains the signed copy and the company signature. (5) She files the executed agreement and issues a copy to the employee. • Proof it happened: a signed employment agreement filed, with a copy issued to the employee and the approval of the terms behind it. • Where it usually breaks: the employee works for weeks on an unsigned contract, so the terms are unenforceable if a dispute arises. | • Require the agreement to be signed before or on the first working day, since an unsigned contract leaves the terms unenforceable and the position legally weak. • Require the terms to match the approved offer, as differences between offer and contract are the source of most early disputes. • Require legal review for any non standard clause, and state which clauses may never be amended. • Issue a copy to the employee and record that it was issued, because a contract the employee never received is contestable. • Track unsigned agreements as a reported exception.
1011 | People & Culture | Collect completed employee information form | HR & Admin Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Assistant completes the work item “Collect completed employee information form” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Assistant completes the work item “Collect completed employee information form” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she collects the employee's personal and bank details on the standard form, so records and payroll are set up correctly. • Starts when: on or before the joining date. • How it runs: (1) she issues the employee information form. (2) She collects it completed and signed. (3) She checks the mandatory fields are complete, including bank and emergency contact. (4) She enters the data into the system. (5) She files the form and confirms the data with the employee. • Proof it happened: a completed and signed employee information form with the data entered in the system and verified. • Where it usually breaks: bank details are entered from a verbal or messaged instruction rather than the signed form, and the first salary goes astray. | • Require bank details to be taken only from the signed form, never from a message or verbal instruction, since this is a payroll fraud and error route. • Require the entered data to be verified back against the form by a second person for bank and identity fields. • Require an emergency contact as a mandatory field, because it is only needed in an emergency and never available then. • State the process for later changes to bank details, with verification, as changes are riskier than the initial entry. • State the data protection basis for holding the information and who may access it.
1012 | People & Culture | Manage passport receipt and acknowledgement under approved policy | HR & Admin Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Assistant completes the work item “Manage passport receipt and acknowledgement under approved policy” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Assistant completes the work item “Manage passport receipt and acknowledgement under approved policy” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: where the company holds an employee's passport under policy, she records it properly and gives the employee an acknowledgement. • Starts when: a passport is received for processing or safekeeping under the approved policy. • How it runs: (1) she confirms the policy basis and the employee's written consent. (2) She records receipt in the document register. (3) She issues the employee a signed acknowledgement of receipt. (4) She stores it in the controlled secure location. (5) She records every movement in and out. • Proof it happened: a document register entry with the employee's consent, the issued acknowledgement and a movement log. • Where it usually breaks: passports are held without written consent or acknowledgement, which is both a legal exposure and impossible to reconcile. | • Require written employee consent and a signed acknowledgement for every document held, since holding identity documents without either is a serious legal exposure. • Require the document to be returned on request without condition or delay, and state that plainly in the policy. • Log every movement in and out with dates and signatures, because a register without movements cannot be reconciled. • Require periodic physical reconciliation of held documents against the register. • State who has access to the storage and require it to be a controlled secure location, not a desk drawer.
1013 | People & Culture | Register employee biometric attendance | HR & Admin Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Assistant completes the work item “Register employee biometric attendance” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Assistant completes the work item “Register employee biometric attendance” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she registers the new employee on the attendance system so their time is recorded from day one. • Starts when: on the joining date. • How it runs: (1) she enrols the employee's biometric on the system. (2) She assigns the correct department, site and shift. (3) She verifies the enrolment works with a test scan. (4) She confirms the record appears in the attendance report. (5) She informs the supervisor that the employee is registered. • Proof it happened: a biometric enrolment record with the correct assignment and a verified first attendance entry. • Where it usually breaks: enrolment is done but the department or site assignment is wrong, so the attendance and the labour cost land against the wrong project. | • Require the department, site and project assignment to be verified at enrolment, since a wrong assignment misallocates labour cost to the wrong project. • Require a test scan and a check of the first attendance record, because failed enrolments are only discovered at payroll. • Require enrolment on the joining date, as manual attendance for the first period creates disputes and payroll corrections. • Require deregistration on exit as a matching step, otherwise leavers remain active on the attendance system. • State who may change a shift or site assignment, since this affects overtime and allowances.
1014 | People & Culture | Confirm employment record in employee register and ERP | HR & Admin Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The HR & Admin Assistant completes the work item “Confirm employment record in employee register and ERP” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The HR & Admin Assistant completes the work item “Confirm employment record in employee register and ERP” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she makes sure the employee exists properly in the official register and in the system, with the right details. • Starts when: on joining, after the documents and the agreement are complete. • How it runs: (1) she creates the employee record in the ERP. (2) She enters the position, department, grade, salary and start date. (3) She records the employee in the statutory employee register. (4) She checks the record against the signed agreement. (5) She confirms the record is active for payroll. • Proof it happened: an active employee record in the ERP and the statutory register, reconciled against the signed agreement. • Where it usually breaks: the salary entered differs from the signed agreement, and the error persists for months before anyone reconciles it. | • Require the system record to be checked against the signed agreement by a second person, since a salary entry error persists silently and is expensive to correct. • Require the statutory register to be updated within the legal timeframe, as this is a compliance obligation with penalties. • Restrict who may create or amend employee master records, and prohibit the same person from also processing payroll. • Log all master data changes with the reason, so unauthorised changes are visible. • Reconcile the active employee list to payroll periodically, to catch both missing and fictitious records.
1015 | People & Culture | Process work permit and visa cancellation | HR & Admin Assistant | Trigger: When a resignation, termination or employee exit is formally approved. Action: The HR & Admin Assistant completes the work item “Process work permit and visa cancellation” using approved records and systems. Output/Evidence: a completed clearance file covering handover, access, assets, government cancellation and employee records. Control/Handoff: The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When a resignation, termination or employee exit is formally approved. | The HR & Admin Assistant completes the work item “Process work permit and visa cancellation” using approved records and systems. | a completed clearance file covering handover, access, assets, government cancellation and employee records. | The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: when someone leaves, she cancels their work permit and visa so the company's obligation properly ends. • Starts when: a resignation or termination is confirmed and the last working date is set. • How it runs: (1) she confirms the last working date and the settlement position. (2) She prepares the cancellation documents. (3) She obtains the employee's signature where required. (4) She submits the cancellation through the authorised channel. (5) She obtains the cancellation confirmation and files it. • Proof it happened: a submitted and confirmed visa and permit cancellation with the documents and the confirmation filed. • Where it usually breaks: cancellation is delayed past the legal deadline, and the company incurs fines that grow daily. | • Diarise the cancellation deadline from the last working date with an advance warning, since fines for late cancellation accrue daily and are entirely avoidable. • Require the cancellation to be initiated on confirmation of the leaving date rather than after the final settlement. • Require the cancellation confirmation to be obtained and filed, because an unconfirmed submission is not a completed cancellation. • Coordinate with the settlement process so the two are not each waiting for the other. • Track pending cancellations as a reported list, as these carry both cost and compliance risk.
1016 | People & Culture | Update ERP termination status and last working date | HR & Admin Assistant | Trigger: When a resignation, termination or employee exit is formally approved. Action: The HR & Admin Assistant completes the work item “Update ERP termination status and last working date” using approved records and systems. Output/Evidence: a completed clearance file covering handover, access, assets, government cancellation and employee records. Control/Handoff: The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When a resignation, termination or employee exit is formally approved. | The HR & Admin Assistant completes the work item “Update ERP termination status and last working date” using approved records and systems. | a completed clearance file covering handover, access, assets, government cancellation and employee records. | The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she updates the system so the leaver stops appearing as an active employee. • Starts when: the last working date is confirmed. • How it runs: (1) she records the termination type and reason. (2) She enters the last working date. (3) She deactivates the record for payroll and attendance. (4) She triggers the settlement calculation. (5) She confirms the employee no longer appears in the active headcount. • Proof it happened: an updated ERP record with the termination status, last working date and deactivation from payroll and attendance. • Where it usually breaks: the record is left active, so the leaver is paid in the following payroll run. | • Require deactivation to be completed before the next payroll cut off, since an active leaver record results in a payment that is very hard to recover. • Require the termination reason to be recorded consistently from a defined list, so turnover analysis is possible. • Require the active headcount to be reconciled to payroll every period, which catches both leavers still active and joiners missing. • Require system access and email deactivation to be triggered at the same time, not handled separately. • Retain the record rather than deleting it, as employment records must be kept for the statutory retention period.
1017 | People & Culture | Return passport or controlled personal documents and obtain acknowledgement | HR & Admin Assistant | Trigger: When a resignation, termination or employee exit is formally approved. Action: The HR & Admin Assistant completes the work item “Return passport or controlled personal documents and obtain acknowledgement” using approved records and systems. Output/Evidence: a completed clearance file covering handover, access, assets, government cancellation and employee records. Control/Handoff: The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When a resignation, termination or employee exit is formally approved. | The HR & Admin Assistant completes the work item “Return passport or controlled personal documents and obtain acknowledgement” using approved records and systems. | a completed clearance file covering handover, access, assets, government cancellation and employee records. | The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she returns the employee's passport or other held documents and gets written confirmation that they received them. • Starts when: the employee requests return, or on exit. • How it runs: (1) she retrieves the document from the controlled storage. (2) She verifies the identity of the person collecting. (3) She hands it over and obtains a signed acknowledgement. (4) She records the return in the document register. (5) She reconciles the register to confirm nothing is left held. • Proof it happened: a signed return acknowledgement with the document register updated and reconciled. • Where it usually breaks: documents are returned without a signed acknowledgement, so a later claim that a passport was not returned cannot be answered. | • Require a signed acknowledgement on every return, since without it the company cannot answer a claim that a document was never returned. • Require identity verification before handover, and state the process where a third party collects on the employee's behalf. • Update the register at the moment of return, not later, so the register is always current. • Reconcile held documents at every exit, to ensure nothing remains held for a former employee. • Prohibit withholding documents as leverage over any outstanding matter, as this is unlawful.
1018 | People & Culture | Process employee visas and renewals | HR & Admin Assistant | Trigger: When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. Action: The HR & Admin Assistant completes the work item “Process employee visas and renewals” using approved records and systems. Output/Evidence: an updated visa, permit, travel, accommodation or PRO transaction record with evidence. Control/Handoff: The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. | The HR & Admin Assistant completes the work item “Process employee visas and renewals” using approved records and systems. | an updated visa, permit, travel, accommodation or PRO transaction record with evidence. | The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she handles the employment visas and their renewals, so people stay legally able to work. • Starts when: a new employee needs a visa, or an existing visa approaches expiry. • How it runs: (1) she tracks the visa expiry dates and the renewal lead times. (2) She prepares the application or renewal documents. (3) She arranges the medical, biometrics and other required steps. (4) She submits through the authorised channel and tracks progress. (5) She confirms the issued visa and updates the records. • Proof it happened: issued visas and renewals with the application records, the tracked progress and the updated expiry register. • Where it usually breaks: renewals are started too late, so the employee is working on an expired visa and the company is exposed to fines. | • Set the renewal trigger by lead time rather than by expiry date, so processing starts early enough to avoid working on an expired visa. • Require an escalation where a renewal cannot be completed before expiry, since continuing to work is a compliance breach with daily penalties. • Track the required steps per application, as a missed medical or biometric stalls the whole process silently. • Maintain a single expiry register covering visas, permits and identity documents with owners. • Report upcoming expiries monthly, because the cost of lateness falls entirely on the company.
1019 | People & Culture | Arrange approved visit visas and air tickets | HR & Admin Assistant | Trigger: When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. Action: The HR & Admin Assistant completes the work item “Arrange approved visit visas and air tickets” using approved records and systems. Output/Evidence: an updated visa, permit, travel, accommodation or PRO transaction record with evidence. Control/Handoff: The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. | The HR & Admin Assistant completes the work item “Arrange approved visit visas and air tickets” using approved records and systems. | an updated visa, permit, travel, accommodation or PRO transaction record with evidence. | The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she arranges visit visas and flights when they have been approved. • Starts when: an approved travel or visit request is received. • How it runs: (1) she confirms the approval and the authorised traveller. (2) She checks the visa requirement and the processing time. (3) She obtains quotations within the travel policy. (4) She books after approval and issues the documents. (5) She files the records for cost allocation. • Proof it happened: approved travel and visa bookings with the approval, the quotations and the issued documents filed. • Where it usually breaks: bookings are made on verbal approval, and the cost is later disputed or charged to the wrong project. | • Require written approval before booking, since verbal approvals leave disputed costs and no record of who authorised them. • Require the cost centre or project to be stated at booking, so travel cost lands in the right place. • State the travel policy limits by grade, so bookings do not need case by case negotiation. • Check the visa lead time before committing to travel dates, because a booked flight with an unissued visa is a wasted cost. • Require unused tickets and cancellations to be tracked for refund, as this money is routinely lost.
1020 | People & Culture | Coordinate authorised PRO transactions | HR & Admin Assistant | Trigger: When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. Action: The HR & Admin Assistant completes the work item “Coordinate authorised PRO transactions” using approved records and systems. Output/Evidence: an updated visa, permit, travel, accommodation or PRO transaction record with evidence. Control/Handoff: The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved employment, renewal, cancellation, visit or travel requirement is received or an expiry alert becomes due. | The HR & Admin Assistant completes the work item “Coordinate authorised PRO transactions” using approved records and systems. | an updated visa, permit, travel, accommodation or PRO transaction record with evidence. | The HR & Admin Lead verifies eligibility and approvals; authorised government portal access and Finance payment evidence are retained. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she coordinates the government paperwork handled through the PRO, and tracks it to completion. • Starts when: a government transaction is required and authorised. • How it runs: (1) she confirms the transaction is authorised and identifies the documents needed. (2) She prepares and hands over the documents to the PRO with a record. (3) She provides the funds required against a record. (4) She tracks the transaction to completion. (5) She obtains the outcome documents and reconciles the funds spent. • Proof it happened: a PRO transaction log with documents handed over, funds provided, the outcome and the reconciliation. • Where it usually breaks: original documents and cash are handed over without a record, so neither can be reconciled or traced. | • Require a signed record for every original document and every amount of cash handed to the PRO, since neither can be traced afterwards without it. • Require funds to be reconciled against receipts per transaction, as unreconciled government fee cash is a standard leakage point. • Track each transaction to a stated completion date, otherwise submissions stall invisibly. • Require the outcome document to be filed and the relevant register updated on completion. • Limit who may authorise a PRO transaction, so government submissions are not made on informal request.
1021 | People & Culture | Manage approved Instagram and LinkedIn updates | HR & Admin Assistant | Trigger: When an approved joiner, employee change, access request, asset requirement or system update is received. Action: The HR & Admin Assistant completes the work item “Manage approved Instagram and LinkedIn updates” using approved records and systems. Output/Evidence: a configured account, system or asset record with access and completion evidence. Control/Handoff: Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved joiner, employee change, access request, asset requirement or system update is received. | The HR & Admin Assistant completes the work item “Manage approved Instagram and LinkedIn updates” using approved records and systems. | a configured account, system or asset record with access and completion evidence. | Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she posts the approved content on the company's social accounts, and only the approved content. • Starts when: approved content is released for publication. • How it runs: (1) she receives the content with the documented approval. (2) She checks it matches the approved version exactly. (3) She publishes on the approved schedule. (4) She monitors comments and messages and routes them appropriately. (5) She reports the activity and any issues. • Proof it happened: published posts matching the approved content, with the approval record and the monitoring notes. • Where it usually breaks: content is edited at the point of posting, so what goes out is not what was approved. | • Prohibit any editing at the point of posting, and require the published version to match the approved version exactly. • State who may respond to comments and messages, and require complaints and client matters to be routed rather than answered. • Require account credentials to be held centrally, since accounts controlled by one individual are lost when they leave. • Require client permission evidence for any project image or name before publication. • Require deletions and corrections to be approved and recorded, because silent deletion of a live post looks like concealment.
1022 | People & Culture | Prepare employee and administrative request letters | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Prepare employee and administrative request letters” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Prepare employee and administrative request letters” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she prepares the letters employees ask for, such as salary certificates and NOC letters, and the company's administrative letters. • Starts when: an employee or department requests a letter. • How it runs: (1) she confirms the request and the purpose. (2) She uses the approved template for that letter type. (3) She verifies the details against the employee record. (4) She obtains the required authorised signature. (5) She issues the letter and records it in the letter register. • Proof it happened: issued letters recorded in a register with the request, the verified details and the authorising signature. • Where it usually breaks: letters are issued with details taken from the request rather than the employee record, so incorrect salaries and titles go out on company letterhead. | • Require every detail to be verified against the employee record rather than taken from the request, since letters on company letterhead carry legal weight. • Maintain a letter register with the type, recipient, purpose and date, so the company knows what it has certified and to whom. • State who may sign each letter type, particularly those making financial statements about the company or an employee. • Use controlled templates only, and prohibit letters drafted from scratch. • State the turnaround commitment, as slow issuance of routine letters is a common source of employee frustration.
1023 | People & Culture | Maintain employee master data in Excel and ERP | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Maintain employee master data in Excel and ERP” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Maintain employee master data in Excel and ERP” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she keeps the employee data accurate in both the spreadsheet and the ERP, and makes sure they agree. • Starts when: on any employee change, and at the periodic reconciliation point. • How it runs: (1) she records changes as they are approved. (2) She updates both the ERP and the working records. (3) She reconciles the two for differences. (4) She corrects differences and identifies the cause. (5) She reports the data quality position. • Proof it happened: reconciled employee master data across the ERP and the working records, with the differences resolved. • Where it usually breaks: two versions of the data are maintained and diverge, so different departments quote different figures for headcount and salary. | • Name the ERP as the single source of truth and treat any spreadsheet as a working extract, since parallel masters always diverge. • Require reconciliation at a set frequency with the differences investigated rather than overwritten. • Restrict who may change master data and log every change with the reason. • Require changes to be supported by an approval document, particularly salary and position changes. • State the retention and access rules, as this data is both sensitive and legally protected.
1024 | People & Culture | Maintain physical and digital employee files | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Maintain physical and digital employee files” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Maintain physical and digital employee files” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she keeps the employee files, physical and digital, complete and secure. • Starts when: on joining, and on every event that produces a document. • How it runs: (1) she creates the file with the standard index on joining. (2) She files each document in the correct section. (3) She keeps the digital copies in the controlled location. (4) She checks the files for completeness periodically. (5) She retains and disposes of them per the retention policy. • Proof it happened: complete and indexed employee files, physical and digital, held in controlled storage with completeness checks. • Where it usually breaks: documents accumulate unfiled, so a file cannot be produced when an inspection or a dispute requires it. | • Define the standard file index and require periodic completeness checks, since an incomplete file is only discovered when an inspection or a dispute demands it. • State who may access employee files and require access to be logged, as these contain sensitive personal data. • Require physical files to be held in locked storage, not in open offices. • State the retention period and the disposal method, because holding personal data indefinitely is itself a breach. • Require a file check at exit, so the record is complete before the person leaves.
1025 | People & Culture | Distribute payslips securely | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Distribute payslips securely” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Distribute payslips securely” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she gets payslips to employees without anyone else seeing them. • Starts when: payroll is completed and payslips are released. • How it runs: (1) she obtains the approved payslips. (2) She distributes them individually through the approved secure method. (3) She confirms receipt where required. (4) She handles queries confidentially and routes them to Finance. (5) She retains the distribution record. • Proof it happened: a payslip distribution record confirming individual secure delivery, with queries routed and recorded. • Where it usually breaks: payslips are handed out in bulk through a supervisor, so salary information circulates and creates disputes. | • Prohibit bulk distribution through supervisors or colleagues, since salary confidentiality once lost cannot be restored and causes lasting disputes. • State the approved delivery method, with individual email or in person collection against signature. • Route salary queries to Finance rather than answering them, so incorrect explanations are not given. • Require the distribution record to be retained as evidence that payslips were issued. • State the confidentiality obligation on the person distributing, in writing.
1026 | People & Culture | Track annual leave balances and requests | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Track annual leave balances and requests” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Track annual leave balances and requests” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she keeps track of who has how much leave left, and processes leave requests. • Starts when: a leave request is submitted, and at the periodic balance review. • How it runs: (1) she checks the entitlement and the available balance. (2) She confirms the approval from the line manager. (3) She records the leave in the system and updates the balance. (4) She informs payroll where the leave affects pay. (5) She reports the balances and the accrued liability. • Proof it happened: recorded leave with approvals, updated balances and reported accrued leave liability. • Where it usually breaks: leave taken is not recorded, so balances are wrong and the accrued liability in the accounts is understated. | • Require every absence to be recorded against a leave type, since unrecorded leave corrupts both the balance and the accrued liability in the accounts. • Require approval before the leave is taken, not retrospectively, and state the exception route for emergencies. • Report accrued leave liability to Finance each period, as this is a real cost that grows unnoticed. • Flag excessive accumulated balances, because large untaken balances create both cost and continuity risk. • Reconcile leave records to attendance data, which catches both unrecorded absence and unrecorded leave.
1027 | People & Culture | Consolidate site and office attendance | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Consolidate site and office attendance” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Consolidate site and office attendance” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she brings together the attendance from the sites and the office into one set of records for payroll. • Starts when: at each attendance cut off before payroll. • How it runs: (1) she collects the attendance data from all locations. (2) She checks for missing punches, duplicates and anomalies. (3) She reconciles against the leave records. (4) She obtains supervisor confirmation for the corrections. (5) She issues the consolidated attendance for payroll. • Proof it happened: a consolidated attendance record with anomalies resolved, supervisor confirmations and reconciliation to leave. • Where it usually breaks: missing punches are corrected on assumption rather than supervisor confirmation, which becomes payment for time not worked. | • Require written supervisor confirmation for every manual attendance correction, since assumed corrections become payment for time not worked. • Reconcile attendance to the active employee list, which catches both missing employees and records for people who have left. • Require anomalies such as duplicate punches and impossible hours to be investigated rather than adjusted. • Set the cut off and state that late submissions move to the next period, or payroll is permanently rushed. • Report the volume of manual corrections, as a high volume indicates a system or discipline problem.
1028 | People & Culture | Submit Emirates ID data for C3 payroll card processing | HR & Admin Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The HR & Admin Assistant completes the work item “Submit Emirates ID data for C3 payroll card processing” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The HR & Admin Assistant completes the work item “Submit Emirates ID data for C3 payroll card processing” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she submits the identity data needed to get employees their payroll cards, so they can be paid. • Starts when: a new employee needs a payroll card, or a card needs replacement. • How it runs: (1) she collects the Emirates ID data required. (2) She checks the data is accurate and complete. (3) She submits it through the approved channel. (4) She tracks the card issuance. (5) She confirms the card details are recorded for payroll. • Proof it happened: submitted card applications with tracked issuance and the card details recorded for payroll. • Where it usually breaks: the submission is delayed or rejected for a data error, so the employee misses a salary cycle. | • Require the data to be verified against the identity document before submission, since a single character error causes rejection and a missed salary cycle. • Start the process on joining rather than at the first payroll, as the issuance lead time is outside the company's control. • Track rejections and their causes, so the same data errors are not repeated. • State the interim payment arrangement where a card is not yet issued, so nobody goes unpaid. • Confirm the card details are recorded correctly for payroll before the first payment.
1029 | People & Culture | Track expiry and renewal of company documents, licences and visas | HR & Admin Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Assistant completes the work item “Track expiry and renewal of company documents, licences and visas” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Assistant completes the work item “Track expiry and renewal of company documents, licences and visas” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she keeps track of when the company's licences, documents and visas expire, so they get renewed in time. • Starts when: continuously, with formal review at the periodic cycle. • How it runs: (1) she maintains the register of all company documents with expiry dates. (2) She sets advance warnings by lead time. (3) She initiates the renewal process in time. (4) She tracks the renewal to completion. (5) She reports the upcoming and overdue items. • Proof it happened: a maintained document register with expiry dates, advance warnings and evidence of completed renewals. • Where it usually breaks: a licence lapses because the renewal warning was set at the expiry date rather than at the lead time needed. | • Set warnings by required lead time rather than by expiry date, since a warning on the expiry day is already too late for most renewals. • Require the register to cover every licence, permit, registration, insurance and certificate with a named owner each. • Report overdue and upcoming expiries monthly to the CPCO, as a lapsed trade licence can halt operations entirely. • Require the renewal evidence to be filed and the register updated on completion. • Include documents held by other departments, otherwise the register covers only what HR happens to know about.
1030 | People & Culture | Process authorised transactions on the MOHRE portal | HR & Admin Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Assistant completes the work item “Process authorised transactions on the MOHRE portal” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Assistant completes the work item “Process authorised transactions on the MOHRE portal” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she carries out the authorised labour ministry transactions on the MOHRE portal. • Starts when: a labour transaction is required and authorised. • How it runs: (1) she confirms the transaction is authorised. (2) She prepares the required data and documents. (3) She processes it on the portal. (4) She pays or arranges the fees against a record. (5) She obtains the confirmation and files it with the register updated. • Proof it happened: completed portal transactions with authorisation, fee records and the filed confirmations. • Where it usually breaks: transactions are processed without a record, so the company cannot show what was submitted or when. | • Require a transaction log with the reference, date, purpose and outcome, since portal submissions leave no internal record otherwise. • Restrict portal credentials and prohibit sharing, because these submissions legally bind the company. • Require authorisation before processing, with the authoriser named in the log. • File every confirmation, as these are the evidence in any labour inspection or dispute. • Reconcile portal fees to the finance records, so government fee spending is traceable.
1031 | People & Culture | Process authorised transactions on the Invest in Dubai portal | HR & Admin Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Assistant completes the work item “Process authorised transactions on the Invest in Dubai portal” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Assistant completes the work item “Process authorised transactions on the Invest in Dubai portal” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she carries out the authorised licensing transactions on the Invest in Dubai portal. • Starts when: a licensing or registration transaction is required and authorised. • How it runs: (1) she confirms the transaction and its authorisation. (2) She prepares the documents and data required. (3) She processes it on the portal. (4) She arranges the fees against a record. (5) She obtains the outcome documents and updates the register. • Proof it happened: completed portal transactions with authorisation, fee records and the outcome documents filed. • Where it usually breaks: a licence amendment is processed without the internal records being updated, so the company's own records show the old position. | • Require the internal registers and records to be updated on completion, since a licence changed on the portal but not internally leads to wrong information being quoted. • Require authorisation before any licensing change, as these affect what the company is legally permitted to do. • Maintain a transaction log with references and outcomes. • Restrict credentials and prohibit sharing, and record who holds them. • Distribute the updated licence to the departments that need it, particularly Finance and Procurement.
1032 | People & Culture | Track DEQ portal updates and required actions | HR & Admin Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The HR & Admin Assistant completes the work item “Track DEQ portal updates and required actions” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The HR & Admin Assistant completes the work item “Track DEQ portal updates and required actions” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she watches the DEQ portal for updates and required actions, and makes sure they are dealt with. • Starts when: at the monitoring frequency, and when a notification is received. • How it runs: (1) she checks the portal on the set schedule. (2) She identifies new requirements, notices and deadlines. (3) She informs the responsible party. (4) She tracks the action to completion. (5) She files the evidence of compliance. • Proof it happened: a portal monitoring log with identified actions, the parties informed and evidence of completion. • Where it usually breaks: portal notices are seen but not routed to anyone, so a deadline passes with no action taken. | • Require every notice to be logged and assigned to a named owner with a deadline, since a notice seen and not routed is the same as a notice missed. • Set a monitoring frequency, as portal notices are not always pushed by email. • Escalate approaching deadlines rather than continuing to remind quietly. • File the compliance evidence, because the portal record alone may not be retrievable later. • Name a deputy for monitoring, so notices are not missed during absence.
1033 | People & Culture | Track probation deadlines and confirmation decisions | HR & Admin Assistant | Trigger: From the employee joining date. Action: Maintain probation milestones and obtain the reporting manager's assessment before the decision deadline. Output/Evidence: The employee file and ERP updated with the confirmation, extension or termination evidence. Control/Handoff: Confirmation, extension or termination is routed for approval before records are updated. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | From the employee joining date. | Maintain probation milestones and obtain the reporting manager's assessment before the decision deadline. | The employee file and ERP updated with the confirmation, extension or termination evidence. | Confirmation, extension or termination is routed for approval before records are updated. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she tracks when each new employee's probation ends, so a decision is actually taken rather than defaulting. • Starts when: on joining, with the probation end date recorded. • How it runs: (1) she records the probation end date at joining. (2) She notifies the line manager in advance of the deadline. (3) She obtains the confirmation, extension or termination decision. (4) She issues the resulting letter. (5) She updates the employee record and files the decision. • Proof it happened: a probation tracker with advance notifications, the recorded decision and the issued confirmation letter. • Where it usually breaks: the deadline passes without a decision, so the employee is confirmed by default and the opportunity to act on poor performance is lost. | • Notify the line manager well before the deadline and require a written decision, since a passed deadline confirms the employee by default and removes the option to act. • State the notice requirement for termination during probation, as this differs from the confirmed position and getting it wrong creates a claim. • Require the decision to be supported by documented performance discussions, not a single judgement at the end. • Issue the confirmation letter and file it, because employees frequently need it for banking and visa purposes. • Report upcoming probation deadlines monthly, as this is one of the most commonly missed HR deadlines.
1034 | People & Culture | Maintain controlled HR forms, templates and revision index | HR & Admin Assistant | Trigger: When a form, letter or checklist is created or revised. Action: Apply the approved template, owner, revision, effective date and approval record. Output/Evidence: The controlled template index accessible to authorised users. Control/Handoff: Superseded versions are withdrawn from use. Continuity/Escalation: The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. Timing: To be confirmed. | When a form, letter or checklist is created or revised. | Apply the approved template, owner, revision, effective date and approval record. | The controlled template index accessible to authorised users. | Superseded versions are withdrawn from use. | The HR & Admin Lead reviews the evidence and provides backup; overdue manager, government, legal or payment dependencies escalate to the CPCO. | To be confirmed. | • In plain words: she keeps the HR forms and templates controlled, so everyone uses the current version. • Starts when: a form is created or revised, and at the periodic review. • How it runs: (1) she maintains the register of HR forms with version numbers. (2) She issues revisions from a single controlled location. (3) She withdraws superseded versions. (4) She informs users of the changes. (5) She reviews the forms periodically for currency. • Proof it happened: a controlled forms register with version numbers, issued current versions and withdrawn superseded ones. • Where it usually breaks: old forms remain in circulation on personal drives, so submissions arrive on outdated templates that miss required fields. | • Require forms to be used from a single controlled location and prohibit personal copies, since old versions in circulation miss the fields that were added for a reason. • Require explicit withdrawal of superseded versions with users informed. • Keep a version history, as knowing which version applied at a given date matters in a dispute. • Require legal review of forms that capture consent or contractual terms. • Reject submissions on withdrawn forms rather than accepting and reworking them.
1035 | People & Culture | Conduct office and facility orientation | Office Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The Office Assistant completes the work item “Conduct office and facility orientation” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The Office Assistant completes the work item “Conduct office and facility orientation” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he shows new joiners around the office and explains how the place works. • Starts when: on the joining date. • How it runs: (1) he shows the workspace, facilities and amenities. (2) He explains the access arrangements and working hours. (3) He points out the fire exits, assembly point and first aid provision. (4) He explains the practical arrangements such as parking and pantry. (5) He records the orientation. • Proof it happened: a recorded office orientation covering facilities, access and emergency arrangements. • Where it usually breaks: the emergency arrangements are skipped, so a new employee does not know where to go if the alarm sounds. | • Require the fire exits, assembly point and first aid provision to be covered on day one, since a person who does not know the route is the one who does not get out. • Include the practical arrangements, as these are what new joiners actually struggle with in the first week. • Record the orientation, so it is evidenced rather than assumed. • Cover the access and security arrangements, including who to contact out of hours. • Repeat the orientation when the office layout or emergency arrangements change.
1036 | People & Culture | Allocate workstation and company assets | Office Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The Office Assistant completes the work item “Allocate workstation and company assets” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The Office Assistant completes the work item “Allocate workstation and company assets” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he sets up the desk and hands over the company items the new joiner needs. • Starts when: before or on the joining date. • How it runs: (1) he prepares the workstation. (2) He issues the allocated assets against a record. (3) He records the condition and the serial numbers. (4) He obtains the employee's signature. (5) He updates the asset register. • Proof it happened: an asset issue record with serial numbers, condition and the employee's signature, and the register updated. • Where it usually breaks: items are handed over without a signed record, so when the person leaves nobody can say what they were given. | • Require a signed issue record with serial numbers for every asset, since without it nobody can establish what the person holds when they leave. • Record the condition at issue, so damage on return is attributable. • Update the asset register at issue rather than later. • Prepare the workstation before the joining date, as an unprepared arrival is the commonest onboarding complaint. • Include the asset list in the exit clearance checklist.
1037 | People & Culture | Arrange approved employee transportation | Office Assistant | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The Office Assistant completes the work item “Arrange approved employee transportation” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The Office Assistant completes the work item “Arrange approved employee transportation” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he arranges the approved transport for employees. • Starts when: transport is required and approved. • How it runs: (1) he confirms the entitlement and the approval. (2) He arranges the transport within the policy. (3) He confirms the arrangements with the employees. (4) He monitors the service. (5) He records the arrangement and the cost allocation. • Proof it happened: arranged transport with entitlement confirmed, employees informed and cost allocation recorded. • Where it usually breaks: transport is arranged on verbal request, so cost accumulates with no approval and no clear allocation. | • Require written approval and a cost allocation before arranging transport, since verbally arranged transport accumulates cost that nobody owns. • Confirm the driver and vehicle meet the requirements for carrying passengers. • Record the entitlement basis per employee, so provision is consistent. • Monitor the service against what is being paid for, as unused routes continue being charged. • Report transport cost by project or department.
1038 | People & Culture | Issue uniforms and colour-coded safety helmets | Office Assistant | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The Office Assistant completes the work item “Issue uniforms and colour-coded safety helmets” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The Office Assistant completes the work item “Issue uniforms and colour-coded safety helmets” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he issues the uniforms and the colour coded safety helmets. • Starts when: an employee joins, or replacement is required. • How it runs: (1) he confirms the entitlement and the correct colour code for the role. (2) He issues against a record. (3) He obtains the employee's signature. (4) He records the issue and the size. (5) He handles replacements against the policy. • Proof it happened: an issue record with the correct colour code, size and the employee's signature. • Where it usually breaks: the wrong helmet colour is issued, so the site's visual identification of roles breaks down and safety supervision is weakened. | • Check the helmet colour against the role every time, since colour coding is how supervisors identify roles and competencies at a glance on site. • Replace damaged PPE immediately and free of charge, as charging for replacement leads to people wearing damaged PPE. • Record the issue and the size, so replacements are straightforward. • Include PPE in the exit clearance. • Report unusual replacement rates, as these can indicate either misuse or poor quality.
1039 | People & Culture | Collect and reconcile vehicle tracking sheets | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Collect and reconcile vehicle tracking sheets” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Collect and reconcile vehicle tracking sheets” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he collects the vehicle tracking sheets and checks they reconcile. • Starts when: at the collection cycle. • How it runs: (1) he collects the sheets from each driver. (2) He checks the readings and the journeys recorded. (3) He reconciles against the fuel and tracking data. (4) He queries discrepancies with the driver. (5) He reports the position. • Proof it happened: collected and reconciled vehicle tracking sheets with discrepancies queried and reported. • Where it usually breaks: sheets are collected but never reconciled to fuel or tracking data, so private use and fuel loss are invisible. | • Reconcile the sheets against the fuel and GPS data rather than filing them, since an unreconciled sheet makes private use and fuel loss completely invisible. • Query gaps and unexplained journeys with the driver rather than absorbing them. • Report recurring discrepancies by vehicle and driver. • Require the sheet to be completed daily rather than reconstructed at collection. • Escalate unexplained fuel consumption, as this is a common and significant loss.
1040 | People & Culture | Maintain controlled company document files | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Maintain controlled company document files” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Maintain controlled company document files” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he keeps the company document files in order and controlled. • Starts when: documents are received for filing. • How it runs: (1) he files documents per the filing structure. (2) He records the location. (3) He controls access to the files. (4) He checks for completeness periodically. (5) He retains and archives per the retention rules. • Proof it happened: controlled document files with locations recorded, access controlled and completeness checked. • Where it usually breaks: documents are filed where there is space rather than per the structure, so they cannot be found when needed. | • File to the defined structure and record the location, since documents filed where there is space cannot be found when they are urgently needed. • Control access to files containing personal or commercial information. • Keep original documents in locked storage. • Check for completeness at a set frequency rather than on demand. • Apply the retention rules rather than keeping everything indefinitely.
1041 | People & Culture | Handle office correspondence, calls and shared email | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Handle office correspondence, calls and shared email” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Handle office correspondence, calls and shared email” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he handles the office post, calls and the shared email inbox. • Starts when: continuously during office hours. • How it runs: (1) he receives and records incoming correspondence. (2) He routes it to the correct person. (3) He answers and routes calls. (4) He monitors the shared inbox and routes items. (5) He tracks anything requiring a response. • Proof it happened: recorded incoming correspondence routed to the correct owner, with responses tracked. • Where it usually breaks: items in the shared inbox are read and left, so an enquiry or a notice with a deadline sits unactioned. | • Require every item in the shared inbox to be routed to a named owner rather than left read, since an unrouted enquiry or legal notice sits until the deadline passes. • Register incoming correspondence, particularly anything from a client, authority or lawyer. • Route business enquiries to the CRM registration process immediately. • Name a deputy for the inbox during absence. • Flag anything appearing time critical for immediate escalation.
1042 | People & Culture | Coordinate vehicle insurance and Mulkiya renewal | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Coordinate vehicle insurance and Mulkiya renewal” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Coordinate vehicle insurance and Mulkiya renewal” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he arranges the vehicle insurance and registration renewals. • Starts when: renewal approaches, or a vehicle is acquired. • How it runs: (1) he tracks the expiry dates. (2) He initiates the renewal in advance. (3) He arranges the insurance and the registration. (4) He confirms the documents are issued. (5) He files them and updates the register. • Proof it happened: renewed insurance and registration with documents filed and the register updated. • Where it usually breaks: a renewal lapses, so the vehicle is driven uninsured and unregistered, which is both illegal and uninsured exposure. | • Set the renewal warning by lead time and escalate any at risk, since driving an unregistered or uninsured vehicle is both illegal and leaves any accident entirely uncovered. • Prohibit vehicle use where insurance or registration has lapsed, and name who enforces it. • Keep the documents in the vehicle as required and a copy on file. • Check the insurance covers the actual use, including passengers and site access. • Maintain one register covering every vehicle with a named owner.
1043 | People & Culture | Coordinate RTA fines, testing and vehicle passing | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Coordinate RTA fines, testing and vehicle passing” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Coordinate RTA fines, testing and vehicle passing” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he deals with the traffic fines and the vehicle testing. • Starts when: a fine is received, or testing is due. • How it runs: (1) he checks for fines at the set frequency. (2) He identifies the driver responsible. (3) He processes the payment or the dispute. (4) He arranges the vehicle testing before expiry. (5) He records the fines and the outcomes. • Proof it happened: recorded fines with the driver identified and the payment or dispute processed, and testing completed. • Where it usually breaks: fines are paid without identifying the driver, so there is no consequence and the behaviour continues. | • Identify the driver for every fine and apply the stated policy, since paying fines centrally without consequence means the behaviour continues and the cost grows. • Check for fines at a set frequency, as unpaid fines escalate and can block registration. • Report fines by driver, because the pattern identifies a real safety risk. • Arrange testing before expiry rather than after, as an untested vehicle cannot be driven. • Dispute incorrect fines within the allowed period.
1044 | People & Culture | Register Salik for new vehicles | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Register Salik for new vehicles” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Register Salik for new vehicles” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he registers new vehicles for the road toll system. • Starts when: a vehicle is acquired. • How it runs: (1) he obtains the vehicle details. (2) He registers it on the toll system. (3) He confirms the tag is fitted and active. (4) He confirms the account is funded. (5) He records the registration. • Proof it happened: a completed toll registration with the tag active, account funded and registration recorded. • Where it usually breaks: the account runs out of funds, so fines accumulate on every journey until someone notices. | • Set a low balance alert on the toll account, since an unfunded account generates a penalty on every single journey until somebody notices. • Register the vehicle before it is put into use. • Confirm the tag is fitted and reading correctly, as an unread tag also generates penalties. • Reconcile toll charges to the vehicle log, which reveals unauthorised use. • Deregister vehicles on disposal.
1045 | People & Culture | Register vehicles in ENOC VIP | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Register vehicles in ENOC VIP” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Register vehicles in ENOC VIP” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he registers the vehicles on the fuel card system. • Starts when: a vehicle is acquired. • How it runs: (1) he obtains the vehicle and driver details. (2) He registers the vehicle on the fuel system. (3) He obtains the fuel card and assigns it. (4) He records the assignment. (5) He monitors the consumption. • Proof it happened: a fuel system registration with the card assigned and recorded, and consumption monitored. • Where it usually breaks: fuel cards are shared between vehicles, so consumption cannot be attributed and fuel theft is undetectable. | • Assign each fuel card to a single vehicle and prohibit sharing, since shared cards make consumption unattributable and fuel theft undetectable. • Monitor consumption against mileage per vehicle, as this is the control that reveals theft. • Set a transaction limit per fill, so unusual transactions are blocked. • Reconcile fuel statements to the vehicle logs monthly. • Deactivate the card immediately on vehicle disposal or driver change.
1046 | People & Culture | Upload approved purchase details and receipts to Pluto | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Upload approved purchase details and receipts to Pluto” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Upload approved purchase details and receipts to Pluto” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he uploads the purchase details and receipts to the system. • Starts when: approved purchases are made. • How it runs: (1) he collects the receipts and purchase details. (2) He checks each has its approval. (3) He uploads them to the system. (4) He confirms the upload is complete and legible. (5) He files the originals where required. • Proof it happened: uploaded purchase details and receipts with approvals verified and the originals filed. • Where it usually breaks: receipts are uploaded without approval evidence, so unapproved spending enters the records looking legitimate. | • Require the approval evidence to be uploaded with the receipt, since a receipt alone makes unapproved spending look legitimate in the records. • Check the upload is legible, as an unreadable receipt cannot support the expense or the tax recovery. • Upload promptly rather than in batches, because receipts accumulate and are lost. • Retain originals where the tax rules require them. • Report purchases without approval as exceptions.
1047 | People & Culture | Maintain office and pantry supplies | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Maintain office and pantry supplies” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Maintain office and pantry supplies” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he keeps the office and pantry supplies stocked. • Starts when: stock runs low, or at the replenishment cycle. • How it runs: (1) he checks the stock levels. (2) He raises the requirement within the approved limits. (3) He orders through the approved route. (4) He receives and checks the delivery. (5) He records the stock and the consumption. • Proof it happened: maintained supplies with requirements raised through the approved route and consumption recorded. • Where it usually breaks: supplies are bought directly with cash, so spend accumulates outside any control or visibility. | • Route supply purchases through the approved procurement route rather than cash, since direct cash purchasing accumulates significant untracked spend. • Set reorder levels so ordering is planned rather than urgent. • Record consumption, because unusual consumption indicates either waste or removal. • Consolidate orders to reduce cost and administration. • Report monthly spend against the allocation.
1048 | People & Culture | Coordinate office requirements with building management | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Coordinate office requirements with building management” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Coordinate office requirements with building management” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he deals with the building management on office issues. • Starts when: a building related requirement or issue arises. • How it runs: (1) he records the requirement or issue. (2) He raises it with building management. (3) He tracks the response. (4) He escalates where it is not resolved. (5) He records the resolution. • Proof it happened: raised building requirements with the response tracked, escalated where needed and resolution recorded. • Where it usually breaks: issues are raised verbally and forgotten, so recurring problems such as cooling or cleaning are never actually fixed. | • Raise building issues in writing with a reference and track them, since verbally raised issues are forgotten and recurring problems persist for months. • Escalate unresolved issues to the landlord under the lease terms rather than continuing to ask. • Record recurring issues, as these may be a lease compliance matter. • Prioritise issues affecting safety and working conditions. • Report unresolved items to the CPCO.
1049 | People & Culture | Coordinate GPS installation for new vehicles | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Coordinate GPS installation for new vehicles” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Coordinate GPS installation for new vehicles” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he arranges GPS installation on new vehicles. • Starts when: a vehicle is acquired. • How it runs: (1) he arranges the installation with the approved supplier. (2) He confirms the device is active and reporting. (3) He confirms the vehicle appears on the tracking system. (4) He records the installation. (5) He confirms the driver is informed. • Proof it happened: a completed GPS installation with the device confirmed active and reporting on the system. • Where it usually breaks: the device is installed but never verified as reporting, so the vehicle is untracked and nobody knows. | • Verify the device is reporting on the tracking system after installation, since an installed device that is not reporting leaves the vehicle untracked and unnoticed. • Install before the vehicle is put into use. • Check periodically that all vehicles are reporting, as devices fail silently. • Inform the driver that tracking is in place, which is both fair and legally advisable. • Investigate any vehicle that stops reporting.
1050 | People & Culture | Maintain the PWD sheet after purpose and data-standard approval | Office Assistant | Trigger: Only after the CPCO approves the PWD sheet's purpose, required fields, data sources, owner, review frequency and approver. Action: The Office Assistant updates the controlled PWD sheet using approved source evidence and maintains its revision status. Output/Evidence: an approved, current PWD sheet and update record. Control/Handoff: The item remains inactive until the definition is formally approved. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | Only after the CPCO approves the PWD sheet's purpose, required fields, data sources, owner, review frequency and approver. | The Office Assistant updates the controlled PWD sheet using approved source evidence and maintains its revision status. | an approved, current PWD sheet and update record. | The item remains inactive until the definition is formally approved. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he maintains the PWD sheet once its purpose and data standards are approved. • Starts when: the purpose and standards are approved. • How it runs: (1) he confirms the approved purpose and the required fields. (2) He collects the data from the approved sources. (3) He enters it per the standard. (4) He checks completeness and accuracy. (5) He issues or reports it as required. • Proof it happened: a maintained PWD sheet per the approved purpose and data standard, checked for completeness. • Where it usually breaks: the sheet accumulates fields nobody asked for, so it becomes large, unreliable and used by nobody. | • Require the purpose and the field list to be approved before the sheet is maintained, since sheets that grow by accumulation become unreliable and used by nobody. • State the source for each field, so the data is verifiable rather than assumed. • Review the sheet's continued usefulness periodically, and stop maintaining it if nobody uses it. • Check completeness rather than only filling what is easy to obtain. • State who may add or change a field.
1051 | People & Culture | Track cleaner attendance and service completion | Office Assistant | Trigger: When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. Action: The Office Assistant completes the work item “Track cleaner attendance and service completion” using approved records and systems. Output/Evidence: a completed administrative transaction and updated register with supporting evidence. Control/Handoff: The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved office, vehicle, portal, vendor, document or project-support requirement is received or a renewal becomes due. | The Office Assistant completes the work item “Track cleaner attendance and service completion” using approved records and systems. | a completed administrative transaction and updated register with supporting evidence. | The HR & Admin Lead verifies the transaction and coordinates the relevant department or authorised approver before commitment or closure. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he tracks the cleaners' attendance and whether the work was actually done. • Starts when: daily. • How it runs: (1) he records the cleaner attendance. (2) He checks the areas were actually cleaned. (3) He records the service completion. (4) He raises shortfalls with the supplier. (5) He reconciles the invoice against the record. • Proof it happened: attendance and service completion records with shortfalls raised and invoices reconciled. • Where it usually breaks: attendance is recorded but the work is never checked, so the company pays for cleaning that did not happen. | • Check the work was actually done rather than only recording attendance, since attendance alone means the company pays for cleaning that may not have happened. • Reconcile the supplier invoice against the attendance and completion record. • Raise shortfalls with the supplier at the time, as retrospective deductions are disputed. • Record recurring shortfalls for the contract review. • Check the areas that are easy to skip, such as stores and back offices.
1052 | People & Culture | Prepare meeting rooms, refreshments and internal logistics | Office Assistant | Trigger: When an approved meeting or company activity is scheduled. Action: Prepare the room, seating, refreshments, equipment and visitor logistics before the required time. Output/Evidence: Confirmed completion of the preparation. Control/Handoff: Shortages or facility issues are reported to the HR & Admin Lead. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an approved meeting or company activity is scheduled. | Prepare the room, seating, refreshments, equipment and visitor logistics before the required time. | Confirmed completion of the preparation. | Shortages or facility issues are reported to the HR & Admin Lead. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he prepares the meeting rooms and handles the internal logistics. • Starts when: a meeting or internal requirement is scheduled. • How it runs: (1) he confirms the booking and the requirements. (2) He prepares the room and the equipment. (3) He arranges the refreshments where required. (4) He checks the equipment works before the meeting. (5) He clears the room afterwards. • Proof it happened: prepared meeting rooms with equipment checked and requirements met. • Where it usually breaks: the equipment is not tested, so a client meeting starts with ten minutes of technical problems. | • Test the room equipment before every external meeting, since a client meeting starting with technical problems damages the impression before anyone speaks. • Confirm the requirements in advance rather than assuming. • Check the room is cleared and presentable before the meeting, not only after. • Maintain a booking system so double bookings do not occur. • Report recurring equipment faults to IT rather than working around them.
1053 | People & Culture | Support filing, scanning, copying and dispatch | Office Assistant | Trigger: When an authorised document request is received. Action: Reproduce, scan, file or dispatch the controlled document to the correct recipient. Output/Evidence: Retained dispatch or filing evidence where required. Control/Handoff: Confidential information is protected and released only to the correct recipient. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | When an authorised document request is received. | Reproduce, scan, file or dispatch the controlled document to the correct recipient. | Retained dispatch or filing evidence where required. | Confidential information is protected and released only to the correct recipient. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he supports the filing, scanning, copying and sending out of documents. • Starts when: a request is received. • How it runs: (1) he receives the request. (2) He performs the scanning, copying or dispatch. (3) He checks the output is complete and legible. (4) He obtains dispatch evidence where required. (5) He records the request as completed. • Proof it happened: completed document support requests with output checked and dispatch evidence retained. • Where it usually breaks: a document is dispatched without proof of sending, so a missed delivery cannot be evidenced or traced. | • Obtain and retain dispatch evidence for anything contractually significant, since a delivery that cannot be evidenced is treated as never sent. • Check scans are complete and legible before the original is returned or filed. • Handle confidential documents separately with controlled access. • Record the request and its completion, so queries can be answered. • Use the required dispatch method for formal notices rather than the convenient one.
1054 | People & Culture | Report facility maintenance and office safety issues | Office Assistant | Trigger: During daily office checks or when an issue is reported. Action: Record the location, risk and evidence of the facility or office-service issue. Output/Evidence: The recorded issue with the repair or corrective action tracked to verified closure. Control/Handoff: The HR & Admin Lead or building management is notified for action. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | During daily office checks or when an issue is reported. | Record the location, risk and evidence of the facility or office-service issue. | The recorded issue with the repair or corrective action tracked to verified closure. | The HR & Admin Lead or building management is notified for action. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he reports the maintenance and safety problems he sees in the office. • Starts when: an issue is identified. • How it runs: (1) he identifies the maintenance or safety issue. (2) He assesses whether it needs immediate action. (3) He reports it to the responsible party. (4) He takes immediate action where the risk is high. (5) He tracks it to resolution. • Proof it happened: reported maintenance and safety issues with immediate action where needed and resolution tracked. • Where it usually breaks: a safety issue such as a trailing cable or a blocked exit is noticed and reported but not made safe immediately. | • Require immediate action on any safety issue rather than only reporting it, since a blocked exit or trip hazard causes harm before the report is actioned. • Give explicit authority to make an area safe without waiting for approval. • Track reported issues to resolution rather than treating the report as the end. • Escalate unresolved safety issues, as these carry real liability. • Record recurring issues, because these indicate a facility problem.
1055 | People & Culture | Maintain office support request and completion log | Office Assistant | Trigger: For each office-support request. Action: Record the requester, requirement, priority, responsible person and due date. Output/Evidence: Updated completion evidence in the office-support register. Control/Handoff: Overdue items are escalated and recurring support issues reported to the HR & Admin Lead. Continuity/Escalation: The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. Timing: To be confirmed. | For each office-support request. | Record the requester, requirement, priority, responsible person and due date. | Updated completion evidence in the office-support register. | Overdue items are escalated and recurring support issues reported to the HR & Admin Lead. | The HR & Admin Assistant or HR & Admin Lead provides operational backup; building, vehicle, vendor or service exceptions escalate to the HR & Admin Lead. | To be confirmed. | • In plain words: he keeps the log of office support requests and what was done. • Starts when: a request is received. • How it runs: (1) he logs the request with the requester and the date. (2) He records the action required. (3) He records the completion. (4) He reports outstanding requests. (5) He identifies recurring requests. • Proof it happened: a support request log with requests, actions and completions recorded. • Where it usually breaks: requests are handled informally and never logged, so the workload and the recurring problems are both invisible. | • Log every request even when handled immediately, since an unlogged workload is invisible and recurring problems are never identified. • Report outstanding requests with ageing. • Analyse recurring requests, as these usually indicate a fixable underlying problem. • Record who requested, so completion can be confirmed back. • Use the log to justify resourcing rather than arguing from impression.
1056 | People & Culture | Prepare system, software, email and server access before joining | IT Support Engineer | Trigger: When an approved manpower requirement reaches the recruitment stage. Action: The IT Support Engineer completes the work item “Prepare system, software, email and server access before joining” using approved records and systems. Output/Evidence: an updated candidate file, recruitment tracker and supporting evidence. Control/Handoff: The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an approved manpower requirement reaches the recruitment stage. | The IT Support Engineer completes the work item “Prepare system, software, email and server access before joining” using approved records and systems. | an updated candidate file, recruitment tracker and supporting evidence. | The HR & Admin Lead reviews the file; the hiring manager provides technical input; the CPCO approves employment and compensation decisions within authority. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he sets up the accounts and access a new joiner needs before their first day. • Starts when: a joining date is confirmed. • How it runs: (1) he receives the access requirement for the role. (2) He creates the accounts needed. (3) He configures the access rights per the role profile. (4) He tests the access works. (5) He confirms readiness before the joining date. • Proof it happened: created and tested accounts with role based access configured before the joining date. • Where it usually breaks: access rights are copied from an existing user, so the new joiner inherits permissions they should not have. | • Configure access from the role profile and never by copying an existing user, since copying is how excess permissions spread invisibly through the company. • Test the access before the joining date, as a first day without working access wastes the day. • Require the access requirement to be approved by the manager, not requested informally. • Record what was granted, so it can be reviewed and revoked. • Apply least privilege as the default and add access on request.
1057 | People & Culture | Issue approved email and ERP access and deliver system training | IT Support Engineer | Trigger: When an approved candidate accepts the offer and a joining date is confirmed. Action: The IT Support Engineer completes the work item “Issue approved email and ERP access and deliver system training” using approved records and systems. Output/Evidence: a completed onboarding checklist, employee file and updated ERP record. Control/Handoff: The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an approved candidate accepts the offer and a joining date is confirmed. | The IT Support Engineer completes the work item “Issue approved email and ERP access and deliver system training” using approved records and systems. | a completed onboarding checklist, employee file and updated ERP record. | The HR & Admin Lead verifies completion and coordinates the reporting manager, Office Assistant and IT Support Engineer before the employee is released to work. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he issues the email and system access and shows the new joiner how to use them. • Starts when: on the joining date. • How it runs: (1) he issues the credentials securely. (2) He requires the password to be changed on first use. (3) He delivers the system training for the role. (4) He briefs the acceptable use and security rules. (5) He records the issue and the training. • Proof it happened: issued credentials with password change enforced, training delivered and the security briefing acknowledged. • Where it usually breaks: credentials are shared by message and never changed, so the original password remains in a chat history indefinitely. | • Issue credentials through a secure route and force a change on first use, since a password sent by message remains in the chat history indefinitely. • Require acknowledgement of the acceptable use and security rules, as enforcement needs evidence. • Deliver training on the actual system rather than as documentation. • Enable multi factor authentication at issue rather than later. • Record what was issued and trained, for the access review.
1058 | People & Culture | Revoke user access and recover company-controlled accounts | IT Support Engineer | Trigger: When a resignation, termination or employee exit is formally approved. Action: The IT Support Engineer completes the work item “Revoke user access and recover company-controlled accounts” using approved records and systems. Output/Evidence: a completed clearance file covering handover, access, assets, government cancellation and employee records. Control/Handoff: The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When a resignation, termination or employee exit is formally approved. | The IT Support Engineer completes the work item “Revoke user access and recover company-controlled accounts” using approved records and systems. | a completed clearance file covering handover, access, assets, government cancellation and employee records. | The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: when someone leaves he removes their access and recovers the company accounts. • Starts when: a departure is confirmed, or immediately on an involuntary exit. • How it runs: (1) he receives the exit notification with the timing. (2) He revokes the access at the agreed moment. (3) He recovers or redirects the mailbox. (4) He recovers company controlled accounts and credentials. (5) He records the revocation. • Proof it happened: revoked access with the timing recorded, mailbox recovered and company accounts recovered. • Where it usually breaks: access is revoked days after departure, which is exactly the window in which deliberate damage or data removal happens. | • Revoke access at the exit moment itself, and immediately with no notice on an involuntary exit, since the gap between departure and revocation is when deliberate damage happens. • Include every system, not just email, as secondary systems are routinely forgotten. • Recover control of any account registered in the individual's name, particularly social and vendor portals. • Preserve the mailbox rather than deleting it, as it may be needed as evidence. • Reconcile the leaver list to the active user list monthly.
1059 | People & Culture | Recover and reconcile company assets | IT Support Engineer | Trigger: When a resignation, termination or employee exit is formally approved. Action: The IT Support Engineer completes the work item “Recover and reconcile company assets” using approved records and systems. Output/Evidence: a completed clearance file covering handover, access, assets, government cancellation and employee records. Control/Handoff: The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When a resignation, termination or employee exit is formally approved. | The IT Support Engineer completes the work item “Recover and reconcile company assets” using approved records and systems. | a completed clearance file covering handover, access, assets, government cancellation and employee records. | The HR & Admin Lead controls clearance; the reporting manager confirms handover; IT closes access; Finance completes the approved final settlement. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he recovers the company IT assets from leavers and checks nothing is missing. • Starts when: a departure is confirmed. • How it runs: (1) he identifies the assets issued to the person. (2) He recovers them and checks the condition. (3) He checks the data on them. (4) He records the return and any shortfall. (5) He reports outstanding items before the settlement. • Proof it happened: recovered and reconciled IT assets with condition recorded and shortfalls reported. • Where it usually breaks: assets are reported outstanding after the settlement has been paid, so recovery is impossible. | • Report outstanding assets before the final settlement is released, since recovery after the person has been paid and left is effectively impossible. • Check the device for company data before reissue or disposal, and wipe it securely. • Record the condition on return so damage is attributable. • Reconcile against the issue record rather than memory. • Report unrecovered assets by value, as this is a real loss.
1060 | People & Culture | Manage IT asset allocation and return | IT Support Engineer | Trigger: When an approved joiner, employee change, access request, asset requirement or system update is received. Action: The IT Support Engineer completes the work item “Manage IT asset allocation and return” using approved records and systems. Output/Evidence: a configured account, system or asset record with access and completion evidence. Control/Handoff: Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an approved joiner, employee change, access request, asset requirement or system update is received. | The IT Support Engineer completes the work item “Manage IT asset allocation and return” using approved records and systems. | a configured account, system or asset record with access and completion evidence. | Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he manages issuing and taking back IT equipment. • Starts when: equipment is issued, transferred or returned. • How it runs: (1) he records the asset with its serial number. (2) He issues it against a signed record. (3) He records transfers between users. (4) He checks the condition on return. (5) He updates the register. • Proof it happened: an IT asset register with issues, transfers and returns recorded against signatures. • Where it usually breaks: equipment is passed between users informally, so the register shows it with someone who no longer has it. | • Require every transfer between users to be recorded, since informal handovers leave the register pointing at someone who no longer holds the asset. • Require a signed record at issue with the serial number and condition. • Reconcile the register physically at a set frequency. • Record the assigned user for every device, as unassigned devices are untraceable. • Include IT assets in the exit clearance.
1061 | People & Culture | Configure employee software and systems | IT Support Engineer | Trigger: When an approved joiner, employee change, access request, asset requirement or system update is received. Action: The IT Support Engineer completes the work item “Configure employee software and systems” using approved records and systems. Output/Evidence: a configured account, system or asset record with access and completion evidence. Control/Handoff: Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an approved joiner, employee change, access request, asset requirement or system update is received. | The IT Support Engineer completes the work item “Configure employee software and systems” using approved records and systems. | a configured account, system or asset record with access and completion evidence. | Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he sets up the software and systems each employee needs. • Starts when: a new device is issued or software is required. • How it runs: (1) he confirms the software required for the role. (2) He confirms the licence is available. (3) He installs and configures it. (4) He applies the security configuration. (5) He records the installation against the licence. • Proof it happened: configured systems with licences confirmed and the installation recorded against the licence register. • Where it usually breaks: software is installed without a licence, so the company is exposed to an audit claim it cannot defend. | • Prohibit installing any software without a recorded licence, since unlicensed software exposes the company to an audit claim it cannot defend. • Record every installation against the licence, so utilisation and compliance are known. • Prohibit users installing software themselves, as this is how unlicensed and unsafe software arrives. • Apply the standard security configuration to every device. • Remove software when a user no longer needs it, so licences can be reassigned.
1062 | People & Culture | Maintain company website in WIX | IT Support Engineer | Trigger: When an approved joiner, employee change, access request, asset requirement or system update is received. Action: The IT Support Engineer completes the work item “Maintain company website in WIX” using approved records and systems. Output/Evidence: a configured account, system or asset record with access and completion evidence. Control/Handoff: Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an approved joiner, employee change, access request, asset requirement or system update is received. | The IT Support Engineer completes the work item “Maintain company website in WIX” using approved records and systems. | a configured account, system or asset record with access and completion evidence. | Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he maintains the company website. • Starts when: a website change is approved or required. • How it runs: (1) he receives the approved content. (2) He implements the change. (3) He checks the site works, including forms and links. (4) He confirms the change with the requester. (5) He records the change. • Proof it happened: implemented website changes from approved content with functionality checked and the change recorded. • Where it usually breaks: a change breaks the enquiry form and nobody notices, so enquiries are lost silently. | • Test the enquiry form and contact routes after every change and at a set frequency, since a broken form loses enquiries silently for months. • Require content approval before publishing, as unapproved claims create real exposure. • Keep a backup before making changes, so a bad change can be reversed. • Check the site on mobile devices, because most visitors use them. • Hold the site credentials centrally rather than with one individual.
1063 | People & Culture | Create approved company email accounts | IT Support Engineer | Trigger: When an approved joiner, employee change, access request, asset requirement or system update is received. Action: The IT Support Engineer completes the work item “Create approved company email accounts” using approved records and systems. Output/Evidence: a configured account, system or asset record with access and completion evidence. Control/Handoff: Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an approved joiner, employee change, access request, asset requirement or system update is received. | The IT Support Engineer completes the work item “Create approved company email accounts” using approved records and systems. | a configured account, system or asset record with access and completion evidence. | Access must be approved, least-privilege based and recorded in the IT asset and access register; exceptions are escalated to the HR & Admin Lead and CPCO. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he creates the company email accounts when approved. • Starts when: an approved request is received. • How it runs: (1) he confirms the approval. (2) He creates the account per the naming standard. (3) He applies the security settings including multi factor authentication. (4) He issues the credentials securely. (5) He records the account in the register. • Proof it happened: created email accounts per the naming standard with security applied and recorded in the register. • Where it usually breaks: accounts are created on informal request, so accounts exist for people who never joined or who left. | • Require documented approval before creating any account, since informally created accounts exist for people who never joined or who left long ago. • Enable multi factor authentication at creation rather than later. • Follow the naming standard, as inconsistent naming makes the register unusable. • Reconcile the account list to the active employee list monthly. • Prohibit shared accounts, because these destroy the audit trail entirely.
1064 | People & Culture | Create approved ERP user accounts | IT Support Engineer | Trigger: When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. Action: The IT Support Engineer completes the work item “Create approved ERP user accounts” using approved records and systems. Output/Evidence: an updated employee, attendance, payroll, performance, insurance or correspondence record. Control/Handoff: The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When an employee lifecycle event, approved request or scheduled People & Culture activity becomes due. | The IT Support Engineer completes the work item “Create approved ERP user accounts” using approved records and systems. | an updated employee, attendance, payroll, performance, insurance or correspondence record. | The HR & Admin Lead checks completeness; CPCO and Finance approvals are obtained where the activity changes employment, compensation or payment. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he creates the ERP user accounts when approved. • Starts when: an approved request is received. • How it runs: (1) he confirms the approval and the role profile. (2) He creates the account with the role based permissions. (3) He checks the permissions against the segregation of duties requirements. (4) He issues the credentials securely. (5) He records the account and its permissions. • Proof it happened: created ERP accounts with role based permissions checked against segregation of duties and recorded. • Where it usually breaks: permissions are granted to match a request rather than a role profile, so one user ends up able to complete a transaction end to end. | • Check every permission set against the segregation of duties requirements, since a user able to raise, approve and pay defeats the entire control framework. • Grant from the role profile rather than from the individual request. • Require approval from the process owner as well as the manager for financial permissions. • Record the permissions granted, so the periodic review is possible. • Review permissions on every role change, not only on joining and leaving.
1065 | People & Culture | Maintain IT asset, software licence and access registers | IT Support Engineer | Trigger: Whenever an IT asset, licence or access permission is issued, changed, renewed or returned. Action: Update the controlled register with user, serial/reference, approval, validity and status. Output/Evidence: The reconciled IT asset, licence and access register. Control/Handoff: The register is reconciled periodically and exceptions are escalated. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | Whenever an IT asset, licence or access permission is issued, changed, renewed or returned. | Update the controlled register with user, serial/reference, approval, validity and status. | The reconciled IT asset, licence and access register. | The register is reconciled periodically and exceptions are escalated. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he keeps the registers of IT assets, software licences and user access. • Starts when: continuously as changes occur, and at the review cycle. • How it runs: (1) he records every asset, licence and account. (2) He records the assigned user. (3) He reconciles the registers physically and against the employee list. (4) He identifies discrepancies. (5) He reports the position. • Proof it happened: maintained IT asset, licence and access registers reconciled and with discrepancies reported. • Where it usually breaks: the access register is never reconciled to the employee list, so leaver accounts remain active indefinitely. | • Reconcile the access register to the active employee list monthly, since unreconciled registers leave leaver accounts active indefinitely and this is the standard audit finding. • Reconcile licences to installations, as both over and under licensing are costly. • Reconcile assets physically at a set frequency rather than relying on the record. • Record the assigned user for every asset and account. • Report discrepancies rather than adjusting the register to match.
1066 | People & Culture | Resolve user hardware, software and connectivity incidents | IT Support Engineer | Trigger: When a user reports an IT incident. Action: Log severity, diagnose the problem and restore service or escalate to the approved vendor. Output/Evidence: Recorded resolution evidence with response time. Control/Handoff: Recurring causes are tracked and reported. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When a user reports an IT incident. | Log severity, diagnose the problem and restore service or escalate to the approved vendor. | Recorded resolution evidence with response time. | Recurring causes are tracked and reported. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he fixes the hardware, software and connectivity problems people report. • Starts when: an incident is reported. • How it runs: (1) he logs the incident. (2) He assesses the impact and the priority. (3) He resolves it or escalates to the supplier. (4) He confirms resolution with the user. (5) He records the cause and the fix. • Proof it happened: logged incidents with priority, resolution and the cause recorded. • Where it usually breaks: recurring incidents are fixed individually without addressing the cause, so the same problem consumes time indefinitely. | • Record the cause of every incident and address recurring causes, since fixing the same problem repeatedly consumes time indefinitely and never improves. • Log every incident including those resolved immediately, as the workload is otherwise invisible. • Set priorities by business impact rather than by who reported it. • Confirm resolution with the user rather than assuming. • Report recurring incidents to justify addressing the underlying cause.
1067 | People & Culture | Perform backup, endpoint security and patch controls | IT Support Engineer | Trigger: At the approved security cadence. Action: Verify backups, antivirus/endpoint status, critical patches and device compliance. Output/Evidence: Recorded verification results and corrections of failures. Control/Handoff: Material security exposure is escalated immediately. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | At the approved security cadence. | Verify backups, antivirus/endpoint status, critical patches and device compliance. | Recorded verification results and corrections of failures. | Material security exposure is escalated immediately. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he runs the backups, the endpoint protection and the software patching. • Starts when: on the scheduled cycle, and continuously. • How it runs: (1) he confirms the backups ran and completed. (2) He tests a restore periodically. (3) He confirms endpoint protection is active on every device. (4) He applies the security patches. (5) He records the checks and any failures. • Proof it happened: backup completion and restore test records, endpoint protection confirmed and patching applied and recorded. • Where it usually breaks: backups are confirmed as running but never restored, so the failure is only discovered when data is actually needed. | • Test restore a backup at a set frequency, since a backup never restored is an assumption and the failure is discovered only when the data is needed. • Keep at least one backup copy offline or immutable, because ransomware encrypts connected backups too. • Confirm endpoint protection is active on every device rather than assuming, as devices drop off. • Apply security patches within a stated period and report exceptions. • Report backup failures immediately rather than at the monthly review.
1068 | People & Culture | Report security incidents, downtime and recurring IT issues | IT Support Engineer | Trigger: When a security event, material outage or recurring IT failure occurs. Action: Preserve evidence, notify the authorised management contacts and contain the issue. Output/Evidence: A closure report with root cause and preventive action. Control/Handoff: The closure report is issued to the authorised management contacts. Continuity/Escalation: An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. Timing: To be confirmed. | When a security event, material outage or recurring IT failure occurs. | Preserve evidence, notify the authorised management contacts and contain the issue. | A closure report with root cause and preventive action. | The closure report is issued to the authorised management contacts. | An approved IT support resource may provide technical backup; access, security, data-loss or material downtime exceptions escalate to the HR & Admin Lead and CPCO. | To be confirmed. | • In plain words: he reports the security incidents, the downtime and the problems that keep happening. • Starts when: an incident occurs, and at the reporting cycle. • How it runs: (1) he records the incident with the facts and the timing. (2) He assesses whether data may have been exposed. (3) He reports it immediately per the severity. (4) He records the containment and the resolution. (5) He reports the recurring issues and the downtime. • Proof it happened: reported security incidents with the facts, data exposure assessment, containment and resolution recorded. • Where it usually breaks: a security incident is contained quietly and never reported, so nobody assesses whether personal or client data was exposed. | • Require every security incident to be reported regardless of how quickly it was contained, since the company must assess whether personal or client data was exposed and that carries notification obligations. • Set reporting timelines by severity, with immediate reporting for suspected data exposure. • Record the facts and the timing, as these are needed for any regulatory notification. • Report recurring issues and downtime with their business impact. • Involve the CLO where personal or client data may have been exposed.
1069 | Research & Development | Set R&D and process-excellence strategy, policies and annual objectives | Chief Research Officer (CRO) | Trigger: When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. Action: The Chief Research Officer (CRO) completes “Set R&D and process-excellence strategy, policies and annual objectives” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. Control/Handoff: The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. | The Chief Research Officer (CRO) completes “Set R&D and process-excellence strategy, policies and annual objectives” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. | The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he decides how the company will improve the way it works, and sets the rules for how processes and SOPs are created. • Starts when: the annual planning cycle opens, or the business changes enough that the current way of working stops fitting. • How it runs: (1) he reviews where the company loses time, money and quality through how it works. (2) He sets the improvement objectives for the year. (3) He drafts or updates the process and SOP policies. (4) He obtains the CEO's approval. (5) He issues it to the chiefs who own the processes. • Proof it happened: an approved R&D and process strategy with annual objectives and policies, issued to the business. • Where it usually breaks: improvement is treated as a project run by one team, so the departments who own the work never take responsibility for it. | • State clearly that process ownership sits with the department chiefs and R&D facilitates, since improvement imposed by a central team is not sustained. • Set measurable objectives: SOPs approved, cycle time reduction, workflow adoption and error rate. Objectives without measures cannot be reviewed. • Require the strategy to name the specific processes to be tackled in the year rather than stating intentions. • State the policy review frequency and who may approve a deviation. • Link improvement priorities to the business plan, so the effort goes where the money is lost.
1070 | Research & Development | Define priorities for process, data, digital, knowledge and innovation improvement | Chief Research Officer (CRO) | Trigger: When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. Action: The Chief Research Officer (CRO) completes “Define priorities for process, data, digital, knowledge and innovation improvement” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. Control/Handoff: The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. | The Chief Research Officer (CRO) completes “Define priorities for process, data, digital, knowledge and innovation improvement” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. | The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he decides which improvements matter most, across process, data, digital tools, knowledge and innovation. • Starts when: at the planning cycle, and when new problems or opportunities emerge. • How it runs: (1) he collects the candidate improvement areas from the departments and the performance data. (2) He assesses each on value, risk and effort. (3) He groups them into the five improvement themes. (4) He agrees the priorities with the CEO and the chiefs. (5) He publishes the priorities so effort is not spread thin. • Proof it happened: published improvement priorities across the five themes, with the basis for prioritisation recorded. • Where it usually breaks: everything is a priority, so a large number of initiatives start and very few finish. | • Limit the number of active priorities explicitly, since capacity rather than ambition is what determines how many improvements actually complete. • Require prioritisation against stated criteria, so the ranking can be explained to the department that was deprioritised. • Require the department chief to confirm the capacity to support each priority, otherwise initiatives stall waiting for their people. • Publish what is deliberately not being done, as this is what protects the active list. • Review priorities at a fixed frequency rather than adding continuously.
1071 | Research & Development | Maintain the company improvement and innovation initiative portfolio | Chief Research Officer (CRO) | Trigger: When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. Action: The Chief Research Officer (CRO) completes “Maintain the company improvement and innovation initiative portfolio” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. Control/Handoff: The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. | The Chief Research Officer (CRO) completes “Maintain the company improvement and innovation initiative portfolio” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. | The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he keeps one list of every improvement initiative running in the company and what state each is in. • Starts when: an initiative is approved, and continuously as initiatives progress. • How it runs: (1) he records each initiative with its owner, scope and stage. (2) He records the expected benefit and the target date. (3) He updates the stage and the status as it progresses. (4) He identifies stalled and overlapping initiatives. (5) He reports the portfolio position. • Proof it happened: a maintained initiative portfolio with owners, stages, expected benefits and current status. • Where it usually breaks: initiatives are added and never closed, so the portfolio grows into a list nobody can act on. | • Require every initiative to be closed formally, either delivered, deferred or terminated, since a portfolio of permanently open items conveys nothing. • Show ageing per initiative, as an initiative open for a year without progress needs a decision rather than a status update. • Require overlap checks before adding, because parallel initiatives on the same process conflict with each other. • Record the expected benefit at entry so it can be tested at closure. • Name a single accountable owner per initiative, not a department.
1072 | Research & Development | Approve initiative charters, business cases, owners and stage-gate plans | Chief Research Officer (CRO) | Trigger: When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. Action: The Chief Research Officer (CRO) completes “Approve initiative charters, business cases, owners and stage-gate plans” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. Control/Handoff: The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. | The Chief Research Officer (CRO) completes “Approve initiative charters, business cases, owners and stage-gate plans” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. | The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he approves what each initiative is actually trying to do, who owns it, and the checkpoints it must pass. • Starts when: an initiative is proposed for approval. • How it runs: (1) he reviews the problem statement and the proposed scope. (2) He reviews the business case and the expected benefit. (3) He confirms the owner has the authority and the capacity. (4) He sets the stage gates and what must be demonstrated at each. (5) He approves the charter or returns it. • Proof it happened: an approved initiative charter with the scope, owner, business case and stage gate plan. • Where it usually breaks: the charter states an activity rather than an outcome, so nobody can tell whether the initiative succeeded. | • Require the charter to state a measurable outcome rather than an activity, since an activity based charter cannot be assessed at closure. • Require the process owner rather than R&D to be the accountable owner, as this is what determines whether the change survives. • Define what must be demonstrated at each stage gate, so gates are decisions rather than status meetings. • Require the baseline measurement to be taken before the initiative starts, or benefit can never be proven. • State the authority to stop an initiative at any gate, and use it.
1073 | Research & Development | Align the R&D portfolio with company strategy, budget and delivery capacity | Chief Research Officer (CRO) | Trigger: When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. Action: The Chief Research Officer (CRO) completes “Align the R&D portfolio with company strategy, budget and delivery capacity” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. Control/Handoff: The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. | The Chief Research Officer (CRO) completes “Align the R&D portfolio with company strategy, budget and delivery capacity” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. | The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he makes sure the improvement work matches what the company is trying to achieve, what it can fund and what it can absorb. • Starts when: at the portfolio review, and when strategy or capacity changes. • How it runs: (1) he maps the initiatives against the strategic priorities. (2) He checks the total resource demand against the available capacity. (3) He checks the funding against the budget. (4) He defers or stops what cannot be supported. (5) He confirms the balanced portfolio with the CEO. • Proof it happened: a portfolio alignment review with the capacity and funding position and the deferral decisions recorded. • Where it usually breaks: the portfolio is approved on funding alone, ignoring that the same few people are needed on every initiative. | • Test the portfolio against the availability of the specific people required, since the same key individuals are usually needed on every initiative. • Require initiatives to be deferred explicitly rather than left approved and unstaffed, which is how portfolios silently stall. • Check the demand on the operating departments, because improvement work competes with delivery. • Reconcile the portfolio to the budget, so unfunded initiatives are not carried as active. • Review alignment whenever the business plan changes, otherwise the portfolio serves last year's strategy.
1074 | Research & Development | Report portfolio value, progress, risks and decisions to the CEO | Chief Research Officer (CRO) | Trigger: When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. Action: The Chief Research Officer (CRO) completes “Report portfolio value, progress, risks and decisions to the CEO” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. Control/Handoff: The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When the annual strategy cycle, executive instruction, new initiative or portfolio review requires R&D direction. | The Chief Research Officer (CRO) completes “Report portfolio value, progress, risks and decisions to the CEO” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved R&D strategy, prioritised initiative portfolio, controlled business case, stage-gate decision or executive report. | The CEO approves company priorities and material investment; CFO confirms budget, functional chiefs own implementation capacity, and the CRO governs method, evidence and portfolio control. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he tells the CEO what the improvement work has actually delivered, what is at risk and what needs a decision. • Starts when: at the reporting cycle, and immediately for material issues. • How it runs: (1) he reports the portfolio progress against plan. (2) He reports the benefits realised against those expected. (3) He states the risks and the blocked initiatives. (4) He raises the decisions needed. (5) He records the CEO's directions and acts on them. • Proof it happened: a reported portfolio pack with progress, realised benefit, risks and the CEO's recorded directions. • Where it usually breaks: reporting covers activity and progress but never realised benefit, so the value of the function is never demonstrated. | • Require realised benefit to be reported alongside progress, since a function that reports only activity cannot justify its cost. • Report blocked initiatives with the blocker named, as most stall for reasons only the CEO can remove. • Distinguish measured benefit from estimated benefit in the report, to keep credibility. • Keep the format consistent so periods can be compared. • Record decisions taken, because portfolio decisions are otherwise revisited repeatedly.
1075 | Research & Development | Design and maintain the end-to-end company process architecture | Chief Research Officer (CRO) | Trigger: When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. Action: The Chief Research Officer (CRO) completes “Design and maintain the end-to-end company process architecture” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. Control/Handoff: Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. | The Chief Research Officer (CRO) completes “Design and maintain the end-to-end company process architecture” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. | Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he builds the map of how work actually flows across the whole company, from end to end. • Starts when: the architecture is first established, and when the organisation or the business model changes. • How it runs: (1) he identifies the end to end value streams. (2) He maps the processes within each and how they connect. (3) He identifies where processes cross department boundaries. (4) He validates the map with the process owners. (5) He publishes and maintains it as the reference. • Proof it happened: a maintained end to end process architecture, validated by the process owners and published as the reference. • Where it usually breaks: the architecture is drawn department by department, so the handoffs between them, which is where work actually fails, are never mapped. | • Map end to end value streams rather than departments, since the failures occur at the handoffs and a departmental map hides them entirely. • Require validation by the process owners, otherwise the architecture describes how work is supposed to flow rather than how it does. • Keep the architecture at a level people can use, as an overly detailed map is maintained by nobody. • Require it to be updated on organisational change, or it becomes a historical document. • Use it as the reference for SOP scoping, so SOPs cover the flow rather than fragments of it.
1076 | Research & Development | Define process hierarchy, naming, numbering and classification standards | Chief Research Officer (CRO) | Trigger: When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. Action: The Chief Research Officer (CRO) completes “Define process hierarchy, naming, numbering and classification standards” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. Control/Handoff: Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. | The Chief Research Officer (CRO) completes “Define process hierarchy, naming, numbering and classification standards” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. | Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he sets the naming and numbering rules so processes and documents can be found and referred to reliably. • Starts when: the standards are established, and when the architecture is extended. • How it runs: (1) he defines the process hierarchy levels. (2) He sets the naming convention and the numbering structure. (3) He sets the classification rules. (4) He publishes the standard. (5) He applies it consistently and corrects deviations. • Proof it happened: a published process hierarchy, naming and numbering standard, applied consistently across the inventory. • Where it usually breaks: the standard is set after documents already exist, so half the inventory follows it and half does not. | • Plan a migration for the existing inventory when the standard is introduced, since a partially applied convention is worse than none. • Keep the numbering stable and never reuse a retired number, as reuse makes historical references ambiguous. • Require the standard to be applied at creation, with a check before a document is issued. • Keep the hierarchy shallow enough to be usable, because deep hierarchies are abandoned in practice. • Publish the standard with worked examples rather than rules alone.
1077 | Research & Development | Maintain the process inventory and accountable process-owner register | Chief Research Officer (CRO) | Trigger: When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. Action: The Chief Research Officer (CRO) completes “Maintain the process inventory and accountable process-owner register” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. Control/Handoff: Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. | The Chief Research Officer (CRO) completes “Maintain the process inventory and accountable process-owner register” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. | Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he keeps the list of all the company's processes and who is accountable for each one. • Starts when: the inventory is established, and on every organisational or process change. • How it runs: (1) he lists every process in the architecture. (2) He assigns a named accountable owner to each. (3) He records the SOP status and the last review date. (4) He obtains the owners' acceptance of accountability. (5) He reviews and updates the inventory periodically. • Proof it happened: a process inventory with named accountable owners who have accepted the role, and current SOP status. • Where it usually breaks: owners are assigned without being told, so the inventory shows accountability that the named person does not know they hold. | • Require the named owner to accept accountability in writing, since ownership assigned without acknowledgement is not ownership. • Assign ownership to a role rather than an individual name, so it survives staff changes. • Require review on organisational change, as reorganisation is where processes become unowned. • Flag unowned processes as a reported exception to the CEO, because these are where work falls between departments. • Record the SOP status per process, so the inventory doubles as the coverage measure.
1078 | Research & Development | Define cross-department inputs, outputs, handoffs and service levels | Chief Research Officer (CRO) | Trigger: When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. Action: The Chief Research Officer (CRO) completes “Define cross-department inputs, outputs, handoffs and service levels” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. Control/Handoff: Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. | The Chief Research Officer (CRO) completes “Define cross-department inputs, outputs, handoffs and service levels” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. | Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he defines what each department must give the next one, in what form and by when. • Starts when: mapping a cross department process, and when handoff failures are reported. • How it runs: (1) he identifies the handoff points between departments. (2) He defines what is handed over and in what form. (3) He defines the timing and the service level. (4) He agrees it with both departments. (5) He builds it into the SOPs and the workflows. • Proof it happened: defined handoffs with agreed content, format and service levels, built into the SOPs of both sides. • Where it usually breaks: the receiving department's requirements are never stated, so incomplete handovers are accepted and the rework is invisible. | • Require the receiving department to define what it needs, since a handoff defined only by the sender is what produces incomplete handovers. • Require both departments to sign the service level, so it is an agreement rather than an imposed standard. • State the right to reject an incomplete handover, and require the rejection to be recorded rather than absorbed. • Measure handoff timeliness and completeness, as this is where cross department performance actually shows. • Build the handoff into both SOPs, otherwise each side documents only its own half.
1079 | Research & Development | Resolve duplicated, conflicting, missing or unowned company work | Chief Research Officer (CRO) | Trigger: When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. Action: The Chief Research Officer (CRO) completes “Resolve duplicated, conflicting, missing or unowned company work” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. Control/Handoff: Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. | The Chief Research Officer (CRO) completes “Resolve duplicated, conflicting, missing or unowned company work” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. | Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he finds work that is done twice, done inconsistently, not done at all, or owned by nobody, and fixes it. • Starts when: duplication or gaps are identified through mapping, audits or reported failures. • How it runs: (1) he identifies the duplicated, conflicting, missing or unowned work. (2) He establishes the facts with the departments involved. (3) He proposes the allocation of the work. (4) He escalates to the CEO where the chiefs cannot agree. (5) He records the decision and updates the process records. • Proof it happened: a resolution record with the issue, the departments involved, the agreed allocation and the updated process records. • Where it usually breaks: the decision is made in a meeting but never written into the SOPs, so the same argument recurs in six months. | • Require every allocation decision to be written into the affected SOPs, since a decision that exists only in minutes will be relitigated. • Escalate to the CEO on a defined timescale rather than allowing an unowned gap to persist while departments negotiate. • Prioritise unowned work over duplicated work, as gaps cause failures while duplication causes waste. • Record the decision basis, so a future reorganisation does not reverse it by accident. • Track recurring disputes, because these usually indicate a structural problem rather than a process one.
1080 | Research & Development | Maintain RACI, Delegation-of-Authority and approval-control links | Chief Research Officer (CRO) | Trigger: When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. Action: The Chief Research Officer (CRO) completes “Maintain RACI, Delegation-of-Authority and approval-control links” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. Control/Handoff: Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new service, department change, workflow conflict, ownership gap or process review affects the company operating model. | The Chief Research Officer (CRO) completes “Maintain RACI, Delegation-of-Authority and approval-control links” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled process architecture, process inventory, owner assignment, handoff map, RACI or resolved ownership decision. | Functional chiefs remain accountable for department outcomes; the CRO controls company-process design and escalates unresolved cross-functional ownership or authority conflicts to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he keeps the links between who does what, who approves what, and the approval limits, so they all agree. • Starts when: the framework is set, and whenever authority, roles or processes change. • How it runs: (1) he maps the RACI for each process. (2) He links the approval points to the delegation of authority. (3) He checks the limits in the process match the approved matrix. (4) He identifies conflicts and resolves them. (5) He maintains the links as changes occur. • Proof it happened: maintained RACI and authority links with the process approval points reconciled to the approved matrix. • Where it usually breaks: the authority matrix is updated but the SOPs and workflows keep the old limits, so the system enforces the wrong thresholds. | • Require SOPs and system workflows to be updated whenever the authority matrix changes, since stale limits in the system enforce the wrong control. • Maintain a cross reference from each authority line to the SOPs and workflows that implement it, so the update scope is known. • Require a single accountable person per process step in the RACI, because shared accountability means none. • Reconcile the system permissions to the matrix periodically. • Flag approval points with no matching authority line, as these are approvals nobody actually authorised.
1081 | Research & Development | Set the SOP framework, templates, lifecycle and minimum control requirements | Chief Research Officer (CRO) | Trigger: When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. Action: The Chief Research Officer (CRO) completes “Set the SOP framework, templates, lifecycle and minimum control requirements” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. Control/Handoff: The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. | The Chief Research Officer (CRO) completes “Set the SOP framework, templates, lifecycle and minimum control requirements” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. | The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he sets what an SOP must contain, how it is created and approved, and the minimum controls it must include. • Starts when: the framework is established, and when it is reviewed. • How it runs: (1) he defines the SOP template and its mandatory sections. (2) He sets the lifecycle: draft, review, approve, issue, review, retire. (3) He sets the minimum control requirements every SOP must address. (4) He obtains approval of the framework. (5) He issues it and trains the process owners. • Proof it happened: an approved SOP framework with template, lifecycle and minimum control requirements, issued to the process owners. • Where it usually breaks: the template demands so much detail that SOPs are never finished, so the process stays undocumented. | • Keep the template proportionate, since an over engineered template produces unfinished SOPs and no documentation at all. • Require every SOP to state its trigger, steps, outputs, evidence, controls and escalation as mandatory sections. • Set the review frequency and an expiry date, so an unreviewed SOP becomes visibly out of date rather than silently wrong. • Require a named owner and approver on every SOP. • State the minimum controls: segregation of duties, authority limits and record retention, so each SOP addresses them explicitly.
1082 | Research & Development | Maintain the annual SOP creation, review and expiry calendar | Chief Research Officer (CRO) | Trigger: When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. Action: The Chief Research Officer (CRO) completes “Maintain the annual SOP creation, review and expiry calendar” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. Control/Handoff: The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. | The Chief Research Officer (CRO) completes “Maintain the annual SOP creation, review and expiry calendar” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. | The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he keeps the calendar of which SOPs are being written, which are due for review, and which are expiring. • Starts when: at the start of the year, and updated as SOPs are approved. • How it runs: (1) he lists the SOPs to be created and their target dates. (2) He lists the SOPs due for review with their expiry dates. (3) He agrees the dates with the process owners. (4) He publishes the calendar. (5) He tracks progress and escalates slippage. • Proof it happened: a published SOP calendar with creation, review and expiry dates, tracked against actual progress. • Where it usually breaks: the calendar is built on R&D's capacity rather than the process owners', so the dates are missed from the start. | • Build the calendar against the process owners' availability, since SOPs are written with their knowledge and time, not by R&D alone. • Prioritise by risk and value rather than by ease, or the important processes are documented last. • Report SOPs past their expiry date as a compliance exception, because an expired SOP is in use and unreviewed. • Set realistic creation dates, as a permanently overdue calendar is ignored. • Show coverage as a percentage of the process inventory, so progress is visible.
1083 | Research & Development | Lead process-discovery and SOP-design workshops with process owners | Chief Research Officer (CRO) | Trigger: When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. Action: The Chief Research Officer (CRO) completes “Lead process-discovery and SOP-design workshops with process owners” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. Control/Handoff: The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. | The Chief Research Officer (CRO) completes “Lead process-discovery and SOP-design workshops with process owners” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. | The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he runs the workshops where the people who actually do the work describe it, so the SOP reflects reality. • Starts when: an SOP is scheduled for creation or major revision. • How it runs: (1) he identifies the people who actually perform the work. (2) He runs the discovery session to capture the real steps. (3) He captures the exceptions and the workarounds people use. (4) He drafts the process flow and confirms it with the group. (5) He records the design decisions and the open points. • Proof it happened: workshop records with the captured process flow, the exceptions and the design decisions, confirmed by the participants. • Where it usually breaks: only the manager attends, so the documented process is what management believes happens rather than what does. | • Require the people who actually perform the work to attend, since a process described only by the manager documents belief rather than practice. • Capture the workarounds explicitly, because a workaround always indicates a real constraint the SOP must address. • Document the exceptions, as the exception path is where most process failures happen and it is usually undocumented. • Confirm the flow with the participants before drafting, to avoid rewriting later. • Record the open points and who will resolve them, otherwise drafting stalls on unanswered questions.
1084 | Research & Development | Verify SOP triggers, actions, outputs, evidence, controls and escalations | Chief Research Officer (CRO) | Trigger: When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. Action: The Chief Research Officer (CRO) completes “Verify SOP triggers, actions, outputs, evidence, controls and escalations” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. Control/Handoff: The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. | The Chief Research Officer (CRO) completes “Verify SOP triggers, actions, outputs, evidence, controls and escalations” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. | The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he checks each SOP actually makes sense, that the steps, evidence and controls hold together. • Starts when: an SOP draft is submitted for verification. • How it runs: (1) he checks the trigger is specific and observable. (2) He checks the actions are in sequence and complete. (3) He checks each output has stated evidence. (4) He checks the controls actually prevent the failure they address. (5) He checks the escalation route and returns the draft with findings. • Proof it happened: a verification record per SOP with the findings against triggers, actions, outputs, evidence, controls and escalation. • Where it usually breaks: the SOP describes the steps well but names no evidence, so compliance can never be demonstrated or audited. | • Require a named evidence record for every output, since a step with no evidence cannot be audited and effectively did not happen. • Test each control against the failure it is meant to prevent, because many documented controls do not actually address the risk. • Require the trigger to be observable rather than a general condition, otherwise nobody knows when the process starts. • Require the escalation route to name a role and a timeframe. • Check that the SOP matches the system workflow, as divergence between them makes both unreliable.
1085 | Research & Development | Route new and revised SOPs through functional and executive approval | Chief Research Officer (CRO) | Trigger: When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. Action: The Chief Research Officer (CRO) completes “Route new and revised SOPs through functional and executive approval” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. Control/Handoff: The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. | The Chief Research Officer (CRO) completes “Route new and revised SOPs through functional and executive approval” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. | The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he takes SOPs through the right people for approval before they are issued. • Starts when: an SOP draft is verified and ready for approval. • How it runs: (1) he identifies the functional reviewers affected. (2) He circulates for review with a deadline. (3) He consolidates the comments and resolves conflicts. (4) He submits to the executive approver. (5) He obtains the approval and releases for issue. • Proof it happened: an approval record with the functional reviews, resolved comments and the executive approval. • Where it usually breaks: approval stalls because a reviewer does not respond, and the SOP sits unapproved for months while the process continues undocumented. | • Set a review period with a stated consequence for silence, such as deemed acceptance, since unanswered reviews are the main cause of SOP backlog. • Require the affected departments to review, not only the owner, because cross department steps are where conflicts appear. • Require conflicts to be resolved and recorded before submission, rather than presented to the approver unresolved. • Track approval ageing and escalate, as an SOP in approval limbo provides no control. • State who the executive approver is per SOP category, so routing is not decided case by case.
1086 | Research & Development | Govern temporary process deviations, waivers and exception expiry | Chief Research Officer (CRO) | Trigger: When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. Action: The Chief Research Officer (CRO) completes “Govern temporary process deviations, waivers and exception expiry” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. Control/Handoff: The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new process, control gap, audit finding, policy change or scheduled SOP review requires documented control. | The Chief Research Officer (CRO) completes “Govern temporary process deviations, waivers and exception expiry” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved SOP, form, checklist, revision decision, review schedule or time-bound deviation record. | The process owner validates operational content, the relevant functional chief approves responsibility and risk, and the CRO verifies company-standard structure and cross-department consistency before release. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: when a process cannot be followed, he controls the exception rather than letting people quietly work around it. • Starts when: a deviation or waiver is requested, or an unauthorised workaround is discovered. • How it runs: (1) he receives the request with the reason and the duration needed. (2) He assesses the risk the deviation creates. (3) He obtains approval at the appropriate level. (4) He records it with a mandatory expiry date. (5) He reviews it at expiry and either closes it or fixes the process. • Proof it happened: a deviation register with approved waivers, risk assessments and expiry dates, reviewed at expiry. • Where it usually breaks: waivers are granted without an expiry, so the deviation becomes the permanent process without ever being designed. | • Require a mandatory expiry date on every waiver, since a waiver without one becomes the permanent undesigned process. • Require the risk created by the deviation to be stated and accepted by a named approver. • Treat a repeated waiver as evidence the process needs redesign rather than continued exemption. • Report open waivers to the CEO, as the total picture reveals where the process framework does not fit reality. • Treat an undeclared workaround as a compliance matter, and provide an easy declaration route so people use it.
1087 | Research & Development | Receive and qualify FirstBit ERP workflow requirements from departments | Chief Research Officer (CRO) | Trigger: When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. Action: The Chief Research Officer (CRO) completes “Receive and qualify FirstBit ERP workflow requirements from departments” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. Control/Handoff: Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. | The Chief Research Officer (CRO) completes “Receive and qualify FirstBit ERP workflow requirements from departments” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. | Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he takes in what departments want the ERP to do and checks whether the requirement is clear and real. • Starts when: a department submits a workflow requirement for the ERP. • How it runs: (1) he receives the requirement with its business reason. (2) He checks it against the existing process and workflow. (3) He tests whether the underlying need is a system need or a process need. (4) He confirms the sponsor and the expected benefit. (5) He accepts, returns or reclassifies the requirement. • Proof it happened: a qualified requirement record with the business reason, the sponsor and the accept or return decision. • Where it usually breaks: system changes are built to support a broken process, so the ERP automates the problem. | • Require the process to be reviewed before any system change is accepted, since automating a broken process makes the problem faster and harder to see. • Require a named sponsor with the authority to make the process change the system change implies. • Require the requirement to state the outcome needed rather than the screen or field wanted. • Check whether existing functionality already meets the need, because much requested development is already available. • Keep a single register of requirements, so departments cannot bypass the queue through informal requests.
1088 | Research & Development | Map approved processes into statuses, roles, approvals and exception routes | Chief Research Officer (CRO) | Trigger: When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. Action: The Chief Research Officer (CRO) completes “Map approved processes into statuses, roles, approvals and exception routes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. Control/Handoff: Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. | The Chief Research Officer (CRO) completes “Map approved processes into statuses, roles, approvals and exception routes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. | Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he turns the approved process into the actual statuses, roles and approval steps the system will use. • Starts when: a requirement is accepted and the process design is approved. • How it runs: (1) he maps each process step to a system status. (2) He maps the roles to system permissions. (3) He defines the approval points and their limits. (4) He defines the exception and rejection routes. (5) He documents the mapping for build and testing. • Proof it happened: a documented workflow mapping with statuses, roles, approvals and exception routes, traceable to the approved process. • Where it usually breaks: only the successful path is mapped, so the system has no route for rejections and exceptions and users go outside it. | • Require the rejection and exception routes to be mapped, since a system with only a happy path forces users outside it and destroys the audit trail. • Require the mapping to be traceable to the approved process step by step, so the system and the SOP cannot diverge. • Map the approval limits from the authority matrix rather than restating them. • Define what happens to an in progress transaction when someone is absent, as this is the commonest reason for bypass. • Require the mapping to be reviewed by the process owner before build.
1089 | Research & Development | Approve workflow blueprints, mandatory fields, permissions and audit evidence | Chief Research Officer (CRO) | Trigger: When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. Action: The Chief Research Officer (CRO) completes “Approve workflow blueprints, mandatory fields, permissions and audit evidence” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. Control/Handoff: Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. | The Chief Research Officer (CRO) completes “Approve workflow blueprints, mandatory fields, permissions and audit evidence” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. | Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he approves the detailed system design, including which fields are compulsory, who can see what, and what evidence the system keeps. • Starts when: the workflow blueprint is prepared for approval. • How it runs: (1) he reviews the blueprint against the approved process. (2) He confirms the mandatory fields capture the required evidence. (3) He confirms the permissions enforce segregation of duties. (4) He confirms the audit trail captures who did what and when. (5) He approves the blueprint for build. • Proof it happened: an approved workflow blueprint with mandatory fields, permissions and audit evidence requirements confirmed. • Where it usually breaks: permissions are set for convenience, so one role can raise, approve and record, and the control exists only in the SOP. | • Require permissions to enforce segregation of duties in the system, since a control that exists only in the SOP is not enforced at all. • Require mandatory fields to capture the evidence the SOP names, so compliance is a by product of using the system. • Require the audit trail to record the user, the action and the timestamp for every approval. • Limit mandatory fields to what is genuinely needed, because excessive mandatory fields drive users to enter false data. • Require sign off by the process owner and, for financial controls, by the CFO.
1090 | Research & Development | Coordinate ERP build, user-acceptance testing, deployment and controlled release | Chief Research Officer (CRO) | Trigger: When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. Action: The Chief Research Officer (CRO) completes “Coordinate ERP build, user-acceptance testing, deployment and controlled release” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. Control/Handoff: Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. | The Chief Research Officer (CRO) completes “Coordinate ERP build, user-acceptance testing, deployment and controlled release” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. | Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he coordinates the building, testing and release of the system change, so it goes live working. • Starts when: the blueprint is approved and build begins. • How it runs: (1) he coordinates the build with the vendor or IT. (2) He prepares the test cases from the approved process, including exceptions. (3) He arranges user acceptance testing by the actual users. (4) He obtains sign off or logs the defects for correction. (5) He coordinates the controlled release and confirms it in the live system. • Proof it happened: completed user acceptance testing with signed results, a defect log and a controlled release record. • Where it usually breaks: testing is done by the project team rather than the users, so problems are found in live use. | • Require the actual users to perform acceptance testing, since testing by the project team finds only the errors they did not make. • Require the test cases to include exceptions and rejections, because these are where untested workflows fail. • Require a documented go live decision with the open defects listed and accepted, rather than an assumed release. • Require a rollback plan before release, as a failed release without one halts the business. • Provide a hypercare period with a named support contact, since the first week determines whether users adopt or bypass.
1091 | Research & Development | Control FirstBit workflow change requests and configuration versions | Chief Research Officer (CRO) | Trigger: When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. Action: The Chief Research Officer (CRO) completes “Control FirstBit workflow change requests and configuration versions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. Control/Handoff: Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. | The Chief Research Officer (CRO) completes “Control FirstBit workflow change requests and configuration versions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. | Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he controls changes to the system workflows, so nothing is altered without approval and a record. • Starts when: a change to an existing workflow or configuration is requested. • How it runs: (1) he receives the change request with the reason. (2) He assesses the impact on other processes and reports. (3) He obtains approval at the appropriate level. (4) He records the configuration version before and after. (5) He implements through the controlled release process. • Proof it happened: a change register with approved requests, impact assessments and the configuration versions recorded. • Where it usually breaks: configuration is changed directly in the live system to solve an urgent problem, and nobody knows later what was changed or why. | • Prohibit direct changes in the live system outside the change process, and name who may authorise an emergency change with mandatory retrospective recording. • Require an impact assessment on reports and other workflows, since configuration changes have effects far from where they are made. • Record the configuration before and after, because without the previous state a change cannot be reversed. • Restrict configuration access to named people and review it periodically. • Require the SOP to be updated whenever the workflow changes, or documentation and system diverge immediately.
1092 | Research & Development | Monitor workflow adoption, overdue steps, bypasses and audit-trail quality | Chief Research Officer (CRO) | Trigger: When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. Action: The Chief Research Officer (CRO) completes “Monitor workflow adoption, overdue steps, bypasses and audit-trail quality” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. Control/Handoff: Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a department requests a new or changed FirstBit workflow, approval, status, field, role or exception route. | The Chief Research Officer (CRO) completes “Monitor workflow adoption, overdue steps, bypasses and audit-trail quality” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | an approved workflow blueprint, UAT evidence, controlled configuration release, change record and adoption report. | Business owners approve requirements, IT or the ERP implementer controls technical configuration, and the CRO prevents deployment without mapped process, authority, test and rollback evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he watches whether people actually use the system properly, or work around it. • Starts when: after a workflow goes live, and continuously thereafter. • How it runs: (1) he monitors the transaction volumes against expected usage. (2) He identifies steps that are overdue or sitting unactioned. (3) He identifies bypasses and manual overrides. (4) He checks the audit trail is complete and meaningful. (5) He reports and addresses the adoption gaps. • Proof it happened: adoption monitoring reports showing usage, overdue steps, bypasses and audit trail quality, with the actions taken. • Where it usually breaks: low adoption is treated as a training problem when it is usually a design problem the users are working around. | • Investigate the reason for each bypass rather than treating it as non compliance, since a bypass almost always indicates the workflow does not fit the work. • Monitor overdue and ageing steps, because a workflow full of stalled transactions is not in use even if it is technically live. • Check the audit trail is meaningful, as approvals recorded under a shared login prove nothing. • Report retrospective and backdated entries, which indicate the process is being followed on paper afterwards. • Fix the design where the bypass is justified, and enforce where it is not, but decide explicitly.
1093 | Research & Development | Set master-data taxonomy, naming, ownership and mandatory-field standards | Chief Research Officer (CRO) | Trigger: When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. Action: The Chief Research Officer (CRO) completes “Set master-data taxonomy, naming, ownership and mandatory-field standards” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. Control/Handoff: The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. | The Chief Research Officer (CRO) completes “Set master-data taxonomy, naming, ownership and mandatory-field standards” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. | The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he sets the rules for how master data is named, classified and owned, so the data stays usable. • Starts when: the standards are established, and when new data categories are introduced. • How it runs: (1) he defines the categories of master data and their structures. (2) He sets the naming and classification conventions. (3) He sets the mandatory fields per category. (4) He assigns ownership per category. (5) He publishes the standard and applies it. • Proof it happened: published master data standards with naming, classification, mandatory fields and named owners per category. • Where it usually breaks: naming is left to whoever creates the record, so the same item exists several times under different names. | • Define the naming convention field by field and enforce it at creation, since inconsistent naming is what creates duplicate records that are impossible to find. • Assign a named owner per data category, because unowned master data degrades continuously and nobody notices. • Require classification at creation rather than later, as unclassified records are never reclassified. • Set the mandatory fields to what reporting actually needs, so the data supports the reports people ask for. • Include units of measure in the standard, as inconsistent units cause quantity and cost errors throughout.
1094 | Research & Development | Review new item, service, project and other master-data requests | Chief Research Officer (CRO) | Trigger: When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. Action: The Chief Research Officer (CRO) completes “Review new item, service, project and other master-data requests” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. Control/Handoff: The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. | The Chief Research Officer (CRO) completes “Review new item, service, project and other master-data requests” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. | The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he reviews requests to add new items, services or projects to the system before they are created. • Starts when: a master data creation request is submitted. • How it runs: (1) he receives the request with the required attributes. (2) He checks whether the record already exists in another form. (3) He checks the classification and the naming against the standard. (4) He requests the missing information. (5) He accepts or returns the request. • Proof it happened: reviewed master data requests with the duplicate check, the standard compliance check and the decision recorded. • Where it usually breaks: requests are created under time pressure without a duplicate check, so the same item accumulates several codes. | • Require a duplicate search before every creation, including near matches and alternative spellings, since duplicates are the primary damage to master data quality. • Set a service level for review, because slow creation is what drives users to request duplicates urgently. • Require the requester to state the intended use, as this reveals whether an existing record would serve. • Return incomplete requests rather than creating records with placeholder data, which is never corrected. • Track duplicate request volumes by requester, so training can be targeted.
1095 | Research & Development | Verify master-data completeness, uniqueness, classification and source ownership | Chief Research Officer (CRO) | Trigger: When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. Action: The Chief Research Officer (CRO) completes “Verify master-data completeness, uniqueness, classification and source ownership” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. Control/Handoff: The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. | The Chief Research Officer (CRO) completes “Verify master-data completeness, uniqueness, classification and source ownership” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. | The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he checks each new record is complete, unique, correctly classified and owned by the right function. • Starts when: a request has been reviewed and is being prepared for creation. • How it runs: (1) he verifies all mandatory attributes are present and valid. (2) He verifies uniqueness against the existing data. (3) He verifies the classification is correct. (4) He confirms the owning function for the record. (5) He confirms it is ready for creation. • Proof it happened: a verification record confirming completeness, uniqueness, classification and source ownership before creation. • Where it usually breaks: verification checks the fields are filled rather than whether the values are correct, so plausible but wrong data enters the system. | • Require validation of the values rather than the presence of values, since a filled field with a wrong value is more damaging than an empty one. • Require verification against a source document rather than the requester's statement, particularly for technical specifications. • Check the unit of measure explicitly, as this single field causes the most downstream cost and quantity errors. • Confirm the owning function, so future maintenance of the record has an owner. • Record who verified, as accountability for data quality otherwise disappears.
1096 | Research & Development | Create approved master-data records in FirstBit ERP | Chief Research Officer (CRO) | Trigger: When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. Action: The Chief Research Officer (CRO) completes “Create approved master-data records in FirstBit ERP” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. Control/Handoff: The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. | The Chief Research Officer (CRO) completes “Create approved master-data records in FirstBit ERP” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. | The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he creates the approved records in the ERP, so only checked data enters the system. • Starts when: a verified request is approved for creation. • How it runs: (1) he creates the record with the verified attributes. (2) He applies the naming and classification standards. (3) He sets the record status and any restrictions. (4) He checks the created record against the request. (5) He informs the requester with the record reference. • Proof it happened: created master data records matching the approved requests, with the creation confirmed back to the requester. • Where it usually breaks: creation rights are widely held, so records are created directly by users and the standards are bypassed entirely. | • Restrict creation rights to the data governance role, since widely held creation rights make every standard advisory. • Require the created record to be checked against the request, because transcription errors at creation are permanent. • Provide a fast track for genuinely urgent creation, otherwise pressure forces workarounds. • Notify the requester with the reference, so they do not create a second record believing the first failed. • Log all creations for periodic quality review.
1097 | Research & Development | Control master-data correction, merge, deactivation and reactivation requests | Chief Research Officer (CRO) | Trigger: When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. Action: The Chief Research Officer (CRO) completes “Control master-data correction, merge, deactivation and reactivation requests” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. Control/Handoff: The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. | The Chief Research Officer (CRO) completes “Control master-data correction, merge, deactivation and reactivation requests” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. | The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he controls corrections, merging duplicates, and switching records on or off, because these changes affect history. • Starts when: a correction, merge, deactivation or reactivation is requested. • How it runs: (1) he receives the request with the reason. (2) He assesses the effect on historical transactions and reports. (3) He obtains approval where the impact is material. (4) He performs the change with a record of the before and after state. (5) He verifies the affected reports still reconcile. • Proof it happened: a change record with the reason, the impact assessment, the approval and the before and after state. • Where it usually breaks: duplicates are merged without assessing history, so past transactions and reports change retrospectively. | • Require an impact assessment on historical transactions before any merge, since merging records rewrites history and can change closed period reports. • Prefer deactivation over deletion, as deletion breaks the audit trail on past transactions. • Record the before and after state, so any change can be traced and reversed. • Require approval for changes affecting closed periods, with Finance involved. • Verify the affected reports reconcile after the change rather than assuming they will.
1098 | Research & Development | Measure master-data quality and direct recurring-error corrective actions | Chief Research Officer (CRO) | Trigger: When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. Action: The Chief Research Officer (CRO) completes “Measure master-data quality and direct recurring-error corrective actions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. Control/Handoff: The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new master-data record, correction, duplicate, merge, deactivation or recurring data-quality issue is submitted. | The Chief Research Officer (CRO) completes “Measure master-data quality and direct recurring-error corrective actions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a valid FirstBit master-data record or controlled rejection with source owner, classification, approval and complete audit trail. | The originating department owns source accuracy, Finance/Procurement/Technical owners retain their domain approvals, and the CRO controls naming, uniqueness, classification and change governance. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he measures how good the data actually is and fixes the causes of the recurring errors. • Starts when: at the data quality review cycle, and when errors are reported. • How it runs: (1) he measures the agreed quality indicators: duplicates, incomplete records and misclassifications. (2) He identifies the recurring error patterns. (3) He traces each pattern to its cause. (4) He directs the corrective action, whether training, system control or standard change. (5) He verifies the improvement in the next measurement. • Proof it happened: data quality measurements with identified error patterns, directed corrective actions and evidence of improvement. • Where it usually breaks: errors are corrected one by one without addressing the cause, so the same errors are created continuously. | • Require the cause of each recurring error to be addressed, since correcting individual records without fixing the cause is endless work with no improvement. • Prefer a system validation over training where the error is mechanical, as validation prevents while training only reduces. • Report data quality measures to the CEO, because poor master data undermines every report the executive relies on. • Set a target and track the trend rather than reporting absolute error counts. • Run periodic duplicate detection across the whole master rather than only at creation.
1099 | Research & Development | Define the company process KPI dictionary, owners and reporting frequency | Chief Research Officer (CRO) | Trigger: When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. Action: The Chief Research Officer (CRO) completes “Define the company process KPI dictionary, owners and reporting frequency” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. Control/Handoff: KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. | The Chief Research Officer (CRO) completes “Define the company process KPI dictionary, owners and reporting frequency” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. | KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he defines the measures the company uses to judge its processes, who owns each and how often they are reported. • Starts when: the measurement framework is established, and when processes or priorities change. • How it runs: (1) he identifies what each process must be measured on. (2) He defines each measure's calculation precisely. (3) He assigns a named owner per measure. (4) He sets the reporting frequency. (5) He publishes the dictionary as the single reference. • Proof it happened: a published KPI dictionary with calculation definitions, named owners and reporting frequencies. • Where it usually breaks: the same measure is calculated differently by different departments, so numbers are argued over instead of acted on. | • Define each measure's calculation to the level of which records are included and excluded, since undefined measures produce competing numbers and endless argument. • Assign a named owner per measure, because a measure nobody owns is neither maintained nor acted on. • Limit the number of measures per process, as a long list dilutes attention and none get managed. • Include both outcome and leading measures, so problems are visible before they show in results. • Version the dictionary, so a change in definition does not look like a change in performance.
1100 | Research & Development | Design process dashboards, service levels and exception thresholds | Chief Research Officer (CRO) | Trigger: When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. Action: The Chief Research Officer (CRO) completes “Design process dashboards, service levels and exception thresholds” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. Control/Handoff: KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. | The Chief Research Officer (CRO) completes “Design process dashboards, service levels and exception thresholds” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. | KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he designs the dashboards, the service levels and the thresholds that decide when something counts as a problem. • Starts when: the measures are defined, and when reporting needs change. • How it runs: (1) he designs the dashboard layout for each audience. (2) He sets the service levels for each process step. (3) He sets the exception thresholds that trigger attention. (4) He validates the design with the users. (5) He implements and maintains it. • Proof it happened: implemented dashboards with defined service levels and exception thresholds, validated with the users. • Where it usually breaks: the dashboard shows everything at once, so the exceptions that need action are lost among the normal results. | • Design the dashboard to surface exceptions rather than display all data, since a dashboard where nothing stands out drives no action. • Set thresholds that reflect genuine tolerance, because thresholds set too tight produce alert fatigue and are then ignored. • Design separately per audience, as the executive and the process owner need different levels of detail. • Require every threshold breach to have a defined response, otherwise the dashboard reports problems nobody owns. • Automate the dashboard from the system, since manually compiled dashboards are always late and often wrong.
1101 | Research & Development | Validate performance data sources, calculations and reconciliation controls | Chief Research Officer (CRO) | Trigger: When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. Action: The Chief Research Officer (CRO) completes “Validate performance data sources, calculations and reconciliation controls” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. Control/Handoff: KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. | The Chief Research Officer (CRO) completes “Validate performance data sources, calculations and reconciliation controls” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. | KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he checks that the numbers on the dashboards are actually right, by tracing them back to the source. • Starts when: a new measure or report is implemented, and at the periodic validation cycle. • How it runs: (1) he traces each measure back to its source data. (2) He verifies the calculation matches the definition. (3) He reconciles the reported figures to the source system. (4) He documents the data lineage. (5) He corrects the discrepancies and re validates. • Proof it happened: validated data sources with documented lineage, verified calculations and reconciliation to the source system. • Where it usually breaks: a reporting error is discovered after decisions have been taken on the wrong numbers, which destroys trust in all reporting. | • Validate every measure before it is published, since a single wrong figure discovered later destroys confidence in the entire reporting set. • Document the data lineage from source to report, so any figure can be traced when challenged. • Require reconciliation to the source system at a set frequency, not only at implementation. • State the data cut off and the refresh timing on every report, because comparing figures from different moments produces false conclusions. • Investigate any manual adjustment applied to reported figures, as these usually mask a data problem.
1102 | Research & Development | Issue weekly and monthly process-performance and compliance analysis | Chief Research Officer (CRO) | Trigger: When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. Action: The Chief Research Officer (CRO) completes “Issue weekly and monthly process-performance and compliance analysis” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. Control/Handoff: KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. | The Chief Research Officer (CRO) completes “Issue weekly and monthly process-performance and compliance analysis” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. | KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he publishes the regular analysis of how the processes are performing and where compliance is slipping. • Starts when: at the weekly and monthly reporting cycles. • How it runs: (1) he compiles the performance data for the period. (2) He identifies the exceptions and the trends. (3) He analyses the causes rather than just reporting the numbers. (4) He states the actions needed and the owners. (5) He issues to the process owners and the CEO. • Proof it happened: issued weekly and monthly performance and compliance analysis with causes, actions and owners. • Where it usually breaks: the report presents numbers without analysis, so each recipient forms their own explanation and nothing is agreed. | • Require the report to state the cause and the recommended action, not only the numbers, since a report without analysis produces discussion rather than decisions. • Lead with exceptions and deterioration, as this is what needs the reader's attention. • Show the trend rather than the single period, because one period rarely justifies a change. • Send the process owner their own section, so accountability is direct rather than diffused across a company report. • Keep the issue date fixed, as a late report is read after the decisions have already been made.
1103 | Research & Development | Identify workflow bottlenecks, ageing, rework, delay and control leakage | Chief Research Officer (CRO) | Trigger: When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. Action: The Chief Research Officer (CRO) completes “Identify workflow bottlenecks, ageing, rework, delay and control leakage” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. Control/Handoff: KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. | The Chief Research Officer (CRO) completes “Identify workflow bottlenecks, ageing, rework, delay and control leakage” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. | KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he finds where work gets stuck, redone, delayed or slips past controls. • Starts when: at the analysis cycle, and when performance problems are reported. • How it runs: (1) he analyses the workflow data for queue times and ageing. (2) He identifies where work is returned or redone. (3) He identifies where controls are bypassed or overridden. (4) He quantifies the cost or delay each causes. (5) He reports the findings with the improvement opportunities. • Proof it happened: a bottleneck and leakage analysis with quantified delay, rework and control bypass findings. • Where it usually breaks: the bottleneck is identified as a person or department rather than a design constraint, so the response is pressure instead of a fix. | • Frame findings as design constraints rather than individual performance, since pressure on a person at a bottleneck does not increase capacity and does damage trust. • Quantify the cost or delay of each finding, because unquantified findings do not attract the resources needed to fix them. • Measure rework specifically, as it is usually the largest hidden cost and rarely visible in any report. • Analyse control overrides for pattern, since a frequently overridden control is either wrong or unworkable. • Require the data source to be the system rather than opinion, so the findings survive challenge.
1104 | Research & Development | Assign performance corrective actions and verify effective closure | Chief Research Officer (CRO) | Trigger: When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. Action: The Chief Research Officer (CRO) completes “Assign performance corrective actions and verify effective closure” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. Control/Handoff: KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a KPI design, weekly/monthly cutoff, threshold breach, reconciliation issue or performance review becomes due. | The Chief Research Officer (CRO) completes “Assign performance corrective actions and verify effective closure” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a controlled KPI definition, reconciled dashboard, exception analysis, corrective action and verified closure record. | KPI owners certify source data and functional chiefs own recovery actions; the CRO challenges data quality, highlights systemic issues and escalates material unresolved performance gaps to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he assigns the fixes for performance problems and checks they actually worked. • Starts when: an analysis identifies a corrective action, and at the follow up review. • How it runs: (1) he agrees the action with the process owner. (2) He records it with an owner and a date. (3) He tracks progress and chases overdue items. (4) He verifies effectiveness through the next measurement rather than by confirmation. (5) He closes or reopens the action. • Proof it happened: an action register with owners, dates and closure verified through measurement rather than self declaration. • Where it usually breaks: actions are closed on the owner's confirmation, so ineffective fixes are recorded as resolved and the problem persists. | • Verify closure through the measurement rather than the owner's confirmation, since an action can be complete while the problem remains unchanged. • Distinguish the action being done from the problem being solved, and keep the finding open until the measure moves. • Escalate overdue actions on a defined timescale, as ageing actions are the standard failure of any improvement function. • Require the process owner to own the action, not R&D, or the fix does not survive. • Report closure rate and ageing, because the count of open actions alone hides how long they have been open.
1105 | Research & Development | Register improvement requests, audit findings and recurring process failures | Chief Research Officer (CRO) | Trigger: When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. Action: The Chief Research Officer (CRO) completes “Register improvement requests, audit findings and recurring process failures” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. Control/Handoff: No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. | The Chief Research Officer (CRO) completes “Register improvement requests, audit findings and recurring process failures” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. | No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he collects all the improvement ideas, audit findings and repeated failures in one place so nothing is lost. • Starts when: an idea, finding or failure is raised, from any source. • How it runs: (1) he registers each item with its source and description. (2) He classifies it by process and type. (3) He identifies items that are the same problem reported differently. (4) He confirms receipt to the person who raised it. (5) He carries them into prioritisation. • Proof it happened: an improvement register with all sources captured, classified and acknowledged to the raiser. • Where it usually breaks: ideas are raised and never acknowledged, so people stop raising them and the company loses its best source of improvement. | • Acknowledge every submission with an outcome, even a rejection with a reason, since unacknowledged suggestions stop the flow of ideas permanently. • Group items that describe the same underlying problem, as repeated reports of one issue indicate its real priority. • Accept submissions from any level, because the people closest to the work see the failures first. • Include audit findings and incident causes in the same register, so improvement effort is not fragmented across separate lists. • Report submission volumes by department, as silence usually indicates that raising things is not welcomed.
1106 | Research & Development | Prioritise improvements by risk, value, frequency and implementation effort | Chief Research Officer (CRO) | Trigger: When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. Action: The Chief Research Officer (CRO) completes “Prioritise improvements by risk, value, frequency and implementation effort” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. Control/Handoff: No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. | The Chief Research Officer (CRO) completes “Prioritise improvements by risk, value, frequency and implementation effort” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. | No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he decides which improvements to do first, weighing risk, value, how often the problem happens and the effort to fix it. • Starts when: at the prioritisation cycle, and when a high risk item is registered. • How it runs: (1) he assesses each item on risk, value, frequency and effort. (2) He scores and ranks them. (3) He identifies the quick wins separately from the major changes. (4) He agrees the ranking with the affected owners. (5) He publishes the ranked list and the deferred items. • Proof it happened: a ranked improvement list with the scoring basis and the deferred items visible. • Where it usually breaks: prioritisation follows whoever is loudest, so genuinely high risk items sit behind visible but minor irritations. | • Require scoring against stated criteria, since prioritisation by influence puts high risk items behind visible minor ones. • Reserve capacity for quick wins, because visible early results are what sustain support for the function. • Weight safety and compliance items above efficiency items explicitly. • Publish the deferred list with reasons, so the departments deprioritised understand why. • Reprioritise on a fixed cycle rather than continuously, otherwise nothing stays in progress long enough to finish.
1107 | Research & Development | Map the current state and identify waste, failure points and root causes | Chief Research Officer (CRO) | Trigger: When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. Action: The Chief Research Officer (CRO) completes “Map the current state and identify waste, failure points and root causes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. Control/Handoff: No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. | The Chief Research Officer (CRO) completes “Map the current state and identify waste, failure points and root causes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. | No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he documents how the process works today and finds the waste and the real causes of failure. • Starts when: an improvement is approved and analysis begins. • How it runs: (1) he maps the current process as actually performed. (2) He measures the time, cost and error rates at each step. (3) He identifies the waste: waiting, rework, duplication and unnecessary steps. (4) He traces the failures to root causes rather than symptoms. (5) He documents the baseline for later comparison. • Proof it happened: a current state map with measured baseline data, identified waste and documented root causes. • Where it usually breaks: the current state is mapped from the SOP rather than from observation, so the real problems never appear on the map. | • Require the current state to be mapped from observation, not from the SOP, since the documented process is rarely the one being performed. • Require the baseline to be measured before any change, because without it benefit can only be asserted. • Require root cause analysis to reach a system or management cause, as stopping at human error prevents any effective fix. • Include the waiting time between steps, which is usually far larger than the processing time and is routinely ignored. • Validate the map with the people who perform the work before designing anything.
1108 | Research & Development | Design the future-state workflow, roles, controls and measurable benefits | Chief Research Officer (CRO) | Trigger: When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. Action: The Chief Research Officer (CRO) completes “Design the future-state workflow, roles, controls and measurable benefits” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. Control/Handoff: No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. | The Chief Research Officer (CRO) completes “Design the future-state workflow, roles, controls and measurable benefits” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. | No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he designs how the process should work instead, with the controls and the benefits stated. • Starts when: the current state analysis is complete. • How it runs: (1) he designs the future state flow removing the identified waste. (2) He assigns the roles and the decision points. (3) He designs the controls into the flow rather than adding them on. (4) He quantifies the expected benefit against the baseline. (5) He validates the design with the owners and the users. • Proof it happened: a future state design with roles, controls and quantified expected benefits measured against the baseline. • Where it usually breaks: the design is elegant but assumes resources or behaviour that do not exist, so it is never implemented. | • Test the design against the actual resources and skills available, since a design that assumes capacity the company does not have is never implemented. • Design the controls into the flow rather than as separate checks, because bolted on controls are the first thing dropped under pressure. • Quantify the expected benefit against the measured baseline, so the case can be tested at closure. • Validate with the users, as a design they do not accept will be worked around from day one. • State what will get worse as well as better, since every design involves a trade off and hiding it destroys trust.
1109 | Research & Development | Coordinate controlled improvement trials, feedback and issue correction | Chief Research Officer (CRO) | Trigger: When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. Action: The Chief Research Officer (CRO) completes “Coordinate controlled improvement trials, feedback and issue correction” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. Control/Handoff: No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. | The Chief Research Officer (CRO) completes “Coordinate controlled improvement trials, feedback and issue correction” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. | No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he runs the change as a controlled trial first, gathers feedback and fixes the problems before rolling it out. • Starts when: the future state design is approved and a trial is arranged. • How it runs: (1) he selects the trial scope and duration. (2) He briefs and trains the participants. (3) He runs the trial and gathers the data and the feedback. (4) He corrects the issues found. (5) He reports the trial outcome with a recommendation. • Proof it happened: a trial record with the scope, the data gathered, the feedback, the corrections made and the recommendation. • Where it usually breaks: the trial is declared successful without measuring anything, so the rollout carries the unresolved problems company wide. | • Define the trial success criteria and the measurement before the trial starts, since a trial assessed on impressions always appears successful. • Choose a trial scope representative of normal conditions, because a trial in ideal conditions proves nothing about rollout. • Gather feedback from the participants formally, as they see the practical failures that data does not show. • Allow the trial to fail and be reported as such, otherwise the trial is a formality. • Correct and retest rather than carrying known issues into rollout.
1110 | Research & Development | Verify benefit realisation, control effectiveness and improvement closure | Chief Research Officer (CRO) | Trigger: When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. Action: The Chief Research Officer (CRO) completes “Verify benefit realisation, control effectiveness and improvement closure” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. Control/Handoff: No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an audit finding, recurring failure, delay, rework pattern, user suggestion or control gap requires improvement. | The Chief Research Officer (CRO) completes “Verify benefit realisation, control effectiveness and improvement closure” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a prioritised improvement record, current-state/root-cause analysis, future-state design, trial evidence, benefit result and closure decision. | No workflow or authority change becomes permanent without owner approval, controlled trial evidence, updated documents/system controls and an effectiveness review. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he proves the improvement actually delivered what was promised, then closes it properly. • Starts when: an improvement has been implemented and had time to take effect. • How it runs: (1) he measures the process against the baseline. (2) He compares the realised benefit against the expected. (3) He verifies the new controls are operating. (4) He confirms the SOP and the workflow reflect the change. (5) He closes the initiative with the outcome recorded. • Proof it happened: a benefit realisation record comparing measured outcome to baseline, with control effectiveness verified and the initiative closed. • Where it usually breaks: initiatives are closed at implementation rather than at benefit, so nobody ever learns whether the change worked. | • Separate implementation closure from benefit closure, since closing at go live means the company never learns whether its improvements work. • Allow a stabilisation period before measuring, because performance always dips immediately after a change. • Verify the controls are actually being used, not just documented, as new controls decay quickly without attention. • Report where benefit was not realised, since suppressing failures prevents any improvement in how initiatives are selected. • Confirm the SOP and workflow were updated, otherwise the change reverses as soon as attention moves on.
1111 | Research & Development | Scan construction, operational and management innovations relevant to Sevents | Chief Research Officer (CRO) | Trigger: When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. Action: The Chief Research Officer (CRO) completes “Scan construction, operational and management innovations relevant to Sevents” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. Control/Handoff: CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. | The Chief Research Officer (CRO) completes “Scan construction, operational and management innovations relevant to Sevents” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. | CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he looks outward for new methods, tools and practices in construction and management that could help the company. • Starts when: continuously, with formal review at the innovation cycle. • How it runs: (1) he monitors industry developments, publications and suppliers. (2) He identifies what is relevant to the company's actual work. (3) He assesses maturity and applicability. (4) He records the candidates with their potential. (5) He proposes the ones worth evaluating properly. • Proof it happened: a scanning record with identified developments, relevance assessments and the proposed candidates. • Where it usually breaks: scanning produces interesting technology with no connection to an actual company problem, so nothing is ever adopted. | • Require every candidate to be linked to a known company problem or cost, since technology adopted for its own sake is abandoned within a year. • Assess maturity honestly, as early stage technology carries implementation cost the business case rarely includes. • Check what comparable contractors are actually using rather than what vendors present. • Record rejected candidates with reasons, so the same proposals are not re evaluated repeatedly. • Limit the scanning effort proportionate to the company's capacity to adopt.
1112 | Research & Development | Benchmark contractor practices, workflows, tools and productivity methods | Chief Research Officer (CRO) | Trigger: When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. Action: The Chief Research Officer (CRO) completes “Benchmark contractor practices, workflows, tools and productivity methods” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. Control/Handoff: CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. | The Chief Research Officer (CRO) completes “Benchmark contractor practices, workflows, tools and productivity methods” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. | CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he compares how the company works against how other contractors work, to find where it is behind. • Starts when: at the benchmarking cycle, and when performance appears out of line. • How it runs: (1) he identifies the practices worth comparing. (2) He gathers comparable information from available sources. (3) He compares against the company's own measured performance. (4) He identifies the meaningful gaps. (5) He reports the findings with improvement candidates. • Proof it happened: a benchmarking record comparing practices and performance, with the identified gaps and candidates. • Where it usually breaks: comparisons are made against different definitions, so the company appears behind or ahead for reasons that are purely measurement. | • Verify the definitions match before comparing any figure, since most benchmarking conclusions are measurement artefacts rather than real differences. • Compare practices as well as numbers, because knowing another company is faster is useless without knowing how. • Account for context differences such as project type and client, otherwise the comparison misleads. • Prefer a few well understood comparisons over many superficial ones. • Convert findings into specific improvement candidates, or benchmarking becomes an annual report nobody uses.
1113 | Research & Development | Evaluate automation, analytics, AI and digital-workflow opportunities | Chief Research Officer (CRO) | Trigger: When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. Action: The Chief Research Officer (CRO) completes “Evaluate automation, analytics, AI and digital-workflow opportunities” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. Control/Handoff: CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. | The Chief Research Officer (CRO) completes “Evaluate automation, analytics, AI and digital-workflow opportunities” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. | CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he assesses where automation, data analysis or AI tools could genuinely help, and where they would not. • Starts when: an opportunity is identified, or a process problem suggests an automation option. • How it runs: (1) he identifies the processes with high volume, repetition or data intensity. (2) He assesses the suitability for automation or analytics. (3) He checks the data quality the tool would depend on. (4) He assesses the cost, the integration effort and the ongoing support. (5) He recommends or rules out with reasons. • Proof it happened: an assessment record per opportunity with the suitability, data readiness, cost and recommendation. • Where it usually breaks: automation is proposed on a process that is not stable, so the tool automates inconsistency and produces unreliable output. | • Require the process to be stable and documented before automating it, since automating an inconsistent process produces unreliable output at speed. • Assess the underlying data quality first, because analytics and AI amplify data problems rather than resolving them. • Include ongoing support, licensing and skill requirements in the case, as these usually exceed the implementation cost. • Require a named business owner rather than a technology owner. • State what happens when the tool fails, since automated steps with no manual fallback stop the business.
1114 | Research & Development | Prepare innovation business cases with cost, benefit, risk and ownership | Chief Research Officer (CRO) | Trigger: When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. Action: The Chief Research Officer (CRO) completes “Prepare innovation business cases with cost, benefit, risk and ownership” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. Control/Handoff: CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. | The Chief Research Officer (CRO) completes “Prepare innovation business cases with cost, benefit, risk and ownership” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. | CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he builds the case for each innovation, with real costs, real benefits, the risks and who will own it. • Starts when: an opportunity is assessed as worth pursuing. • How it runs: (1) he quantifies the costs including implementation and ongoing. (2) He quantifies the benefits with the evidence behind them. (3) He states the risks and the dependencies. (4) He identifies the accountable business owner. (5) He submits the case for decision. • Proof it happened: a business case with quantified cost and benefit, stated risks, dependencies and a named owner. • Where it usually breaks: benefits are stated as percentages of large numbers with no evidence, so the case is either rejected or approved on faith. | • Require the benefit to be evidenced from the company's own measured data, since a percentage applied to a large figure is not a business case. • Include implementation, training, support and licensing over a stated period, as first year cost alone understates commitment. • Require a named business owner accountable for the benefit, not just for the implementation. • State the risks and what would cause the case to fail, since a case with no risks stated is not credible. • Require a post implementation review commitment as part of approval.
1115 | Research & Development | Coordinate proof-of-concept and pilot testing with affected departments | Chief Research Officer (CRO) | Trigger: When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. Action: The Chief Research Officer (CRO) completes “Coordinate proof-of-concept and pilot testing with affected departments” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. Control/Handoff: CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. | The Chief Research Officer (CRO) completes “Coordinate proof-of-concept and pilot testing with affected departments” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. | CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he runs the small scale test with the departments affected, so the idea is proven before it is scaled. • Starts when: a business case is approved for piloting. • How it runs: (1) he agrees the pilot scope, duration and success criteria. (2) He arranges the resources and the participating departments. (3) He runs the pilot with data collection throughout. (4) He gathers structured feedback from the participants. (5) He documents the results against the criteria. • Proof it happened: a pilot record with the agreed criteria, the collected data, the participant feedback and the documented results. • Where it usually breaks: the pilot has no end date, so it continues indefinitely as a semi permanent arrangement that is neither adopted nor stopped. | • Set a fixed end date and a decision point, since pilots without one become permanent unmanaged arrangements. • Agree the success criteria before the pilot begins, so the assessment cannot be adjusted to fit the outcome. • Require the participating department to commit resources formally, as under resourced pilots fail for the wrong reasons. • Collect data throughout rather than at the end, because the end state does not show what went wrong. • State how the pilot will be reversed if terminated, so the company is not left with a partial implementation.
1116 | Research & Development | Recommend scale-up, modification, deferment or termination of pilots | Chief Research Officer (CRO) | Trigger: When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. Action: The Chief Research Officer (CRO) completes “Recommend scale-up, modification, deferment or termination of pilots” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. Control/Handoff: CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a new method, tool, automation opportunity, benchmark finding or approved innovation idea requires evaluation. | The Chief Research Officer (CRO) completes “Recommend scale-up, modification, deferment or termination of pilots” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a benchmark, feasibility assessment, business case, proof-of-concept result and scale/modify/stop recommendation. | CTO owns technical-engineering acceptance, COO owns project-execution suitability, CFO confirms financial case, CLO controls legal/data risk and the CRO governs evaluation and evidence. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: after the pilot he recommends whether to roll it out, change it, wait, or stop. • Starts when: a pilot reaches its decision point. • How it runs: (1) he assesses the results against the success criteria. (2) He assesses the readiness of the business to adopt. (3) He assesses the cost and effort of scaling. (4) He makes a clear recommendation with the reasoning. (5) He submits for decision and records the outcome. • Proof it happened: a pilot decision record with the results against criteria and a documented recommendation and decision. • Where it usually breaks: nobody wants to declare a pilot a failure, so unsuccessful pilots are extended repeatedly rather than stopped. | • State explicitly that terminating a pilot is a successful outcome of piloting, since the fear of declaring failure is what keeps bad pilots alive. • Require the recommendation to be one of four clear options rather than a general assessment. • Assess business readiness separately from technical success, as a working solution the business cannot absorb still fails. • Require the scale up cost to be quantified before the decision, because pilots rarely scale linearly. • Record the lessons from terminated pilots, as these are the most valuable and most often discarded.
1117 | Research & Development | Collect lessons from stage gates, incidents, failures and project closeout | Chief Research Officer (CRO) | Trigger: When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. Action: The Chief Research Officer (CRO) completes “Collect lessons from stage gates, incidents, failures and project closeout” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. Control/Handoff: Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. | The Chief Research Officer (CRO) completes “Collect lessons from stage gates, incidents, failures and project closeout” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. | Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he gathers the lessons from gates, incidents, failures and finished projects, so the company does not repeat them. • Starts when: at a stage gate, after an incident or failure, and at project closeout. • How it runs: (1) he identifies the events worth learning from. (2) He collects the facts and the outcomes. (3) He gathers the participants' accounts. (4) He distinguishes the lesson from the blame. (5) He records the candidate lessons for review. • Proof it happened: collected lessons with the source events, facts and participant input recorded. • Where it usually breaks: collection only happens at project closeout, when the people involved have already moved on and the detail is lost. | • Collect lessons at the point of the event rather than at closeout, since by closeout the people have moved on and the detail is gone. • Separate the lesson from individual blame explicitly, because a process that assigns fault stops producing information. • Include successes as well as failures, as what worked is usually undocumented and therefore not repeated. • Capture the specific circumstances, since a lesson without context cannot be applied correctly elsewhere. • Require lesson collection as a mandatory step at gates and closeout, not an optional one.
1118 | Research & Development | Facilitate structured lessons-learned and root-cause review sessions | Chief Research Officer (CRO) | Trigger: When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. Action: The Chief Research Officer (CRO) completes “Facilitate structured lessons-learned and root-cause review sessions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. Control/Handoff: Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. | The Chief Research Officer (CRO) completes “Facilitate structured lessons-learned and root-cause review sessions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. | Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he runs the sessions that work out why something happened, rather than settling for the obvious answer. • Starts when: a significant failure, incident or missed outcome requires review. • How it runs: (1) he assembles the people with direct knowledge. (2) He establishes the factual sequence first. (3) He works back through the causes using a structured method. (4) He identifies the system and management causes, not only the immediate act. (5) He records the causes and the recommended changes. • Proof it happened: a structured review record with the factual sequence, the identified root causes and the recommended changes. • Where it usually breaks: the session stops at the first plausible cause, which is usually a person, so the system that allowed it stays unchanged. | • Require the analysis to continue past the immediate human action to the system and management causes, since stopping at the person guarantees recurrence. • Establish the facts before discussing causes, because opinions form fast and then resist evidence. • Hold the session without the people who will be judged by it present as authority figures, or the accounts will be guarded. • Require recommendations to be specific and assignable, not general statements about awareness. • Run the review promptly, as memory and evidence both degrade quickly.
1119 | Research & Development | Maintain the company knowledge repository and controlled taxonomy | Chief Research Officer (CRO) | Trigger: When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. Action: The Chief Research Officer (CRO) completes “Maintain the company knowledge repository and controlled taxonomy” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. Control/Handoff: Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. | The Chief Research Officer (CRO) completes “Maintain the company knowledge repository and controlled taxonomy” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. | Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he keeps the company's knowledge in one organised place where people can actually find it. • Starts when: the repository is established, and continuously as knowledge is produced. • How it runs: (1) he defines the structure and the classification. (2) He requires knowledge to be filed against it. (3) He controls what enters, so quality is maintained. (4) He removes or archives what is superseded. (5) He monitors whether it is actually being used. • Proof it happened: a maintained knowledge repository with a controlled structure, current content and usage monitoring. • Where it usually breaks: everything is added and nothing is removed, so the repository fills with outdated material and people stop trusting it. | • Require superseded content to be archived or removed, since a repository containing outdated material is one people stop trusting and therefore stop using. • Control what enters, because an unmoderated repository becomes a dumping ground rather than a resource. • Design the classification around how people search rather than how the company is organised. • Monitor usage, as an unused repository is a cost with no benefit and needs redesign rather than more content. • Require an owner per knowledge area responsible for currency.
1120 | Research & Development | Convert accepted lessons into SOP, workflow, checklist or training changes | Chief Research Officer (CRO) | Trigger: When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. Action: The Chief Research Officer (CRO) completes “Convert accepted lessons into SOP, workflow, checklist or training changes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. Control/Handoff: Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. | The Chief Research Officer (CRO) completes “Convert accepted lessons into SOP, workflow, checklist or training changes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. | Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he turns accepted lessons into actual changes in the SOPs, workflows, checklists or training. • Starts when: a lesson is accepted and requires a change. • How it runs: (1) he identifies which documents or systems must change. (2) He drafts the change with the process owner. (3) He routes it through the normal approval process. (4) He issues the change and communicates it. (5) He records the link from the lesson to the change. • Proof it happened: implemented changes to SOPs, workflows, checklists or training, traceable back to the originating lesson. • Where it usually breaks: lessons are recorded in a lessons register and never converted into anything, so the same failure recurs with the lesson already documented. | • Require every accepted lesson to result in a specific document, system or training change, since a lesson recorded but not embedded changes nothing. • Maintain the traceable link from lesson to change, so the register shows what was actually acted on. • Set a deadline for conversion, because unconverted lessons accumulate until the register is abandoned. • Prefer a checklist or system control over a training message, as controls persist while awareness fades. • Report unconverted lessons, as these represent known failures the company has chosen not to prevent.
1121 | Research & Development | Coordinate knowledge-sharing workshops and cross-project learning sessions | Chief Research Officer (CRO) | Trigger: When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. Action: The Chief Research Officer (CRO) completes “Coordinate knowledge-sharing workshops and cross-project learning sessions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. Control/Handoff: Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. | The Chief Research Officer (CRO) completes “Coordinate knowledge-sharing workshops and cross-project learning sessions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. | Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he arranges the sessions where teams share what they have learnt across projects. • Starts when: at the scheduled sharing cycle, and after significant events worth sharing. • How it runs: (1) he identifies the topics with cross project value. (2) He arranges the session with the relevant teams. (3) He facilitates a structured discussion rather than a presentation. (4) He captures the points raised. (5) He follows up on the actions arising. • Proof it happened: knowledge sharing session records with the topics, participants, points captured and actions arising. • Where it usually breaks: sessions become presentations of successes, so nobody discusses the failures that carry the real learning. | • Require failures and near misses to be part of every session, since a forum of successes teaches nothing and everyone knows it. • Facilitate discussion rather than presentation, because the useful information emerges in questions. • Invite the people who do the work, not only the managers who report on it. • Capture and circulate the points raised, otherwise the value stays with the attendees. • Keep the sessions short and regular rather than long and occasional.
1122 | Research & Development | Track lesson adoption, reuse and recurrence of previously identified failures | Chief Research Officer (CRO) | Trigger: When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. Action: The Chief Research Officer (CRO) completes “Track lesson adoption, reuse and recurrence of previously identified failures” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. Control/Handoff: Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When a stage gate, incident, recurring problem, completed project or management review produces a reusable lesson. | The Chief Research Officer (CRO) completes “Track lesson adoption, reuse and recurrence of previously identified failures” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a validated lesson, root cause, repository entry, approved SOP/workflow/training change and adoption/effectiveness record. | Lessons are evidence-based and reviewed by the responsible functional owner; confidential, legal, commercial and personal data are protected before company-wide reuse. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he checks whether lessons are actually being used, and whether old failures are happening again. • Starts when: at the review cycle, and when a failure resembles a previously recorded one. • How it runs: (1) he reviews whether the accepted lessons have been embedded. (2) He checks whether the changes are being followed in practice. (3) He compares new failures against the historical register. (4) He identifies recurrences of known failures. (5) He escalates recurrences as a governance matter. • Proof it happened: an adoption and recurrence review showing embedded lessons, practice checks and identified recurrences. • Where it usually breaks: recurrence is never checked, so the company repeatedly pays for failures it already documented and understood. | • Check every significant failure against the historical register, since paying twice for the same documented failure is the clearest governance failure available. • Escalate recurrences of known failures to the CEO, because these indicate the learning system is not working. • Verify adoption in practice rather than confirming the document was changed. • Track the reuse of knowledge, as unused knowledge means the repository is not reaching the people who need it. • Report recurrence rate as the primary measure of the learning function's effectiveness.
1123 | Research & Development | Assess stakeholder, role, system, data and control impacts of approved changes | Chief Research Officer (CRO) | Trigger: When an approved process, system, data or organisational change moves toward deployment or requires continuity control. Action: The Chief Research Officer (CRO) completes “Assess stakeholder, role, system, data and control impacts of approved changes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. Control/Handoff: CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an approved process, system, data or organisational change moves toward deployment or requires continuity control. | The Chief Research Officer (CRO) completes “Assess stakeholder, role, system, data and control impacts of approved changes” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. | CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: before a change goes live he works out who and what it affects, including systems, data and controls. • Starts when: a change is approved and before it is deployed. • How it runs: (1) he identifies the roles and people affected. (2) He identifies the systems, data and reports affected. (3) He identifies the controls that change or are removed. (4) He assesses the readiness of each affected group. (5) He documents the impact assessment for the deployment plan. • Proof it happened: a documented impact assessment covering stakeholders, roles, systems, data and controls. • Where it usually breaks: the impact on downstream reports and controls is missed, so a change fixes one process and breaks the reporting that depends on it. | • Require downstream reports and dependent controls to be assessed, since changes commonly fix one process and silently break the reporting built on it. • Identify which controls are removed or weakened by the change, and require explicit acceptance of that. • Assess each affected group's readiness separately, as an average readiness hides the group that will block adoption. • Include the effect on external parties such as clients and suppliers where relevant. • Require the assessment before the deployment plan is approved, not alongside it.
1124 | Research & Development | Approve change communication, training, deployment and readiness plans | Chief Research Officer (CRO) | Trigger: When an approved process, system, data or organisational change moves toward deployment or requires continuity control. Action: The Chief Research Officer (CRO) completes “Approve change communication, training, deployment and readiness plans” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. Control/Handoff: CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an approved process, system, data or organisational change moves toward deployment or requires continuity control. | The Chief Research Officer (CRO) completes “Approve change communication, training, deployment and readiness plans” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. | CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he approves how the change will be communicated, trained and rolled out, and whether the business is ready. • Starts when: the impact assessment is complete and deployment is planned. • How it runs: (1) he reviews the communication plan and its timing. (2) He reviews the training plan against the affected roles. (3) He reviews the deployment sequence and the fallback. (4) He confirms the readiness criteria are met. (5) He approves deployment or defers it. • Proof it happened: approved communication, training and deployment plans with a documented readiness confirmation. • Where it usually breaks: deployment proceeds on the planned date despite readiness criteria not being met, because the date has been announced. | • Require readiness criteria to be met before deployment regardless of the announced date, since deploying to an unready business creates resistance that lasts far longer than a delay. • Require a fallback plan, as a change that cannot be reversed will be endured rather than adopted. • Require training to be delivered close to go live, because training too early is forgotten. • Communicate the reason for the change, not only the instruction, as compliance without understanding decays. • Name who may authorise deployment against unmet criteria, and require it in writing.
1125 | Research & Development | Coordinate process and system training with CPCO and functional owners | Chief Research Officer (CRO) | Trigger: When an approved process, system, data or organisational change moves toward deployment or requires continuity control. Action: The Chief Research Officer (CRO) completes “Coordinate process and system training with CPCO and functional owners” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. Control/Handoff: CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an approved process, system, data or organisational change moves toward deployment or requires continuity control. | The Chief Research Officer (CRO) completes “Coordinate process and system training with CPCO and functional owners” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. | CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he arranges the training on new processes and systems with HR and the departments involved. • Starts when: a change requires training, and at the training planning cycle. • How it runs: (1) he identifies the training needed per role. (2) He prepares or commissions the materials. (3) He coordinates the scheduling with the CPCO and the department heads. (4) He delivers or arranges delivery. (5) He records attendance and confirms understanding. • Proof it happened: delivered training with materials, attendance records and evidence of understanding rather than attendance alone. • Where it usually breaks: training is recorded as attendance, so people are marked trained on a process they cannot actually perform. | • Require evidence of understanding rather than attendance, since an attendance record marks people as trained on processes they cannot perform. • Train on the actual system and the actual documents, not on slides describing them. • Schedule with the department heads so training does not collide with delivery peaks, which is why sessions are poorly attended. • Provide a short reference the person keeps, as recall from a single session is low. • Include the exception paths in the training, because these are where users get stuck and abandon the process.
1126 | Research & Development | Monitor adoption, resistance, hypercare issues and stabilisation actions | Chief Research Officer (CRO) | Trigger: When an approved process, system, data or organisational change moves toward deployment or requires continuity control. Action: The Chief Research Officer (CRO) completes “Monitor adoption, resistance, hypercare issues and stabilisation actions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. Control/Handoff: CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an approved process, system, data or organisational change moves toward deployment or requires continuity control. | The Chief Research Officer (CRO) completes “Monitor adoption, resistance, hypercare issues and stabilisation actions” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. | CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: after a change goes live he watches whether it is being used, where people are struggling, and fixes the early problems. • Starts when: immediately after deployment, through the stabilisation period. • How it runs: (1) he monitors usage and completion of the new process. (2) He collects the issues users raise. (3) He identifies resistance and its reasons. (4) He resolves the issues quickly during hypercare. (5) He confirms stabilisation and hands over to normal operation. • Proof it happened: post deployment monitoring records with issues logged and resolved, and a documented stabilisation confirmation. • Where it usually breaks: support is withdrawn immediately after go live, so early problems harden into permanent workarounds. | • Provide a defined hypercare period with named support, since problems in the first days harden into permanent workarounds if not resolved quickly. • Treat resistance as information about the design rather than as an attitude problem, because it usually identifies a genuine flaw. • Monitor actual usage rather than reported adoption, as reported adoption is consistently optimistic. • Fix small irritations quickly, since these determine whether users accept or reject the whole change. • Require a formal stabilisation confirmation before support is withdrawn.
1127 | Research & Development | Govern R&D access, delegation, backup and business-continuity arrangements | Chief Research Officer (CRO) | Trigger: When an approved process, system, data or organisational change moves toward deployment or requires continuity control. Action: The Chief Research Officer (CRO) completes “Govern R&D access, delegation, backup and business-continuity arrangements” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. Control/Handoff: CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an approved process, system, data or organisational change moves toward deployment or requires continuity control. | The Chief Research Officer (CRO) completes “Govern R&D access, delegation, backup and business-continuity arrangements” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. | CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he makes sure the R&D function keeps working when people are away and that its records are protected. • Starts when: at the continuity review, on staff changes, and before planned absences. • How it runs: (1) he defines the system and configuration access per role. (2) He names deputies for the critical activities. (3) He documents the delegations with limits and end dates. (4) He confirms the backup of the process, SOP and configuration records. (5) He tests that the arrangements work. • Proof it happened: reviewed access rights, named deputies with written delegations and confirmed and tested backup arrangements. • Where it usually breaks: configuration knowledge sits with one person, so nothing can be changed or fixed while they are unavailable. | • Require configuration knowledge to be documented rather than held by one person, since concentrated system knowledge halts all change during any absence. • Require deputies to hold the necessary access before the absence and test it. • Set delegation end dates and withdraw access on return, so permissions do not accumulate. • Back up the SOP library and the configuration records, as these represent years of accumulated work. • Review access on every leaver, particularly configuration rights which are powerful and rarely reviewed.
1128 | Research & Development | Maintain R&D risk, decision, dependency and executive-action registers | Chief Research Officer (CRO) | Trigger: When an approved process, system, data or organisational change moves toward deployment or requires continuity control. Action: The Chief Research Officer (CRO) completes “Maintain R&D risk, decision, dependency and executive-action registers” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. Output/Evidence: a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. Control/Handoff: CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. Continuity/Escalation: A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. Timing: To be confirmed. | When an approved process, system, data or organisational change moves toward deployment or requires continuity control. | The Chief Research Officer (CRO) completes “Maintain R&D risk, decision, dependency and executive-action registers” using approved company strategy, department requirements, process evidence, audit findings, FirstBit records, KPI data, authority limits and controlled R&D registers. | a change-impact assessment, readiness plan, training/hypercare record, continuity arrangement and controlled risk/decision/action register. | CPCO coordinates people/training actions, IT controls technical continuity and access, functional chiefs own adoption, and material resistance, disruption or unresolved dependency escalates to the CEO. | A CEO-approved competent process-governance delegate may coordinate routine reviews, but company architecture, SOP governance, material ERP/master-data change, pilot scale decisions and unresolved cross-department ownership remain with the CRO or escalate to the CEO. | To be confirmed. | • In plain words: he keeps the registers of R&D risks, decisions, dependencies and the actions owed by the executive. • Starts when: continuously as items arise, with formal review at the reporting cycle. • How it runs: (1) he records the risks with their owners and mitigations. (2) He records the decisions taken with the date and the basis. (3) He records the dependencies on other functions. (4) He records the actions owed by the executive. (5) He reviews and reports the registers. • Proof it happened: maintained risk, decision, dependency and executive action registers, reviewed and reported. • Where it usually breaks: the decision register is not maintained, so agreed decisions are revisited and reversed with nobody able to show what was decided or why. | • Maintain the decision register with the date, the basis and the approver, since undocumented decisions are relitigated repeatedly and expensively. • Report executive actions owed to the CEO, as initiatives most often stall on decisions only the executive can make. • Record dependencies with the responsible function named, so blockages have an owner. • Show ageing on all registers, because an open risk from a year ago needs a decision rather than a status update. • Review the registers at a fixed frequency rather than only when reporting is due.
1129 | Research & Development | Receive and acknowledge each document-control submission | Document Controller | Trigger: When a company, project or external document enters the controlled-document process. Action: The Document Controller completes “Receive and acknowledge each document-control submission” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. Control/Handoff: The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a company, project or external document enters the controlled-document process. | The Document Controller completes “Receive and acknowledge each document-control submission” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. | The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: every document that comes in for control is logged and the sender is told it arrived, so nothing goes missing silently. • Starts when: a document is submitted for control from any internal or external source. • How it runs: (1) he receives the submission through the approved channel. (2) He checks it is legible and complete enough to process. (3) He logs the receipt with the date and the source. (4) He issues an acknowledgement to the sender. (5) He places it in the processing queue. • Proof it happened: a receipt log entry with the date, source and content, and an acknowledgement issued to the sender. • Where it usually breaks: documents are sent directly to individuals rather than through document control, so they are never registered and cannot be traced. | • State a single submission channel and require documents sent directly to individuals to be redirected, since unregistered documents cannot be traced and are the root of most document control failure. • Require acknowledgement within a stated period, as this is what tells the sender the document is in the system. • Log the receipt date separately from the document date, because the difference matters in any delay claim. • Require the submitter to be identified, so incomplete submissions can be returned to a named person. • Keep the receipt log unbroken and sequential, as gaps destroy its evidential value.
1130 | Research & Development | Verify the document author, owner, reviewer and approval authority | Document Controller | Trigger: When a company, project or external document enters the controlled-document process. Action: The Document Controller completes “Verify the document author, owner, reviewer and approval authority” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. Control/Handoff: The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a company, project or external document enters the controlled-document process. | The Document Controller completes “Verify the document author, owner, reviewer and approval authority” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. | The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he checks the document came from someone entitled to issue it, and that the right people are named as reviewer and approver. • Starts when: a submission is being processed for registration. • How it runs: (1) he identifies the stated author and owner. (2) He checks the author is authorised to issue that document type. (3) He checks the reviewer and approver named match the approved authority. (4) He queries any mismatch with the originating department. (5) He records the verified roles against the document. • Proof it happened: a verification record confirming the author, owner, reviewer and approver against the approved authority. • Where it usually breaks: the approver named is whoever was available rather than the person with authority, so the document is issued without valid approval. | • Check the named approver against the authority matrix before processing, since a document approved by the wrong person is not approved at all. • Require a named document owner distinct from the author, because the author leaves and the document still needs an owner. • Reject submissions with no stated reviewer rather than assigning one, as document control must not choose the technical reviewer. • Record the verification, so the file shows the authority was checked rather than assumed. • Maintain a reference list of who may approve each document category.
1131 | Research & Development | Verify title, category, project, discipline and required metadata | Document Controller | Trigger: When a company, project or external document enters the controlled-document process. Action: The Document Controller completes “Verify title, category, project, discipline and required metadata” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. Control/Handoff: The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a company, project or external document enters the controlled-document process. | The Document Controller completes “Verify title, category, project, discipline and required metadata” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. | The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he checks the document has the right title, project, discipline and other details so it can be found again. • Starts when: a submission is being processed for registration. • How it runs: (1) he checks the title describes the content accurately. (2) He checks the project, discipline and category are stated and correct. (3) He checks the mandatory metadata fields are complete. (4) He returns submissions with missing or wrong metadata. (5) He records the verified metadata. • Proof it happened: verified metadata against the required fields, with returns recorded where it was incomplete. • Where it usually breaks: titles are vague or inconsistent, so documents cannot be found later and duplicates are created instead. | • Require titles to follow a stated convention, since inconsistent titling is what makes documents unfindable and causes duplicates to be created. • Define the mandatory metadata per document type and reject incomplete submissions rather than filling gaps. • Check the discipline and category against the document content, not just that a value was entered. • Prohibit placeholder values, as these are never corrected once the document is registered. • Keep the metadata list short enough that submitters complete it properly.
1132 | Research & Development | Assign the approved unique document number | Document Controller | Trigger: When a company, project or external document enters the controlled-document process. Action: The Document Controller completes “Assign the approved unique document number” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. Control/Handoff: The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a company, project or external document enters the controlled-document process. | The Document Controller completes “Assign the approved unique document number” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. | The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he gives the document its unique number, which is how it will be referred to for the rest of its life. • Starts when: the submission is verified and ready for registration. • How it runs: (1) he determines the correct number format for the document type. (2) He checks the number has not already been used. (3) He assigns the next available number in sequence. (4) He records the number against the document in the register. (5) He informs the originator of the assigned number. • Proof it happened: an assigned unique document number recorded in the register and communicated to the originator. • Where it usually breaks: numbers are assigned by the originating department rather than centrally, so the same number is used twice. | • Assign all numbers centrally and prohibit departments from self numbering, since duplicate numbers are the single most damaging error in document control. • Never reuse a number, even for a cancelled document, because historical references become ambiguous. • Keep the numbering structure stable, as changing it mid project makes the register unsearchable. • Record the number allocation sequentially, so gaps can be explained. • Communicate the number to the originator immediately, otherwise they continue circulating the document under a working title.
1133 | Research & Development | Register source, receipt date, status, owner and required response date | Document Controller | Trigger: When a company, project or external document enters the controlled-document process. Action: The Document Controller completes “Register source, receipt date, status, owner and required response date” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. Control/Handoff: The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a company, project or external document enters the controlled-document process. | The Document Controller completes “Register source, receipt date, status, owner and required response date” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. | The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he records where the document came from, when it arrived, its status, who owns it and when a response is due. • Starts when: the document number is assigned. • How it runs: (1) he records the source and the receipt date. (2) He records the current status. (3) He records the responsible owner. (4) He records the required response or action date where one applies. (5) He confirms the register entry is complete. • Proof it happened: a complete register entry with source, dates, status, owner and required response date. • Where it usually breaks: the response due date is left blank, so time sensitive documents sit unactioned with nothing flagging them. | • Require a response due date on every document that carries one, since a blank date means nothing will flag the document before the deadline passes. • Derive the due date from the contract or the document itself rather than from convenience, as contractual response periods are binding. • Require a named owner rather than a department, because departmental ownership means nobody acts. • Keep the status values from a defined list, so the register can be filtered and reported. • Require the register to be updated at each status change, not reconstructed later.
1134 | Research & Development | Return incomplete, duplicate or unauthorised submissions for correction | Document Controller | Trigger: When a company, project or external document enters the controlled-document process. Action: The Document Controller completes “Return incomplete, duplicate or unauthorised submissions for correction” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. Control/Handoff: The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a company, project or external document enters the controlled-document process. | The Document Controller completes “Return incomplete, duplicate or unauthorised submissions for correction” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a uniquely registered document with verified ownership, metadata, source, status, due date and correction record where required. | The author owns content accuracy and the approver owns acceptance; the Document Controller verifies administrative control and rejects incomplete, duplicate or unauthorised submissions. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: when a submission is incomplete, duplicated or not properly authorised, he sends it back rather than fixing it himself. • Starts when: a verification check fails. • How it runs: (1) he identifies the specific deficiency. (2) He records the return with the reason. (3) He returns it to the named submitter. (4) He states what is required to resubmit. (5) He tracks the resubmission. • Proof it happened: a return record with the specific reason, the submitter notified and the resubmission tracked. • Where it usually breaks: document control completes the missing information itself to keep things moving, which makes it responsible for content it cannot verify. | • Prohibit document control from completing missing information, since doing so makes the function responsible for content it cannot verify and conceals the originator's error. • Require the return reason to be specific, as a general rejection produces a resubmission with the same problem. • Track returns by originating department, because a high return rate indicates a training need rather than a document control problem. • Set a resubmission deadline, otherwise returned documents disappear. • Escalate repeated deficient submissions to the department head.
1135 | Research & Development | Classify document type, confidentiality, retention and distribution level | Document Controller | Trigger: When a document is registered, revised, reclassified or requires controlled access. Action: The Document Controller completes “Classify document type, confidentiality, retention and distribution level” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a correctly classified, named, numbered and access-controlled document with complete version history and repository index. Control/Handoff: Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a document is registered, revised, reclassified or requires controlled access. | The Document Controller completes “Classify document type, confidentiality, retention and distribution level” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a correctly classified, named, numbered and access-controlled document with complete version history and repository index. | Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he decides how confidential the document is, how long it must be kept and who may receive it. • Starts when: at registration, and when the classification needs review. • How it runs: (1) he determines the document type and its classification. (2) He applies the confidentiality level. (3) He applies the retention period. (4) He sets the distribution level. (5) He records the classification against the document. • Proof it happened: a recorded classification covering type, confidentiality, retention and distribution level. • Where it usually breaks: everything is classified at the same level, so genuinely confidential documents are as widely available as routine ones. | • Define the classification levels with examples, since a scheme applied uniformly to everything provides no protection for what actually matters. • Require confidential classification for commercial, legal and personnel documents by default, with distribution restricted accordingly. • Set retention periods from the legal and contractual requirement rather than by habit, as both under and over retention carry risk. • Require classification at registration, because unclassified documents are never classified later. • Review classification when a document's status changes, such as a tender becoming a contract.
1136 | Research & Development | Apply approved file-naming and folder-structure conventions | Document Controller | Trigger: When a document is registered, revised, reclassified or requires controlled access. Action: The Document Controller completes “Apply approved file-naming and folder-structure conventions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a correctly classified, named, numbered and access-controlled document with complete version history and repository index. Control/Handoff: Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a document is registered, revised, reclassified or requires controlled access. | The Document Controller completes “Apply approved file-naming and folder-structure conventions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a correctly classified, named, numbered and access-controlled document with complete version history and repository index. | Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he names and files the document consistently, so the repository stays navigable. • Starts when: the document is registered and being filed. • How it runs: (1) he applies the approved file naming convention. (2) He places it in the correct folder in the structure. (3) He checks it is not also stored elsewhere. (4) He verifies the file opens and is complete. (5) He records the location in the register. • Proof it happened: documents named and filed per the convention, with the location recorded and the file verified as readable. • Where it usually breaks: documents are stored in several places, so people work from whichever copy they find first. | • Maintain a single controlled location per document and prohibit duplicate storage, since multiple copies guarantee someone works from the wrong one. • Include the revision in the file name, so the version is visible without opening the file. • Verify the file opens and is complete at filing, because corrupt files are discovered when they are urgently needed. • Keep the folder structure aligned to how people search rather than to the organisation chart. • Prohibit personal drive storage of controlled documents, and say so explicitly.
1137 | Research & Development | Assign revision, issue purpose and document-status codes | Document Controller | Trigger: When a document is registered, revised, reclassified or requires controlled access. Action: The Document Controller completes “Assign revision, issue purpose and document-status codes” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a correctly classified, named, numbered and access-controlled document with complete version history and repository index. Control/Handoff: Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a document is registered, revised, reclassified or requires controlled access. | The Document Controller completes “Assign revision, issue purpose and document-status codes” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a correctly classified, named, numbered and access-controlled document with complete version history and repository index. | Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he applies the revision number, the reason it was issued and the status code, so everyone knows what they are looking at. • Starts when: a document is registered or reissued. • How it runs: (1) he determines the correct revision based on the history. (2) He records the issue purpose, such as for review, for approval or for construction. (3) He applies the document status code. (4) He checks the revision does not conflict with an existing issue. (5) He records all three against the document. • Proof it happened: correct revision, issue purpose and status codes recorded and shown on the issued document. • Where it usually breaks: the issue purpose is omitted, so a document issued for review is used for construction. | • Require the issue purpose to be stated on the document itself, since a drawing issued for review and used for construction is one of the most expensive document errors possible. • Increment the revision on every reissue without exception, because two documents bearing the same revision cannot be distinguished. • Use a defined status code list, so status cannot be described in free text. • Check for revision conflicts before issuing, particularly where parallel drafts exist. • Show the revision prominently on the document face, not only in the register.
1138 | Research & Development | Maintain document version history and revision traceability | Document Controller | Trigger: When a document is registered, revised, reclassified or requires controlled access. Action: The Document Controller completes “Maintain document version history and revision traceability” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a correctly classified, named, numbered and access-controlled document with complete version history and repository index. Control/Handoff: Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a document is registered, revised, reclassified or requires controlled access. | The Document Controller completes “Maintain document version history and revision traceability” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a correctly classified, named, numbered and access-controlled document with complete version history and repository index. | Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the full history of a document's versions, so you can see what changed and when. • Starts when: a document is revised, and continuously through its life. • How it runs: (1) he retains the previous version on supersession. (2) He records what changed between revisions. (3) He records the date and the approver for each revision. (4) He maintains the chain so every revision is traceable. (5) He makes the history available when needed. • Proof it happened: a complete version history with change descriptions, dates and approvers for every revision. • Where it usually breaks: superseded versions are deleted, so it becomes impossible to prove what was issued at a given date. | • Retain every superseded version rather than deleting it, since proving what was issued on a given date is frequently the decisive evidence in a dispute. • Require a change description per revision, because a revision history of dates alone does not show what changed. • Mark superseded versions clearly so they cannot be mistaken for current, while remaining retrievable. • Record the approver per revision, as approval authority may differ between revisions. • Keep the history for the full retention period, not only for the project duration.
1139 | Research & Development | Apply approved access, editing and distribution permissions | Document Controller | Trigger: When a document is registered, revised, reclassified or requires controlled access. Action: The Document Controller completes “Apply approved access, editing and distribution permissions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a correctly classified, named, numbered and access-controlled document with complete version history and repository index. Control/Handoff: Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a document is registered, revised, reclassified or requires controlled access. | The Document Controller completes “Apply approved access, editing and distribution permissions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a correctly classified, named, numbered and access-controlled document with complete version history and repository index. | Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he sets who can see, edit and receive each document, in line with its classification. • Starts when: at filing, and when classification or roles change. • How it runs: (1) he applies the access permissions per the classification. (2) He restricts editing to the authorised author and owner. (3) He sets the distribution list. (4) He reviews the permissions when roles change. (5) He records the permissions applied. • Proof it happened: applied and recorded access, editing and distribution permissions consistent with the classification. • Where it usually breaks: edit rights are granted widely so that people can work faster, and the controlled document is altered outside the revision process. | • Restrict edit rights on controlled documents to the author and owner only, since wide edit access means the controlled version can be altered without a revision. • Review permissions on every role change and leaver, as retained access is the standard finding in any audit. • Issue read only copies for distribution, so recipients cannot alter and recirculate. • Record who has access to confidential documents, because otherwise a leak cannot be investigated. • Require permissions to follow the classification automatically rather than being set case by case.
1140 | Research & Development | Maintain the controlled document index and repository structure | Document Controller | Trigger: When a document is registered, revised, reclassified or requires controlled access. Action: The Document Controller completes “Maintain the controlled document index and repository structure” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a correctly classified, named, numbered and access-controlled document with complete version history and repository index. Control/Handoff: Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a document is registered, revised, reclassified or requires controlled access. | The Document Controller completes “Maintain the controlled document index and repository structure” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a correctly classified, named, numbered and access-controlled document with complete version history and repository index. | Confidentiality and access follow approved owner/CLO/IT rules; revision identity cannot be overwritten and any conflict is escalated before issue. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the master index of controlled documents and the structure of the repository they live in. • Starts when: continuously, with formal review at set intervals. • How it runs: (1) he maintains the index of all controlled documents with their current status. (2) He keeps the repository structure consistent with the index. (3) He checks for documents in the repository but not in the index. (4) He checks for indexed documents missing from the repository. (5) He corrects the discrepancies. • Proof it happened: a maintained document index reconciled to the repository, with discrepancies identified and corrected. • Where it usually breaks: the index and the repository drift apart, so the index cannot be trusted and people search the folders directly instead. | • Reconcile the index against the repository at a set frequency in both directions, since drift makes the index untrustworthy and people then bypass it entirely. • Investigate documents found in the repository but not indexed, as these are uncontrolled documents in use. • Make the index the entry point for users, so searching the folders directly is unnecessary. • Show the current revision and status in the index, not only the document title. • Keep the index accessible to everyone who needs documents, because a restricted index drives informal copies.
1141 | Research & Development | Route documents through the approved review and approval workflow | Document Controller | Trigger: When a registered document is ready for review, approval, correction or controlled release. Action: The Document Controller completes “Route documents through the approved review and approval workflow” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. Control/Handoff: The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a registered document is ready for review, approval, correction or controlled release. | The Document Controller completes “Route documents through the approved review and approval workflow” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. | The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he sends the document to the right reviewers and approvers in the right order. • Starts when: a document is registered and requires review or approval. • How it runs: (1) he identifies the required reviewers for the document type. (2) He issues it for review with a deadline. (3) He follows the approval sequence in order. (4) He forwards to the approver once reviews are complete. (5) He records the workflow progress. • Proof it happened: a routing record showing the reviewers, the sequence followed and the workflow progress. • Where it usually breaks: documents are sent to everyone at once to save time, so conflicting comments arrive and nobody resolves them. | • Follow the defined review sequence rather than issuing to everyone simultaneously, since parallel review produces conflicting comments that nobody owns resolving. • Set a review period per document type and state what happens when it expires. • Require the reviewer list to come from the document type definition, not from the author's preference. • Record the routing, so delays can be attributed rather than argued about. • Prohibit approval before the required reviews are complete, and enforce it in the workflow.
1142 | Research & Development | Track reviewer comments, due dates and overdue review actions | Document Controller | Trigger: When a registered document is ready for review, approval, correction or controlled release. Action: The Document Controller completes “Track reviewer comments, due dates and overdue review actions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. Control/Handoff: The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a registered document is ready for review, approval, correction or controlled release. | The Document Controller completes “Track reviewer comments, due dates and overdue review actions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. | The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he chases reviewers, records their comments and flags the reviews that are late. • Starts when: a document is issued for review. • How it runs: (1) he records the review due date per reviewer. (2) He collects the comments as they arrive. (3) He chases the reviewers approaching or past the deadline. (4) He records the overdue reviews. (5) He escalates reviews that remain outstanding. • Proof it happened: a review tracking record with comments received, due dates and overdue reviews escalated. • Where it usually breaks: overdue reviews are chased informally and never escalated, so documents sit in review for months. | • Escalate overdue reviews on a defined timescale rather than chasing indefinitely, since documents stalled in review provide no control while the work continues. • Report review ageing by reviewer, because this is the only way persistent delay gets addressed. • Record comments as received rather than consolidating at the end, so nothing is lost. • State whether silence at the deadline constitutes acceptance, and apply it consistently. • Track review turnaround as a measure, as slow internal review is a common hidden cause of project delay.
1143 | Research & Development | Return consolidated review comments to the document author | Document Controller | Trigger: When a registered document is ready for review, approval, correction or controlled release. Action: The Document Controller completes “Return consolidated review comments to the document author” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. Control/Handoff: The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a registered document is ready for review, approval, correction or controlled release. | The Document Controller completes “Return consolidated review comments to the document author” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. | The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he collects all the review comments together and gives them back to the author in one set. • Starts when: the review period closes or all reviews are received. • How it runs: (1) he consolidates the comments from all reviewers. (2) He identifies conflicting comments. (3) He refers conflicts back for resolution rather than deciding them. (4) He issues the consolidated set to the author. (5) He tracks the author's response to each comment. • Proof it happened: a consolidated comment set issued to the author, with conflicts referred and responses tracked per comment. • Where it usually breaks: comments are passed on piecemeal, so the author revises several times and reviewers see different versions. | • Consolidate and issue comments once, since piecemeal comments cause repeated revision cycles and reviewers then comment on different versions. • Refer conflicting technical comments back to the reviewers rather than deciding, because document control must not resolve technical disagreement. • Require the author to respond to each comment individually, so nothing is silently ignored. • Track unresolved comments as open items, as these are what resurface after approval. • Retain the comment set with the document, since the comment history explains why the document says what it says.
1144 | Research & Development | Verify approval evidence, authority, signatures and release conditions | Document Controller | Trigger: When a registered document is ready for review, approval, correction or controlled release. Action: The Document Controller completes “Verify approval evidence, authority, signatures and release conditions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. Control/Handoff: The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a registered document is ready for review, approval, correction or controlled release. | The Document Controller completes “Verify approval evidence, authority, signatures and release conditions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. | The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: before issuing he checks the document really is approved, by the right person, and that any conditions are met. • Starts when: a document is returned as approved and ready for issue. • How it runs: (1) he checks the approval is present and legible. (2) He checks the approver holds the authority for that document. (3) He checks the signature or electronic approval is valid. (4) He checks any conditions attached to the approval are satisfied. (5) He confirms the document is releasable. • Proof it happened: verified approval evidence with the authority confirmed, signatures valid and release conditions satisfied. • Where it usually breaks: a document approved with conditions is issued as unconditionally approved, so the conditions are never met. | • Treat a conditional approval as not releasable until the conditions are evidenced, since issuing it as approved means the conditions are never satisfied. • Verify the approver's authority at the point of issue, not only at routing, because approvers change during long review cycles. • Reject illegible or undated approvals rather than accepting them, as these fail in audit and dispute. • Require the approval to reference the specific revision, so an approval cannot be carried across to a later version. • Record the verification, making the check evidenced rather than assumed.
1145 | Research & Development | Issue only the approved controlled document version | Document Controller | Trigger: When a registered document is ready for review, approval, correction or controlled release. Action: The Document Controller completes “Issue only the approved controlled document version” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. Control/Handoff: The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a registered document is ready for review, approval, correction or controlled release. | The Document Controller completes “Issue only the approved controlled document version” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. | The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he issues only the approved version, never a draft or a working copy. • Starts when: the document is verified as approved and releasable. • How it runs: (1) he confirms the version being issued is the approved one. (2) He applies the controlled issue marking. (3) He converts it to the distribution format. (4) He checks the issued file against the approved version. (5) He releases it for distribution. • Proof it happened: the issued document matching the approved version, in controlled format, with the pre issue check recorded. • Where it usually breaks: a later working copy is issued by mistake, so the document in circulation was never approved. | • Require a check of the file being issued against the approved version immediately before release, since issuing an unapproved working copy puts uncontrolled information into circulation. • Prohibit issue of drafts to external parties in any circumstance, and name who may authorise an exception internally. • Issue in a non editable format, so recipients cannot alter and recirculate. • Mark controlled copies distinctly from uncontrolled ones, because recipients cannot otherwise tell. • Keep the issued file itself as the record, not a link to a location whose content can change.
1146 | Research & Development | Record approval, issue, status and supersession evidence | Document Controller | Trigger: When a registered document is ready for review, approval, correction or controlled release. Action: The Document Controller completes “Record approval, issue, status and supersession evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. Control/Handoff: The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a registered document is ready for review, approval, correction or controlled release. | The Document Controller completes “Record approval, issue, status and supersession evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a completed review trail, consolidated comments, approval evidence, controlled issue and recorded status/supersession link. | The Document Controller never approves technical, legal, commercial or financial content; only the authorised approver may release content, and overdue or rejected reviews return to the owner. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he records that the document was approved and issued, and that the previous version is now superseded. • Starts when: the document is issued. • How it runs: (1) he records the approval date and the approver. (2) He records the issue date and the revision. (3) He updates the document status. (4) He marks the previous version superseded. (5) He confirms the register reflects the current position. • Proof it happened: register entries recording approval, issue, current status and supersession of the previous version. • Where it usually breaks: the previous version is not marked superseded, so both versions appear current in the register. | • Mark the previous version superseded in the same action as issuing the new one, since two versions appearing current is exactly how the wrong drawing reaches site. • Record the approval date and the issue date separately, as the gap between them matters in delay analysis. • Require the status to be updated at issue rather than in a later housekeeping pass. • Keep supersession traceable, so the chain from first issue to current is visible. • Reconcile current status entries periodically, to catch documents left in a transitional status.
1147 | Research & Development | Prepare controlled document transmittals with complete issue details | Document Controller | Trigger: When an approved document or correspondence requires internal or external transmission and response tracking. Action: The Document Controller completes “Prepare controlled document transmittals with complete issue details” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. Control/Handoff: Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an approved document or correspondence requires internal or external transmission and response tracking. | The Document Controller completes “Prepare controlled document transmittals with complete issue details” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. | Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he prepares the transmittal, the formal cover note that records exactly what is being sent and why. • Starts when: an approved document is ready for distribution. • How it runs: (1) he lists the documents with their numbers and revisions. (2) He states the issue purpose. (3) He states the recipients and the action required. (4) He states any response deadline. (5) He issues the transmittal with the documents. • Proof it happened: a complete transmittal listing document numbers, revisions, purpose, recipients, action and deadlines. • Where it usually breaks: revisions are omitted from the transmittal, so what was actually sent cannot be proven later. | • Require the revision of every document to be stated on the transmittal, since the transmittal is the primary evidence of what was issued and when. • State the action required and the response deadline, because a transmittal without them creates no obligation on the recipient. • Number transmittals sequentially, as gaps and duplicates undermine their evidential value. • Require the issue purpose on the transmittal as well as on the document. • Retain the transmittal with the issued files, so the record is self contained.
1148 | Research & Development | Distribute approved documents to authorised internal and external recipients | Document Controller | Trigger: When an approved document or correspondence requires internal or external transmission and response tracking. Action: The Document Controller completes “Distribute approved documents to authorised internal and external recipients” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. Control/Handoff: Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an approved document or correspondence requires internal or external transmission and response tracking. | The Document Controller completes “Distribute approved documents to authorised internal and external recipients” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. | Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he sends the approved documents to the people entitled to receive them, inside and outside the company. • Starts when: the transmittal is prepared and ready for issue. • How it runs: (1) he confirms the recipient list against the distribution matrix. (2) He confirms external recipients are authorised to receive the content. (3) He issues through the approved channel. (4) He confirms delivery. (5) He records the distribution. • Proof it happened: a distribution record showing authorised recipients, the channel used and delivery confirmed. • Where it usually breaks: confidential commercial documents are distributed on a standard project list, so information reaches parties who should not have it. | • Check the recipient list against the document's confidentiality level rather than using a standard project list, since this is how commercial information reaches the wrong parties. • Require authorisation for any new external recipient, because distribution lists otherwise grow without review. • Use the approved channel only, as documents issued from personal email are outside the record entirely. • Review distribution lists periodically, since leavers and replaced consultants persist on them. • Record what each recipient received, as partial distribution is a common cause of parties working from different information.
1149 | Research & Development | Record recipients, issue dates, acknowledgements and delivery evidence | Document Controller | Trigger: When an approved document or correspondence requires internal or external transmission and response tracking. Action: The Document Controller completes “Record recipients, issue dates, acknowledgements and delivery evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. Control/Handoff: Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an approved document or correspondence requires internal or external transmission and response tracking. | The Document Controller completes “Record recipients, issue dates, acknowledgements and delivery evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. | Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he records who received what, when, and gets confirmation they received it. • Starts when: documents are distributed. • How it runs: (1) he records the recipient, the document and the issue date. (2) He requests acknowledgement where required. (3) He records the acknowledgements received. (4) He chases missing acknowledgements. (5) He retains the delivery evidence. • Proof it happened: a distribution register with recipients, dates, acknowledgements and retained delivery evidence. • Where it usually breaks: acknowledgements are not obtained, so a recipient can later deny having received a drawing or instruction. | • Require acknowledgement for contractually significant issues, since a recipient denying receipt of a drawing or instruction is a common and costly dispute. • Chase unacknowledged issues rather than assuming delivery, and record the chase. • Retain the delivery evidence itself, as a register entry alone may not be accepted as proof. • Record partial or failed deliveries, because these are what cause parties to work from superseded information. • Keep the register for the full retention period, as these questions arise years later.
1150 | Research & Development | Register incoming client, consultant, authority and supplier correspondence | Document Controller | Trigger: When an approved document or correspondence requires internal or external transmission and response tracking. Action: The Document Controller completes “Register incoming client, consultant, authority and supplier correspondence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. Control/Handoff: Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an approved document or correspondence requires internal or external transmission and response tracking. | The Document Controller completes “Register incoming client, consultant, authority and supplier correspondence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. | Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he registers every letter and formal message coming in from clients, consultants, authorities and suppliers. • Starts when: incoming correspondence is received through any channel. • How it runs: (1) he registers it with the date, sender and subject. (2) He identifies whether it carries a contractual or time bound requirement. (3) He assigns it to the responsible owner. (4) He records the response due date. (5) He tracks it until the response is issued. • Proof it happened: a correspondence register with dates, senders, subjects, owners and response due dates. • Where it usually breaks: correspondence received directly by individuals is never registered, so contractual notices are missed entirely. | • Require all project correspondence to be registered regardless of who received it, since unregistered client correspondence is how contractual notice periods are missed. • Flag correspondence carrying a contractual time limit at registration, because these are the ones with real consequences. • Record the received date, as this is what starts any response period. • Assign a named owner immediately rather than leaving it to be picked up. • Train the team that forwarding to document control is mandatory, not optional courtesy.
1151 | Research & Development | Register approved outgoing company and project correspondence | Document Controller | Trigger: When an approved document or correspondence requires internal or external transmission and response tracking. Action: The Document Controller completes “Register approved outgoing company and project correspondence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. Control/Handoff: Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an approved document or correspondence requires internal or external transmission and response tracking. | The Document Controller completes “Register approved outgoing company and project correspondence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. | Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he registers the letters the company sends out, once they have been approved. • Starts when: approved outgoing correspondence is ready for issue. • How it runs: (1) he confirms the correspondence is approved by the authorised signatory. (2) He assigns the reference number. (3) He registers it with the date, recipient and subject. (4) He issues it through the approved channel. (5) He retains the issued copy and the delivery evidence. • Proof it happened: an outgoing correspondence register with references, dates, recipients and retained issued copies. • Where it usually breaks: letters are sent directly by individuals without registration, so the company has no record of its own contractual position. | • Require all external project correspondence to be issued through document control, since letters sent directly leave the company unable to evidence its own contractual position. • Verify the signatory's authority before issue, as unauthorised correspondence can bind the company. • Number outgoing correspondence sequentially, because gaps suggest withheld documents in any dispute. • Retain the issued version rather than the draft, as these frequently differ. • Record the delivery evidence, particularly for notices with contractual effect.
1152 | Research & Development | Track correspondence response owners, commitments, due dates and closure | Document Controller | Trigger: When an approved document or correspondence requires internal or external transmission and response tracking. Action: The Document Controller completes “Track correspondence response owners, commitments, due dates and closure” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. Control/Handoff: Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an approved document or correspondence requires internal or external transmission and response tracking. | The Document Controller completes “Track correspondence response owners, commitments, due dates and closure” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled transmittal or correspondence record with authorised recipients, delivery evidence, response owner, due date and closure status. | Only approved content is distributed; client/consultant commitments remain with the responsible functional owner, and failed delivery or overdue response is escalated according to project priority. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he tracks what the company has promised in its correspondence and whether it has been delivered. • Starts when: correspondence is registered, incoming or outgoing. • How it runs: (1) he identifies the commitments and required responses. (2) He records the owner and the due date for each. (3) He tracks progress against the due dates. (4) He escalates overdue items. (5) He records closure with the evidence. • Proof it happened: a commitment register with owners, due dates, escalations and recorded closure evidence. • Where it usually breaks: commitments made in letters are never tracked, so the company fails to deliver what it has stated in writing. | • Extract commitments from outgoing correspondence into the tracker, since a promise made in a letter and forgotten is both a contractual and a reputational failure. • Prioritise items with contractual time limits and flag them distinctly. • Escalate overdue responses to the project manager, as a missed response can constitute deemed acceptance. • Require closure evidence rather than a status change, so closure is verifiable. • Report open and overdue commitments weekly, because these age invisibly.
1153 | Research & Development | Maintain the project drawing and revision register | Document Controller | Trigger: When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. Action: The Document Controller completes “Maintain the project drawing and revision register” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current project technical register, controlled submission, response status and complete IFC handover evidence. Control/Handoff: CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. | The Document Controller completes “Maintain the project drawing and revision register” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current project technical register, controlled submission, response status and complete IFC handover evidence. | CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the register of every project drawing and which revision is current. • Starts when: drawings are first issued, and on every revision. • How it runs: (1) he records each drawing with its number and title. (2) He records the current revision and its issue date. (3) He records the issue purpose and status. (4) He updates it on every reissue and marks supersession. (5) He reconciles the register against what site is actually holding. • Proof it happened: a drawing register showing current revisions, issue dates, purposes and supersession status, reconciled with site. • Where it usually breaks: the register is current but site is still working from an earlier revision, because reconciliation never happens. | • Reconcile the register against the drawings physically held at site periodically, since a correct register does not prevent construction from a superseded revision. • Require confirmation that superseded drawings were withdrawn at site, not merely that new ones were issued. • Show the issue purpose in the register, so drawings issued for review are not mistaken for construction issues. • Make the register available to site in a form they will actually check. • Highlight recently revised drawings, as these are the ones most likely to cause rework.
1154 | Research & Development | Maintain specifications, BOQ, schedule and technical-document registers | Document Controller | Trigger: When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. Action: The Document Controller completes “Maintain specifications, BOQ, schedule and technical-document registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current project technical register, controlled submission, response status and complete IFC handover evidence. Control/Handoff: CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. | The Document Controller completes “Maintain specifications, BOQ, schedule and technical-document registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current project technical register, controlled submission, response status and complete IFC handover evidence. | CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the registers for specifications, bills of quantities, schedules and other technical documents. • Starts when: these documents are first issued, and on every revision. • How it runs: (1) he registers each document with its number and revision. (2) He records the issue and approval status. (3) He records the relationships to drawings and packages. (4) He updates on revision with supersession. (5) He reconciles the set for completeness. • Proof it happened: maintained technical document registers with revisions, status and package relationships, reconciled for completeness. • Where it usually breaks: the specification is revised without the affected drawings being identified, so the two no longer agree. | • Record the relationship between specifications, BOQ items and drawings, since a specification revised in isolation creates contradictions that surface as claims. • Require the affected documents to be identified on every revision, so the full impact is visible. • State the order of precedence between document types, because contradictions are inevitable. • Notify Procurement and Estimating of specification revisions, as these change what has been priced. • Reconcile the set for completeness, since a missing specification section is discovered at the worst moment.
1155 | Research & Development | Maintain material, shop-drawing and technical-submittal status registers | Document Controller | Trigger: When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. Action: The Document Controller completes “Maintain material, shop-drawing and technical-submittal status registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current project technical register, controlled submission, response status and complete IFC handover evidence. Control/Handoff: CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. | The Document Controller completes “Maintain material, shop-drawing and technical-submittal status registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current project technical register, controlled submission, response status and complete IFC handover evidence. | CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he tracks material and shop drawing submittals and where each one stands in approval. • Starts when: a submittal is received for processing. • How it runs: (1) he registers the submittal with its reference and subject. (2) He records the submission date and the review due date. (3) He routes it for review and tracks progress. (4) He records the outcome: approved, approved with comments or rejected. (5) He tracks resubmissions to final approval. • Proof it happened: a submittal register with submission dates, review status, outcomes and resubmission tracking. • Where it usually breaks: the register records submission but not the approval outcome, so a rejected submittal looks the same as an approved one. | • Record the approval outcome and not only the submission, since a rejected submittal indistinguishable from an approved one is worse than no register at all. • Show the ageing of submittals awaiting review, because internal and consultant review delay is a major hidden cause of late delivery. • Track resubmission cycles per item, as repeated rejection indicates a supplier who does not understand the specification. • Link submittals to the affected procurement packages, so approval delay is visible to Procurement. • Escalate submittals overdue beyond a stated period rather than continuing to chase.
1156 | Research & Development | Maintain RFI, technical-clarification and response registers | Document Controller | Trigger: When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. Action: The Document Controller completes “Maintain RFI, technical-clarification and response registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current project technical register, controlled submission, response status and complete IFC handover evidence. Control/Handoff: CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. | The Document Controller completes “Maintain RFI, technical-clarification and response registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current project technical register, controlled submission, response status and complete IFC handover evidence. | CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he tracks the questions raised to the consultant or client and the answers received. • Starts when: an RFI or clarification is raised. • How it runs: (1) he registers it with the question, the date and the required response date. (2) He issues it to the recipient. (3) He tracks the response. (4) He records the answer and distributes it. (5) He identifies where the answer changes the design or the cost. • Proof it happened: an RFI register with questions, dates, responses and identification of answers with design or cost impact. • Where it usually breaks: an answer that changes the design is filed as a response rather than triggering a drawing revision or a variation. | • Flag every response that changes the design, scope or cost, since an RFI answer filed without a consequent revision or variation loses both the design control and the entitlement. • Track response ageing, as an unanswered RFI blocking work is a claimable delay only if it is evidenced. • Require the question to be specific and self contained, because vague RFIs generate vague answers and further rounds. • Distribute answers to everyone affected, not only the originator. • Link RFIs to the affected drawings, so the design record is complete.
1157 | Research & Development | Maintain authority, client and consultant submission and approval registers | Document Controller | Trigger: When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. Action: The Document Controller completes “Maintain authority, client and consultant submission and approval registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current project technical register, controlled submission, response status and complete IFC handover evidence. Control/Handoff: CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. | The Document Controller completes “Maintain authority, client and consultant submission and approval registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current project technical register, controlled submission, response status and complete IFC handover evidence. | CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he tracks what has been submitted to authorities, clients and consultants, and what has come back approved. • Starts when: a submission is prepared for an external party. • How it runs: (1) he registers the submission with the date and the recipient. (2) He records what was submitted, including revisions. (3) He tracks the review and approval. (4) He records the outcome and any conditions imposed. (5) He distributes the approval and its conditions. • Proof it happened: submission and approval registers with dates, content, outcomes and any conditions recorded. • Where it usually breaks: approval conditions are recorded in the register but never extracted into an action list, so the conditions are not complied with. | • Extract every approval condition into a tracked action list with owners, since conditions recorded but not actioned are a compliance failure waiting to be found at inspection. • Record exactly what was submitted, including revisions, because approvals apply to specific submitted versions. • Track submission ageing, as authority approval is often the longest lead item in a project. • Distribute approvals with their conditions to everyone affected, not only to the submitter. • Keep authority approvals accessible, as these are demanded at inspection and at handover.
1158 | Research & Development | Control IFC handover completeness, revision alignment and transmittal evidence | Document Controller | Trigger: When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. Action: The Document Controller completes “Control IFC handover completeness, revision alignment and transmittal evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current project technical register, controlled submission, response status and complete IFC handover evidence. Control/Handoff: CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a drawing, BOQ, specification, submittal, RFI, authority submission or IFC package is created, revised or returned. | The Document Controller completes “Control IFC handover completeness, revision alignment and transmittal evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current project technical register, controlled submission, response status and complete IFC handover evidence. | CTO and discipline owners certify technical content, COO accepts the construction handover, and the Document Controller controls completeness, revision alignment, distribution and traceability. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he controls the issued for construction handover, making sure the set is complete and the revisions all match. • Starts when: a design package is released for construction. • How it runs: (1) he checks the IFC set is complete against the drawing list. (2) He checks the revisions are consistent across disciplines. (3) He checks all required approvals are in place. (4) He prepares the transmittal with the full listing. (5) He obtains site acknowledgement of receipt. • Proof it happened: a complete IFC handover with revision alignment checked, approvals confirmed and site acknowledgement obtained. • Where it usually breaks: disciplines are issued at different revisions, so site builds from an architectural drawing that does not match the structural one. | • Check revision alignment across disciplines before IFC release, since building from a matched architectural and unmatched structural set is a direct cause of rework and safety risk. • Check completeness against the drawing list rather than against what was submitted, so missing drawings are identified. • Require site acknowledgement of the IFC set, because this is the record that construction had the correct information. • Confirm all approvals are in place, as issuing unapproved drawings for construction transfers the risk to the company. • Require superseded revisions to be withdrawn at site with confirmation, not merely superseded in the register.
1159 | Research & Development | Maintain the controlled SOP register and scheduled-review status | Document Controller | Trigger: When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. Action: The Document Controller completes “Maintain the controlled SOP register and scheduled-review status” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. Control/Handoff: CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. | The Document Controller completes “Maintain the controlled SOP register and scheduled-review status” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. | CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the register of all SOPs and when each is due for review. • Starts when: an SOP is approved, and continuously as review dates approach. • How it runs: (1) he registers each approved SOP with its number, owner and version. (2) He records the approval date and the next review date. (3) He flags SOPs approaching or past review. (4) He notifies the owners and R&D. (5) He updates the register on each revision. • Proof it happened: a controlled SOP register with versions, owners, approval dates and review status flagged. • Where it usually breaks: SOPs pass their review date and stay in use unreviewed, because nothing flags them. | • Flag and report SOPs past their review date as a compliance exception, since an unreviewed SOP in active use is a control the company believes it has and does not. • Record the owner per SOP, because review requires the owner and an unowned SOP is never reviewed. • Notify owners in advance of the review date rather than after it passes. • Show the version in the register so users can confirm they hold the current one. • Reconcile the register against the process inventory, to identify processes with no SOP at all.
1160 | Research & Development | Maintain controlled policies, manuals and governance documents | Document Controller | Trigger: When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. Action: The Document Controller completes “Maintain controlled policies, manuals and governance documents” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. Control/Handoff: CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. | The Document Controller completes “Maintain controlled policies, manuals and governance documents” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. | CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the policies, manuals and governance documents under control, so the current versions are known. • Starts when: a policy or manual is approved, and on each revision. • How it runs: (1) he registers each document with its version and approval. (2) He records the approving authority. (3) He issues the current version and withdraws the previous. (4) He records the distribution. (5) He tracks the review dates. • Proof it happened: a controlled register of policies, manuals and governance documents with versions, approvals and distribution recorded. • Where it usually breaks: an old policy version stays in circulation, so people comply with rules the company has already changed. | • Require explicit withdrawal of superseded policy versions with recipients notified, since compliance with a withdrawn policy is a real and common failure. • Record the approving authority per policy, as policies approved below the required level are unenforceable. • Distribute policies to everyone bound by them, not only to the owning department. • Record acknowledgement for policies with disciplinary consequences, because enforcement requires evidence the person was informed. • Track review dates, as policies referencing outdated law or structure are worse than none.
1161 | Research & Development | Maintain approved forms, templates, checklists and work instructions | Document Controller | Trigger: When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. Action: The Document Controller completes “Maintain approved forms, templates, checklists and work instructions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. Control/Handoff: CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. | The Document Controller completes “Maintain approved forms, templates, checklists and work instructions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. | CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the forms, templates, checklists and work instructions controlled, so people use the current versions. • Starts when: a form or template is approved, and on each revision. • How it runs: (1) he registers each with its version and owner. (2) He issues from a single controlled location. (3) He withdraws superseded versions. (4) He notifies users of changes. (5) He tracks usage and review. • Proof it happened: a controlled forms and templates register with versions issued from a single location and superseded versions withdrawn. • Where it usually breaks: old forms remain on personal drives, so submissions arrive on outdated templates missing required fields. | • Require forms to be used from the controlled location and prohibit personal copies, since old versions miss the fields that were added for a reason. • Reject submissions on withdrawn versions rather than accepting and reworking them, as acceptance perpetuates the problem. • Notify users of changes with a summary of what changed, so they know why the form is different. • Keep a version history, because knowing which version applied at a given date matters in a dispute. • Review forms that capture consent or contractual terms with Legal.
1162 | Research & Development | Maintain controlled organisation charts, job descriptions and process maps | Document Controller | Trigger: When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. Action: The Document Controller completes “Maintain controlled organisation charts, job descriptions and process maps” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. Control/Handoff: CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. | The Document Controller completes “Maintain controlled organisation charts, job descriptions and process maps” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. | CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the organisation charts, job descriptions and process maps controlled and current. • Starts when: these documents are approved, and on organisational change. • How it runs: (1) he registers each with its version and approval. (2) He issues the current versions. (3) He withdraws superseded versions on change. (4) He records the distribution. (5) He flags documents not reviewed after an organisational change. • Proof it happened: a controlled register of charts, job descriptions and process maps with current versions issued and superseded ones withdrawn. • Where it usually breaks: the organisation changes but the charts and job descriptions do not, so decisions are justified using an outdated structure. | • Trigger a review of charts, job descriptions and process maps on every organisational change, since an outdated chart is used to justify decisions long after it is wrong. • Record the approval date prominently, so users can see how current the document is. • Reconcile job descriptions against the authority matrix, as these frequently contradict each other. • Issue job descriptions to the post holder and record it, because enforcement of duties requires evidence of issue. • Flag documents unreviewed beyond a stated period.
1163 | Research & Development | Maintain RACI, authority, approval and responsibility matrices | Document Controller | Trigger: When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. Action: The Document Controller completes “Maintain RACI, authority, approval and responsibility matrices” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. Control/Handoff: CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. | The Document Controller completes “Maintain RACI, authority, approval and responsibility matrices” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. | CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the responsibility and authority matrices controlled, since these define who may decide what. • Starts when: a matrix is approved, and on every authority or role change. • How it runs: (1) he registers each matrix with its version and approval. (2) He issues the current version to all affected roles. (3) He withdraws the previous version explicitly. (4) He records the distribution and acknowledgements. (5) He flags matrices due for review. • Proof it happened: controlled authority and responsibility matrices with versions, approvals, distribution and withdrawal of previous versions. • Where it usually breaks: two versions of the authority matrix are in circulation, so approvals are taken against whichever limits are convenient. | • Require explicit withdrawal of the previous authority matrix with confirmation, since two versions in circulation means approvals are taken against whichever is convenient. • Record acknowledgement by every affected approver, because authority limits are only enforceable if the approver was informed. • Show the effective date on the matrix, as this determines which version governs a past decision. • Notify the system administrator on every change, so workflow limits are updated in step. • Keep superseded versions retrievable, since the limits in force at the time of a past decision may be questioned.
1164 | Research & Development | Maintain controlled standards, references and supporting corporate records | Document Controller | Trigger: When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. Action: The Document Controller completes “Maintain controlled standards, references and supporting corporate records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. Control/Handoff: CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When an SOP, policy, form, organisation record, matrix or corporate reference is approved, revised or scheduled for review. | The Document Controller completes “Maintain controlled standards, references and supporting corporate records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a current controlled corporate-document register with owner, approver, revision, effective date, review date and linked superseded version. | CRO governs SOP/process standards, CPCO owns people records, CLO owns legal records and each functional owner approves content; the Document Controller administers the official version. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the standards, codes and reference documents the company works to, and makes sure they are current editions. • Starts when: a standard is adopted, and when new editions are published. • How it runs: (1) he registers each standard with its edition and date. (2) He records which processes and projects rely on it. (3) He monitors for new editions. (4) He notifies the technical owners of updates. (5) He replaces superseded editions in the controlled set. • Proof it happened: a controlled standards register with editions, dependencies recorded and superseded editions replaced. • Where it usually breaks: the company works to a superseded edition of a code, which is discovered at an authority inspection. | • Monitor for new editions of the standards the company relies on, since designing or building to a superseded code is discovered at inspection when correction is most expensive. • Record which contracts specify which edition, because the contractual edition governs rather than the latest. • Notify the technical owners of changes rather than only updating the register. • Retain superseded editions, as projects designed under them remain governed by them. • Control access, since many standards are licensed and uncontrolled copying is a breach.
1165 | Research & Development | Register and issue approved meeting agendas, minutes and attendance records | Document Controller | Trigger: When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. Action: The Document Controller completes “Register and issue approved meeting agendas, minutes and attendance records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. Control/Handoff: Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. | The Document Controller completes “Register and issue approved meeting agendas, minutes and attendance records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. | Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he registers and issues the meeting agendas, minutes and attendance records. • Starts when: a meeting is scheduled, and after it is held. • How it runs: (1) he registers and issues the agenda before the meeting. (2) He records the attendance. (3) He registers the minutes once approved. (4) He issues the minutes to the attendees and those affected. (5) He extracts the actions into the action register. • Proof it happened: registered agendas, attendance records and approved minutes issued, with actions extracted into the register. • Where it usually breaks: minutes are issued but the actions in them are never extracted, so decisions are recorded and nothing happens. | • Extract every action from the minutes into the tracked action register, since actions that live only in minutes are not managed and do not get done. • Require minutes to be issued within a stated period, because minutes issued weeks later are disputed and useless. • Record attendance, as decisions taken without the accountable person present are frequently reopened. • Require minutes to record decisions distinctly from discussion, so the decision is unambiguous. • Issue minutes to those affected, not only to attendees.
1166 | Research & Development | Maintain the cross-department and project action registers | Document Controller | Trigger: When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. Action: The Document Controller completes “Maintain the cross-department and project action registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. Control/Handoff: Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. | The Document Controller completes “Maintain the cross-department and project action registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. | Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the action registers across departments and projects, so agreed actions are tracked to closure. • Starts when: actions are raised, and continuously until closed. • How it runs: (1) he records each action with its owner, source and due date. (2) He updates the status as it progresses. (3) He flags and reports overdue actions. (4) He records closure with evidence. (5) He carries open actions to the next review. • Proof it happened: maintained action registers with owners, due dates, status, escalations and closure evidence. • Where it usually breaks: actions accumulate without closure, so the register becomes too long to be useful and is abandoned. | • Require closure evidence rather than a status change, since actions marked done without evidence are how registers lose credibility and get abandoned. • Show ageing on every action, because an action overdue by six months needs a decision rather than another reminder. • Require a named individual owner, as departmental ownership means nobody acts. • Escalate on a defined timescale rather than repeating reminders indefinitely. • Report the overdue list to the accountable chief, which is what actually drives closure.
1167 | Research & Development | Maintain executive, technical and project decision registers | Document Controller | Trigger: When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. Action: The Document Controller completes “Maintain executive, technical and project decision registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. Control/Handoff: Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. | The Document Controller completes “Maintain executive, technical and project decision registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. | Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the record of decisions taken, at executive, technical and project level. • Starts when: a decision is taken that others will rely on. • How it runs: (1) he records the decision with its date and the decision maker. (2) He records the basis and the information relied on. (3) He records what it supersedes where applicable. (4) He distributes it to those affected. (5) He keeps it retrievable for future reference. • Proof it happened: decision registers recording the decision, date, decision maker, basis and distribution. • Where it usually breaks: decisions are taken in conversation and never recorded, so they are revisited repeatedly with different outcomes. | • Record the basis of the decision as well as the decision, since without it the decision is reopened whenever circumstances are questioned. • Record the decision maker by name and role, as authority to decide may later be challenged. • Record what the decision supersedes, otherwise contradictory decisions coexist. • Distribute decisions to everyone who must act on them, not only to those present. • Keep the register searchable, because its value is in being found years later.
1168 | Research & Development | Maintain risk, assumption, issue, constraint and change registers | Document Controller | Trigger: When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. Action: The Document Controller completes “Maintain risk, assumption, issue, constraint and change registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. Control/Handoff: Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. | The Document Controller completes “Maintain risk, assumption, issue, constraint and change registers” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. | Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he keeps the registers of risks, assumptions, issues, constraints and changes. • Starts when: items are identified, and continuously as they change. • How it runs: (1) he records each item with its owner and description. (2) He records the assessment and the mitigation or response. (3) He updates the status as it evolves. (4) He flags items needing review or escalation. (5) He reports the registers at the review cycle. • Proof it happened: maintained risk, assumption, issue, constraint and change registers with owners, assessments and current status. • Where it usually breaks: the registers are created at project start and never updated, so they describe the risks as they were understood on day one. | • Require the registers to be reviewed at a fixed frequency, since registers created at project start and never updated describe risks as understood on day one. • Require assumptions to be tested and either confirmed or converted to risks, because unvalidated assumptions are the commonest source of surprise. • Show ageing, as a risk unchanged for months has either been accepted silently or forgotten. • Require closed items to state how they were resolved, so the register carries learning value. • Report the top items to the project manager rather than the whole register.
1169 | Research & Development | Register daily, weekly and monthly project reports | Document Controller | Trigger: When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. Action: The Document Controller completes “Register daily, weekly and monthly project reports” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. Control/Handoff: Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. | The Document Controller completes “Register daily, weekly and monthly project reports” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. | Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he registers the routine project reports, so the reporting record is complete and traceable. • Starts when: daily, weekly and monthly reports are issued. • How it runs: (1) he receives the reports from the responsible parties. (2) He registers each with its date and period. (3) He identifies missing reports and chases them. (4) He files them in the controlled location. (5) He confirms the reporting set is complete for the period. • Proof it happened: a report register with all periodic reports received, missing ones chased and the set filed completely. • Where it usually breaks: missing daily reports are never chased, and the gap becomes critical when a delay claim depends on that day's record. | • Chase missing daily reports the same week, since a gap in the daily record becomes decisive when a delay claim turns on what happened that day. • Report completeness as a measure, because nobody notices a missing report until it is needed. • Require reports to be submitted rather than collected, with a stated deadline. • File reports where they can be retrieved by date and project, as these are the primary contemporaneous evidence. • Retain them for the full retention period, not only for the project duration.
1170 | Research & Development | Register approvals, inspections, tests, certificates and completion evidence | Document Controller | Trigger: When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. Action: The Document Controller completes “Register approvals, inspections, tests, certificates and completion evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. Control/Handoff: Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a meeting, decision, action, risk, change, report, inspection or certificate record is approved for control. | The Document Controller completes “Register approvals, inspections, tests, certificates and completion evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a registered and searchable evidence record linked to the correct project/process, owner, date, status and required follow-up. | Meeting chairs and functional owners approve content and actions; the Document Controller maintains evidence and status without changing substantive decisions or accountable owners. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he registers the approvals, inspections, tests and certificates that prove the work was done correctly. • Starts when: an approval, inspection result or certificate is produced. • How it runs: (1) he registers each with its reference, date and subject. (2) He records what element or location it covers. (3) He checks it is signed and complete. (4) He identifies missing records against the requirement list. (5) He files them for the closeout dossier. • Proof it happened: a register of approvals, inspections, tests and certificates with coverage recorded and gaps identified. • Where it usually breaks: records are filed without checking they are signed and dated, and the gaps are discovered at handover when they cannot be fixed. | • Check each record is signed, dated and traceable to a location at registration, since an unsigned certificate discovered at handover cannot usually be rectified. • Reconcile against the required record list progressively, because end loading this check is the standard cause of handover delay. • Record the element and location covered, as a certificate that cannot be tied to work proves nothing. • Report the completeness percentage monthly, so the gap is visible while it can still be closed. • Chase missing records from subcontractors before they demobilise.
1171 | Research & Development | Register document-change requests and affected-document references | Document Controller | Trigger: When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. Action: The Document Controller completes “Register document-change requests and affected-document references” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. Control/Handoff: Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. | The Document Controller completes “Register document-change requests and affected-document references” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. | Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he registers requests to change documents and identifies which other documents are affected. • Starts when: a document change request is raised. • How it runs: (1) he registers the request with the reason and the requester. (2) He identifies the document to be changed. (3) He identifies the other documents referencing or depending on it. (4) He records the affected document list. (5) He routes it for impact assessment. • Proof it happened: a change request register with the affected document references identified and recorded. • Where it usually breaks: only the primary document is changed, so the drawings, specifications and forms that referenced it now contradict it. | • Require the affected document list to be produced for every change, since changing one document and leaving its dependants creates contradictions that surface as claims. • Maintain cross references between documents so the affected list can actually be produced. • Require the requester to state the reason, as this determines whether the change is necessary. • Register all requests centrally, so parallel changes to the same document are detected. • Track requests to closure, because an open change request means the current document is known to be wrong.
1172 | Research & Development | Verify change impact, dependencies and required reapproval route | Document Controller | Trigger: When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. Action: The Document Controller completes “Verify change impact, dependencies and required reapproval route” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. Control/Handoff: Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. | The Document Controller completes “Verify change impact, dependencies and required reapproval route” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. | Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he checks what a document change affects and whether it needs to go back for approval. • Starts when: a change request is registered and needs assessment. • How it runs: (1) he assesses the extent of the change. (2) He identifies the dependencies and downstream effects. (3) He determines whether reapproval is required and at what level. (4) He identifies who must review it. (5) He records the assessment and the required route. • Proof it happened: a documented impact assessment with the dependencies identified and the required reapproval route determined. • Where it usually breaks: a change is treated as minor and reissued without reapproval, when it actually altered a technical or contractual requirement. | • Define what constitutes a minor change in the SOP, since treating a technical or contractual change as minor reissues an unapproved requirement into use. • Require the document owner rather than document control to determine materiality, as this is a technical judgement. • Require reapproval at the original approval level where the content changes materially. • Assess the effect on work already executed, because some changes require rework rather than just reissue. • Record the assessment, so the decision not to reapprove is evidenced.
1173 | Research & Development | Coordinate revised document review, approval and controlled reissue | Document Controller | Trigger: When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. Action: The Document Controller completes “Coordinate revised document review, approval and controlled reissue” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. Control/Handoff: Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. | The Document Controller completes “Coordinate revised document review, approval and controlled reissue” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. | Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he takes the revised document through review and approval and reissues it under control. • Starts when: the impact assessment is complete and the revision is prepared. • How it runs: (1) he routes the revision through the required review. (2) He tracks the review and consolidates comments. (3) He obtains the approval at the required level. (4) He assigns the new revision and issues it. (5) He records the supersession and distributes to all affected holders. • Proof it happened: an approved and reissued revision with the review record, the new revision assigned and distribution to all holders. • Where it usually breaks: the revision is issued only to the requester, so other holders continue working from the superseded version. | • Reissue to every holder of the previous version, not only to the requester, since partial reissue guarantees some parties work from superseded information. • Identify the holders from the original distribution record, which is why that record must be complete. • Require acknowledgement of the reissue for contractually significant documents. • State on the reissue what changed, so recipients do not have to compare versions. • Confirm the superseded version was withdrawn at site rather than assuming replacement.
1174 | Research & Development | Withdraw and supersede obsolete document versions | Document Controller | Trigger: When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. Action: The Document Controller completes “Withdraw and supersede obsolete document versions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. Control/Handoff: Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. | The Document Controller completes “Withdraw and supersede obsolete document versions” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. | Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he formally withdraws the old version so nobody can mistake it for current. • Starts when: a new revision is issued or a document is cancelled. • How it runs: (1) he marks the previous version superseded in the register. (2) He marks or removes the superseded file from the active location. (3) He retains it in the archive for traceability. (4) He notifies the holders of the withdrawal. (5) He confirms the withdrawal is complete. • Proof it happened: superseded versions marked and removed from active use, retained in archive, with holders notified. • Where it usually breaks: the superseded version stays in the active folder alongside the new one, so both appear available. | • Remove superseded versions from the active location rather than relying on a status marking, since a file that can be opened will be used. • Retain the superseded version in an archive, as it remains the evidence of what was issued at the time. • Notify holders explicitly of the withdrawal rather than relying on the new issue to imply it. • Mark archived copies clearly as superseded on their face, not only in the file name. • Confirm withdrawal completion, since an incomplete withdrawal is the same as none.
1175 | Research & Development | Recall uncontrolled copies and notify affected recipients | Document Controller | Trigger: When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. Action: The Document Controller completes “Recall uncontrolled copies and notify affected recipients” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. Control/Handoff: Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. | The Document Controller completes “Recall uncontrolled copies and notify affected recipients” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. | Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he recalls uncontrolled printed or emailed copies and tells the recipients they are out of date. • Starts when: a document is superseded or an uncontrolled copy is identified in use. • How it runs: (1) he identifies who holds uncontrolled copies. (2) He issues a recall notice stating the copy is superseded. (3) He arranges collection or destruction of printed copies. (4) He issues the current version where needed. (5) He records the recall and its completion. • Proof it happened: recall notices issued with printed copies collected or destroyed, and the recall recorded as complete. • Where it usually breaks: printed drawings remain in site offices and vehicles long after supersession, and work continues from them. | • Require physical collection or witnessed destruction of superseded printed drawings at site, since a printed copy in a vehicle or site office is exactly what gets built from. • Mark controlled printed copies distinctly, so uncontrolled prints can be identified on sight. • Require the recall to be confirmed complete by the site, not assumed from the notice. • Limit printing of controlled documents and record who holds printed copies. • Record recall failures as nonconformities, because these are the direct cause of building to superseded information.
1176 | Research & Development | Record document-control nonconformities and corrective-action closure | Document Controller | Trigger: When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. Action: The Document Controller completes “Record document-control nonconformities and corrective-action closure” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. Control/Handoff: Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a controlled document change, revision conflict, obsolete copy, unauthorised issue or document-control nonconformity is identified. | The Document Controller completes “Record document-control nonconformities and corrective-action closure” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a controlled change/reissue, withdrawn obsolete version, recipient notification, exception record and verified corrective-action closure. | Affected work is paused where an incorrect revision could cause execution risk; technical/project owners assess impact and the CRO receives systemic or repeated control failures. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he records where document control has broken down and makes sure it is corrected. • Starts when: a document control failure is identified, by anyone. • How it runs: (1) he records the nonconformity with the facts. (2) He identifies the cause. (3) He agrees the corrective action with the responsible party. (4) He tracks it to completion. (5) He verifies effectiveness and closes it. • Proof it happened: a nonconformity register with causes, corrective actions and verified closure. • Where it usually breaks: failures are corrected quietly without being recorded, so the same weaknesses recur and nobody sees the pattern. | • Record every document control failure even when corrected immediately, since the pattern is what identifies the systemic weakness and quiet fixes hide it. • Require the cause to be recorded, particularly where the failure originated outside document control. • Report recurring nonconformities to R&D and the CEO, as these indicate a process or training failure. • Verify corrective action effectiveness rather than accepting completion. • Treat any instance of work executed from a superseded document as a serious nonconformity, not an administrative one.
1177 | Research & Development | Prepare the project document-handover and final-record index | Document Controller | Trigger: When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. Action: The Document Controller completes “Prepare the project document-handover and final-record index” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. Control/Handoff: Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. | The Document Controller completes “Prepare the project document-handover and final-record index” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. | Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he prepares the handover index, the list of everything the project must deliver as records. • Starts when: closeout planning begins, well before completion. • How it runs: (1) he identifies the handover requirements from the contract. (2) He builds the index of required records. (3) He records the status of each item. (4) He identifies the gaps and their owners. (5) He reports the completeness position. • Proof it happened: a handover index built from the contract requirements with the status of every item and the gaps owned. • Where it usually breaks: the index is built at the end from what exists rather than from what the contract requires, so the gaps are never identified. | • Build the index from the contract requirements rather than from what has been collected, since an index of what exists cannot reveal what is missing. • Start the index at project start and report completeness monthly, because gaps found at the end cannot be filled. • Assign a named owner per gap, as unowned gaps persist to handover. • Agree the index format with the client early, so it is not rebuilt at the end. • Include subcontractor records in the index, and make them a condition of final payment.
1178 | Research & Development | Reconcile the latest approved drawings, documents and register status | Document Controller | Trigger: When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. Action: The Document Controller completes “Reconcile the latest approved drawings, documents and register status” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. Control/Handoff: Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. | The Document Controller completes “Reconcile the latest approved drawings, documents and register status” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. | Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he checks that the drawings and documents being handed over are the latest approved versions. • Starts when: handover preparation begins. • How it runs: (1) he lists the documents to be handed over. (2) He checks each against the register for the current approved revision. (3) He identifies documents superseded after the handover set was assembled. (4) He replaces outdated items. (5) He confirms the set matches the register. • Proof it happened: a reconciled handover set confirmed as matching the register's current approved revisions. • Where it usually breaks: the handover set is assembled early and not rechecked, so it contains revisions superseded during closeout. | • Recheck the handover set against the register immediately before submission, since revisions issued during closeout otherwise leave the client holding superseded documents. • Reconcile in both directions, so documents in the register but missing from the set are also found. • Require the as built revisions rather than the IFC revisions where as builts exist. • Record the revision of every document handed over, as this is the client's reference point thereafter. • Obtain the client's acknowledgement of the set received.
1179 | Research & Development | Compile as-built, O&M, warranty, certificate and approval records | Document Controller | Trigger: When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. Action: The Document Controller completes “Compile as-built, O&M, warranty, certificate and approval records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. Control/Handoff: Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. | The Document Controller completes “Compile as-built, O&M, warranty, certificate and approval records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. | Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he compiles the as built drawings, operating manuals, warranties and certificates into the handover dossier. • Starts when: closeout compilation begins. • How it runs: (1) he collects the as built drawings and verifies they are approved. (2) He collects the operation and maintenance manuals. (3) He collects the warranties and guarantees with their validity dates. (4) He collects the certificates and approvals. (5) He assembles and indexes the dossier. • Proof it happened: a compiled and indexed dossier containing verified as builts, manuals, warranties and certificates. • Where it usually breaks: warranties are collected without checking their start dates, so they are already part expired at handover. | • Check the start date and duration of every warranty, since warranties running from delivery rather than handover are already part expired when the client receives them. • Require manuals to cover the equipment actually installed rather than the specified model, as substitutions are common. • Verify as builts are approved rather than marked up, because unapproved as builts are not a record. • Make manual and warranty submission a condition of subcontractor final payment. • Index the dossier so items can be found, as an unindexed dossier is functionally useless to the client.
1180 | Research & Development | Close missing transmittal, correspondence, action and approval records | Document Controller | Trigger: When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. Action: The Document Controller completes “Close missing transmittal, correspondence, action and approval records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. Control/Handoff: Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. | The Document Controller completes “Close missing transmittal, correspondence, action and approval records” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. | Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he closes out the missing transmittals, correspondence, actions and approvals before the project file is closed. • Starts when: closeout reconciliation identifies gaps. • How it runs: (1) he identifies the missing records against the registers. (2) He traces each to its likely holder. (3) He obtains and files the missing items. (4) He records those that cannot be obtained with the reason. (5) He reports the residual gaps before closure. • Proof it happened: closed gaps in the transmittal, correspondence, action and approval records, with unobtainable items recorded and reported. • Where it usually breaks: gaps are closed by marking them not applicable, so the record appears complete when it is not. | • Prohibit closing a gap as not applicable without a stated justification and approval, since this is how incomplete records are made to look complete. • Record unobtainable items explicitly with the reason, so the company knows where its record is weak before a dispute. • Chase records from parties before they demobilise, as recovery afterwards rarely succeeds. • Report the residual gaps to the project manager before file closure, as this is a risk acceptance decision. • Prioritise gaps in contractually significant records over administrative ones.
1181 | Research & Development | Archive final project records, lessons learned and closeout evidence | Document Controller | Trigger: When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. Action: The Document Controller completes “Archive final project records, lessons learned and closeout evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. Control/Handoff: Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. | The Document Controller completes “Archive final project records, lessons learned and closeout evidence” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. | Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he archives the final project records, the lessons and the closeout evidence. • Starts when: closeout is complete and the project is closed. • How it runs: (1) he assembles the complete project record set. (2) He applies the archive structure and index. (3) He records the retention period and the review date. (4) He transfers it to the archive location. (5) He verifies the archive is complete and retrievable. • Proof it happened: a complete indexed archive with retention recorded and retrievability verified. • Where it usually breaks: the archive is created but never tested, so when a record is needed years later it cannot be opened or found. | • Verify retrievability at the point of archiving by actually retrieving sample records, since an archive that cannot be opened is not an archive. • Archive the native files as well as the issued formats, because native files are needed for any future modification. • Record the retention period and the review date at archiving, so disposal is controlled rather than accidental. • Include the registers themselves in the archive, as the records are unusable without their index. • Archive the lessons learned with the project record, so they are found by whoever looks at the project later.
1182 | Research & Development | Apply retention, retrieval, legal-hold and approved-disposal controls | Document Controller | Trigger: When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. Action: The Document Controller completes “Apply retention, retrieval, legal-hold and approved-disposal controls” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. Control/Handoff: Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When a project stage, completion, DLP closeout, matter closure or retention event requires final record control. | The Document Controller completes “Apply retention, retrieval, legal-hold and approved-disposal controls” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | a reconciled handover index, complete final-record package, controlled archive, retrieval path and approved retention/disposal status. | Project/Technical/Legal/Finance owners confirm their records, unresolved claims or missing approvals remain open, legal holds override disposal and the Document Controller records every residual gap. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he applies the rules on how long records are kept, how they are retrieved, when they must be preserved for legal reasons, and how they are destroyed. • Starts when: records are archived, and when retention or legal hold requirements arise. • How it runs: (1) he applies the retention period per record type. (2) He maintains the retrieval process and tests it. (3) He applies legal holds when instructed and suspends disposal. (4) He identifies records due for disposal. (5) He obtains approval and disposes of them with a record. • Proof it happened: applied retention periods, a tested retrieval process, recorded legal holds and approved disposal records. • Where it usually breaks: records under legal hold are destroyed in a routine disposal cycle, which is a serious legal exposure. | • Require legal holds to suspend disposal absolutely and to be checked before every disposal cycle, since destroying records under hold is a serious legal exposure. • Require approval before any disposal, with a record of what was destroyed and when. • Set retention from the legal and contractual requirement, as both premature disposal and indefinite retention carry risk. • Test the retrieval process periodically rather than assuming it works. • Require CLO instruction to place and release a legal hold, and record both.
1183 | Research & Development | Issue the weekly overdue-document, review and response status report | Document Controller | Trigger: When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. Action: The Document Controller completes “Issue the weekly overdue-document, review and response status report” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. Control/Handoff: The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. | The Document Controller completes “Issue the weekly overdue-document, review and response status report” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. | The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: every week he reports what is overdue, what is stuck in review and what responses are outstanding. • Starts when: weekly on the reporting cycle. • How it runs: (1) he compiles the overdue documents, reviews and responses. (2) He shows the ageing of each. (3) He identifies the items with contractual deadlines. (4) He issues the report to the owners and the project manager. (5) He tracks the actions arising. • Proof it happened: an issued weekly status report with overdue items, ageing and contractual deadlines highlighted. • Where it usually breaks: the report lists everything outstanding without distinguishing what has a deadline, so the urgent items are lost among the routine. | • Separate items with contractual deadlines from routine outstanding items, since mixing them means the consequential ones get the same attention as the trivial. • Show ageing rather than just status, because the length of the delay determines the response. • Send each owner their own items as well as issuing the full report, as a company wide list is nobody's responsibility. • Generate the report from the registers so it cannot disagree with them. • Keep the issue day fixed, since a predictable report gets read.
1184 | Research & Development | Prepare the monthly document-control KPI and exception report | Document Controller | Trigger: When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. Action: The Document Controller completes “Prepare the monthly document-control KPI and exception report” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. Control/Handoff: The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. | The Document Controller completes “Prepare the monthly document-control KPI and exception report” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. | The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: monthly he reports how document control is performing and where the exceptions are. • Starts when: monthly on the reporting cycle. • How it runs: (1) he compiles the measures: turnaround times, overdue volumes, return rates and completeness. (2) He identifies the trends. (3) He reports the exceptions and their causes. (4) He states the actions needed. (5) He issues to the CRO and the project managers. • Proof it happened: a monthly KPI and exception report with measures, trends, causes and recommended actions. • Where it usually breaks: the report measures document control's own activity rather than whether the project has the information it needs. | • Measure whether the project has correct current information, not only document control's processing volumes, since the function exists for the former. • Report review turnaround by reviewing party, as internal review delay is usually the largest component and is rarely owned. • Report submission return rates by department, because these indicate where training is needed. • Show trend rather than single month figures. • Include closeout record completeness, as this is the measure that predicts handover delay.
1185 | Research & Development | Perform document-register and controlled-repository spot checks | Document Controller | Trigger: When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. Action: The Document Controller completes “Perform document-register and controlled-repository spot checks” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. Control/Handoff: The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. | The Document Controller completes “Perform document-register and controlled-repository spot checks” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. | The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he spot checks the registers and the repository to confirm they actually reflect reality. • Starts when: at the scheduled spot check frequency. • How it runs: (1) he selects a sample of documents and register entries. (2) He checks the register against the actual file and its revision. (3) He checks the repository for unregistered documents. (4) He checks permissions and classifications are applied. (5) He records the findings and corrects the discrepancies. • Proof it happened: spot check records with the sample tested, discrepancies found and corrections applied. • Where it usually breaks: spot checks are done on the documents processed most recently, which are the ones most likely to be correct. | • Select the sample randomly and include older records, since checking recent work tests the least likely place for errors to exist. • Check in both directions: register to file and file to register, as unregistered documents are the more serious finding. • Verify permissions and classifications, not only existence, because access errors are invisible until information leaks. • Record findings as nonconformities so the pattern is visible. • Include documents held at site in the sample, since these are furthest from control.
1186 | Research & Development | Train and support users on document-control procedures and templates | Document Controller | Trigger: When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. Action: The Document Controller completes “Train and support users on document-control procedures and templates” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. Control/Handoff: The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. | The Document Controller completes “Train and support users on document-control procedures and templates” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. | The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he teaches people how to use the document control system and the templates properly. • Starts when: on joining, when procedures change, and when repeated errors indicate a need. • How it runs: (1) he identifies the training needs from the error patterns. (2) He prepares the guidance and the materials. (3) He delivers the training or the briefing. (4) He provides ongoing support to users. (5) He checks whether the errors reduce afterwards. • Proof it happened: delivered training and guidance with attendance recorded and the subsequent error rate checked. • Where it usually breaks: training is delivered once at induction, so people who join or change roles later never receive it. | • Require document control training for every new joiner and role change, since people who never received it generate the errors indefinitely. • Target training at the actual error patterns rather than delivering a general overview. • Provide a short reference guide, because recall from a single session is low. • Check the error rate after training, as this is the only evidence the training worked. • Include the reason for the controls, since people comply better when they understand the consequence of not doing so.
1187 | Research & Development | Maintain document-control access, backup and absence-cover arrangements | Document Controller | Trigger: When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. Action: The Document Controller completes “Maintain document-control access, backup and absence-cover arrangements” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. Control/Handoff: The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. | The Document Controller completes “Maintain document-control access, backup and absence-cover arrangements” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. | The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he makes sure document control keeps working when he is away, and that the records are backed up. • Starts when: at the continuity review, and before planned absences. • How it runs: (1) he documents the procedures so another person can follow them. (2) He names and trains a deputy. (3) He confirms the deputy has the necessary access. (4) He confirms the backup arrangements cover the registers and the repository. (5) He tests that the cover arrangement works. • Proof it happened: documented procedures, a trained deputy with verified access and confirmed backup arrangements. • Where it usually breaks: document control stops entirely during absence, so documents accumulate unregistered and the register develops a gap. | • Require a trained deputy with access in place before any absence, since a document control gap means unregistered documents circulating uncontrolled. • Document the procedures in enough detail that a deputy can follow them, because this knowledge is usually held by one person. • Back up the registers as well as the documents, as the registers are what make the documents usable. • Set a minimum service level during absence, such as registration and issue continuing even if reporting pauses. • Review access on any change of role, since document control access is powerful.
1188 | Research & Development | Test archive retrieval and document-recovery readiness with IT | Document Controller | Trigger: When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. Action: The Document Controller completes “Test archive retrieval and document-recovery readiness with IT” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. Output/Evidence: an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. Control/Handoff: The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. Continuity/Escalation: A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. Timing: To be confirmed. | When the weekly/monthly cutoff, spot-check cycle, user-support request, absence, access issue or recovery test becomes due. | The Document Controller completes “Test archive retrieval and document-recovery readiness with IT” using approved source documents, metadata standards, revision rules, authority evidence, project registers, repository controls and authorised distribution instructions. | an overdue/KPI report, audit result, user guidance, continuity record or successful archive-recovery test with corrective actions. | The Document Controller reports exceptions without concealing overdue items; IT owns system recovery, functional owners correct their documents, and recurring control failures escalate to the CRO. | A trained authorised Document Controller may provide operational backup using controlled repository access; missing approvals, revision conflicts, confidentiality incidents, failed delivery, incomplete handover and systemic nonconformities escalate to the CRO and responsible functional chief. | To be confirmed. | • In plain words: he tests with IT that archived documents can actually be recovered when needed. • Starts when: at the scheduled test frequency, and after any change to the archive or backup arrangements. • How it runs: (1) he agrees the test scope with IT. (2) He selects sample records including old ones. (3) He requests their retrieval. (4) He verifies the retrieved files open and are complete. (5) He records the results and raises the failures. • Proof it happened: a documented retrieval test with the sample, the results and any failures raised for correction. • Where it usually breaks: the test is never performed, so nobody knows the archive is unrecoverable until a record is urgently needed. | • Perform an actual retrieval test at a set frequency, since an untested archive is an assumption and the failure is only discovered when a record is urgently needed. • Include the oldest records in the test, as these are most likely to have format or media problems. • Verify the retrieved files open and are complete, not just that they were located. • Test after any change to the backup arrangement or storage platform. • Record the results and escalate failures immediately, because an unrecoverable archive is a serious exposure.
1189 | Legal | Set Legal strategy, policies and annual operating objectives | Chief Legal Officer (CLO) | Trigger: When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. Action: The Chief Legal Officer (CLO) completes “Set Legal strategy, policies and annual operating objectives” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. Control/Handoff: The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. | The Chief Legal Officer (CLO) completes “Set Legal strategy, policies and annual operating objectives” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. | The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how legal will work for the year, what it is trying to protect and the rules everyone must follow on contracts. • Starts when: the annual planning cycle opens, or the business changes enough that the current legal approach no longer fits. • How it runs: (1) he reviews the legal exposure the business plan creates. (2) He sets the objectives for the function for the year. (3) He drafts or updates the legal policies. (4) He obtains the CEO's approval. (5) He issues them to the departments that sign, commit or negotiate. • Proof it happened: an approved legal strategy with annual objectives and policies, issued to the business. • Where it usually breaks: the policies stay inside Legal, so the people actually signing and negotiating never see the rules they are meant to follow. | • Issue the legal policies to every department that negotiates, signs or commits, since the breaches happen outside Legal and not within it. • Set measurable objectives: review turnaround, notices issued on time, disputes avoided and deviation volumes. Objectives without measures cannot be reviewed. • State the policy review frequency and who may approve an exception. • Keep the rules short and practical, because a policy written in legal language is not followed by commercial staff. • Link the strategy to the authority matrix, so what may be signed is defined alongside the legal rules.
1190 | Legal | Define legal risk appetite, materiality thresholds and escalation criteria | Chief Legal Officer (CLO) | Trigger: When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. Action: The Chief Legal Officer (CLO) completes “Define legal risk appetite, materiality thresholds and escalation criteria” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. Control/Handoff: The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. | The Chief Legal Officer (CLO) completes “Define legal risk appetite, materiality thresholds and escalation criteria” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. | The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets how much legal risk the company will accept, what counts as significant, and when something must come to him. • Starts when: the framework is established, and when the risk profile of the business changes. • How it runs: (1) he identifies the categories of legal risk the company faces. (2) He sets the tolerance for each. (3) He sets the value and severity thresholds that define material. (4) He sets the escalation criteria and timeframes. (5) He obtains approval and issues it to the business. • Proof it happened: an approved legal risk appetite with materiality thresholds and escalation criteria, issued to the business. • Where it usually breaks: materiality is left to judgement, so significant exposures are handled locally and Legal learns of them once they have escalated. | • Define materiality with numbers and named event types, since judgement based escalation means Legal hears about exposures only after they have become problems. • State escalation timeframes in hours or days per severity, not as a general obligation to inform. • Name the events that must always escalate regardless of value: personal injury, regulatory contact, insolvency of a counterparty and any allegation of fraud. • State that uncertainty about materiality means escalating, so the default is disclosure. • Review the thresholds annually, as a threshold set years ago no longer reflects the size of the business.
1191 | Legal | Approve Legal Delegation of Authority and reserved-matter matrix | Chief Legal Officer (CLO) | Trigger: When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. Action: The Chief Legal Officer (CLO) completes “Approve Legal Delegation of Authority and reserved-matter matrix” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. Control/Handoff: The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. | The Chief Legal Officer (CLO) completes “Approve Legal Delegation of Authority and reserved-matter matrix” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. | The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets who may approve legal positions and which legal matters only the owners may decide. • Starts when: the framework is set, and when roles or the organisation change. • How it runs: (1) he maps the legal decision points across the business. (2) He assigns each to a role with limits. (3) He identifies the matters reserved to ownership. (4) He obtains CEO and ownership approval. (5) He issues the matrix and reconciles it to the company authority matrix. • Proof it happened: an approved legal authority and reserved matter matrix, issued and reconciled to the company authority matrix. • Where it usually breaks: the legal matrix and the company matrix state different limits, so approvals are valid under one and invalid under the other. | • Reconcile the legal matrix against the company authority matrix, since conflicting limits make every approval arguable. • Name the reserved matters explicitly: litigation commencement, settlement above a value, guarantees, and any change of legal structure. • State that legal risk acceptance is a separate decision from commercial approval, and name who may accept it. • Require written temporary delegation with an end date, as legal authority exercised informally is contestable. • Reissue and withdraw previous versions explicitly, because two matrices in circulation is worse than none.
1192 | Legal | Approve contract standards, clause library and deviation controls | Chief Legal Officer (CLO) | Trigger: When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. Action: The Chief Legal Officer (CLO) completes “Approve contract standards, clause library and deviation controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. Control/Handoff: The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. | The Chief Legal Officer (CLO) completes “Approve contract standards, clause library and deviation controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. | The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the standard contract wording the company uses and controls when it may be departed from. • Starts when: the standards are established, and when law, market practice or repeated disputes require revision. • How it runs: (1) he prepares the standard contract templates by type. (2) He builds the clause library with approved alternatives. (3) He defines which clauses are non negotiable. (4) He sets the approval route for deviations. (5) He issues the standards and withdraws previous versions. • Proof it happened: approved contract standards and a clause library with non negotiable clauses identified and a deviation approval route. • Where it usually breaks: the standard is ignored under commercial pressure and deviations are accepted at negotiation with no record of what was given away. | • Identify the non negotiable clauses explicitly and state that only the CLO may approve departure, since these are exactly the clauses conceded under deadline pressure. • Provide pre approved fallback wording in the clause library, so negotiators have an acceptable alternative rather than inventing one. • Require every deviation to be recorded against the contract, as unrecorded concessions are discovered only in a dispute. • Maintain a deviation register by counterparty, because a concession granted once will be demanded again. • Review the standards after every significant dispute, since disputes reveal which clauses actually failed.
1193 | Legal | Approve matter classification, confidentiality, privilege and access controls | Chief Legal Officer (CLO) | Trigger: When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. Action: The Chief Legal Officer (CLO) completes “Approve matter classification, confidentiality, privilege and access controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. Control/Handoff: The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the annual planning cycle, policy review, authority change or material legal-control issue requires direction. | The Chief Legal Officer (CLO) completes “Approve matter classification, confidentiality, privilege and access controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved Legal strategy, risk rule, authority matrix, contract standard or confidentiality/access control. | The CLO owns legal-risk governance; business executives retain technical, commercial, operational and financial decisions, while matters above legal authority or risk appetite escalate to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets how legal matters are classified and protected, including which documents are privileged and who may see them. • Starts when: the framework is set, and when a sensitive matter arises. • How it runs: (1) he defines the matter categories. (2) He sets the confidentiality level for each. (3) He defines what is privileged and how privilege is preserved. (4) He sets the access controls per category. (5) He issues the framework and enforces it. • Proof it happened: an approved matter classification framework with confidentiality levels, privilege rules and access controls applied. • Where it usually breaks: privileged advice is circulated widely or forwarded to a counterparty, which waives the privilege permanently. | • State plainly how privilege is lost, since forwarding legal advice to a counterparty or a wide internal list waives it permanently and irreversibly. • Require privileged documents to be marked and their distribution restricted to a named list. • Prohibit legal advice being summarised into general circulation documents, as this is the commonest inadvertent waiver. • Restrict access to dispute and investigation files, because these are the most damaging documents if disclosed. • State the rule for external counsel communications, which carry the strongest protection and the greatest exposure if mishandled.
1194 | Legal | Approve legal review strategy for client construction and design contracts | Chief Legal Officer (CLO) | Trigger: When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. Action: The Chief Legal Officer (CLO) completes “Approve legal review strategy for client construction and design contracts” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. Control/Handoff: CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. | The Chief Legal Officer (CLO) completes “Approve legal review strategy for client construction and design contracts” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. | CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how client construction and design contracts are legally reviewed before the company signs them. • Starts when: a client contract is received for review, and when the review approach is set. • How it runs: (1) he defines what must be reviewed and to what depth by contract value and risk. (2) He identifies the key risk areas for construction contracts. (3) He sets the review checklist. (4) He sets the turnaround expectations. (5) He reviews or assigns the review and records the position. • Proof it happened: an approved legal review approach with checklists applied, and a recorded legal position per contract. • Where it usually breaks: the contract is reviewed after the commercial terms have been agreed, so the advice cannot change anything. | • Require legal review before the commercial position is closed, since advice delivered after agreement cannot change anything and is wasted. • Build a construction specific checklist covering time, payment, variations, delay, liability caps, indemnities and termination. • Set review turnaround by value band, because slow review is the reason contracts are signed unreviewed. • Require the legal position to be recorded in writing, so the accepted risks are known after the negotiators move on. • Require the flow down obligations to be identified, as these must be passed to subcontractors.
1195 | Legal | Approve tender qualifications, exclusions and legal risk positions | Chief Legal Officer (CLO) | Trigger: When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. Action: The Chief Legal Officer (CLO) completes “Approve tender qualifications, exclusions and legal risk positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. Control/Handoff: CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. | The Chief Legal Officer (CLO) completes “Approve tender qualifications, exclusions and legal risk positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. | CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the qualifications and exclusions the company attaches to its tenders, which is how it limits its risk. • Starts when: a tender is being prepared for submission. • How it runs: (1) he reviews the tender conditions for unacceptable risk. (2) He identifies the qualifications needed. (3) He drafts the wording so it is clear and defensible. (4) He confirms the commercial team understands the effect. (5) He approves the qualifications for submission. • Proof it happened: approved tender qualifications and exclusions with the legal risk position recorded. • Where it usually breaks: qualifications are removed at the last moment to avoid appearing non compliant, so the tender accepts risk nobody assessed. | • Require CLO approval to remove a qualification as well as to add one, since qualifications are stripped out at submission to look compliant and the risk then arrives unassessed. • Require the commercial effect of each qualification to be explained to the bid team, so they can defend it in clarification. • Draft qualifications to be specific and priced where possible, as vague qualifications are rejected or ignored. • Record which qualifications the client accepted, because unaccepted ones do not form part of the contract. • Check the final submitted document against the approved version, as late edits are common.
1196 | Legal | Approve material client contract deviations before signature | Chief Legal Officer (CLO) | Trigger: When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. Action: The Chief Legal Officer (CLO) completes “Approve material client contract deviations before signature” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. Control/Handoff: CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. | The Chief Legal Officer (CLO) completes “Approve material client contract deviations before signature” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. | CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: before the company signs a client contract, he approves any departure from the acceptable legal position. • Starts when: a client contract contains terms outside the standard or previously approved position. • How it runs: (1) he identifies the deviations and their effect. (2) He quantifies the exposure each creates. (3) He attempts to negotiate them out. (4) He recommends acceptance, rejection or mitigation. (5) He records the approved position before signature. • Proof it happened: a recorded schedule of approved deviations with the exposure assessed, dated before signature. • Where it usually breaks: the contract is signed first and reviewed afterwards, so the company discovers what it agreed to when a problem arises. | • Make legal approval a precondition of signature, since a contract signed and reviewed afterwards means the company learns its obligations from the dispute. • Require unlimited liability, uncapped indemnities and unlimited delay damages to be escalated to the CEO and ownership rather than decided in Legal. • Require the exposure to be quantified where possible, so the commercial decision is informed rather than instinctive. • Record the accepted deviations in one schedule attached to the contract file, as these are the terms that will be argued. • Verify the signed version matches the approved version, because late client edits happen routinely.
1197 | Legal | Approve material supplier, subcontract and consultancy contract deviations | Chief Legal Officer (CLO) | Trigger: When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. Action: The Chief Legal Officer (CLO) completes “Approve material supplier, subcontract and consultancy contract deviations” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. Control/Handoff: CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. | The Chief Legal Officer (CLO) completes “Approve material supplier, subcontract and consultancy contract deviations” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. | CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves departures from standard terms in contracts with suppliers, subcontractors and consultants. • Starts when: a supplier or subcontract contains terms outside the standard position. • How it runs: (1) he identifies the deviations. (2) He checks the back to back position against the main contract. (3) He assesses the exposure created by any gap. (4) He negotiates or accepts with mitigation. (5) He records the approved position before signature. • Proof it happened: approved deviations with the back to back position checked and the residual gap recorded. • Where it usually breaks: subcontracts are signed without back to back terms, so obligations the company owes the client are not passed down and it carries the gap alone. | • Require a back to back check against the main contract on time, damages, defects liability, notices and payment, since the gap left behind is carried by the company alone. • Require insurance, bonds and guarantees to be verified before mobilisation rather than before payment. • Record the residual gap where back to back cannot be achieved, so the exposure is known rather than assumed away. • Require the scope to reference drawings and specification clauses, as scope in words generates variation claims. • Prohibit mobilisation before signature, with a capped and dated letter of intent as the only exception.
1198 | Legal | Approve joint venture, consortium, partnership, MOU and NDA positions | Chief Legal Officer (CLO) | Trigger: When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. Action: The Chief Legal Officer (CLO) completes “Approve joint venture, consortium, partnership, MOU and NDA positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. Control/Handoff: CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a tender, client award, material contract, subcontract or strategic agreement reaches the legal approval gate. | The Chief Legal Officer (CLO) completes “Approve joint venture, consortium, partnership, MOU and NDA positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved legal review strategy, risk qualification, deviation decision or transaction position recorded in the legal decision register. | CMO owns the client/commercial interface, CTO owns technical scope, CPO owns procurement, CFO owns financial controls and COO owns execution; the CLO approves material legal exposure before commitment. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the legal position on partnerships, joint ventures, memoranda of understanding and confidentiality agreements. • Starts when: a collaboration or information sharing arrangement is proposed. • How it runs: (1) he reviews the commercial intent and the structure proposed. (2) He assesses the liability, control and exit implications. (3) He identifies the regulatory and tax consequences with the CFO. (4) He drafts or reviews the agreement. (5) He approves the position before signature. • Proof it happened: an approved legal position on the arrangement with liability, control and exit terms recorded. • Where it usually breaks: an MOU intended as non binding is drafted in terms that actually create obligations, and the company is bound before any due diligence. | • Require every MOU and letter of intent to state explicitly whether it is binding, since documents intended as non binding routinely create enforceable obligations. • Require joint and several liability in any joint venture to be escalated, as this exposes the company to its partner's failures in full. • Require an exit mechanism in every collaboration, because arrangements with no exit become permanent and unmanageable. • Require NDAs to be mutual and time limited, and to state what happens to information on termination. • Require partner due diligence before signature, not after, particularly on financial standing.
1199 | Legal | Approve contractual notice and claim strategy | Chief Legal Officer (CLO) | Trigger: When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. Action: The Chief Legal Officer (CLO) completes “Approve contractual notice and claim strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. Control/Handoff: No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. | The Chief Legal Officer (CLO) completes “Approve contractual notice and claim strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. | No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how and when the company issues formal contractual notices, which is how entitlement is preserved. • Starts when: an event occurs that may require notice, or the notice strategy is being set for a project. • How it runs: (1) he identifies the notice provisions in the contract with their time limits. (2) He ensures the project team knows the triggers and deadlines. (3) He approves the notice wording. (4) He confirms the notice was served correctly and on time. (5) He records the notice and tracks the follow up. • Proof it happened: served notices with the contractual basis stated, evidence of correct and timely service, and follow up tracked. • Where it usually breaks: notices are not served because the team hopes to resolve the matter amicably, and the entitlement is lost on time bar rather than on merit. | • Require notices to be served within their time limits regardless of whether the claim will be pursued, since entitlement is lost on time bar far more often than on merit. • State that serving a notice is not an act of aggression, because that belief is why notices go unserved. • Extract every notice provision and its time limit into a project notice register at contract activation. • Require service by the exact contractual method and address, as a notice served incorrectly is no notice. • Retain proof of service, since the date of service is what determines whether entitlement survives.
1200 | Legal | Approve variation, extension-of-time and delay-claim legal positions | Chief Legal Officer (CLO) | Trigger: When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. Action: The Chief Legal Officer (CLO) completes “Approve variation, extension-of-time and delay-claim legal positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. Control/Handoff: No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. | The Chief Legal Officer (CLO) completes “Approve variation, extension-of-time and delay-claim legal positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. | No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the legal position on variations, time extensions and delay claims, so the company claims on a proper basis. • Starts when: a variation, delay or extension claim arises or is received. • How it runs: (1) he identifies the contractual basis for the entitlement. (2) He reviews the evidence supporting cause and effect. (3) He confirms the notices required were served. (4) He approves the legal position and the claim structure. (5) He directs the preparation and records the position. • Proof it happened: an approved legal position per claim with the contractual basis, the notice position and the evidence assessed. • Where it usually breaks: claims are built on cost incurred without establishing the contractual entitlement or the causal link, so they are rejected outright. | • Require the contractual entitlement and the causal link to be established before any claim is prepared, since a claim built on cost alone is rejected without consideration. • Check the notice position first, as a time barred claim should not consume preparation effort. • Require contemporaneous records as the evidence base, because reconstructed records are challenged and discounted. • Distinguish time entitlement from cost entitlement, as these are separate and frequently conflated. • Record the legal position taken, so the claim remains consistent if the team changes.
1201 | Legal | Approve dispute escalation, without-prejudice negotiation and settlement strategy | Chief Legal Officer (CLO) | Trigger: When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. Action: The Chief Legal Officer (CLO) completes “Approve dispute escalation, without-prejudice negotiation and settlement strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. Control/Handoff: No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. | The Chief Legal Officer (CLO) completes “Approve dispute escalation, without-prejudice negotiation and settlement strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. | No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how disputes are escalated, negotiated and settled. • Starts when: a dispute arises or negotiation is proposed. • How it runs: (1) he assesses the merits and the exposure. (2) He assesses the cost and time of pursuing versus settling. (3) He sets the negotiation strategy and the authority limits. (4) He conducts or directs the negotiation on a without prejudice basis. (5) He documents any settlement and obtains the required approval. • Proof it happened: a documented dispute strategy with the merits assessed, negotiation conducted and the settlement approved and recorded. • Where it usually breaks: settlement discussions happen without prejudice protection, so admissions made in negotiation become evidence. | • Require settlement discussions to be expressly without prejudice and in writing, since admissions made in unprotected negotiation become evidence against the company. • Require settlement authority limits to be set before negotiation begins, so the negotiator cannot exceed them in the room. • Require every settlement to be documented and to include a full release, otherwise the same claim returns in another form. • Compare the cost of pursuing against the amount in dispute, as litigation cost frequently exceeds the claim. • Prohibit anyone other than authorised persons from discussing settlement with a counterparty.
1202 | Legal | Approve litigation, arbitration and expert-determination strategy | Chief Legal Officer (CLO) | Trigger: When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. Action: The Chief Legal Officer (CLO) completes “Approve litigation, arbitration and expert-determination strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. Control/Handoff: No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. | The Chief Legal Officer (CLO) completes “Approve litigation, arbitration and expert-determination strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. | No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides whether the company litigates or arbitrates, and how the case is run. • Starts when: a dispute cannot be resolved by negotiation, or proceedings are commenced against the company. • How it runs: (1) he assesses the merits, the costs and the recovery prospects. (2) He confirms the dispute resolution mechanism in the contract. (3) He obtains the required approval to commence or defend. (4) He appoints and instructs counsel. (5) He directs the case and reports the position. • Proof it happened: an approved litigation or arbitration strategy with the merits assessment, the approval obtained and counsel instructed. • Where it usually breaks: proceedings are commenced without a realistic assessment of recovery, so the company wins a judgment against a party that cannot pay. | • Require an assessment of the counterparty's ability to pay before commencing, since a judgment against an insolvent party is an expensive worthless asset. • Require the contractual dispute mechanism and jurisdiction to be confirmed first, as proceedings in the wrong forum are struck out at the company's cost. • Require a cost estimate to conclusion and ownership approval above a threshold. • Preserve all relevant documents immediately and issue a hold instruction, because destruction after proceedings begin is severely penalised. • Reassess the position at each stage rather than proceeding on the original decision.
1203 | Legal | Appoint and direct external counsel, experts and claims advisers | Chief Legal Officer (CLO) | Trigger: When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. Action: The Chief Legal Officer (CLO) completes “Appoint and direct external counsel, experts and claims advisers” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. Control/Handoff: No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a claim event, adverse notice, unresolved dispute, settlement proposal or formal proceeding requires legal authority. | The Chief Legal Officer (CLO) completes “Appoint and direct external counsel, experts and claims advisers” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved notice, claim, dispute, settlement, proceeding or external-counsel strategy with decision owner, deadline and exposure. | No settlement, admission, waiver or formal proceeding is committed outside the Delegation of Authority; material exposure, urgent deadlines and adverse developments escalate to the CEO immediately. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he appoints outside lawyers and experts and directs what they do, so their cost is controlled and useful. • Starts when: external support is needed on a matter. • How it runs: (1) he defines the scope of work required. (2) He selects the firm or expert with the relevant expertise. (3) He agrees the fee basis and the cost estimate. (4) He instructs them with a clear scope and deliverable. (5) He monitors the work and the fees against the estimate. • Proof it happened: appointment records with the defined scope, agreed fee basis, instructions issued and fees monitored against estimate. • Where it usually breaks: counsel are instructed with an open scope on an hourly basis, so the fees exceed the value of the matter. | • Require a written scope and a fee estimate with a cap or staged authorisation, since an open instruction on an hourly basis routinely costs more than the matter is worth. • Require approval before scope extensions, as fee overruns arrive as a completed fact otherwise. • Keep control of the strategy internally rather than delegating it with the work. • Require deliverables in a usable form, because advice the business cannot act on has no value. • Review fees monthly against the estimate and challenge variances.
1204 | Legal | Oversee corporate licences, registrations, permits and renewals | Chief Legal Officer (CLO) | Trigger: When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. Action: The Chief Legal Officer (CLO) completes “Oversee corporate licences, registrations, permits and renewals” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. Control/Handoff: The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. | The Chief Legal Officer (CLO) completes “Oversee corporate licences, registrations, permits and renewals” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. | The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he oversees the company's licences and registrations so the business stays legally able to operate. • Starts when: at scheduled compliance reviews, and when renewals approach. • How it runs: (1) he maintains oversight of the licence and registration register. (2) He confirms the renewal responsibilities are assigned. (3) He monitors the upcoming expiries. (4) He escalates renewals at risk. (5) He confirms the company's licensed activities match what it actually does. • Proof it happened: an overseen licence register with assigned renewal owners, monitored expiries and confirmed activity alignment. • Where it usually breaks: the company performs work outside the scope of its licence, which invalidates contracts and attracts penalties. | • Check that the licensed activities cover the work the company actually performs, since operating outside licence scope can invalidate contracts and attract penalties. • Require a named renewal owner per licence with warnings set by lead time rather than expiry date. • Escalate any renewal at risk immediately, as a lapsed trade licence halts operations entirely. • Check licence requirements before entering a new activity or emirate, not after winning the work. • Keep the register complete across all entities, because group structures create licences nobody tracks.
1205 | Legal | Approve corporate authorities, powers of attorney and signatory controls | Chief Legal Officer (CLO) | Trigger: When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. Action: The Chief Legal Officer (CLO) completes “Approve corporate authorities, powers of attorney and signatory controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. Control/Handoff: The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. | The Chief Legal Officer (CLO) completes “Approve corporate authorities, powers of attorney and signatory controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. | The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he controls who may legally bind the company, including powers of attorney and signing authority. • Starts when: an authority is granted, revoked or reviewed. • How it runs: (1) he defines who may sign what on behalf of the company. (2) He controls the issue of powers of attorney with scope and expiry. (3) He maintains the register of granted authorities. (4) He revokes authorities on role change or exit. (5) He reviews the register periodically. • Proof it happened: a controlled authority and power of attorney register with scopes, expiry dates and revocation evidence. • Where it usually breaks: a power of attorney granted years ago is never revoked, so a former employee can still legally bind the company. | • Revoke and formally register the revocation of every power of attorney on role change or exit, since an unrevoked power of attorney lets a former employee bind the company. • Require scope limits and an expiry date on every power of attorney, and prohibit open ended grants. • Maintain a single register of all signing authorities and reconcile it to the HR leaver process. • Notify banks and authorities of revocations, because internal revocation alone may not be effective externally. • Review the register at a fixed frequency rather than only on request.
1206 | Legal | Review the legal compliance register and material regulatory obligations | Chief Legal Officer (CLO) | Trigger: When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. Action: The Chief Legal Officer (CLO) completes “Review the legal compliance register and material regulatory obligations” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. Control/Handoff: The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. | The Chief Legal Officer (CLO) completes “Review the legal compliance register and material regulatory obligations” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. | The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he reviews the list of legal and regulatory obligations the company must meet, and whether it is meeting them. • Starts when: at the compliance review cycle, and when regulations change. • How it runs: (1) he maintains the register of applicable legal and regulatory obligations. (2) He assigns an owner to each. (3) He reviews the compliance status per obligation. (4) He identifies the gaps and directs the corrective action. (5) He reports the compliance position to the CEO. • Proof it happened: a reviewed compliance register with owners, compliance status, identified gaps and corrective actions. • Where it usually breaks: the register lists obligations without assessing whether the company actually complies, so it documents the requirement rather than the position. | • Require an assessed compliance status per obligation rather than a list of requirements, since a register that does not state the position tells nobody whether the company complies. • Assign a named owner per obligation, because unowned obligations are unmet. • Monitor for regulatory change in the areas that affect the business, as obligations change without notice reaching the company. • Require evidence of compliance rather than assertion, particularly for obligations with penalties. • Report unresolved gaps to the CEO, as accepting a known non compliance is a governance decision.
1207 | Legal | Direct internal investigations, whistleblowing and fraud-related legal response | Chief Legal Officer (CLO) | Trigger: When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. Action: The Chief Legal Officer (CLO) completes “Direct internal investigations, whistleblowing and fraud-related legal response” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. Control/Handoff: The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. | The Chief Legal Officer (CLO) completes “Direct internal investigations, whistleblowing and fraud-related legal response” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. | The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: when there is a whistleblowing report or suspected fraud, he directs the legal side of the investigation. • Starts when: a report is received, or suspected fraud or serious misconduct is identified. • How it runs: (1) he secures the evidence and instructs preservation. (2) He assesses the legal and regulatory implications. (3) He determines whether external investigators are needed. (4) He directs the investigation to preserve privilege and admissibility. (5) He advises on the outcome, including reporting obligations. • Proof it happened: a directed investigation with evidence preserved, privilege protected and the legal advice on outcome recorded. • Where it usually breaks: the investigation starts before evidence is preserved, and the records needed to prove anything are altered or deleted. | • Require evidence and system access to be preserved before anyone is interviewed, since early confrontation destroys the evidence the investigation depends on. • Structure the investigation to preserve privilege from the outset, because a report prepared without it becomes disclosable. • Protect the reporter explicitly, as retaliation is unlawful and destroys the reporting channel permanently. • Assess regulatory and insurer reporting obligations early, as both carry time limits. • Require the control weakness that allowed the conduct to be fixed, not only the individual dealt with.
1208 | Legal | Approve data privacy, intellectual property, brand and confidentiality legal controls | Chief Legal Officer (CLO) | Trigger: When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. Action: The Chief Legal Officer (CLO) completes “Approve data privacy, intellectual property, brand and confidentiality legal controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. Control/Handoff: The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a licence, corporate-authority, regulatory, investigation, privacy, intellectual-property or compliance matter becomes due or material. | The Chief Legal Officer (CLO) completes “Approve data privacy, intellectual property, brand and confidentiality legal controls” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved compliance decision, authority record, investigation direction, renewal action or legal-control position. | The responsible business function owns operational compliance and evidence; Legal interprets and controls legal risk, with material breaches or regulatory exposure escalated to the CEO. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the legal controls on personal data, intellectual property, the brand and confidential information. • Starts when: the framework is established, and when a new risk or obligation arises. • How it runs: (1) he identifies the data protection obligations and the company's processing activities. (2) He sets the controls on collection, use, storage and transfer. (3) He establishes ownership of intellectual property in contracts. (4) He sets the brand and confidentiality controls. (5) He issues the requirements and monitors compliance. • Proof it happened: approved data privacy, intellectual property and confidentiality controls issued and monitored. • Where it usually breaks: intellectual property ownership is not addressed in design contracts, so the company cannot reuse its own drawings or is accused of infringing the client's. | • Address intellectual property ownership and reuse rights explicitly in every design and consultancy contract, since silence leaves the company unable to reuse its own work. • Require a licence to use client and project information for credentials, as using it without one is a real confidentiality breach. • Map the personal data the company holds and its legal basis, because the obligations cannot be met without knowing what is held. • Set the rules for transferring personal data to third parties and outside the jurisdiction. • Require confidentiality obligations in employment and subcontract terms, not only in client NDAs.
1209 | Legal | Approve the contract-activation legal gate and project legal handover | Chief Legal Officer (CLO) | Trigger: When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. Action: The Chief Legal Officer (CLO) completes “Approve the contract-activation legal gate and project legal handover” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. Control/Handoff: Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. | The Chief Legal Officer (CLO) completes “Approve the contract-activation legal gate and project legal handover” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. | Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: before a project starts, he confirms the contract is properly in place and hands the obligations to the delivery team. • Starts when: a contract is awarded and before mobilisation. • How it runs: (1) he confirms the contract is fully executed. (2) He confirms the conditions precedent are satisfied. (3) He extracts the key obligations, notice provisions and deadlines. (4) He briefs the project team on them. (5) He approves the legal gate for activation. • Proof it happened: an approved contract activation gate with execution confirmed, conditions precedent satisfied and the obligations briefed to the project team. • Where it usually breaks: the project starts without the conditions precedent satisfied, so the company performs work under a contract that is not yet effective. | • Make the legal activation gate a hard precondition for mobilisation, since performing work under a contract that is not yet effective leaves the company without entitlement to payment. • Require the conditions precedent to be listed and evidenced as satisfied, particularly advance payment and permits. • Extract the notice provisions and deadlines into a project register and brief them, because the delivery team cannot comply with obligations it has not read. • Confirm insurances and bonds are in place before the gate is passed. • Record the briefing, as the team's knowledge of its obligations is what determines whether entitlement survives.
1210 | Legal | Approve insurance, bond, guarantee, security and indemnity legal positions | Chief Legal Officer (CLO) | Trigger: When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. Action: The Chief Legal Officer (CLO) completes “Approve insurance, bond, guarantee, security and indemnity legal positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. Control/Handoff: Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. | The Chief Legal Officer (CLO) completes “Approve insurance, bond, guarantee, security and indemnity legal positions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. | Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the legal wording of insurance, bonds, guarantees and indemnities, because these decide who pays when something goes wrong. • Starts when: an insurance, bond or indemnity requirement arises in a contract. • How it runs: (1) he reviews the required cover against the contractual obligation. (2) He reviews the indemnity wording and its scope. (3) He checks the bond wording, particularly whether it is on demand. (4) He confirms the exposure created is acceptable. (5) He approves the position and records it. • Proof it happened: an approved legal position on insurance, bonds, guarantees and indemnities with the exposure recorded. • Where it usually breaks: an on demand bond is accepted without noticing, so the client can call it without proving any default. | • Identify whether every bond is on demand or conditional, since an on demand bond can be called without any proven default and the money is gone before any argument. • Require indemnity wording to be capped and limited to the company's own acts, as unlimited indemnities transfer risk without limit. • Check the insurance actually covers the contractual obligation, because a policy in place is not the same as a policy that responds. • Diarise bond and guarantee expiry, since extending under pressure is expensive and lapsing is a breach. • Require the CFO to confirm the facility capacity before committing to security.
1211 | Legal | Approve suspension, default, termination and step-in strategies | Chief Legal Officer (CLO) | Trigger: When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. Action: The Chief Legal Officer (CLO) completes “Approve suspension, default, termination and step-in strategies” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. Control/Handoff: Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. | The Chief Legal Officer (CLO) completes “Approve suspension, default, termination and step-in strategies” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. | Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he decides how the company responds when a counterparty defaults, including suspension, termination and taking over the work. • Starts when: a material default occurs or is anticipated. • How it runs: (1) he confirms the default and the contractual remedies available. (2) He confirms the notice sequence required. (3) He assesses the consequences of each option. (4) He obtains approval for the chosen route. (5) He directs the execution and the recovery of cost. • Proof it happened: an approved default strategy with the contractual basis, the notices served correctly and the recovery position quantified. • Where it usually breaks: termination is executed without following the contractual notice sequence, which turns a valid termination into a repudiation by the company. | • Require the contractual notice sequence to be followed exactly before termination, since defective termination converts the company from the injured party into the one in breach. • Secure the site position first: materials, plant, documents and completed work, before the relationship becomes adversarial. • Call or preserve the bonds and security before terminating, as this may not be possible afterwards. • Record the additional cost of completion contemporaneously, because reconstructed costs are discounted in recovery. • Require CLO approval and ownership approval above a threshold, as termination is rarely reversible.
1212 | Legal | Approve final-account, release, retention and defects-liability-period legal closeout | Chief Legal Officer (CLO) | Trigger: When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. Action: The Chief Legal Officer (CLO) completes “Approve final-account, release, retention and defects-liability-period legal closeout” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. Control/Handoff: Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. | The Chief Legal Officer (CLO) completes “Approve final-account, release, retention and defects-liability-period legal closeout” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. | Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he approves the legal side of closing a project out, including releases, retention and the defects period. • Starts when: a project reaches final account and closeout. • How it runs: (1) he reviews the final account settlement terms. (2) He reviews the release and discharge wording. (3) He confirms the retention release conditions. (4) He confirms the defects liability period and its obligations. (5) He approves the closeout position. • Proof it happened: an approved closeout legal position with release wording reviewed and the retention and defects position confirmed. • Where it usually breaks: a broad release is signed that discharges claims the company has not yet quantified or even identified. | • Review every release for its scope before signature, since a broad release discharges claims the company has not yet identified and cannot recover afterwards. • Carve out pending claims and latent defects explicitly from any release. • Confirm the defects liability period start date and end date in writing, as this determines how long the obligation runs. • Diarise retention release dates with an owner, because unclaimed retention is simply lost money. • Confirm that subcontractor obligations extend through the company's own defects period, or the gap falls on the company.
1213 | Legal | Advise the CEO on material liability, compliance, client and counterparty exposure | Chief Legal Officer (CLO) | Trigger: When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. Action: The Chief Legal Officer (CLO) completes “Advise the CEO on material liability, compliance, client and counterparty exposure” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. Control/Handoff: Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When a contract-activation, security, default, termination, final-account or project-risk decision reaches the Legal gate. | The Chief Legal Officer (CLO) completes “Advise the CEO on material liability, compliance, client and counterparty exposure” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an approved project legal position, controlled legal handover, security decision, remedy strategy or closeout decision. | Legal approval does not replace technical, delivery, commercial or Finance approval; incomplete evidence or unresolved material exposure places the affected gate on hold and escalates through the responsible executive. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he tells the CEO where the company's real legal exposures are and what could go wrong. • Starts when: at the reporting cycle, and immediately for material matters. • How it runs: (1) he identifies the material exposures across contracts, disputes and compliance. (2) He quantifies them where possible. (3) He assesses the counterparty risks. (4) He states the mitigation and what needs a decision. (5) He records the CEO's directions and acts on them. • Proof it happened: a reported exposure assessment with quantification, mitigations and the CEO's recorded directions. • Where it usually breaks: exposure is reported as legal issues rather than as potential financial consequence, so the CEO cannot weigh it against anything else. | • Quantify exposures in money and probability terms, since exposure described in legal language cannot be weighed against commercial decisions. • Name the events that must be reported immediately: proceedings served, regulatory contact, counterparty insolvency and any fraud allegation. • Include contingent exposures such as guarantees and indemnities, because these sit outside the visible accounts. • Report counterparty financial distress early, as this changes both claim strategy and payment decisions. • Record the CEO's decisions on risk acceptance, since these are governance decisions rather than legal ones.
1214 | Legal | Chair the weekly legal deadline, claim and exception review | Chief Legal Officer (CLO) | Trigger: When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. Action: The Chief Legal Officer (CLO) completes “Chair the weekly legal deadline, claim and exception review” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. Control/Handoff: Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. | The Chief Legal Officer (CLO) completes “Chair the weekly legal deadline, claim and exception review” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. | Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: every week he reviews the legal deadlines coming up, the live claims and anything unusual. • Starts when: weekly on the review cycle. • How it runs: (1) he reviews the upcoming and missed legal deadlines. (2) He reviews the status of live claims and disputes. (3) He reviews the exceptions: unsigned contracts, unserved notices and expiring securities. (4) He directs the actions with owners. (5) He carries unresolved items forward with escalation. • Proof it happened: a weekly review record with deadlines, claim status, exceptions and directed actions. • Where it usually breaks: the review covers active disputes but not the quiet deadlines, and entitlement is lost on a date nobody was watching. | • Make contractual deadlines the first item every week, since entitlement is most often lost on a date nobody was watching rather than in an active dispute. • Report unsigned contracts and unserved notices as standing exceptions, as these are invisible exposures. • Include expiring bonds, guarantees and insurances, because lapse is a breach and renewal takes time. • Show ageing on all open items, so persistent exposures are not normalised. • Require a named owner and date on every directed action.
1215 | Legal | Present the monthly Legal dashboard, exposure report and corrective actions | Chief Legal Officer (CLO) | Trigger: When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. Action: The Chief Legal Officer (CLO) completes “Present the monthly Legal dashboard, exposure report and corrective actions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. Control/Handoff: Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. | The Chief Legal Officer (CLO) completes “Present the monthly Legal dashboard, exposure report and corrective actions” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. | Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: monthly he presents the legal picture, the exposures and the corrective actions to the executive. • Starts when: monthly on the reporting cycle. • How it runs: (1) he compiles the measures: contracts reviewed, turnaround, deviations, notices and disputes. (2) He compiles the exposure position. (3) He identifies the trends and the systemic issues. (4) He states the corrective actions and owners. (5) He presents and records the decisions. • Proof it happened: a monthly legal dashboard with measures, exposure, trends and corrective actions, presented and recorded. • Where it usually breaks: the dashboard counts legal activity rather than showing whether the company's exposure is rising or falling. | • Report exposure trend rather than activity volume, since the number of contracts reviewed tells the executive nothing about whether the company is more or less exposed. • Report recurring deviation types, because these indicate where the standard terms or the negotiating position need changing. • Include the cost of disputes and external counsel, as this is the visible price of upstream failures. • Keep the format consistent so periods are comparable. • Require corrective actions with owners outside Legal where the cause sits elsewhere.
1216 | Legal | Approve the Legal budget and external-counsel fee strategy | Chief Legal Officer (CLO) | Trigger: When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. Action: The Chief Legal Officer (CLO) completes “Approve the Legal budget and external-counsel fee strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. Control/Handoff: Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. | The Chief Legal Officer (CLO) completes “Approve the Legal budget and external-counsel fee strategy” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. | Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sets the legal budget and how external lawyers will be used and paid. • Starts when: during annual budgeting, and when a major matter changes the outlook. • How it runs: (1) he estimates the internal and external legal requirement for the year. (2) He sets the fee strategy: panel arrangements, fixed fees or hourly. (3) He builds the budget with a provision for disputes. (4) He obtains approval. (5) He monitors spend against budget and reports variances. • Proof it happened: an approved legal budget with the external fee strategy and monitored spend against it. • Where it usually breaks: no provision is made for disputes, so a single significant matter consumes the entire annual budget. | • Include an explicit provision for dispute costs, since a single significant matter otherwise consumes the whole annual budget and constrains necessary advice. • Negotiate panel or fixed fee arrangements for routine work, as hourly billing on predictable work is the most expensive option. • Require approval for external instructions above a threshold, so spend is controlled at commitment rather than at invoice. • Track external spend by matter, because this reveals which parts of the business generate legal cost. • Report the cost of disputes back to the originating department, as this is what drives upstream improvement.
1217 | Legal | Approve Legal delegation, backup, continuity and records-recovery arrangements | Chief Legal Officer (CLO) | Trigger: When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. Action: The Chief Legal Officer (CLO) completes “Approve Legal delegation, backup, continuity and records-recovery arrangements” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. Control/Handoff: Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. | The Chief Legal Officer (CLO) completes “Approve Legal delegation, backup, continuity and records-recovery arrangements” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. | Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he makes sure legal keeps functioning when he is unavailable and that its records are protected. • Starts when: at the continuity review, on staff changes, and before planned absences. • How it runs: (1) he defines the delegation arrangements with limits and end dates. (2) He names deputies and confirms their authority. (3) He confirms external counsel know the escalation route in his absence. (4) He confirms the contract and matter records are backed up. (5) He tests the arrangements. • Proof it happened: written delegations with limits and end dates, named deputies, and confirmed and tested record backup arrangements. • Where it usually breaks: nothing can be legally approved during an absence, so contracts are signed unreviewed to keep the business moving. | • Provide a written delegation with defined limits for absences, since the alternative is contracts being signed unreviewed to keep the business moving. • Set delegation end dates and confirm the authority is withdrawn on return. • Ensure external counsel have a named alternative contact and escalation route. • Back up the contract register and matter files, as these carry the company's obligations and its evidence. • State which decisions may never be delegated, such as litigation commencement and settlement above a value.
1218 | Legal | Sponsor legal templates, training, workflow and control improvements | Chief Legal Officer (CLO) | Trigger: When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. Action: The Chief Legal Officer (CLO) completes “Sponsor legal templates, training, workflow and control improvements” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. Output/Evidence: an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. Control/Handoff: Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. Continuity/Escalation: A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. Timing: To be confirmed. | When the weekly/monthly review, budget cycle, absence, access failure, control gap or improvement need occurs. | The Chief Legal Officer (CLO) completes “Sponsor legal templates, training, workflow and control improvements” using approved contracts, executive instructions, risk and exposure records, legal advice, authority limits and controlled Legal registers. | an accurate Legal dashboard, exposure decision, approved budget route, continuity control or process-improvement action. | Critical deadlines, claims, proceedings, renewals and authority exceptions remain visible with named owners and dates; reserved decisions remain with the CLO or CEO despite delegation. | A CEO-approved qualified legal delegate may coordinate routine matters, but material deviations, settlements, proceedings, termination, regulatory response and reserved legal decisions remain with the CLO or escalate under the Delegation of Authority. | To be confirmed. | • In plain words: he sponsors improving the legal templates, training and workflows so the business gets it right the first time. • Starts when: improvement needs are identified, and at the annual planning cycle. • How it runs: (1) he identifies where legal problems recur. (2) He identifies whether the cause is template, training or process. (3) He prioritises the improvements. (4) He sponsors the delivery with R&D and the departments. (5) He confirms the recurrence reduces. • Proof it happened: an improvement plan with sponsored initiatives, delivery status and evidence that recurrence reduced. • Where it usually breaks: improvement focuses on legal's own processes, when most legal problems originate in commercial behaviour elsewhere. | • Direct improvement at the departments where the problems originate, since most legal exposure is created by commercial behaviour rather than by Legal's own processes. • Train the people who negotiate and sign, because they make the decisions Legal is later asked to fix. • Prefer a template or system control over training where possible, as controls persist while awareness fades. • Measure recurrence of the same legal problems, which is the only evidence the improvement worked. • Feed dispute lessons back into the standard terms, since disputes reveal exactly which clauses failed.
1219 | Legal | Triage legal service requests and assign matter risk, priority and response deadline | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Triage legal service requests and assign matter risk, priority and response deadline” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Triage legal service requests and assign matter risk, priority and response deadline” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she sorts incoming legal requests by how serious and urgent they are, and sets a response deadline for each. • Starts when: a legal request is received from any department. • How it runs: (1) she reviews the request and what is actually being asked. (2) She assesses the legal risk and the value involved. (3) She assigns a priority and a response deadline. (4) She confirms the deadline with the requester. (5) She logs it and starts work or queues it. • Proof it happened: a matter log with the risk rating, priority, assigned deadline and confirmation to the requester. • Where it usually breaks: everything arrives marked urgent, so genuinely high risk matters sit behind routine ones that simply came with more pressure. | • Set triage criteria based on risk and value rather than the requester's stated urgency, since everything arrives urgent and the genuinely serious matters then queue behind routine ones. • Publish the response times by category, so departments plan around them instead of escalating to jump the queue. • Require the request to state the decision needed and the deadline, because vague requests consume the most time. • Reject requests that arrive after the decision has been taken, and record them, as these indicate a process failure elsewhere. • Track request volumes by department, since a high volume from one area usually points at a template or training gap.
1220 | Legal | Conduct conflict checks and complete the matter-opening review | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Conduct conflict checks and complete the matter-opening review” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Conduct conflict checks and complete the matter-opening review” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: before taking on a matter she checks there is no conflict of interest and records the basic details. • Starts when: a new matter is being opened. • How it runs: (1) she identifies the parties involved. (2) She checks for conflicts against existing matters and relationships. (3) She confirms confidentiality requirements. (4) She opens the matter file with the classification. (5) She escalates any conflict identified. • Proof it happened: a completed conflict check and matter opening record with the parties, classification and confidentiality level. • Where it usually breaks: conflict checks are skipped on internal matters, so advice is given on a dispute involving someone who is also the requester's manager. | • Require a conflict check on internal matters too, particularly employment and conduct matters, since advising where the requester has a personal interest invalidates the advice. • Require the matter to be classified for confidentiality at opening, as reclassification later does not undo disclosure. • Record the parties fully, including related entities, because conflicts arise through group relationships. • Escalate identified conflicts to the CLO rather than managing them informally. • Open a matter file for every request, so advice given informally does not sit outside the record.
1221 | Legal | Confirm facts, instructions, objectives, decision owner and required deadline | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Confirm facts, instructions, objectives, decision owner and required deadline” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Confirm facts, instructions, objectives, decision owner and required deadline” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she establishes what actually happened, what is being asked, who will decide and by when. • Starts when: a matter is opened and work begins. • How it runs: (1) she obtains the facts from the requester and the records. (2) She confirms the instruction and what decision is needed. (3) She identifies the business owner who will decide. (4) She confirms the deadline and what drives it. (5) She records the instruction in writing. • Proof it happened: a written record of the confirmed facts, the instruction, the decision owner and the deadline. • Where it usually breaks: advice is given on the facts as described rather than as documented, and the facts turn out differently when the records are examined. | • Verify the facts against the documents rather than relying on the description, since advice based on a mistaken account of events is worse than no advice. • Record the instruction in writing and confirm it back, as the scope of what was asked is frequently disputed afterwards. • Identify the business owner who will act on the advice, because advice with no owner is not implemented. • Establish what drives the deadline, as artificial deadlines distort the analysis. • State what facts were assumed rather than verified, so the advice is correctly qualified.
1222 | Legal | Identify the applicable contract, authority, policy and regulatory framework | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Identify the applicable contract, authority, policy and regulatory framework” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Identify the applicable contract, authority, policy and regulatory framework” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she works out which contract, policy, authority and regulation actually govern the question. • Starts when: the facts and instruction are confirmed. • How it runs: (1) she identifies the governing contract and its version. (2) She identifies the applicable internal policies and authority limits. (3) She identifies the applicable law and regulation. (4) She identifies the order of precedence where documents conflict. (5) She records the framework applied. • Proof it happened: a recorded framework identifying the governing contract, policies, authority limits and applicable regulation. • Where it usually breaks: advice is given on the standard contract terms when the executed contract contains negotiated amendments that change the position entirely. | • Work from the executed contract including all amendments rather than the standard template, since negotiated changes frequently reverse the position the template would give. • Check for subsequent variations, addenda and agreed correspondence, as these modify the contract even when not formally issued as amendments. • Identify the order of precedence, because contradictions between contract, specification and drawings are the norm. • Confirm the governing law and jurisdiction clause, as this determines which rules apply at all. • Record the documents relied on, so the advice can be reassessed if a further document emerges.
1223 | Legal | Research legal issues and validate the current legal position | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Research legal issues and validate the current legal position” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Research legal issues and validate the current legal position” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she researches the legal position and confirms it is still current before advising on it. • Starts when: the framework is identified and analysis begins. • How it runs: (1) she identifies the legal issues requiring research. (2) She researches the applicable law and its current state. (3) She checks for recent changes or developments. (4) She identifies where the position is uncertain. (5) She records the research and the sources. • Proof it happened: research records with the sources relied on, the position established and any uncertainty identified. • Where it usually breaks: the position is taken from a previous matter without checking whether the law or the contract terms have changed since. | • Verify the position is current rather than reusing a prior matter's conclusion, since both the law and the company's contract terms change and stale advice is confidently wrong. • Record the sources, so the advice can be reviewed and updated when the law moves. • State explicitly where the position is uncertain, because false confidence in advice leads to worse decisions than acknowledged doubt. • Escalate to external counsel where the position is genuinely unsettled and the exposure is material. • Build a reference note for recurring issues, so the same research is not repeated.
1224 | Legal | Prepare written legal advice, options and recommended controls | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Prepare written legal advice, options and recommended controls” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Prepare written legal advice, options and recommended controls” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she writes the advice, setting out the options and what controls the business should put in place. • Starts when: the analysis is complete. • How it runs: (1) she states the question and the facts relied on. (2) She sets out the position and the reasoning. (3) She sets out the options with their risks. (4) She recommends a course and the controls needed. (5) She issues it to the business owner. • Proof it happened: written legal advice stating the facts, position, options, recommendation and the controls required. • Where it usually breaks: the advice explains the legal position without saying what the business should actually do, so nothing changes. | • Require the advice to state a recommendation and the practical steps, since advice that only describes the legal position leaves the business unable to act on it. • State the facts relied on at the front, so the advice is visibly conditional on them. • Present options with their consequences rather than a single answer, because the business owner makes the decision. • Write in plain language, as advice the requester cannot follow is not implemented. • Mark the advice as privileged and restrict its distribution, since wide circulation waives the protection.
1225 | Legal | Record advice assumptions, limitations, actions and business-owner acceptance | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Record advice assumptions, limitations, actions and business-owner acceptance” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Record advice assumptions, limitations, actions and business-owner acceptance” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she records what the advice assumed, what it did not cover, and that the business accepted it. • Starts when: advice is issued. • How it runs: (1) she records the assumptions the advice rests on. (2) She records the limitations and what was excluded. (3) She records the actions recommended and their owners. (4) She obtains the business owner's acknowledgement. (5) She files it with the matter. • Proof it happened: a record of assumptions, limitations, recommended actions and the business owner's acknowledgement. • Where it usually breaks: advice is given verbally and never recorded, so its scope and conditions are disputed when the outcome is bad. | • Require verbal advice on material matters to be confirmed in writing, since undocumented advice becomes whatever each party later recalls when the outcome is poor. • Record what the advice does not cover, as advice is routinely applied to situations it was never given for. • Obtain the business owner's acknowledgement, because this establishes that the decision and its risk sit with the business. • Record where the business chose not to follow the advice, and who accepted that risk. • File everything with the matter, so the file shows the basis on which decisions were made.
1226 | Legal | Close the advice matter and confirm implementation or outstanding actions | Legal Counsel (Lead) | Trigger: When a department submits a legal request, issue, decision deadline or potential exposure. Action: The Legal Counsel (Lead) completes “Close the advice matter and confirm implementation or outstanding actions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. Control/Handoff: Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a department submits a legal request, issue, decision deadline or potential exposure. | The Legal Counsel (Lead) completes “Close the advice matter and confirm implementation or outstanding actions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled Legal matter with verified instructions, analysis, written advice, actions, assumptions and closure status. | Only qualified Legal Counsel provides legal advice; the requesting business owner decides and implements business action, while high-risk, precedent-setting or authority-sensitive matters escalate to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she closes the matter, confirming either that the advice was implemented or what remains outstanding. • Starts when: the advice has been issued and the business has had time to act. • How it runs: (1) she confirms with the business owner whether the advice was implemented. (2) She records the outstanding actions. (3) She records the outcome. (4) She identifies any lesson for templates or training. (5) She closes the matter or keeps it open on the outstanding items. • Proof it happened: a matter closure record with implementation confirmed, outstanding actions recorded and any lessons identified. • Where it usually breaks: matters are closed when the advice is sent, so nobody knows whether the risk was actually addressed. | • Close matters on implementation rather than on issue of the advice, since closing at issue means Legal never learns whether the exposure was addressed. • Record outstanding actions with owners rather than closing with them open. • Capture lessons for the standard terms or training, as recurring advice on the same issue indicates an upstream fix is available. • Report unimplemented material advice to the CLO, because this is an accepted risk nobody formally accepted. • Keep the matter file retrievable, since the same question returns and the analysis should not be repeated.
1227 | Legal | Review tender invitations and conditions of participation | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review tender invitations and conditions of participation” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review tender invitations and conditions of participation” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she reads the tender documents to find the risks buried in the conditions before the company bids. • Starts when: a tender invitation is received and a bid decision is being made. • How it runs: (1) she reviews the conditions of participation and eligibility. (2) She identifies the onerous or unacceptable terms. (3) She checks the bid validity, bond and security requirements. (4) She identifies what must be qualified or clarified. (5) She reports the legal position for the bid decision. • Proof it happened: a tender legal review identifying onerous terms, security requirements and the matters needing qualification. • Where it usually breaks: the review happens after the decision to bid, so terms that should have caused a no bid decision are simply absorbed. | • Require the legal review before the bid or no bid decision, since terms serious enough to decline the tender are otherwise discovered once the company is committed. • Check bid bond and security requirements early, as these consume facility capacity and take time to arrange. • Identify terms that cannot be qualified because the client prohibits qualifications, as this changes the bid decision entirely. • Check the bid validity period, since a long validity leaves the company's price exposed to cost movement. • Note the clarification deadline, because questions cannot be raised afterwards.