1228 | Legal | Prepare the tender legal-risk and deviation matrix | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Prepare the tender legal-risk and deviation matrix” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Prepare the tender legal-risk and deviation matrix” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she lists every term the company cannot accept and what it proposes instead. • Starts when: the tender legal review is complete. • How it runs: (1) she lists each unacceptable term with the clause reference. (2) She states the risk each creates. (3) She states the proposed alternative wording. (4) She classifies each as essential or negotiable. (5) She obtains approval of the matrix before submission. • Proof it happened: an approved deviation matrix with clause references, risks, proposed wording and the essential items identified. • Where it usually breaks: deviations are described in general terms rather than with clause references and wording, so the client rejects them all as unclear. | • Require clause references and proposed replacement wording, since deviations expressed as general concerns are rejected wholesale as unclear. • Classify each deviation as essential or negotiable, so the negotiating team knows what it may concede. • Price the risk where a deviation will not be accepted, as the alternative to removing the risk is charging for it. • Carry the matrix through to contract signature, because deviations raised at tender are frequently forgotten at award. • Record which deviations the client accepted, as only these form part of the contract.
1229 | Legal | Review contract scope, schedules, document priority and interpretation clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review contract scope, schedules, document priority and interpretation clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review contract scope, schedules, document priority and interpretation clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks the scope, the schedules and the rules for reading the contract when documents contradict each other. • Starts when: a contract is under review. • How it runs: (1) she reviews the scope definition for gaps and ambiguity. (2) She checks the schedules are attached and consistent. (3) She checks the document priority clause. (4) She checks the interpretation and definitions clauses. (5) She records the findings and the required changes. • Proof it happened: a review record covering scope definition, schedule consistency, document priority and interpretation clauses. • Where it usually breaks: the scope is defined by a general obligation to complete the works, so anything not excluded becomes included at no extra cost. | • Challenge any general obligation to complete the works or similar catch all wording, since this makes everything not excluded into free scope. • Check every schedule referenced is actually attached, because a missing schedule is interpreted against the party relying on it. • Require a document priority clause, as contradictions between documents are certain and someone must win. • Check the definitions for terms used differently elsewhere in the contract. • Require the drawing revisions forming the contract to be listed, since this determines what was priced.
1230 | Legal | Review price, payment, certification, set-off and retention clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review price, payment, certification, set-off and retention clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review price, payment, certification, set-off and retention clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks how and when the company gets paid, and what can be deducted from it. • Starts when: a contract is under review. • How it runs: (1) she reviews the payment terms and the trigger for payment. (2) She reviews the certification process and the timeframes. (3) She reviews the set off and deduction rights. (4) She reviews the retention percentage and release conditions. (5) She records the findings and the required changes. • Proof it happened: a review record covering payment triggers, certification, set off rights and retention terms. • Where it usually breaks: the client has an unlimited right of set off, so any alleged claim can be deducted from payment without being proven. | • Challenge unlimited set off rights, since these allow the client to withhold payment against unproven allegations and the company must then litigate for its own money. • Check whether payment depends on certification and what happens if certification is simply not issued, as this is a common cash trap. • Require the payment period to start from a definite event rather than at the client's discretion. • Check the retention release conditions and whether they depend on events outside the company's control. • Require interest on late payment, or there is no cost to the client in paying late.
1231 | Legal | Review programme, delay, liquidated-damages and extension-of-time clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review programme, delay, liquidated-damages and extension-of-time clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review programme, delay, liquidated-damages and extension-of-time clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks the time obligations, the penalties for being late and how extensions of time work. • Starts when: a contract is under review. • How it runs: (1) she reviews the completion obligations and the milestones. (2) She reviews the liquidated damages rate and any cap. (3) She reviews the extension of time provisions and the qualifying events. (4) She reviews the notice requirements for claiming time. (5) She records the findings and the required changes. • Proof it happened: a review record covering completion obligations, damages, extension provisions and notice requirements. • Where it usually breaks: liquidated damages are uncapped, so a delay the company did not cause can exceed the entire contract value. | • Require a cap on liquidated damages, since uncapped delay damages can exceed the contract value and turn a delay into an existential loss. • Check the qualifying events for extension of time cover client and third party delays, not only force majeure. • Check the notice period for claiming time, as this is the most frequently missed and most consequential deadline in construction contracts. • Challenge any provision making liquidated damages a penalty with no cap or relationship to actual loss. • Check whether concurrent delay is addressed, because its treatment determines most delay outcomes.
1232 | Legal | Review variation, change-control and additional-work clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review variation, change-control and additional-work clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review variation, change-control and additional-work clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks how changes to the work are instructed, valued and paid for. • Starts when: a contract is under review. • How it runs: (1) she reviews who may instruct a variation. (2) She reviews the valuation mechanism and the rates applied. (3) She reviews the notice requirements for claiming a variation. (4) She reviews whether time is claimable with cost. (5) She records the findings and the required changes. • Proof it happened: a review record covering variation authority, valuation, notice requirements and time entitlement. • Where it usually breaks: the contract requires written instruction but work proceeds on verbal direction, so the variation is later denied entirely. | • Establish who may instruct a variation and require the project team to be briefed, since work performed on a verbal instruction is routinely denied as a variation. • Check the valuation mechanism provides a fair basis where no contract rate applies, as otherwise the client sets the price. • Check whether time and cost must be claimed together or separately, because claiming one can forfeit the other. • Require a mechanism for instructed work where the price is not yet agreed, so work is not delayed by pricing. • Check the notice period for variation claims, which is frequently shorter than people assume.
1233 | Legal | Review warranty, defects-liability and performance-obligation clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review warranty, defects-liability and performance-obligation clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review warranty, defects-liability and performance-obligation clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks what the company guarantees, for how long, and what it must put right. • Starts when: a contract is under review. • How it runs: (1) she reviews the warranty scope and duration. (2) She reviews the defects liability period and its start date. (3) She reviews the performance obligations and how they are measured. (4) She checks whether obligations extend beyond the company's control. (5) She records the findings and the required changes. • Proof it happened: a review record covering warranty scope, defects liability, performance obligations and their measurement. • Where it usually breaks: a fitness for purpose obligation is accepted rather than reasonable skill and care, which is uninsurable and effectively unlimited. | • Challenge fitness for purpose obligations and seek reasonable skill and care instead, since fitness for purpose is generally uninsurable and exposes the company without cover. • Check the defects liability start date, because a period starting at delivery rather than completion expires before the client even occupies. • Check whether the obligation extends to design the company did not carry out. • Require performance obligations to be measurable, as unmeasurable obligations are never satisfied. • Ensure subcontractor warranties extend at least as long as the company's own obligation.
1234 | Legal | Review indemnity, liability, exclusion and limitation clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review indemnity, liability, exclusion and limitation clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review indemnity, liability, exclusion and limitation clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks the clauses that decide how much the company can be made to pay when something goes wrong. • Starts when: a contract is under review. • How it runs: (1) she reviews the indemnity scope and whether it is capped. (2) She reviews the overall liability cap. (3) She reviews the exclusions of consequential and indirect loss. (4) She identifies liabilities that survive termination. (5) She records the findings and the required changes. • Proof it happened: a review record covering indemnity scope, liability caps, exclusions and surviving liabilities. • Where it usually breaks: an uncapped indemnity is accepted because it appears standard, so the company's exposure on one contract exceeds its entire net worth. | • Escalate any uncapped indemnity or unlimited liability to the CLO and the CEO, since a single such clause can create exposure larger than the company itself. • Require consequential and indirect loss to be excluded, as these are unquantifiable at the time of signing. • Check the indemnity is limited to the company's own negligence rather than extending to the client's. • Check which liabilities survive termination and for how long. • Check the liability cap is not undermined by carve outs that swallow it.
1235 | Legal | Review insurance, bond, guarantee and security clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review insurance, bond, guarantee and security clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review insurance, bond, guarantee and security clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks what insurance and security the company must provide and whether it can actually obtain it. • Starts when: a contract is under review. • How it runs: (1) she reviews the insurance types, limits and periods required. (2) She confirms with the insurer that the cover is obtainable. (3) She reviews the bond and guarantee wording, particularly whether on demand. (4) She reviews the validity periods and release conditions. (5) She records the findings and the required changes. • Proof it happened: a review record covering insurance requirements, confirmed obtainability and the bond and guarantee terms. • Where it usually breaks: insurance is contractually required that the company cannot actually obtain, so it is in breach from the day it signs. | • Confirm with the insurer that the required cover is obtainable before signing, since agreeing to insurance the company cannot obtain puts it in breach from day one. • Identify whether bonds are on demand or conditional, as an on demand bond can be called without any proven default. • Check the bond validity period against the actual project duration including the defects period. • Check the release conditions, because a bond with no clear release mechanism ties up facility capacity indefinitely. • Confirm the CFO has facility capacity before committing to the security.
1236 | Legal | Review suspension, default, termination and step-in clauses | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Review suspension, default, termination and step-in clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Review suspension, default, termination and step-in clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks what happens if either side defaults, and what the client can do to take over the work. • Starts when: a contract is under review. • How it runs: (1) she reviews the client's suspension and termination rights. (2) She reviews the company's own rights in the same events. (3) She reviews the notice and cure periods. (4) She reviews the step in and taking over provisions. (5) She records the findings and the required changes. • Proof it happened: a review record covering suspension, default, termination, notice periods and step in rights. • Where it usually breaks: the client can terminate for convenience with no compensation, so the company can lose the contract and recover nothing for its investment. | • Require compensation for termination for convenience, since without it the company can be removed after investing in mobilisation and recover nothing. • Check the company has reciprocal suspension rights for non payment, because otherwise it must keep performing while unpaid. • Require a cure period before termination for default, as immediate termination rights are routinely used opportunistically. • Check what happens to materials, plant and completed work on termination. • Check the notice requirements the company must follow, since defective notice destroys a valid termination.
1237 | Legal | Draft and negotiate client construction and design contracts | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Draft and negotiate client construction and design contracts” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Draft and negotiate client construction and design contracts” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and negotiates the client contract itself, working the terms into an acceptable position. • Starts when: a contract is to be negotiated after award or during tender clarification. • How it runs: (1) she prepares the position from the review and the deviation matrix. (2) She drafts the proposed amendments. (3) She negotiates with the client, keeping the commercial team informed. (4) She records each agreed change in writing. (5) She prepares the final text for approval. • Proof it happened: a negotiation record with the amendments proposed, agreed and recorded, and the final text prepared. • Where it usually breaks: changes are agreed in meetings and not recorded, so the final document does not reflect what was actually agreed. | • Record every agreed change in writing at the time, since final documents routinely fail to reflect what the parties actually agreed in meetings. • Track the negotiation through versions with changes marked, so nothing is altered without being noticed. • Keep the commercial team informed of what is being conceded, because they must live with the result. • Prohibit anyone other than authorised negotiators from discussing terms with the client. • Compare the final text against the last agreed version before approval, as late unilateral changes are common.
1238 | Legal | Prepare the final client-contract legal approval pack | Legal Counsel (Lead) | Trigger: When a tender or client contract package is received for qualification, drafting, negotiation or final approval. Action: The Legal Counsel (Lead) completes “Prepare the final client-contract legal approval pack” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. Control/Handoff: Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a tender or client contract package is received for qualification, drafting, negotiation or final approval. | The Legal Counsel (Lead) completes “Prepare the final client-contract legal approval pack” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a contract review checklist, legal-risk/deviation matrix, negotiated draft and complete CLO approval pack. | Technical scope and feasibility are confirmed by CTO, commercial terms by CMO, financial/tax terms by CFO and execution capacity by COO; unresolved material legal exposure is reserved for the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she puts together the final pack showing what was agreed and what risks the company is accepting, for approval before signature. • Starts when: negotiation concludes and approval is required. • How it runs: (1) she summarises the final position and the key terms. (2) She lists the accepted deviations and their exposure. (3) She confirms the insurance, bond and security position. (4) She identifies the authority level required. (5) She submits for approval before signature. • Proof it happened: a legal approval pack with the final terms, accepted deviations and exposure, approved at the correct authority level. • Where it usually breaks: the pack goes for signature without the accepted risks being stated, so the signatory does not know what they are accepting. | • Require the accepted risks to be stated plainly in the approval pack, since a signatory who does not know what has been accepted cannot meaningfully approve it. • Quantify the exposure of each accepted deviation where possible. • Determine the authority level from the total exposure rather than the contract value. • Confirm insurance and security are actually in place rather than planned. • Attach the final text to the approval, so what is approved and what is signed are the same document.
1239 | Legal | Draft and review supplier purchase terms and non-standard purchase-order clauses | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review supplier purchase terms and non-standard purchase-order clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review supplier purchase terms and non-standard purchase-order clauses” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she reviews the purchase terms and any non standard clauses suppliers try to introduce on orders. • Starts when: a supplier proposes non standard terms or a purchase order requires special clauses. • How it runs: (1) she reviews the supplier's proposed terms. (2) She identifies the departures from the company's standard terms. (3) She assesses the exposure each creates. (4) She drafts acceptable alternative wording. (5) She records the approved position. • Proof it happened: a review record with the supplier's terms assessed, alternatives drafted and the approved position recorded. • Where it usually breaks: the supplier's terms arrive attached to their quotation and are accepted by default when the order is placed. | • State that the company's terms prevail and that supplier terms attached to quotations are rejected unless expressly accepted, since silence is treated as acceptance. • Require every supplier qualification to be listed and expressly accepted or rejected on the order. • Check for limitation of liability, exclusion of warranty and title retention clauses, which are the most damaging supplier terms. • Check delivery terms and where risk passes, as this determines who bears loss in transit. • Maintain pre approved alternative wording, so buyers are not negotiating legal terms themselves.
1240 | Legal | Draft and review construction and specialist subcontract agreements | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review construction and specialist subcontract agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review construction and specialist subcontract agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews the subcontracts for construction and specialist work. • Starts when: a subcontract is to be prepared or a subcontractor's terms are received. • How it runs: (1) she prepares the subcontract from the approved template. (2) She checks the back to back position against the main contract. (3) She defines the scope by reference to drawings and specifications. (4) She confirms the security and insurance requirements. (5) She prepares it for approval and execution. • Proof it happened: a drafted subcontract with the back to back check completed, scope defined by reference and security requirements stated. • Where it usually breaks: the main contract obligations are not passed down, so the company owes the client more than it can recover from the subcontractor. | • Complete a documented back to back check on time, damages, defects liability, notices and payment, since every gap left is carried by the company alone. • Define scope by drawing and specification reference rather than description, as descriptive scope generates variation claims. • Require the subcontract notice periods to be shorter than the main contract's, so the company can pass claims up in time. • Require insurance and bonds before mobilisation rather than before payment. • Prohibit mobilisation before signature, with only a capped and dated letter of intent as an exception.
1241 | Legal | Draft and review consultancy and professional-services agreements | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review consultancy and professional-services agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review consultancy and professional-services agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews the agreements with consultants and professional service providers. • Starts when: a consultancy appointment is to be made. • How it runs: (1) she prepares the agreement from the approved template. (2) She defines the services and the deliverables. (3) She sets the standard of care and the liability position. (4) She addresses intellectual property and reuse rights. (5) She confirms professional indemnity cover. • Proof it happened: a drafted consultancy agreement with defined deliverables, standard of care, liability terms and intellectual property provisions. • Where it usually breaks: intellectual property is not addressed, so the company cannot reuse designs it has paid for. | • Address intellectual property and reuse rights explicitly, since without them the company cannot reuse designs it has fully paid for. • Require professional indemnity cover to be verified and maintained for the liability period, not just at appointment. • Define the deliverables specifically, as consultancy scope defined by activity rather than output produces disputes. • Set the standard of care as reasonable skill and care rather than fitness for purpose. • Require the liability cap to be proportionate to the fee and the risk, as a low cap on a high risk design is worthless.
1242 | Legal | Draft and review non-disclosure and confidentiality agreements | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review non-disclosure and confidentiality agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review non-disclosure and confidentiality agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews the confidentiality agreements the company signs and asks others to sign. • Starts when: confidential information is to be shared or received. • How it runs: (1) she confirms who is disclosing and who is receiving. (2) She defines the confidential information and the permitted purpose. (3) She sets the duration and the return or destruction obligations. (4) She checks the carve outs are reasonable. (5) She approves and issues for signature. • Proof it happened: an executed confidentiality agreement with defined information, purpose, duration and return obligations. • Where it usually breaks: a one sided NDA is signed on the counterparty's form, so the company is bound and receives no protection in return. | • Require NDAs to be mutual where information flows both ways, since signing a one sided form means the company is bound and unprotected. • Define the permitted purpose narrowly, as a broad purpose allows the recipient to use the information for anything. • Set a duration and state what happens to the information on expiry or termination. • Check the carve outs, because overly broad exceptions can remove the protection entirely. • Maintain a register of NDAs, so the company knows what confidentiality obligations it has undertaken.
1243 | Legal | Draft and review memoranda of understanding, letters of intent and heads of terms | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review memoranda of understanding, letters of intent and heads of terms” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review memoranda of understanding, letters of intent and heads of terms” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews preliminary documents such as MOUs, letters of intent and heads of terms. • Starts when: a preliminary arrangement is proposed before a full contract. • How it runs: (1) she confirms the commercial intent. (2) She determines whether it should be binding or not. (3) She drafts it so the intended effect is unambiguous. (4) She caps any commitment and sets an expiry. (5) She approves it for signature. • Proof it happened: a drafted preliminary document stating clearly whether it binds, with commitments capped and an expiry date. • Where it usually breaks: a document intended as non binding creates enforceable obligations, and the company is committed before due diligence is done. | • Require every preliminary document to state expressly whether it is binding, since documents intended as non binding routinely create enforceable obligations. • Cap the value and set an expiry date on any letter of intent, as open ended ones leave obligations with no protection. • State what happens if the full contract is never concluded, particularly regarding cost recovery. • Avoid language of agreement in non binding documents, because conduct and wording together can create a contract. • Track outstanding letters of intent as a reported exception, since unconverted ones are a common hidden exposure.
1244 | Legal | Draft and review joint-venture, consortium and partnership agreements | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review joint-venture, consortium and partnership agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review joint-venture, consortium and partnership agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews the agreements for joint ventures, consortia and partnerships. • Starts when: a collaboration is agreed in principle. • How it runs: (1) she confirms the structure and the commercial split. (2) She addresses liability between the parties. (3) She addresses governance, decision making and deadlock. (4) She addresses default, exit and termination. (5) She prepares it for approval and signature. • Proof it happened: a drafted joint venture or consortium agreement covering liability, governance, deadlock, default and exit. • Where it usually breaks: joint and several liability is accepted, so the company is fully liable to the client for its partner's failures. | • Escalate joint and several liability to the CLO and ownership, since it exposes the company in full for its partner's failures with only a claim against that partner as recourse. • Require a deadlock mechanism, because collaborations without one become paralysed at the first disagreement. • Require default and exit provisions, including what happens if a partner becomes insolvent mid project. • Address how the client relationship and the work continue if the collaboration ends. • Require partner due diligence on financial standing before signature.
1245 | Legal | Draft and review agency, referral and marketing-service agreements | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review agency, referral and marketing-service agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review agency, referral and marketing-service agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews agency, referral and marketing agreements, which carry particular legal risk. • Starts when: such an arrangement is proposed. • How it runs: (1) she confirms the arrangement and how payment is calculated. (2) She checks the anti bribery position carefully. (3) She checks the agent has no authority to bind the company. (4) She sets the termination rights and any compensation. (5) She prepares it for approval. • Proof it happened: a drafted agreement with the payment basis, anti bribery provisions, authority limits and termination terms. • Where it usually breaks: success fees are paid to an intermediary with no documented service, which is a serious bribery exposure. | • Require documented services and a demonstrable commercial rationale for every payment, since success fees to intermediaries with no evidenced service are a serious bribery exposure for the company and its officers. • Require anti bribery warranties, audit rights and immediate termination for breach. • State expressly that the agent has no authority to bind the company or make representations. • Conduct due diligence on the intermediary, including ownership and any government connections. • Require CLO approval for every such arrangement regardless of value.
1246 | Legal | Draft and review lease, facility and operational-service agreements | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review lease, facility and operational-service agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review lease, facility and operational-service agreements” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews leases and agreements for premises, facilities and operational services. • Starts when: a lease or facility agreement is proposed or renewed. • How it runs: (1) she reviews the term, rent and escalation terms. (2) She reviews the repair and reinstatement obligations. (3) She reviews the termination and break rights. (4) She reviews the permitted use against the company's actual use. (5) She prepares it for approval. • Proof it happened: a review record covering term, rent, repair obligations, termination rights and permitted use. • Where it usually breaks: the reinstatement obligation is overlooked, so a large unbudgeted cost arrives at the end of the lease. | • Identify and quantify the reinstatement obligation at signature, since it arrives as a large unbudgeted cost at the end of the lease when nobody remembers agreeing to it. • Check the permitted use covers the company's actual activities, as operating outside it is a breach. • Check break rights and the notice required to exercise them, because these deadlines are missed and the lease then runs on. • Check the rent review mechanism, as open market reviews can produce large increases. • Notify Finance of the full committed cost over the term, since leases are long term financial commitments.
1247 | Legal | Draft and review amendments, addenda, novations and assignments | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Draft and review amendments, addenda, novations and assignments” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Draft and review amendments, addenda, novations and assignments” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts and reviews changes to existing contracts, including transfers to other parties. • Starts when: an amendment, novation or assignment is required. • How it runs: (1) she identifies what is changing and what stays. (2) She checks the contract permits the change and whether consent is needed. (3) She drafts the document referencing the original contract precisely. (4) She confirms which obligations transfer and which remain. (5) She prepares it for approval and signature. • Proof it happened: a drafted amendment or novation with the original contract referenced, consents obtained and obligations clearly allocated. • Where it usually breaks: an assignment is treated as a novation, so the company remains liable for obligations it believes it has transferred. | • Distinguish assignment from novation explicitly, since assignment transfers benefits but leaves the company liable for the obligations it thinks it has passed on. • Check whether the contract requires consent to assign or novate, as an unconsented transfer can be a breach. • Reference the original contract and all prior amendments precisely, so the document chain remains unambiguous. • State what happens to accrued rights and liabilities up to the date of the change. • Require all parties including the client to sign a novation, as a two party novation is ineffective.
1248 | Legal | Prepare the final agreement execution and business-owner handover pack | Legal Counsel (Lead) | Trigger: When Procurement or another department submits a complete agreement request and approved business terms. Action: The Legal Counsel (Lead) completes “Prepare the final agreement execution and business-owner handover pack” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. Control/Handoff: CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When Procurement or another department submits a complete agreement request and approved business terms. | The Legal Counsel (Lead) completes “Prepare the final agreement execution and business-owner handover pack” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a reviewed or drafted agreement, deviation record, approval route, execution version and business-owner handover. | CPO or the requesting executive owns vendor selection, scope and commercial need; Legal controls contractual wording and risk, and no agreement proceeds with missing authority or unresolved material deviation. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the final pack for signing and hands the contract over to the business owner who must perform it. • Starts when: an agreement is approved and ready for execution. • How it runs: (1) she confirms the final text matches the approved version. (2) She confirms the signatory has authority. (3) She arranges execution and obtains the counterparty's signature. (4) She prepares the handover summary of key obligations. (5) She hands over to the business owner and files the executed document. • Proof it happened: an executed agreement with authority confirmed, a handover summary issued and the document filed. • Where it usually breaks: the contract is signed and filed with nobody briefed, so the obligations it contains are discovered only when breached. | • Require a handover briefing on the key obligations and deadlines, since a contract signed and filed without briefing means its obligations are discovered at the point of breach. • Confirm the signatory's authority against the matrix, as a contract signed without authority is contestable. • Check the executed version against the approved version, because late changes before signature do occur. • Obtain fully signed copies from the counterparty rather than assuming, as unsigned counterparts are common. • File the executed original in the controlled record, not in personal email.
1249 | Legal | Prepare the contract-obligations matrix and notice schedule | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Prepare the contract-obligations matrix and notice schedule” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Prepare the contract-obligations matrix and notice schedule” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she extracts what the company must do under the contract and when, particularly the notice deadlines. • Starts when: a contract is executed, before project activation. • How it runs: (1) she extracts every obligation with its deadline. (2) She extracts every notice provision with its time limit and method. (3) She identifies the obligations that are easy to miss. (4) She assigns each to an owner. (5) She issues the matrix and the notice schedule to the project team. • Proof it happened: an obligations matrix and notice schedule with deadlines, methods and owners, issued to the project team. • Where it usually breaks: the obligations stay inside the contract document, so the project team is expected to comply with terms it has never read. | • Extract the obligations into a usable schedule, since expecting a project team to comply with a contract it has never read is the root of most lost entitlement. • Record the notice method and address as well as the time limit, because a notice served incorrectly is no notice. • Assign each obligation to a named owner, not to the project team collectively. • Load the deadlines into a system that will prompt, as a schedule nobody looks at prevents nothing. • Update the matrix when the contract is amended.
1250 | Legal | Conduct the project legal kickoff and contract-administration handover | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Conduct the project legal kickoff and contract-administration handover” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Conduct the project legal kickoff and contract-administration handover” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she runs the session where the project team is told what the contract actually requires of them. • Starts when: the obligations matrix is prepared and before project mobilisation. • How it runs: (1) she arranges the session with the project team. (2) She briefs the key obligations, deadlines and notice requirements. (3) She explains the consequences of missing them. (4) She confirms who owns each obligation. (5) She records the briefing and the attendance. • Proof it happened: a legal kickoff record with the obligations briefed, owners confirmed and attendance recorded. • Where it usually breaks: no kickoff is held, so the first time the team reads the contract is when a claim is being defended. | • Make the legal kickoff mandatory before mobilisation, since the alternative is the team reading the contract for the first time while defending a claim. • Focus the briefing on notice deadlines and record keeping obligations, as these are what determine whether entitlement survives. • Confirm the owner of each obligation in the session, so accountability is accepted rather than assigned in absence. • Record attendance, and brief anyone who joins the project later. • Repeat the briefing when the contract is materially amended.
1251 | Legal | Review client, consultant and contract-administrator instructions | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Review client, consultant and contract-administrator instructions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Review client, consultant and contract-administrator instructions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks instructions coming from the client or consultant for what they legally mean and oblige. • Starts when: an instruction is received from the client, consultant or contract administrator. • How it runs: (1) she checks the instruction is issued by someone authorised. (2) She checks it is issued in the required form. (3) She assesses whether it constitutes a variation or a direction. (4) She identifies the notice or response required. (5) She advises the project team on the response. • Proof it happened: reviewed instructions with authority and form checked, the legal effect assessed and the required response advised. • Where it usually breaks: an instruction that is actually a variation is treated as clarification, so the work is done with no entitlement to payment. | • Assess every instruction for whether it constitutes a variation, since work done under an instruction treated as clarification is performed for free. • Check the issuer's authority, because an instruction from an unauthorised person creates no entitlement and may create no obligation either. • Identify the response deadline, as failure to respond can constitute acceptance of the client's position. • Require instructions received verbally to be confirmed in writing the same day. • Log all instructions centrally, since the pattern of instructions is itself evidence in any delay claim.
1252 | Legal | Draft contractual notices that preserve company rights and remedies | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Draft contractual notices that preserve company rights and remedies” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Draft contractual notices that preserve company rights and remedies” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she drafts the formal notices that protect the company's contractual rights. • Starts when: an event occurs requiring notice under the contract. • How it runs: (1) she identifies the applicable notice provision and its time limit. (2) She drafts the notice citing the clause and the facts. (3) She reserves the company's rights where the full position is not yet known. (4) She arranges service by the required method. (5) She retains proof of service and diarises the follow up. • Proof it happened: served notices citing the contractual basis, served by the required method with proof retained. • Where it usually breaks: the notice is drafted as a general complaint without citing the clause, so it does not qualify as notice under the contract. | • Require every notice to cite the specific contract clause it is served under, since a general letter of complaint does not qualify as contractual notice and the entitlement is lost. • Include a reservation of rights where the full effect is not yet known, so the position is not limited by an early estimate. • Serve by the exact method and to the exact address the contract requires. • Retain proof of service, as the date of service determines whether the notice was in time. • Diarise the follow up obligations, because many notices require further particulars within a further period.
1253 | Legal | Review variations, additional works and change instructions for legal effect | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Review variations, additional works and change instructions for legal effect” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Review variations, additional works and change instructions for legal effect” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she checks what variations and change instructions actually mean legally, including for time and money. • Starts when: a variation or change instruction is received or proposed. • How it runs: (1) she confirms the instruction is a valid variation. (2) She identifies the entitlement to cost and to time. (3) She identifies the notice requirements triggered. (4) She checks the effect on other obligations. (5) She advises on the position and the required action. • Proof it happened: a review record per variation with validity confirmed, entitlement identified and notice requirements stated. • Where it usually breaks: the cost is claimed and the time entitlement is forgotten, so the company is paid for the work and then penalised for the delay it caused. | • Assess time entitlement alongside cost for every variation, since claiming cost while forgetting time means being paid for the work and penalised for the resulting delay. • Identify the notice requirements triggered by the variation, as these are separate from the variation instruction itself. • Check the cumulative effect of variations, because a series of small changes can amount to a change in the character of the work. • Advise on whether work should proceed before the price is agreed, as this differs by contract. • Record the legal position taken, so the claim remains consistent.
1254 | Legal | Prepare extension-of-time, delay and disruption claim submissions | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Prepare extension-of-time, delay and disruption claim submissions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Prepare extension-of-time, delay and disruption claim submissions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the claims for extra time and for the cost of disruption. • Starts when: a delay or disruption event occurs and a claim is to be prepared. • How it runs: (1) she confirms the contractual entitlement and the notice position. (2) She establishes the cause and the causal link to the delay. (3) She coordinates the programme analysis and the cost evidence. (4) She prepares the submission with the contractual basis. (5) She submits within the time limit and tracks the response. • Proof it happened: a submitted claim with the contractual basis, causal link established, evidence attached and the time limit met. • Where it usually breaks: the claim asserts delay without demonstrating the causal link through the programme, so it is rejected as unsubstantiated. | • Require the causal link to be demonstrated through programme analysis, since a claim asserting delay without showing how the event caused it is rejected as unsubstantiated. • Check the notice position first, as preparing a time barred claim wastes significant effort. • Use contemporaneous records as the evidence base, because reconstructed records are discounted. • Distinguish prolongation cost from disruption cost, as these are proven differently. • Submit within the contractual period even if the quantum is not final, and state that particulars will follow.
1255 | Legal | Prepare payment, non-certification and non-payment notices | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Prepare payment, non-certification and non-payment notices” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Prepare payment, non-certification and non-payment notices” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the notices about payment, including when the client does not certify or does not pay. • Starts when: a payment is not certified or not paid when due. • How it runs: (1) she confirms the payment entitlement and the due date. (2) She identifies the applicable notice provision. (3) She drafts the notice citing the clause and the amount. (4) She states the consequences, including any suspension right. (5) She serves it and tracks the response. • Proof it happened: served payment notices citing the entitlement, the amount and the consequences, with proof of service. • Where it usually breaks: non payment is chased informally for months, so the right to suspend or to claim interest is never triggered. | • Issue formal payment notices rather than chasing informally, since suspension rights and interest entitlement are only triggered by the contractual notice. • State the amount, the due date and the contractual basis precisely, as vague demands are easily disputed. • Identify whether the contract requires a further notice before suspension, and follow the sequence exactly. • Advise on the commercial consequences of suspension before exercising it, as it escalates the relationship. • Track the cumulative unpaid position, because this is what determines whether the company should keep performing.
1256 | Legal | Prepare breach, default, cure and remedy notices | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Prepare breach, default, cure and remedy notices” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Prepare breach, default, cure and remedy notices” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the notices that formally record a breach and require it to be put right. • Starts when: a counterparty breaches the contract. • How it runs: (1) she confirms the breach and the contractual provision. (2) She identifies the cure period required. (3) She drafts the notice specifying the breach and what must be done. (4) She reserves the company's further rights. (5) She serves it and tracks the cure period. • Proof it happened: served breach and cure notices specifying the breach, the required remedy and the cure period, with rights reserved. • Where it usually breaks: the notice describes dissatisfaction rather than specifying the breach and the remedy, so it does not start the cure period. | • Specify the breach, the clause breached and exactly what must be done to cure it, since a notice expressing dissatisfaction does not start the cure period. • State the cure period explicitly and diarise its expiry, because the next step depends on it. • Reserve all further rights, so serving a cure notice does not waive the right to terminate or claim. • Serve by the required method, as defective service invalidates everything that follows. • Record the evidence of breach contemporaneously, since this becomes the foundation of any later termination.
1257 | Legal | Prepare suspension, termination and reservation-of-rights notices | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Prepare suspension, termination and reservation-of-rights notices” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Prepare suspension, termination and reservation-of-rights notices” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the most serious notices, those suspending or ending the contract, and those preserving rights. • Starts when: suspension or termination is approved, or rights must be reserved. • How it runs: (1) she confirms the CLO and required approvals are in place. (2) She confirms every preceding notice was validly served. (3) She drafts the notice strictly per the contract. (4) She confirms the service method and timing. (5) She serves it and records the position. • Proof it happened: served suspension, termination or reservation notices with approvals confirmed and the notice sequence verified. • Where it usually breaks: a termination notice is served without the preceding notices having been validly served, which makes the termination itself a breach. | • Verify every preceding notice was validly served before serving a termination notice, since a defective sequence turns the terminating party into the party in breach. • Require CLO approval for every suspension and termination notice without exception. • Issue a reservation of rights early where the position is developing, as this preserves options cheaply. • Check the service timing against the contract, because some notices cannot be served before a stated period has run. • Prepare the practical consequences before serving, since the notice will change behaviour immediately.
1258 | Legal | Build the claim chronology and coordinate entitlement and quantum evidence | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Build the claim chronology and coordinate entitlement and quantum evidence” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Build the claim chronology and coordinate entitlement and quantum evidence” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she builds the timeline of what happened and gathers the evidence for both entitlement and amount. • Starts when: a claim is being prepared or defended. • How it runs: (1) she builds the chronology from the contemporaneous records. (2) She identifies the documents supporting each event. (3) She coordinates the quantum evidence with the commercial team. (4) She identifies the gaps in the evidence. (5) She assembles the claim file. • Proof it happened: a documented chronology with supporting evidence referenced, quantum coordinated and evidential gaps identified. • Where it usually breaks: the chronology is built from recollection rather than documents, and it collapses when the documents are examined. | • Build the chronology from documents with each event referenced to its source, since a chronology built on recollection collapses the moment the records are examined. • Identify the evidential gaps explicitly, because a gap discovered by the other side is far more damaging than one the company already knows about. • Coordinate entitlement and quantum together, as a well evidenced entitlement with unproven cost recovers nothing. • Secure and preserve the records early, before people leave and systems are archived. • Keep the claim file organised for handover, since claims outlast the people who start them.
1259 | Legal | Prepare responses to claim rejections, counterclaims and contractual allegations | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Prepare responses to claim rejections, counterclaims and contractual allegations” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Prepare responses to claim rejections, counterclaims and contractual allegations” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she responds when a claim is rejected or the other side raises its own allegations. • Starts when: a rejection, counterclaim or allegation is received. • How it runs: (1) she analyses the rejection or allegation against the contract and the evidence. (2) She identifies which points are answerable and which are not. (3) She prepares the response within the required timeframe. (4) She takes CLO direction on material matters. (5) She issues the response and records the position. • Proof it happened: an issued response with the contractual analysis, the points answered and the position recorded. • Where it usually breaks: responses are argumentative rather than evidenced, so the exchange escalates without either side's position improving. | • Respond with contractual basis and evidence rather than argument, since an argumentative exchange escalates the dispute without improving the company's position. • Respond within the contractual timeframe, as silence can be treated as acceptance of the other side's position. • Address every point raised, because an unanswered allegation is treated as admitted. • Take CLO direction before making any concession or admission. • Keep all correspondence through a single controlled route, as parallel exchanges create contradictory positions.
1260 | Legal | Update the claim and dispute strategy with recommended next actions | Legal Counsel (Lead) | Trigger: When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. Action: The Legal Counsel (Lead) completes “Update the claim and dispute strategy with recommended next actions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. Control/Handoff: Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a project instruction, change, delay, payment issue, breach, claim event or contractual deadline occurs. | The Legal Counsel (Lead) completes “Update the claim and dispute strategy with recommended next actions” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a timely obligations update, controlled notice, claim submission, response, chronology, evidence index and recommended next action. | Project teams preserve contemporaneous records, the Quantity Surveyor/Finance support quantum and cost evidence, and Legal controls entitlement and wording; missed or imminent time bars escalate immediately to the CLO and COO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she keeps the claim strategy current as the position develops and recommends what to do next. • Starts when: the claim position changes materially, and at the review cycle. • How it runs: (1) she reassesses the merits in light of new information. (2) She reassesses the exposure and the recovery prospects. (3) She reassesses the cost of continuing. (4) She recommends the next actions. (5) She records the updated strategy and obtains direction. • Proof it happened: an updated strategy record with the reassessed merits, exposure and recommended next actions. • Where it usually breaks: the strategy set at the outset is followed unchanged, even after evidence emerges that materially weakens the position. | • Reassess the merits whenever material evidence emerges, since following the original strategy after the position has weakened is how good money follows bad. • Compare the cost of continuing against the realistic recovery at each review. • Record the changed assessment, because the decision to continue should be a fresh one rather than a default. • Include the counterparty's financial position in the assessment, as this changes what is worth pursuing. • Escalate a material weakening to the CLO immediately rather than at the next cycle.
1261 | Legal | Conduct early dispute assessment and structured resolution planning | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Conduct early dispute assessment and structured resolution planning” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Conduct early dispute assessment and structured resolution planning” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: early on she assesses honestly how strong the dispute position is and plans how to resolve it. • Starts when: a dispute emerges or is anticipated. • How it runs: (1) she assesses the strengths and weaknesses candidly. (2) She estimates the likely outcome and range. (3) She estimates the cost and time to resolve by each route. (4) She recommends the resolution approach. (5) She records the assessment for decision. • Proof it happened: an early dispute assessment with a candid merits view, outcome range, cost estimates and recommended approach. • Where it usually breaks: the assessment is optimistic to avoid difficult conversations, so the company commits to a dispute it was always going to lose. | • Require a candid assessment including the weaknesses, since an optimistic early assessment commits the company to disputes it was always going to lose. • State an outcome range rather than a single figure, as this is what allows a realistic settlement decision. • Estimate the cost and management time of each route, because these frequently exceed the amount in dispute. • Consider the commercial relationship value alongside the legal merits. • Record the assessment, so the decision to proceed is informed and reviewable.
1262 | Legal | Prepare settlement proposals, settlement agreements, releases and waivers | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Prepare settlement proposals, settlement agreements, releases and waivers” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Prepare settlement proposals, settlement agreements, releases and waivers” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the settlement offers and the agreements that formally close a dispute. • Starts when: settlement is authorised and being negotiated or agreed. • How it runs: (1) she prepares the proposal on a without prejudice basis. (2) She confirms the settlement authority limits. (3) She drafts the settlement agreement with the release scope. (4) She confirms the payment and performance terms. (5) She obtains approval and arranges execution. • Proof it happened: an executed settlement agreement with the release scope defined, terms stated and approval evidenced. • Where it usually breaks: the settlement releases more than intended, so claims the company still wanted to pursue are discharged. | • Define the release scope precisely and carve out anything the company still intends to pursue, since a broad release discharges claims that were never part of the settlement. • Mark all settlement correspondence without prejudice, as unprotected admissions become evidence if settlement fails. • Require the settlement to be conditional on payment being received where money is owed to the company. • Confirm the signatory on the other side has authority, otherwise the settlement is unenforceable. • Obtain the required internal approval before making any offer, not after it is accepted.
1263 | Legal | Prepare litigation, arbitration and expert-matter instructions and evidence packs | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Prepare litigation, arbitration and expert-matter instructions and evidence packs” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Prepare litigation, arbitration and expert-matter instructions and evidence packs” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she prepares the instructions and evidence packs for formal proceedings and experts. • Starts when: proceedings are commenced or defended, or an expert is appointed. • How it runs: (1) she prepares the instruction setting out the facts and the issues. (2) She assembles the evidence pack with the chronology and documents. (3) She identifies the witnesses and their evidence. (4) She confirms document preservation is in place. (5) She issues the instruction and manages the information flow. • Proof it happened: issued instructions with the evidence pack, witness identification and document preservation confirmed. • Where it usually breaks: documents are not preserved at the outset, and relevant records are deleted in the ordinary course after proceedings have begun. | • Issue a document preservation hold immediately when proceedings become likely, since routine deletion after that point is treated as destruction of evidence and penalised severely. • Provide the instruction with the weaknesses as well as the strengths, because counsel advising on a partial picture gives partial advice. • Identify the witnesses early, as people leave and their recollection fades. • Organise the evidence pack so it can be used rather than delivered as an undifferentiated bundle. • Keep privileged material clearly separated and marked.
1264 | Legal | Manage external-counsel deliverables, advice, hearings and critical deadlines | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Manage external-counsel deliverables, advice, hearings and critical deadlines” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Manage external-counsel deliverables, advice, hearings and critical deadlines” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she manages what the external lawyers produce, and makes sure hearing and filing deadlines are met. • Starts when: external counsel are instructed and the matter is running. • How it runs: (1) she maintains the schedule of deadlines and hearings. (2) She coordinates the information counsel needs. (3) She reviews their deliverables against the instruction. (4) She monitors the fees against the estimate. (5) She reports the position to the CLO. • Proof it happened: a managed matter record with the deadline schedule, reviewed deliverables and fees monitored against estimate. • Where it usually breaks: a procedural deadline is missed because it was held only by counsel, and the company's position is damaged by default. | • Maintain the deadline schedule internally rather than relying on counsel alone, since a missed procedural deadline can damage the position by default and the company bears the consequence. • Review deliverables against the instruction, as advice that does not address the question asked is common and expensive. • Monitor fees monthly against the estimate and require approval for scope extensions. • Keep control of strategy internally, rather than allowing it to drift to counsel. • Require counsel to identify decisions the company needs to make, with the deadline for each.
1265 | Legal | Provide legal support for employee conduct, grievance and termination matters | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Provide legal support for employee conduct, grievance and termination matters” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Provide legal support for employee conduct, grievance and termination matters” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she advises on employment matters, including conduct, grievances and terminations. • Starts when: an employment matter requires legal input. • How it runs: (1) she establishes the facts and the documentation. (2) She confirms the contractual and legal position. (3) She advises on the process required. (4) She reviews the documents to be issued. (5) She records the advice and the position taken. • Proof it happened: recorded employment advice with the factual and legal position, the process advised and the documents reviewed. • Where it usually breaks: the decision to dismiss is taken before the process is followed, so the outcome is procedurally unfair regardless of the underlying merits. | • Require the process to be followed before the decision is taken, since a procedurally defective dismissal creates liability regardless of how justified the decision was. • Require documented performance or conduct history before any dismissal for cause, as undocumented cause is unprovable. • Check the notice, end of service and settlement calculations against the law and the contract. • Advise on the confidentiality and privilege position, as employment matters generate disclosable documents. • Require legal review of any settlement or waiver with a departing employee.
1266 | Legal | Support investigations, whistleblowing, fraud response and legal holds | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Support investigations, whistleblowing, fraud response and legal holds” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Support investigations, whistleblowing, fraud response and legal holds” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she supports investigations, whistleblowing responses and the preservation of documents for legal reasons. • Starts when: an investigation begins, a report is received, or a legal hold is required. • How it runs: (1) she issues the document preservation instruction. (2) She confirms the scope of records to be held. (3) She supports the investigation to preserve privilege. (4) She monitors compliance with the hold. (5) She releases the hold when instructed and records it. • Proof it happened: an issued and monitored legal hold with the scope defined, privilege preserved and the release recorded. • Where it usually breaks: the legal hold is issued but not monitored, so routine deletion continues and the records are lost anyway. | • Monitor compliance with a legal hold rather than assuming the instruction is enough, since routine deletion continues unless it is actively suspended in the systems. • Include email, messaging, site records and backups in the hold scope, as these are where the relevant material usually sits. • Structure investigation work to preserve privilege from the first document. • Protect the reporter and record that protection, since retaliation is unlawful and destroys the reporting channel. • Record the release of a hold, so disposal can resume in a controlled way.
1267 | Legal | Review corporate licence, registration, compliance and renewal issues | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Review corporate licence, registration, compliance and renewal issues” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Review corporate licence, registration, compliance and renewal issues” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she deals with licence, registration and compliance questions as they arise. • Starts when: a licence or compliance issue is identified or a renewal problem arises. • How it runs: (1) she establishes the requirement and the current position. (2) She identifies the gap and its consequence. (3) She advises on the action required. (4) She supports the renewal or rectification. (5) She records the resolution. • Proof it happened: a resolved licence or compliance matter with the requirement established, the gap identified and the action recorded. • Where it usually breaks: a licence gap is identified and treated as administrative, when it actually means current contracts are being performed without authorisation. | • Assess the contractual consequence of any licence gap, since work performed outside licence scope can render contracts unenforceable and attract penalties. • Escalate lapses immediately rather than treating them as administrative, as the exposure grows daily. • Check the licence requirement before the company enters a new activity or location. • Advise on whether existing contracts must be disclosed or remedied where a gap is found. • Record the resolution, so the same gap is not reopened at the next renewal.
1268 | Legal | Complete contract and project legal closeout for final account, retention and DLP | Legal Counsel (Lead) | Trigger: When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. Action: The Legal Counsel (Lead) completes “Complete contract and project legal closeout for final account, retention and DLP” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. Output/Evidence: a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. Control/Handoff: CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. Continuity/Escalation: Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. Timing: To be confirmed. | When a dispute, proceeding, investigation, employment issue, compliance renewal or contract closeout requires Legal action. | The Legal Counsel (Lead) completes “Complete contract and project legal closeout for final account, retention and DLP” using approved business instructions, contracts, tenders, correspondence, project and commercial evidence, current legal authorities, Delegation of Authority and the controlled matter file. | a controlled resolution plan, counsel instruction, legal-support record, renewal action or documented legal closeout with residual matters. | CPCO owns employee process, business functions own operational facts and CFO owns provisions/payments; Legal protects rights, evidence and deadlines, escalating material exposure to the CLO. | Another authorised qualified Legal Counsel may provide case backup using the controlled matter file; material exposure, conflicting instructions, missed deadlines, settlements and precedent-setting positions escalate to the CLO. | To be confirmed. | • In plain words: she closes out the legal side of a finished project, covering the final account, retention and the defects period. • Starts when: a project reaches final account and closeout. • How it runs: (1) she reviews the final account settlement and release wording. (2) She confirms pending claims are preserved or settled. (3) She confirms the retention release position. (4) She confirms the defects liability obligations and their dates. (5) She records the closeout position and the surviving obligations. • Proof it happened: a legal closeout record with the release reviewed, claims addressed, retention confirmed and surviving obligations recorded. • Where it usually breaks: the project file is closed while obligations survive, so the defects liability period and outstanding retention are forgotten by everyone. | • Record the surviving obligations and their expiry dates at closeout, since the defects liability period and retention continue long after everyone stops thinking about the project. • Review the release wording and carve out unresolved claims, as a broad release discharges them permanently. • Confirm subcontractor obligations run at least as long as the company's own, or the company carries the gap. • Diarise the retention release and the defects period expiry with a named owner. • Archive the contract file with the registers, since these documents are the first evidence needed in any later claim.
1269 | Legal | Register each incoming Legal request and assign a unique matter ID | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Register each incoming Legal request and assign a unique matter ID” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Register each incoming Legal request and assign a unique matter ID” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she logs every legal request that comes in and gives it a unique reference, so nothing gets lost. • Starts when: a legal request is received from any department. • How it runs: (1) she receives it through the approved channel. (2) She records the date, requester and subject. (3) She assigns the unique matter ID. (4) She records it in the matter register. (5) She passes it for triage. • Proof it happened: a matter register entry with the date, requester, subject and unique matter ID assigned. • Where it usually breaks: requests sent directly to a lawyer are never registered, so the work is done off the record and nobody knows the volume or the deadlines. | • State a single intake channel and require requests sent directly to individuals to be registered, since unregistered work has no deadline, no record and no visibility. • Assign the matter ID at registration and require it on all subsequent correspondence, so documents can be tied to the matter. • Never reuse a matter ID, as historical references otherwise become ambiguous. • Record the requester by name, so incomplete requests can be returned to someone. • Keep the register sequential and unbroken, because gaps undermine its reliability.
1270 | Legal | Acknowledge the request and record counsel owner, priority and deadline | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Acknowledge the request and record counsel owner, priority and deadline” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Acknowledge the request and record counsel owner, priority and deadline” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she confirms receipt to the requester and records who is handling it, how urgent it is and when it is due. • Starts when: a matter is registered. • How it runs: (1) she issues the acknowledgement to the requester. (2) She records the counsel assigned. (3) She records the priority from the triage. (4) She records the response deadline. (5) She confirms the deadline to the requester. • Proof it happened: an acknowledgement issued with the assigned counsel, priority and deadline recorded and confirmed. • Where it usually breaks: no acknowledgement is sent, so the requester chases and then escalates, which consumes more time than the matter itself. | • Acknowledge within a stated period with the deadline stated, since an unacknowledged request produces chasing and escalation that costs more time than the work. • Record the assigned counsel, so the requester has one contact rather than chasing the department. • Confirm the deadline explicitly, as an unconfirmed deadline is assumed to be immediate. • Flag where the requested deadline cannot be met, rather than letting it pass. • Report unacknowledged matters as an exception.
1271 | Legal | Issue and track the conflict-check questionnaire and result | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Issue and track the conflict-check questionnaire and result” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Issue and track the conflict-check questionnaire and result” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she sends out and tracks the conflict check before the matter proceeds. • Starts when: a matter is opened and a conflict check is required. • How it runs: (1) she issues the conflict questionnaire to the relevant parties. (2) She records the responses. (3) She checks the parties against the existing matter register. (4) She records the result. (5) She escalates any conflict identified before work proceeds. • Proof it happened: a completed conflict check with the questionnaire issued, responses recorded and the result documented. • Where it usually breaks: work proceeds while the conflict check is outstanding, so advice is given before a conflict is discovered. | • Require the conflict check to be complete before substantive work begins, since a conflict found afterwards may invalidate the advice already given. • Check against the full matter register including closed matters, as conflicts arise from past relationships. • Record the result either way, so the file shows the check was done rather than assumed. • Escalate identified conflicts to the CLO rather than resolving them at assistant level. • Include related entities and individuals in the check, because conflicts arise through group and personal connections.
1272 | Legal | Prepare the matter-opening checklist and required-document list | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Prepare the matter-opening checklist and required-document list” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Prepare the matter-opening checklist and required-document list” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she prepares the checklist of what the matter needs and lists the documents required. • Starts when: a matter is opened. • How it runs: (1) she identifies the matter type and the applicable checklist. (2) She lists the documents required. (3) She issues the list to the requester. (4) She tracks what has been received. (5) She reports the outstanding items. • Proof it happened: a matter opening checklist with the required document list issued and receipt tracked. • Where it usually breaks: documents are requested piecemeal as the work progresses, so the matter stalls repeatedly waiting for information. | • Issue the full document list at opening rather than requesting piecemeal, since repeated requests stall the matter and frustrate the requester. • Maintain checklists per matter type, so the list is complete rather than dependent on memory. • Track outstanding items visibly, as the requester needs to know what is holding the matter. • Set a deadline for provision and escalate where it is not met. • Record where a matter proceeds without a document, so the advice can be qualified accordingly.
1273 | Legal | Collect instructions, contracts, correspondence and supporting evidence | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Collect instructions, contracts, correspondence and supporting evidence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Collect instructions, contracts, correspondence and supporting evidence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she gathers the contracts, correspondence and evidence the lawyer needs to work on the matter. • Starts when: the document list is issued and collection begins. • How it runs: (1) she collects the documents from the requester and the registers. (2) She checks they are complete and legible. (3) She checks she has the executed versions and all amendments. (4) She organises them for review. (5) She records what was collected and from where. • Proof it happened: a collected document set organised for review, with the source recorded and completeness checked. • Where it usually breaks: the draft contract is collected rather than the executed version, so the advice is given on terms that were never agreed. | • Verify that the executed version and all amendments have been collected, since advice given on a draft that was superseded in negotiation is simply wrong. • Collect from the controlled registers rather than from personal email, as personal copies are frequently not the final ones. • Record the source of each document, so its authenticity can be confirmed later. • Check legibility and completeness, because missing pages and unsigned schedules are discovered at the worst moment. • Organise by chronology and type, as an unorganised bundle wastes the most expensive time in the process.
1274 | Legal | Create the controlled electronic matter folder and approved access permissions | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Create the controlled electronic matter folder and approved access permissions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Create the controlled electronic matter folder and approved access permissions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she sets up the electronic folder for the matter with the right access restrictions. • Starts when: a matter is opened. • How it runs: (1) she creates the folder using the standard structure. (2) She applies the access permissions per the confidentiality classification. (3) She restricts access to the named team. (4) She confirms privileged material is separately controlled. (5) She records the permissions applied. • Proof it happened: a created matter folder with the standard structure and access permissions applied per classification. • Where it usually breaks: default wide permissions are applied, so confidential dispute and employment material is visible across the company. | • Apply restricted permissions by default on legal matters, since default wide access exposes dispute, employment and investigation material across the company. • Hold privileged material in a separately controlled area, so it cannot be accessed or forwarded casually. • Record who has access, because a disclosure cannot be investigated without knowing who could see the file. • Review access when the team changes, as retained access is the standard audit finding. • Use a standard folder structure, so any member of the team can find material without asking.
1275 | Legal | Apply Legal file-naming, version and status conventions | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Apply Legal file-naming, version and status conventions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Apply Legal file-naming, version and status conventions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she names and versions the files consistently so the current draft is always identifiable. • Starts when: documents are filed in the matter folder. • How it runs: (1) she applies the naming convention. (2) She applies the version numbering. (3) She marks the status: draft, for review, executed. (4) She ensures superseded versions are marked. (5) She keeps the current version clearly identifiable. • Proof it happened: files named and versioned per the convention, with status marked and the current version identifiable. • Where it usually breaks: several files are named as final, so nobody can tell which version is the one that was actually agreed. | • Prohibit the use of final in file names and require sequential version numbers, since multiple files called final is the standard reason nobody knows which version was agreed. • Include the date and version in the file name, so the sequence is visible without opening files. • Mark the executed version distinctly, as this is the one that matters and must never be confused with a draft. • Mark superseded drafts clearly while retaining them, since the negotiation history has evidential value. • Apply the convention at filing rather than tidying up later.
1276 | Legal | Return incomplete requests and track missing information to closure | Contracts & Legal Assistant | Trigger: When a Legal request or new matter arrives through the approved channel. Action: The Contracts & Legal Assistant completes “Return incomplete requests and track missing information to closure” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. Control/Handoff: The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal request or new matter arrives through the approved channel. | The Contracts & Legal Assistant completes “Return incomplete requests and track missing information to closure” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a uniquely identified, complete, access-controlled Legal matter file with owner, priority, deadline and missing-information status. | The Assistant performs administrative intake only and does not give legal advice or approve legal positions; conflicts, urgency, incomplete instructions and restricted-access issues route to Legal Counsel. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: when a request is incomplete she returns it and chases the missing information. • Starts when: a request is found to be incomplete. • How it runs: (1) she identifies what is missing. (2) She records the return and the reason. (3) She returns it to the requester with the specific list. (4) She tracks the outstanding items. (5) She escalates where they remain outstanding. • Proof it happened: a return record with the specific missing items, tracked to receipt or escalation. • Where it usually breaks: missing information is chased verbally and never tracked, so matters sit dormant and the deadline arrives with nothing done. | • Track outstanding information as a visible item with a deadline, since verbally chased requests leave matters dormant until the deadline arrives. • Record the return so the delay is attributable, because the matter's deadline may need to move. • Escalate to the requester's manager where information remains outstanding beyond a stated period. • State the specific items rather than returning the request generally, or the resubmission has the same gaps. • Report dormant matters, as these accumulate silently and represent unaddressed risk.
1277 | Legal | Populate approved standard contract, notice and letter templates | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Populate approved standard contract, notice and letter templates” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Populate approved standard contract, notice and letter templates” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she fills in the standard contract, notice and letter templates with the details for this matter. • Starts when: a document is to be produced from a template. • How it runs: (1) she selects the current approved template. (2) She populates the party, project and commercial details. (3) She leaves the legal content for counsel to complete. (4) She checks the details against the source records. (5) She passes it to counsel for review. • Proof it happened: a populated template using the current approved version with details verified against the source records. • Where it usually breaks: an old template copy is reused from a previous matter, carrying across the other party's name and negotiated terms. | • Require templates to be taken from the controlled location each time, since reusing a previous matter's document carries across the wrong party details and negotiated concessions. • Verify the party details against the trade licence or registration rather than from the request, as incorrect legal names affect enforceability. • State clearly which fields the assistant completes and which counsel completes, so legal content is not populated administratively. • Check the template version is current before use. • Have a second person check party names, values and dates, as these errors are the most consequential and the easiest to make.
1278 | Legal | Format draft agreements, notices, advice and legal correspondence | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Format draft agreements, notices, advice and legal correspondence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Format draft agreements, notices, advice and legal correspondence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she formats the drafts and correspondence so they are clean, consistent and professional. • Starts when: a draft is prepared and requires formatting. • How it runs: (1) she applies the standard formatting and numbering. (2) She checks the clause numbering is sequential. (3) She applies the company letterhead and reference conventions. (4) She ensures the defined terms are used consistently. (5) She returns it to counsel for final review. • Proof it happened: formatted documents with consistent numbering, letterhead and reference conventions applied. • Where it usually breaks: clause numbering breaks during editing, so cross references point to the wrong clauses in the executed contract. | • Check clause numbering and cross references after every round of edits, since a cross reference pointing at the wrong clause in an executed contract changes its meaning. • Use automatic numbering rather than manual, as manual numbering breaks silently during editing. • Check defined terms are used consistently and are actually defined, because an undefined capitalised term is a gap. • Apply the reference convention so the document can be identified from its face. • Never alter substantive wording while formatting, and flag anything that looks wrong rather than correcting it.
1279 | Legal | Prepare document comparisons and tracked-change mark-ups | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Prepare document comparisons and tracked-change mark-ups” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Prepare document comparisons and tracked-change mark-ups” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she produces the comparison showing exactly what changed between versions. • Starts when: a revised version is received or issued. • How it runs: (1) she identifies the two versions to compare. (2) She produces the comparison document. (3) She checks the comparison captured all changes. (4) She highlights the substantive changes for counsel. (5) She files both versions and the comparison. • Proof it happened: a comparison document between identified versions with the substantive changes highlighted and both versions filed. • Where it usually breaks: the counterparty's clean version is accepted without comparison, so changes they made are never noticed. | • Require a comparison against the last agreed version every time a document is received, since changes made in a clean version are otherwise never noticed and are then executed. • Verify the comparison against the correct baseline version, as comparing to the wrong version hides real changes. • Highlight substantive changes separately from formatting, so counsel's time goes to what matters. • File the comparison with both versions, as the negotiation history has evidential value. • Run a final comparison immediately before execution, because late unilateral changes do happen.
1280 | Legal | Maintain the negotiation comment and deviation matrix | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Maintain the negotiation comment and deviation matrix” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Maintain the negotiation comment and deviation matrix” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the running record of comments and the deviations still open in a negotiation. • Starts when: negotiation begins and continues until it closes. • How it runs: (1) she records each comment and deviation with its clause reference. (2) She records the company's position and the counterparty's. (3) She updates the status as points are agreed or dropped. (4) She identifies the points still open. (5) She reports the open position for each round. • Proof it happened: a maintained negotiation matrix with clause references, both positions, status and the open points identified. • Where it usually breaks: the matrix is not updated during fast negotiation, so points thought to be agreed are not reflected in the final document. | • Update the matrix after every negotiation round, since points believed agreed but never recorded do not appear in the final document. • Record both positions and the final agreed wording, so the executed document can be checked against what was agreed. • Mark clearly which deviations were conceded and which remain, as this is the record of accepted risk. • Carry the matrix through to the approval pack, so the signatory sees what was accepted. • Retain the closed matrix with the contract, because it explains why the clauses say what they say.
1281 | Legal | Compile schedules, annexures, exhibits and referenced documents | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Compile schedules, annexures, exhibits and referenced documents” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Compile schedules, annexures, exhibits and referenced documents” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she assembles all the schedules, annexures and referenced documents that form part of the agreement. • Starts when: an agreement is being finalised for execution. • How it runs: (1) she lists every schedule and annexure the contract references. (2) She obtains each one in its correct version. (3) She checks each is complete and legible. (4) She compiles them in the stated order. (5) She confirms nothing referenced is missing. • Proof it happened: a compiled set of schedules and annexures matching the references, complete and in the correct order. • Where it usually breaks: a referenced schedule is missing at execution, so a material part of the agreement is undefined. | • Check every referenced schedule is actually attached before execution, since a missing schedule leaves a material part of the agreement undefined and is construed against whoever relies on it. • Verify the version of each schedule matches what was agreed, particularly drawing and specification schedules. • Include a drawing register with revisions where drawings form part of the contract. • Number the schedules and list them on the cover, so completeness can be checked at a glance. • Have the counterparty initial each schedule, so receipt cannot be denied.
1282 | Legal | Verify document references, defined terms, cross-references and pagination | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Verify document references, defined terms, cross-references and pagination” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Verify document references, defined terms, cross-references and pagination” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she checks the document's internal references, defined terms and page numbering all line up. • Starts when: a document is prepared for final review or execution. • How it runs: (1) she checks every cross reference points to the correct clause. (2) She checks every defined term is defined and used consistently. (3) She checks references to schedules match their numbering. (4) She checks the pagination is complete and correct. (5) She records the corrections needed. • Proof it happened: a verification record confirming cross references, defined terms, schedule references and pagination. • Where it usually breaks: a cross reference survives from an earlier draft where the clause numbers were different, so it points to something unrelated. | • Check every cross reference against the final numbering, since references carried over from an earlier draft point at unrelated clauses and change the meaning of the contract. • Check each defined term is actually defined, because an undefined capitalised term leaves a material concept open to interpretation. • Verify schedule references match the schedule numbering as compiled. • Check pagination is complete, as missing pages in an executed document create real disputes. • Perform this check on the version being executed, not an earlier one.
1283 | Legal | Proofread draft documents and record quality-control corrections | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Proofread draft documents and record quality-control corrections” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Proofread draft documents and record quality-control corrections” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she proofreads the documents carefully and records what was corrected. • Starts when: a document is prepared for issue or execution. • How it runs: (1) she proofreads for errors in names, dates, figures and terms. (2) She checks the figures against the source records. (3) She marks the corrections for counsel rather than changing substance. (4) She records the corrections made. (5) She confirms the corrected version is the one issued. • Proof it happened: a proofreading record with the corrections identified, referred where substantive and the corrected version confirmed. • Where it usually breaks: a figure or a date is wrong in the executed contract, and it is the wrong number that becomes binding. | • Check every figure, date and party name against the source records, since an incorrect number in an executed contract is the number that binds the company. • Require a second person to check values and dates, as the person who typed them reads what they intended. • Refer anything substantive to counsel rather than correcting it, because an apparent typo can be a negotiated position. • Record the corrections, so the same errors can be designed out of the templates. • Confirm the issued version is the corrected one, as reverting to an earlier file is a common final error.
1284 | Legal | Issue the counsel-approved controlled final version for action | Contracts & Legal Assistant | Trigger: When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. Action: The Contracts & Legal Assistant completes “Issue the counsel-approved controlled final version for action” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. Control/Handoff: All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When Legal Counsel issues a controlled drafting, comparison, formatting or finalisation instruction. | The Contracts & Legal Assistant completes “Issue the counsel-approved controlled final version for action” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | an accurate template draft, redline, comment matrix, compiled schedule, quality-check record or counsel-approved final version. | All substantive wording remains subject to Legal Counsel review; the Assistant controls versions and prevents unapproved drafts, missing annexures or superseded documents from being issued. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she issues the version counsel has approved, and only that version. • Starts when: counsel approves the final version for issue. • How it runs: (1) she confirms which version is approved. (2) She checks the file to be issued is that version. (3) She converts it to the issue format. (4) She issues it to the intended recipients. (5) She records the issue and the version issued. • Proof it happened: the approved version issued in the correct format, with the version and recipients recorded. • Where it usually breaks: a later working file is issued by mistake, so an unapproved version goes to the counterparty. | • Check the file being issued against the approved version immediately before sending, since issuing an unapproved working draft to a counterparty is difficult to retract. • Issue in a non editable format, so the recipient cannot alter and return it as agreed. • Record the version issued, as this becomes the reference point for the next round. • Require counsel's approval to be explicit and recorded rather than inferred. • Never issue directly from a shared editing location, because the content can change after sending.
1285 | Legal | Prepare signature-authority and execution-checklist packs | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Prepare signature-authority and execution-checklist packs” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Prepare signature-authority and execution-checklist packs” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she prepares the pack showing who must sign, in what order, and what must be in place first. • Starts when: a document is approved and ready for execution. • How it runs: (1) she identifies the required signatories on both sides. (2) She confirms their authority against the matrix. (3) She prepares the execution checklist including witnesses and stamps. (4) She confirms the conditions precedent to signature. (5) She issues the pack for execution. • Proof it happened: a signature authority and execution checklist pack with signatories, authority confirmed and requirements listed. • Where it usually breaks: the document is signed by someone without authority, so its enforceability is open to challenge. | • Confirm every signatory's authority against the matrix before execution, since a document signed without authority can be challenged as unenforceable. • Confirm the counterparty's signatory authority too, as the company's rights depend on the other side being bound. • List the execution formalities required: witnesses, stamps, initialling of schedules and number of originals. • Confirm the conditions precedent are satisfied before signature rather than after. • State the signing order where it matters, because some documents must be signed in sequence.
1286 | Legal | Coordinate approved signature circulation and execution sequence | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Coordinate approved signature circulation and execution sequence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Coordinate approved signature circulation and execution sequence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she manages getting the document signed by everyone in the right order. • Starts when: the execution pack is issued. • How it runs: (1) she circulates the document per the approved sequence. (2) She confirms each signature is obtained correctly. (3) She checks the signatures are complete including initials and dates. (4) She keeps the parties informed of progress. (5) She confirms execution is complete. • Proof it happened: a circulation record showing the sequence followed and each signature obtained and checked. • Where it usually breaks: signature pages are signed and returned separately from the document, so it is unclear what was actually signed. | • Require signature pages to be returned with the full document rather than separately, since a detached signature page leaves what was signed open to argument. • Check every signature block is completed with name, capacity and date, as undated signatures create uncertainty about when the contract took effect. • Require schedules to be initialled where the contract calls for it. • Follow the signing sequence where it is legally significant. • Track progress visibly, as partially executed documents stall and are forgotten.
1287 | Legal | Track counterparty signatures and outstanding execution actions | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Track counterparty signatures and outstanding execution actions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Track counterparty signatures and outstanding execution actions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she chases the counterparty's signature and tracks what is still outstanding. • Starts when: the document is issued for counterparty signature. • How it runs: (1) she records the date issued for signature. (2) She follows up at set intervals. (3) She records the outstanding actions. (4) She escalates where signature is not returned. (5) She confirms receipt of the fully executed document. • Proof it happened: a signature tracking record with follow ups, outstanding actions and the executed document received. • Where it usually breaks: the company performs the work while the contract remains unsigned by the counterparty, so its terms are unenforceable. | • Report unsigned contracts where work has started as a standing exception, since performing under an unexecuted contract leaves the company without enforceable terms. • Set a follow up schedule rather than chasing occasionally, as unsigned documents are quietly forgotten. • Escalate to the CLO where signature is withheld, because withholding signature while taking the benefit is a deliberate position. • Record the date fully executed, as this may differ from the effective date. • Track outstanding executions by value, so the total exposure is visible.
1288 | Legal | Receive and reconcile executed originals and certified copies | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Receive and reconcile executed originals and certified copies” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Receive and reconcile executed originals and certified copies” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she receives the signed originals, checks them and reconciles them against what should exist. • Starts when: executed documents are returned. • How it runs: (1) she receives the executed originals or certified copies. (2) She checks they are complete and properly signed. (3) She checks the number of originals against the requirement. (4) She records receipt and the location of each original. (5) She reconciles against the execution checklist. • Proof it happened: received originals checked and recorded with their location, reconciled against the execution checklist. • Where it usually breaks: the company never receives its own executed original, so it holds only an unsigned copy of a binding contract. | • Reconcile the originals received against the number required, since the company frequently ends up holding only a copy of a contract it is fully bound by. • Record the physical location of each original, as these are needed for enforcement and cannot be reproduced. • Check the returned document matches the version executed, because substitution at signature does occur. • Store originals in controlled secure storage rather than in project files. • Scan and file a copy immediately, so the content is available without handling the original.
1289 | Legal | Coordinate notarisation, legalisation and attestation when instructed | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Coordinate notarisation, legalisation and attestation when instructed” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Coordinate notarisation, legalisation and attestation when instructed” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: when documents need official certification, notarisation or attestation, she arranges it. • Starts when: notarisation or legalisation is instructed. • How it runs: (1) she confirms exactly what certification is required and for which jurisdiction. (2) She prepares the documents in the required form. (3) She arranges the notary, translation and attestation steps in the correct order. (4) She tracks the process and the fees. (5) She receives, checks and files the certified documents. • Proof it happened: certified or attested documents received and filed, with the process steps and fees recorded. • Where it usually breaks: the steps are done in the wrong order or a translation is missing, so the whole process must be repeated at full cost. | • Confirm the exact sequence of notarisation, translation and attestation required for the destination jurisdiction, since an out of order step means repeating the whole process at full cost and delay. • Confirm whether the original or a copy must be certified, as this cannot be corrected afterwards. • Allow for the processing time in the project timeline, because these steps are slow and outside the company's control. • Check the certified document against the original on return, as errors in transcription occur. • Record the fees and the reference, so the process can be repeated correctly next time.
1290 | Legal | Compile powers of attorney, board resolutions and signatory evidence | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Compile powers of attorney, board resolutions and signatory evidence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Compile powers of attorney, board resolutions and signatory evidence” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she assembles the documents proving the company's authority to sign, such as powers of attorney and resolutions. • Starts when: authority evidence is required for a transaction or a counterparty. • How it runs: (1) she identifies the authority evidence required. (2) She obtains the current power of attorney or resolution. (3) She checks it is valid and covers the transaction. (4) She compiles it with the signatory identification. (5) She issues the pack and records what was provided. • Proof it happened: a compiled authority pack with valid powers of attorney or resolutions covering the transaction. • Where it usually breaks: an expired or superseded power of attorney is provided, which delays the transaction or invalidates the signature. | • Check the validity date and the scope of the authority document before providing it, since an expired or non covering power of attorney invalidates the signature it was meant to support. • Maintain a register of current authority documents with expiry dates, so the correct one can be found quickly. • Check the resolution covers the specific transaction, as a general resolution may be insufficient. • Record what authority evidence was provided to whom, because this is disclosed information about the company's internal authority. • Escalate where no current authority covers the transaction, rather than providing the nearest available document.
1291 | Legal | Coordinate document dispatch, formal service, courier and delivery proof | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Coordinate document dispatch, formal service, courier and delivery proof” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Coordinate document dispatch, formal service, courier and delivery proof” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she arranges the sending of documents, including formal service where the method legally matters. • Starts when: a document must be dispatched or formally served. • How it runs: (1) she confirms the required delivery or service method. (2) She confirms the address per the contract. (3) She arranges the dispatch by that method. (4) She obtains and retains the delivery proof. (5) She records the dispatch and the proof. • Proof it happened: a dispatch record with the method used, the address, and retained delivery proof. • Where it usually breaks: a formal notice is sent by email when the contract requires registered post, so the service is invalid and the notice ineffective. | • Use the exact method and address the contract specifies for notices, since a notice served by the wrong method is no notice at all and the entitlement behind it is lost. • Retain the delivery proof, as the date of service is what determines whether a notice was in time. • Check the contractual address has not been changed by subsequent notice. • Where permitted, serve by more than one method for critical notices. • Record the dispatch date and the method, so the service can be evidenced years later.
1292 | Legal | Distribute executed copies and update agreement execution status | Contracts & Legal Assistant | Trigger: When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. Action: The Contracts & Legal Assistant completes “Distribute executed copies and update agreement execution status” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. Control/Handoff: Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When an agreement or legal document is approved for execution, formal service, notarisation, legalisation or registration support. | The Contracts & Legal Assistant completes “Distribute executed copies and update agreement execution status” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a complete authority pack, signature trail, executed document, attestation evidence, dispatch record and updated execution status. | Signature authority is verified before circulation; the Assistant follows counsel instructions and escalates missing originals, authority defects, rejected filings or delivery failures immediately. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she distributes the executed copies and updates the status so everyone knows the contract is live. • Starts when: execution is complete. • How it runs: (1) she distributes executed copies to the business owner and the counterparty. (2) She files the executed version in the controlled record. (3) She updates the contract register status to executed. (4) She notifies the affected departments. (5) She records the distribution. • Proof it happened: executed copies distributed, filed in the controlled record and the register status updated to executed. • Where it usually breaks: execution is not communicated, so the project team does not know it may proceed and Finance does not know it may invoice. | • Notify the project team, Finance and Procurement on execution, since none of them can act correctly while they do not know the contract is live. • Update the register status at execution rather than later, as the register is what others rely on. • Distribute the executed version rather than the final draft, because these are frequently confused. • File in the controlled record, not in personal email, since this is the enforceable document. • Record the distribution, so it is clear who holds the contract.
1293 | Legal | Maintain the client, supplier, subcontract and other contracts register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the client, supplier, subcontract and other contracts register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the client, supplier, subcontract and other contracts register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the register of all the company's contracts across clients, suppliers and subcontractors. • Starts when: a contract is executed, and on every amendment. • How it runs: (1) she records each contract with its parties, value and dates. (2) She records the type and the owning department. (3) She records the key dates and the current status. (4) She updates on amendment or termination. (5) She reconciles the register periodically for completeness. • Proof it happened: a maintained contracts register with parties, values, dates, status and amendments recorded. • Where it usually breaks: contracts signed by departments never reach the register, so the company does not know what it is bound by. | • Reconcile the register against the finance and procurement systems periodically, since contracts signed within departments otherwise never reach it and the company does not know its own obligations. • Record amendments against the original rather than as separate entries, so the current position is visible. • Record the contract value including variations, as the original value understates the exposure. • Make the register the source for reporting total contractual commitment. • Record the location of the executed original against each entry.
1294 | Legal | Maintain the contractual-obligations, expiry and renewal register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the contractual-obligations, expiry and renewal register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the contractual-obligations, expiry and renewal register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps track of what the company must do under its contracts, and when they expire or renew. • Starts when: a contract is registered, and continuously as dates approach. • How it runs: (1) she records the obligations with their deadlines. (2) She records the expiry and renewal dates. (3) She sets advance reminders by lead time. (4) She notifies the owners in advance. (5) She tracks the action taken. • Proof it happened: an obligations and renewal register with deadlines, advance reminders and the action taken recorded. • Where it usually breaks: a contract auto renews because the notice deadline passed unnoticed, committing the company for another full term. | • Set reminders for auto renewal notice deadlines by lead time, since a missed notice commits the company to another full term at the existing terms. • Flag auto renewal clauses distinctly in the register, as these are the deadlines with the largest silent consequence. • Record the notice period and the method required, not just the expiry date. • Assign a named owner per renewal decision, so the decision is taken rather than defaulted. • Report upcoming expiries and renewals monthly.
1295 | Legal | Maintain the claims, notices, variations and extension-of-time register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the claims, notices, variations and extension-of-time register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the claims, notices, variations and extension-of-time register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the registers of claims, notices, variations and time extension requests. • Starts when: a claim, notice or variation arises. • How it runs: (1) she records each item with its date and reference. (2) She records the contractual basis and the value claimed. (3) She records the response deadline. (4) She records the response received and the outcome. (5) She reports the open position. • Proof it happened: maintained claims, notices and variations registers with dates, bases, values, deadlines and outcomes. • Where it usually breaks: notices served are not registered, so nobody can show later that notice was given within the time limit. | • Register every notice served with its date and proof of service, since the ability to show notice was given in time is frequently what decides an entitlement. • Record the response deadline for each item, as these are the dates that carry consequence. • Track the cumulative claimed and awarded value, so the commercial position is visible. • Flag items where the response deadline has passed without response, as this may itself create entitlement. • Keep the register aligned with the project's own records, since divergence between them is exploited in dispute.
1296 | Legal | Maintain the dispute, court, arbitration and hearing register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the dispute, court, arbitration and hearing register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the dispute, court, arbitration and hearing register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the register of disputes and the associated hearing and filing dates. • Starts when: a dispute is commenced or received. • How it runs: (1) she records the dispute with the parties and the forum. (2) She records the amounts claimed and counterclaimed. (3) She records every procedural deadline and hearing date. (4) She issues reminders ahead of each. (5) She records the status and the outcome. • Proof it happened: a dispute register with parties, forum, amounts, procedural deadlines and hearing dates recorded. • Where it usually breaks: procedural deadlines are held only by external counsel, so a missed date damages the position by default. | • Hold the procedural deadlines internally as well as with counsel, since a missed filing date can decide the matter by default and the company bears the loss. • Set reminders well ahead of each deadline, as preparation time is what is actually needed. • Record the amounts claimed and counterclaimed, so the net exposure is reportable. • Restrict access to the register, because it contains the company's most sensitive exposures. • Report the dispute position to the CLO at a fixed frequency.
1297 | Legal | Maintain the external-counsel, expert and legal-adviser register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the external-counsel, expert and legal-adviser register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the external-counsel, expert and legal-adviser register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the register of external lawyers, experts and advisers and what each is instructed on. • Starts when: an external adviser is instructed. • How it runs: (1) she records the adviser, the matter and the scope. (2) She records the fee basis and the estimate. (3) She records the engagement terms. (4) She tracks the fees against the estimate. (5) She records completion and performance notes. • Proof it happened: an external adviser register with scopes, fee bases, estimates and fees tracked against them. • Where it usually breaks: advisers are instructed without a recorded scope or estimate, so fees arrive unbudgeted and unchallengeable. | • Record the scope and fee estimate at instruction, since fees arriving without a recorded basis cannot be challenged and are simply paid. • Track actual fees against the estimate and flag overruns as they emerge rather than at invoice. • Record the engagement terms, including who may instruct additional work. • Keep performance notes, so adviser selection is informed by experience. • Record which matters each adviser has acted on, as this is relevant to conflicts.
1298 | Legal | Maintain the corporate licence, permit, authority and renewal register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the corporate licence, permit, authority and renewal register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the corporate licence, permit, authority and renewal register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the register of the company's licences and permits and when they expire. • Starts when: a licence is obtained or renewed, and continuously as expiries approach. • How it runs: (1) she records each licence with its number, scope and expiry. (2) She records the issuing authority and the renewal requirements. (3) She sets advance reminders by lead time. (4) She notifies the owners. (5) She records the renewal completion. • Proof it happened: a licence and permit register with scopes, expiry dates, reminders and renewal evidence. • Where it usually breaks: the register records the expiry date but not the lead time needed, so renewal starts too late and the licence lapses. | • Record the renewal lead time as well as the expiry date and set reminders accordingly, since a reminder on the expiry date is too late for most renewals. • Record the licensed scope, so it can be checked against what the company actually does. • Escalate immediately where a renewal is at risk, as a lapsed trade licence halts operations. • Include all entities and locations, because group structures create licences nobody tracks. • File the renewal evidence against the register entry.
1299 | Legal | Maintain the insurance, bond, guarantee and security register | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Maintain the insurance, bond, guarantee and security register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Maintain the insurance, bond, guarantee and security register” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the register of insurance policies, bonds and guarantees and their expiry dates. • Starts when: a policy or instrument is issued, and continuously as expiries approach. • How it runs: (1) she records each policy or instrument with its value and period. (2) She records what it covers and the contract it relates to. (3) She records the expiry and release conditions. (4) She sets advance reminders. (5) She records renewal, extension or release. • Proof it happened: an insurance, bond and guarantee register with values, periods, coverage and release evidence. • Where it usually breaks: a bond stays live after the obligation has ended, so the company pays charges and ties up facility capacity for nothing. | • Record the covered obligation against each instrument, since this is what shows a bond can be released rather than merely that it exists. • Set reminders before expiry for both renewal and release, as lapsing is a breach and leaving it live wastes charges and facility capacity. • Record whether each bond is on demand or conditional, so the risk is visible at a glance. • Report the total contingent exposure to the CFO, because these are real liabilities outside the visible accounts. • File the instrument itself with the register entry, as the wording determines the exposure.
1300 | Legal | Issue deadline reminders and escalate overdue Legal actions | Contracts & Legal Assistant | Trigger: When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. Action: The Contracts & Legal Assistant completes “Issue deadline reminders and escalate overdue Legal actions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. Control/Handoff: Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a contract, obligation, notice, claim, proceeding, licence, security or deadline is created or changes. | The Contracts & Legal Assistant completes “Issue deadline reminders and escalate overdue Legal actions” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | a current controlled register entry with document link, owner, due date, status, reminder and escalation evidence. | Register entries reconcile to controlled source documents; overdue or conflicting dates are not silently changed and are escalated to Legal Counsel and the CLO according to urgency. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she sends out the reminders before legal deadlines and escalates the ones that pass. • Starts when: deadlines approach, and when they pass unmet. • How it runs: (1) she maintains the consolidated deadline list. (2) She issues reminders at the set intervals before each. (3) She confirms the action taken. (4) She escalates overdue items to the CLO. (5) She records the reminders and escalations issued. • Proof it happened: issued reminders with the action confirmed and overdue items escalated and recorded. • Where it usually breaks: reminders are issued but the action is never confirmed, so everyone assumes the deadline was met and nobody checks. | • Require confirmation that the action was taken rather than assuming the reminder was enough, since an unconfirmed reminder leaves everyone believing a deadline was met. • Escalate on a defined timescale rather than repeating reminders, as repeated reminders without escalation are ignored. • Set reminders by the preparation time needed, not by the deadline itself. • Maintain one consolidated deadline list, because deadlines held in several places are the ones missed. • Record the reminders and escalations, so the record shows the deadline was managed.
1301 | Legal | Coordinate the Legal calendar, meetings, agendas and attendance records | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Coordinate the Legal calendar, meetings, agendas and attendance records” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Coordinate the Legal calendar, meetings, agendas and attendance records” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she manages the legal calendar, arranges meetings and keeps the attendance records. • Starts when: meetings are to be scheduled, and continuously. • How it runs: (1) she maintains the legal calendar of meetings and deadlines. (2) She schedules meetings and confirms attendance. (3) She prepares and circulates the agendas in advance. (4) She records the attendance. (5) She files the meeting records. • Proof it happened: a maintained calendar with scheduled meetings, circulated agendas and recorded attendance. • Where it usually breaks: agendas are circulated at the meeting, so attendees are unprepared and decisions are deferred to the next one. | • Circulate agendas and papers a stated period in advance, since unprepared attendees defer decisions and the meeting achieves nothing. • Require the agenda to state the decisions needed rather than the topics for discussion. • Record attendance, as decisions taken without the accountable person are reopened. • Keep the calendar consolidated with the deadline list, so meetings are scheduled before the deadlines they must address. • Confirm attendance in advance, because a meeting without the key attendee wastes everyone's time.
1302 | Legal | Prepare Legal meeting minutes and maintain the action tracker | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Prepare Legal meeting minutes and maintain the action tracker” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Prepare Legal meeting minutes and maintain the action tracker” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she writes up the legal meeting minutes and keeps the action tracker current. • Starts when: a meeting is held. • How it runs: (1) she records the discussion, decisions and actions. (2) She drafts the minutes and has them approved. (3) She issues them to attendees and those affected. (4) She extracts the actions into the tracker with owners and dates. (5) She follows up the actions to closure. • Proof it happened: approved minutes issued with the actions extracted into a tracker and followed up to closure. • Where it usually breaks: minutes record the discussion but not who agreed to do what by when, so nothing is actionable. | • Require every action to be recorded with a named owner and a date, since minutes describing discussion without actions produce no outcome. • Record decisions distinctly from discussion, so the decision is unambiguous when referred to later. • Issue minutes within a stated period, as minutes issued late are disputed. • Carry open actions forward to the next meeting until closed. • Mark minutes as privileged where they record legal advice, and restrict their distribution.
1303 | Legal | Register external-counsel invoices and supporting fee narratives | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Register external-counsel invoices and supporting fee narratives” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Register external-counsel invoices and supporting fee narratives” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she registers the external lawyers' invoices and checks the fee narratives support them. • Starts when: an external counsel invoice is received. • How it runs: (1) she registers the invoice against the matter. (2) She checks the fee narrative against the instruction and the work expected. (3) She checks the amount against the estimate. (4) She flags variances for counsel review. (5) She passes the approved invoice to Finance. • Proof it happened: registered invoices with narratives checked against instructions and estimates, variances flagged and approvals recorded. • Where it usually breaks: invoices are passed for payment without checking the narrative, so work outside the instruction is paid for without question. | • Check the fee narrative against the instructed scope, since work outside the instruction is otherwise paid for without anyone noticing. • Compare against the estimate and require an explanation for variances before approval. • Require narratives in sufficient detail to be checked, and reject block billing. • Allocate fees to the correct matter, so the cost of each dispute is visible. • Track cumulative spend per matter against the authorised amount.
1304 | Legal | Maintain Legal budget commitments, purchase-order and payment-status records | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Maintain Legal budget commitments, purchase-order and payment-status records” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Maintain Legal budget commitments, purchase-order and payment-status records” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps track of the legal budget commitments and where each payment stands. • Starts when: a commitment is made, and continuously through to payment. • How it runs: (1) she records each commitment against the budget. (2) She records the purchase order reference. (3) She tracks the invoices against the commitment. (4) She tracks the payment status. (5) She reports the budget position. • Proof it happened: a commitment and payment record reconciled to the budget with purchase order references and payment status. • Where it usually breaks: commitments are tracked only when invoiced, so the budget appears available when it is already fully committed. | • Record commitments at instruction rather than at invoice, since a budget that looks available while already committed leads to overspend nobody saw coming. • Reconcile to the finance records at a set frequency, so the two positions do not diverge. • Track payment status so counsel queries can be answered without going to Finance. • Report the committed position rather than the spent position. • Flag where a matter will exceed its authorised amount before it does.
1305 | Legal | Compile weekly and monthly Legal status and deadline reports | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Compile weekly and monthly Legal status and deadline reports” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Compile weekly and monthly Legal status and deadline reports” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she compiles the weekly and monthly reports on where legal matters and deadlines stand. • Starts when: at the weekly and monthly reporting cycles. • How it runs: (1) she compiles the matter status from the registers. (2) She compiles the upcoming and overdue deadlines. (3) She compiles the exceptions: unsigned contracts and unserved notices. (4) She issues the report. (5) She tracks the actions arising. • Proof it happened: issued weekly and monthly reports with matter status, deadlines, exceptions and actions. • Where it usually breaks: the report lists open matters without distinguishing the ones with deadlines, so the urgent items are buried. | • Lead the report with deadlines and exceptions rather than a list of open matters, since a flat list buries the items that carry consequence. • Show ageing on overdue items, because duration determines the response required. • Generate the report from the registers so the two cannot disagree. • Include unsigned contracts and unserved notices as standing exceptions. • Keep the format and issue day fixed, as a predictable report gets read.
1306 | Legal | Maintain the evidence index and preserve legal-hold materials | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Maintain the evidence index and preserve legal-hold materials” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Maintain the evidence index and preserve legal-hold materials” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she keeps the index of evidence and makes sure material under legal hold is preserved. • Starts when: a legal hold is issued, or evidence is collected for a matter. • How it runs: (1) she records each evidence item with its source and date. (2) She maintains the index by matter. (3) She confirms held material is preserved and not deleted. (4) She monitors compliance with the hold. (5) She records the release when instructed. • Proof it happened: a maintained evidence index with sources recorded and the preservation of held material confirmed. • Where it usually breaks: the hold is recorded but never checked, so routine deletion continues and evidence is lost despite the instruction. | • Confirm with IT that deletion has actually been suspended for held material, since a hold that is recorded but not implemented loses the evidence anyway. • Index evidence by source and date, as an unindexed collection cannot be used. • Include email, messaging and backups in the hold scope, because this is where most relevant material sits. • Record the chain of custody for original documents, so authenticity cannot be challenged. • Record the release of a hold, so disposal resumes in a controlled way.
1307 | Legal | Archive superseded and executed Legal records under the retention rules | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Archive superseded and executed Legal records under the retention rules” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Archive superseded and executed Legal records under the retention rules” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she archives the superseded and executed legal records according to the retention rules. • Starts when: records become inactive or a matter closes. • How it runs: (1) she identifies the records to be archived. (2) She applies the retention period per record type. (3) She archives them with the index. (4) She confirms any legal hold is checked before disposal. (5) She verifies the archive is retrievable. • Proof it happened: archived records with retention periods applied, legal holds checked and retrievability verified. • Where it usually breaks: records are disposed of on schedule without checking for a legal hold, which is a serious exposure. | • Check for a legal hold before every disposal, since destroying records under hold is a severe legal exposure regardless of the retention schedule. • Retain executed contracts for the full limitation period rather than the project duration, as claims arrive years later. • Verify retrievability by actually retrieving sample records, because an archive that cannot be opened is not an archive. • Archive the registers with the records, as the records are unusable without their index. • Require approval and a record for every disposal.
1308 | Legal | Close the matter file and verify the complete closure checklist | Contracts & Legal Assistant | Trigger: When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. Action: The Contracts & Legal Assistant completes “Close the matter file and verify the complete closure checklist” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. Output/Evidence: complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. Control/Handoff: Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. Continuity/Escalation: A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. Timing: To be confirmed. | When a Legal meeting, external fee, reporting cutoff, legal hold, archive event or matter closure becomes due. | The Contracts & Legal Assistant completes “Close the matter file and verify the complete closure checklist” using counsel-approved instructions, controlled templates, source documents, execution evidence, approved access rights and Legal registers. | complete minutes, action and fee records, status report, evidence index, retained archive and verified closure checklist. | Counsel approves substantive minutes, fees follow CPO/CFO controls, legal holds override routine disposal and no matter closes while deadlines, originals, invoices or residual actions remain open. | A trained authorised Legal support delegate may maintain records and coordination using controlled access; the Assistant must escalate legal judgment, authority defects, confidentiality incidents, urgent deadlines and incomplete evidence to Legal Counsel. | To be confirmed. | • In plain words: she closes the matter file, checking against the checklist that nothing is left outstanding. • Starts when: a matter is complete and ready to close. • How it runs: (1) she works through the closure checklist. (2) She confirms the executed documents and originals are filed. (3) She confirms the registers are updated. (4) She confirms no actions or holds remain open. (5) She closes the matter and records the closure. • Proof it happened: a completed closure checklist with documents filed, registers updated and no open actions or holds remaining. • Where it usually breaks: matters are closed with actions and surviving obligations still open, so these disappear from view entirely. | • Require the checklist to confirm no open actions or surviving obligations before closure, since anything open at closure disappears from view completely. • Confirm the executed originals are filed and their location recorded, as this is the last opportunity to find them. • Confirm any legal hold has been formally released before closing. • Transfer surviving obligations such as defects periods and retention to a live register rather than closing them with the matter. • Record lessons for templates or training, since matters reveal exactly which documents caused difficulty.

## Read Me & Taxonomy
SEVENTS Jurisdiction Architecture | Country-agnostic ERP core; initial deployment profile is UAE. Do not assume India, INR or GST.
Tax Configuration | GST is not mandatory. Use generic tax types; configure UAE VAT only after SEVENTS finance/tax owners confirm registration status, treatment and applicable rules.
Localization Configuration | Country/legal entity/project configuration should hold jurisdiction, currency, language, timezone, fiscal calendar, statutory identifiers, invoice fields and supported localization-pack version.
Configuration Safety | Do not invent tax rates, legal deadlines, SLA values or approval limits. Unknowns must remain TBD and block consequential activation where appropriate.
Scope Limitation | Country-agnostic architecture does not automatically guarantee compliance in every country; new statutory calculations, reports, integrations or expert reviews may still be required.
SEVENTS Construction ERP — Work Item Configuration Review Workbook
Purpose | Preserve the original 1,308 work-item rows and add a separate review/configuration layer. Blank review columns are intentionally not guessed.
Principle | Source catalogue is configuration input, not a list of 1,308 software features. Build reusable capabilities and map items to them.
Disposition: Configure workflow | Actionable recurring work that fits supported workflow capabilities.
Disposition: Configure approval/decision | A decision with inputs, authorized approver, recorded outcome and follow-up.
Disposition: Track obligation/document | Filing, signature, renewal, paper step, or evidence obligation.
Disposition: Periodic review/monitor | Scheduled review with a defined cadence, output and exception path.
Disposition: Reference/policy only | Broad responsibility or guidance without a discrete task outcome.
Disposition: Clarify/de-duplicate | Ambiguous, overlapping, inconsistent or dependent item requiring process-owner review.
Disposition: Defer | Valid work not needed for the current delivery phase.
Operational fields | Trigger; responsible canonical role; action/capability; output/evidence; SLA/timing; handoff/dependency; exception/escalation; approval/risk/agent policy.
Reference fields | Governance Understanding, Governance Inputs for SOP Creation, and reviewer columns remain reference/provenance by default.
SLA handling | Do not infer or invent. Mark SLA Confirmed only after the owner confirms the timing rule and business calendar.
Role mapping | Map raw role labels to canonical Role IDs. Raw role names are not permission grants.
Leadership and paper-based work | Create tasks only where a record, decision, obligation, measurable outcome or follow-up exists. Track physical signature/custody evidence where needed; do not assume scan equals valid e-signature.
Publication gate | No row becomes executable until the required fields are validated, risk and approval policies are set, and an authorized process owner approves publication.

## Controlled Values
Field | Allowed Value
Disposition | Configure workflow
Disposition | Configure approval/decision
Disposition | Track obligation/document
Disposition | Periodic review/monitor
Disposition | Reference/policy only
Disposition | Clarify/de-duplicate
Disposition | Defer
Priority | P0 - Critical
Priority | P1 - High
Priority | P2 - Medium
Priority | P3 - Low
Priority | Unassessed
Risk Tier | Tier 0 - Read-only
Risk Tier | Tier 1 - Draft/preparation
Risk Tier | Tier 2 - Reversible low-risk
Risk Tier | Tier 3 - Human-approved transaction
Risk Tier | Tier 4 - No autonomous execution
Risk Tier | Unassessed
Mapping Status | Not reviewed
Mapping Status | Needs clarification
Mapping Status | Mapped - pending validation
Mapping Status | Validated - pending approval
Mapping Status | Published/active
Mapping Status | Reference only
Mapping Status | Deferred
Confirmation | Yes
Confirmation | No
Confirmation | TBD
Phase Target | Phase 0
Phase Target | Phase 1
Phase Target | Phase 2
Phase Target | Phase 3
Phase Target | Phase 4+
Phase Target | Deferred
Phase Target | TBD
Jurisdiction Profile | UAE initial profile
Jurisdiction Profile | Other country profile — configure and validate
Tax Type | VAT
Tax Type | GST
Tax Type | Sales tax
Tax Type | Withholding/retention tax
Tax Type | No tax / out of scope
Tax Status | TBD—Finance/Tax Review
Tax Status | Configured—Not Activated
Tax Status | Approved for Use
Localization Status | Not assessed
Localization Status | In review
Localization Status | Validated
Localization Status | Active